## Well & Rig Data
1. Well & Rig Data
1.1. Well Data |  | 1.2. Rig Data
Operator | STATOILHYDRO ASA | Rig name | Mærsk Inspirer
|  | Rig type | Jack - up platform
Well Name | 15/9-F-4 | Rig make | Hyundai Heavy Industries Comp. Ltd
Classification | Water Injector | RKB - mSL | 54 m
Well path | Deviated
|  | Well head make | Vetco Gray mS-700 (Subsea)
Country | Norway | Size | 18¾"
Area | Volve | Rating | 1035bar
Prospect |  | BOP make | Shaffer
Licence | PL 046BS | Annular Preventer | 18¾”
|  | Rating | 690bar (10000psi)
Site position coordinates: |  | Upper Pipe Rams | 5”-7”
Latitude | 58°26’29.807” N | Rating | 1035bar (15000psi)
Longitude | 01°53’14.929” E | Shear Rams | CVX”
UTm Co-ordinates | 6 478 563m N | Rating | 1035bar (15000psi)
435 050m E |  | middle Pipe Rams | 3½”-5½”
Slot centre coordinates F-4: |  | Rating | 1035bar (15000psi)
Latitude | 58° 26' 29.720” N | Lower Pipe Rams | 5½”
Longitude | 01° 53' 14.920” E | Rating | 1035bar (15000psi)
UTm Co-ordinates | 6 478 560.825m N
435 049.831m E |  | Diverter make | Shaffer
|  | Size (OD / ID) | 24" / 49½"
RKB to mSL | 54m | Rating | 34½ BAR
Water depth | 91mMSL
|  | HP Drilling Riser make | Aker Kværner
Spud date | 09th June 2007 | OD / ID | 21” / 19”
TD reached | 15th February 2008 | Rating | 345bar (5000psi)
Total Depth | 3510mMD / 3138.8mTVD
Total Drilling Days | 50 | Choke make | Shaffer
Final Well Status | Completed for water injection | Rating | 1035bar (15000psi)
|  | Rig Pumps make | Wirth
|  | Numbers | 3
|  | model | TRK-7½”x14”/2200
|  | Output 6½” liner | 22.15 l/stk @ 97% efficiency
|  | Rating | 352 bar
|  | Top Drive make | Varco Systems
|  | model | TDS-8SA
|  | Drawworks make | VARCO SYSTEMS
|  | model | ADS-10Q

## Trajectory
mMD | X | Y | mTVD | INC | AZI | DLS (deg/30m)
0 | 435049.831 | 6478560.825 | 0 | 0 | 0
145.6 | 435049.831 | 6478560.825 | 145.6 | 0 | 220 | 0
180 | 435049.7741 | 6478560.7984 | 180 | 0.02 | 205.09 | 0.017442
182.5 | 435049.4834 | 6478561.2925 | 182.5 | 0.18 | 120.47 | 2.1508
206.7 | 435048.4743 | 6478561.3382 | 206.7 | 0.28 | 177.41 | 0.29287
216.5 | 435047.7971 | 6478560.4767 | 216.5 | 0.29 | 231.83 | 0.79832
222.4 | 435047.9283 | 6478560.1529 | 222.4 | 0.09 | 292.07 | 1.3092
237.2 | 435047.8595 | 6478560.0495 | 237.2 | 0.03 | 236.36 | 0.15646
242.4 | 435047.7315 | 6478560.4081 | 242.4 | 0.09 | 109.645 | 0.63797
286.4 | 435039.2604 | 6478556.8298 | 286.4 | 1.84 | 202.9 | 1.2595
327.7 | 435029.2854 | 6478552.6694 | 327.7 | 1.89 | 202.64 | 0.036836
369.1 | 435014.7426 | 6478529.3507 | 369.1 | 4.27 | 238.05 | 2.1309
410 | 434996.0567 | 6478485.3936 | 409.7 | 6.69 | 246.97 | 1.8766
439.6 | 434958.5188 | 6478437.468 | 439.1 | 7.96 | 231.93 | 2.3205
479.3 | 434905.4581 | 6478392.5488 | 478.4 | 8.34 | 220.25 | 1.2814
519.6 | 434827.0562 | 6478365.9044 | 518.2 | 9.17 | 198.77 | 2.495
562 | 434739.3613 | 6478361.2318 | 560.1 | 8.99 | 183.05 | 1.7545
600.1 | 434643.3853 | 6478357.5112 | 597.7 | 9.21 | 182.22 | 0.20172
640 | 434541.233 | 6478368.7167 | 637.2 | 9.24 | 173.74 | 1.0215
680.8 | 434429.498 | 6478384.4201 | 677.3 | 9.54 | 172 | 0.30367
721.3 | 434303.0076 | 6478414.7877 | 717.3 | 10.39 | 166.5 | 0.94456
760.7 | 434139.0905 | 6478467.8263 | 755.9 | 13.09 | 162.07 | 2.1659
801.1 | 433952.2197 | 6478548.5377 | 795 | 14.72 | 156.64 | 1.5492
840.5 | 433733.8238 | 6478651.6797 | 833 | 16.7 | 154.72 | 1.5585
876.2 | 433512.0545 | 6478768.4076 | 867.2 | 16.62 | 152.24 | 0.6012
917.2 | 433288.9844 | 6478876.869 | 906.6 | 15.69 | 154.07 | 0.77572
958.9 | 433070.495 | 6478976.3943 | 946.8 | 14.5 | 155.51 | 0.89755
998.5 | 432856.6311 | 6479072.4637 | 985.2 | 13.58 | 155.81 | 0.69914
1043.5 | 432659.3554 | 6479173.3713 | 1029.1 | 12.26 | 152.91 | 0.98018
1083.9 | 432446.4296 | 6479281.5817 | 1068.5 | 12.73 | 153.06 | 0.34984
1124.3 | 432223.3548 | 6479447.6144 | 1107.8 | 14.32 | 143.34 | 2.0561
1164.6 | 431948.3665 | 6479626.467 | 1146.6 | 16.36 | 146.96 | 1.6769
1204.9 | 431622.7716 | 6479829.1319 | 1185.1 | 18.56 | 148.1 | 1.6573
1240.4 | 431319.3972 | 6480051.4124 | 1218.8 | 17.65 | 143.77 | 1.3723
1284.8 | 431045.4038 | 6480246.6337 | 1261.4 | 15.18 | 144.53 | 1.6752
1325.3 | 430745.4737 | 6480432.8882 | 1300.4 | 15.45 | 148.16 | 0.7377
1335.7 | 430442.1968 | 6480620.7081 | 1310.4 | 15.49 | 148.23 | 0.12734
1369.5 | 430156.0161 | 6480851.0501 | 1343 | 15.56 | 141.17 | 1.6774
1410 | 429909.9023 | 6481140.7447 | 1382.1 | 15.64 | 130.35 | 2.1532
1450.2 | 429715.915 | 6481510.3927 | 1420.7 | 16.73 | 117.69 | 2.7501
1490.7 | 429547.613 | 6481987.5147 | 1459.1 | 19.84 | 109.43 | 2.9934
1531.2 | 429332.3989 | 6482533.5879 | 1496.9 | 22.54 | 111.51 | 2.0758
1571.3 | 429087.4037 | 6483118.9809 | 1533.8 | 23.82 | 112.71 | 1.0207
1611.3 | 428799.9396 | 6483734.6079 | 1570.2 | 24.94 | 115.03 | 1.1051
1651.8 | 428496.5083 | 6484381.1889 | 1606.8 | 25.62 | 115.14 | 0.5049
1692 | 428268.3495 | 6485078.0057 | 1643.1 | 25.68 | 108.13 | 2.2638
1731.8 | 428069.6293 | 6485796.0275 | 1678.9 | 25.48 | 105.47 | 0.87867
1773.4 | 427844.0689 | 6486524.2453 | 1716.5 | 25.46 | 107.21 | 0.53979
1813.4 | 427608.9627 | 6487265.394 | 1752.6 | 25.39 | 107.6 | 0.13611
1853.8 | 427377.2299 | 6488032.4463 | 1789.1 | 25.61 | 106.81 | 0.30078
1894.2 | 427133.0055 | 6488809.8648 | 1825.6 | 25.48 | 107.44 | 0.22364
1934.6 | 426864.7783 | 6489598.6796 | 1862.1 | 25.51 | 108.78 | 0.42887
1974.2 | 426601.3319 | 6490408.0419 | 1897.7 | 25.54 | 108.03 | 0.24588
2014.4 | 426342.7196 | 6491235.8057 | 1934 | 25.5 | 107.35 | 0.22066
2055.6 | 426035.3665 | 6492081.1695 | 1971.2 | 25.95 | 109.98 | 0.8934
2136.2 | 425703.6631 | 6492974.0467 | 2043.5 | 26.48 | 110.38 | 0.20794
2176.5 | 425372.7732 | 6493889.6174 | 2079.6 | 26.57 | 109.87 | 0.1823
2216.6 | 425033.1845 | 6494821.112 | 2115.5 | 26.57 | 110.03 | 0.053541
2256.9 | 424702.3107 | 6495774.4655 | 2151.5 | 26.56 | 109.14 | 0.29638
2296.9 | 424410.1815 | 6496761.3095 | 2187.3 | 26.62 | 106.49 | 0.89068
2337.4 | 424109.7122 | 6497761.5572 | 2223.5 | 26.54 | 106.72 | 0.096555
2378 | 423813.9096 | 6498781.7099 | 2259.8 | 26.53 | 106.17 | 0.18171
2418.9 | 423514.0462 | 6499811.8331 | 2296.3 | 26.33 | 106.23 | 0.148
2458.9 | 423207.4288 | 6500864.4733 | 2332.3 | 26.48 | 106.24 | 0.11255
2499.3 | 422896.7692 | 6501955.7755 | 2368.4 | 27 | 105.89 | 0.40346
2539.6 | 422579.2489 | 6503075.6298 | 2404.2 | 27.28 | 105.83 | 0.20943
2579.9 | 422260.2319 | 6504215.9149 | 2440 | 27.32 | 105.63 | 0.074495
2660.4 | 421693.6491 | 6505319.3131 | 2511.6 | 27.79 | 117.18 | 1.9962
2700.2 | 420951.115 | 6506354.9454 | 2546.7 | 28.16 | 125.64 | 3.0021
2740.8 | 420014.9393 | 6507334.5974 | 2582.3 | 29.63 | 133.7 | 3.0735
2773.9 | 418913.3721 | 6508258.5944 | 2610.2 | 31.22 | 140.01 | 3.2331
2800.7 | 417693.8698 | 6509086.1233 | 2633 | 31.75 | 145.84 | 3.4585
2840.3 | 416397.8044 | 6509819.4018 | 2666.7 | 31.62 | 150.5 | 1.8565
2879.9 | 415007.8421 | 6510460.7716 | 2700.3 | 32.11 | 155.23 | 1.9274
2920.1 | 413518.4398 | 6510988.4892 | 2734.3 | 32.76 | 160.49 | 2.1599
2959.1 | 411922.3086 | 6511491.4412 | 2766.8 | 34.44 | 162.51 | 1.5521
3001.1 | 410244.2976 | 6511931.0331 | 2801.3 | 35.31 | 165.32 | 1.305
3041.5 | 408450.7517 | 6512198.7604 | 2833.9 | 36.6 | 171.51 | 2.8626
3081.3 | 406586.3549 | 6511877.0582 | 2865.7 | 37.88 | 189.79 | 8.3706
3121.8 | 404547.4092 | 6511752.7081 | 2896.9 | 40.87 | 183.49 | 3.6951
3162.8 | 402370.1356 | 6511521.562 | 2927.3 | 43.81 | 186.06 | 2.496
3203.5 | 400051.7763 | 6511216.7558 | 2955.9 | 46.88 | 187.49 | 2.3838
3244.1 | 397590.8718 | 6510774.4126 | 2982.7 | 50.42 | 190.19 | 3.0138
3284.8 | 395050.6454 | 6510183.2834 | 3008 | 52.56 | 193.1 | 2.3031
3325.1 | 392426.252 | 6509473.2018 | 3031.9 | 54.85 | 195.14 | 2.0985
3365.1 | 389770.8157 | 6508705.2431 | 3054.8 | 55.23 | 196.13 | 0.67195
3404.8 | 387099.6118 | 6507885.5143 | 3077.5 | 55.15 | 197.06 | 0.58017
3444.8 | 384450.6922 | 6506925.0498 | 3100.4 | 54.88 | 199.93 | 1.7751
3485 | 381828.1292 | 6505826.9321 | 3123.6 | 54.67 | 202.72 | 1.708

## Formation Summary
Formation |  | depth, m | depth, ft | Thickness., m | Thickness., ft
A | Loose sand | 146 | 479.0026 | 737 | 2417.979
|  | 883 | 2896.9816
B1 | Sandstone/Clay |  |  | 179 | 587.2703
|  | 1062 | 3484.252
B2 | Clay/Sandstone/Limestone |  |  | 164 | 538.0577
|  | 1226 | 4022.3097
C | Claystone |  |  | 1035.2 | 3396.3255
|  | 2261.2 | 7418.6352
D1 | Clay/Sandstone/Limestone |  |  | 62.2 | 204.0682
|  | 2323.4 | 7622.7034
D2 | Clay/Sandstone/Limestone/Tuff |  |  | 64.3 | 210.958
|  | 2387.7 | 7833.6614
D3 | Clay/Sand stringers |  |  | 85.3 | 279.8556
|  | 2473 | 8113.5171
D4 | Clay/Sandstone/Limestone |  |  | 108.6 | 356.2992
|  | 2581.6 | 8469.8163
E | Limestone |  |  | 124.6 | 408.7927
|  | 2706.2 | 8878.6089
F1 | Limestone/Marl |  |  | 81.5 | 267.3885
|  | 2787.7 | 9145.9974
F2 | Grey Marl/Limestone |  |  | 65.6 | 215.2231
|  | 2853.3 | 9361.2205
G | Claystone |  |  | 93.7 | 307.4147
|  | 2947 | 9668.6352
H | Clay/Limestone | 2987 | 9799.8688 | 40 | 131.2336
J | Sandstone/Clay/Limestone/Coal |  |  | 105.6 | 346.4567
|  | 3092.6 | 10146.3255
K | Sandstone/Clay/Siltstone | 3138.8 | 10297.9003 | 46.2 | 151.5748

## Formation
Formation Group | Formation | mMD |  | mTVD |  | Comment
|  | From | To | From | To
Nordland Group |  | 146 | 1077 | 146 | 1062
| Utsira Formation | 891 | 1077 | 883 | 1062 | Utsira Formation consists of sandstone with minor claystone interbeds. The interval interpretation upon ROP.
Hordaland Group |  | 1077 | 2345.6 | 1062 | 2265.1 | The Hordaland Group consists mainly of claystone with traces of sandstone and limestone. Claystone: Predominately olive grey to dark greenish grey, brownish grey, and dark grey, soft to moderately hard, brittle in parts, sub blocky to blocky, calcareous in parts and silty in parts in the upper part of the formation and predominantly dark greenish grey, brownish black, olive black, soft to moderately hard, sub blocky to blocky, non calcareous, silty in parts in the lowermost part of the formation. limestone: yellowish grey, very light grey to white, soft to firm, crumbly, sub blocky, sandy, argillaceous.
| Skade formation | 1248 | 1323 | 1226 | 1296
| Grid Formation | 1294 | 2379 | 1095.2 | 2261.2 | Grid Formation consists mainly of claystone and some sandstone. Sandstone: Clear-translucent loose Quartz grains, medium to coarse in the top of formation and very fine to coarse in lower part, sub angular to sub rounded, moderate sorted. Claystone: Dark greenish gray to olive gray, brownish gray, medium dark gray, firm to moderate hard, sub blocky to blocky, non calcareous and silty in parts.
Rogaland Group |  | 2345.6 | 2703.5 | 2265.1 | 2323.4 | The Rogaland Group consists of the Balder, Sele, Lista, and Ty Formations.
| Balder Formation | 2379 | 2449 | 2261.2 | 2323.4 | This Formation is dominated by claystone with traces of Sandstone and Limestone. Claystone: Greenish gray to dark greenish grey, greyish brown, occasionally olive black and medium bluish, soft to moderately hard, subblocky to blocky, calcareous in parts and silty in parts. Limestone: Yellowish grey, soft, crumbly, sub blocky. Sandstone: Translucent, fine to coarse grains, sub rounded to rounded, moderately sorted.
| Sele Formation | 2449 | 2521 | 2323.4 | 2387.7 | This Formation is dominated by claystone with traces of sandstone, Limestone and Tuff. Claystone: Predominately olive grey, occasionally medium bluish grey, brownish grey and dark greenish grey, soft to firm, sub blocky to blocky, non calcareous, silty in parts. Limetone: Yellowish grey, soft, crumbly, sub blocky, sandy. Sandstone: Translucent, fine to coarse grain, sub rounded to rounded, moderately sorted. Tuff: Greyish white, firm, sub blocky, pyritic, non- calcareous
| Lista Formation | 2521 | 2617 | 2387.7 | 2473 | This Formation is dominated by claystone with traces of limestone. Stringers of sand were found at the top and bottom of the formation. Claystone: Brownish grey to brownish black, medium grey to greyish black, greenish grey to dark greenish grey, olive grey to olive black, soft to moderately hard, sub blocky to blocky, non calcareous, silty in parts. Sand: Clear translucent to milky white, the grains are fine to medium in the upper part of the formation and very fine to fine in the lowermost part, sub angular to sub rounded, moderately to well sorted. Limestone: Yellowish grey, soft, crumbly, sub blocky, sandy
| Ty Formation | 2617 | 2740 | 2473 | 2581.6 | In section 12” the Ty formation appear as claystones mainly, sandstone and Limestone occur in minority. Claystone: Medium dark grey to olive grey, dark greenish grey, moderately hard, sub- blocky to blocky, non-calcareous, silty in parts. Sandstone: Clear transparent, very fine to coarse, predominantly coarse, sub angular to sub rounded. Limestone: Yellowish grey, very light grey to white, soft, crumbly, sub blocky, sandy
| Ekofisk Formation | 2740 | 2770 | 2581.6 | 2607.6 | In the 12” section the Ekofisk formation is dominated by Limestone, some amount of sandstone and a trace of claystone. Limestone: Greyish white to yellowish Grey, moderately hard to hard, sub blocky Sandstone: Translucent, very fine to medium grains, sub- angular to sub- rounded, moderately sorted. Claystone: Medium dark grey to olive grey, dark greenish grey, firm to moderately hard, sub- blocky to blocky, non-calcareous, silty in parts
| Tor Formation | 2770 | 2886.3 | 2607 | 2706.2 | The Tor Formation is dominated by limestone with traces of claystone and sandstone. Claystone: Medium dark grey to dark greenish grey, occasionally olive grey, soft to moderate hard, sub- blocky to blocky, occasionally elongated. Sand: Clear to transparent. In part loose, clear to translucent Quartz grains. Very coarse to very fine grains, predominantly medium to fine, sub-rounded to rounded, poorly sorted. Limestone: Very pale orange to yellowish grey, white, occurs, greyish orange pink, light brown to brownish grey, pale reddish brown, moderate brown in parts, firm to hard, elongated to sub-blocky, occurs blocky, microcrystalline, argillaceous laminations in parts
| Hod Formation | 2886.3 | 2983.8 | 2706.2 | 2787.7 | The Hod Formation is dominated by limestone grading to marl with depth. Limestone: Predominately light brown, white to yellowish grey, white to pinkish grey occasionally greyish red, light yellowish grey, very pale orange in colour. They are soft to firm, brittle in parts, occurs hard, blocky to sub-blocky, elongated lightly silty in parts, Marls: Light bluish grey, sub-blocky, soft to moderate firm, glauconitic. grading to marls. There are argillaceous laminations in places, which become more prevalent downhole.
| Blodøks Formation | 2983.8 | 3034.1 | 2787.7 | 2828.5 | The Blodoks formation consists mainly of grey marls with argillaceous laminations and limestone. Marl: Light grey to very light grey, greyish brown to dark reddish brown in colour. Firm, blocky, elongated, laminated, earthy, glauconitic. Limestone: Yellowish grey, occasionally moderate reddish orange to moderate reddish brown firm to brittle, blocky, platy, elongated, slightly silty, microcrystalline.
| Hildra Formation | 3034.1 | 3054 | 2828.5 | 2844.6 | This formation consists of grey marl with argillaceous limestone. Marl: Light grey to very light grey, firm, blocky and elongated, laminated, earthy, calcareous, silty, organic layers, traces of glauconite. There is also occurrence of olive grey to olive black, firm, blocky and elongated, laminated, earthy, calcareous, silty, argillaceous. Limestone: Moderate reddish orange to moderate reddish brown, moderately hard, platy, microcrystalline, in parts milky white to yellowish grey, firm, blocky, microcrystalline.
Cromer Knoll Group |  | 3054 | 3101 | 2844.6 | 2881.5 | The Cromer Knoll group consists of Roedby and Aasgard formation.
| Roedby Formation | 3054 | 3065 | 2844.6 | 2853.3 | This formation consists mainly of grey marls with argillaceous laminations and limestone. Marl: Light grey to very light grey, medium bluish grey to dark greenish grey, firm, soft in parts, sub blocky to blocky, elongated, laminated, earthy, calcareous, silty to sandy in parts, glauconitic, argillaceous. Limestone: Milky white to yellowish grey, predominantly moderately hard, platy, microcrystalline. Moderate reddish orange to moderate reddish brown, firm, sub blocky, argillaceous laminated, microcrystalline in parts.
| Aasgard Formation | 3065 | 3101 | 2853.3 | 2881.5 | This formation consists of interbedded limestone and marl with some minor layers of claystone. Marl: Olive black to greenish black, firm to moderately hard, sub blocky to blocky, elongated, silty, very silty in parts, occurrence of glauconite. Also occurrence of light bluish grey to yellowish grey, firm, sub blocky to elongated, slightly argillaceous, glauconitic. Limestone: Milky white to yellowish grey, occasionally moderately reddish brown, firm to hard, sub blocky, microcrystalline, argillaceous laminated in parts. Claystone: Olive black to greenish black, firm, sub blocky to elongated, very silty, earthy, slightly calcareous in parts.
Viking Group |  | 3101 | 3250 | 2881.5 | 2987
| Draupne Formation | 3101 | 3190 | 2881.5 | 2947 | The Draupne formation consists of very organic rich claystone. Claystone: Greyish red to very dusky red, firm, blocky, earthy, slightly calcareous, very organic.
| Heather Formation | 3190 | 3250 | 2947 | 2987 | The Heather formation consists mainly of rich organic claystone with stringers of limestone. Claystone: Greyish black to black, occasionally brownish black, firm to moderate hard, blocky, micropyrite, carbonate material, calcareous. Limestone: Light greenish grey to light bluish grey, firm to hard, subplaty, microcrystalline. | Depth | Formation
Vestland Group |  | 3250 | 3510 | 2987.6 | 3138.8 | The Vestland group consists of the Hugin formation and Sleipner formation. | 146-1300 |  | Rogaland Gp.
| Hugin Formation | 3250 | 3430 | 2987 | 3092.6 | The Hugin formation consists of a thin claystone layer at the bottom over the main sandstone section that dominates the entire section. There were also stringers of coal and limestone. Claystone: Brownish grey to brownish black, occasionally greysih black, firm, blocky, crumbly, slightly calcareous, silty, carbonate material. Sandstone: Clear to translucent quartz grain, occasionally milky white, very fine to very coarse, predominantly medium to coarse, subangular to subrounded, well to moderate sorted, calcite cemented, trace of pyrite. Coal: Black, shiny, brittle, blocky. Limestone: White, hard, brittle, microcrystalline, argillaceous laminated. Siltstone: Light olive grey to olive grey to greyish black, firm to hard, amorphous to subblocky, non to slightly calcareous, crumbly, silica cemented, occasionally very fine quartz grains. | 1300-2610 | Clay Stone | Ekofisk/Tor
| Sleipner Formation | 3430 | 3510 | 3092.6 | 3138.8 | The sleipner formation consists mainly of sandstone with thin layers of claystone and siltstone in between. Sandstone: Clear to transparent, occasionaly white very fine to very coarse, predominantly fine, subangular, subspherical, loose quartz grains, firm to moderate hard, occasionally translucent silica cemented, kaolinite matrix. Claystone: Medium grey to bluish grey, firm to moderate hard, blocky, crumbly. Siltstone: Grey olive to brownish grey, soft to firm, crumbly, kaolinite matrix. | 2610-2740 | Medium Sand | Hod/Blodoks/Hidrs
[7 empty] | 2740-2830 | Limestone | romer Knoll Gp.
[7 empty] | 2830-2925 | Marl Shale | Viking Gp.
[7 empty] | 2925-2990 | Limestone | Hugin
[7 empty] | 2990-3090 | Marl Shale | Hegre Gp.
[7 empty] | 3090-3190 | Clay Shale
[7 empty] | 3190-3320 | Silt
[7 empty] | 3320-3420 | Siltstone
[7 empty] | 3420-3450 | Clay Stone
[7 empty] | 3450-3510 | Silt

## PP_FG
Wells Data
Formation | Depth mTVDss (m) | Depth mTVD DFE (m) | Depth mTVD DFE (ft) | Pore Pressure |  |  |  | Frac Pressure
|  |  |  | Exp |  |  |  | Exp
|  |  |  | psi | psi/ft | ppg | SG | psi | psi/ft | ppg | SG
Surface (A) | -54 | 0 | 0 | 0 | 0 | 0
BTM Surface (A) | 92 | 146 | 479.0026 | 0 | 0 | 0
B | 92 | 146 | 479.0026 | 213.6304 | 0.44599 | 8.5799 | 1.03
BTM B | 202 | 256 | 839.895 | 374.5848 | 0.44599 | 8.5799 | 1.03
C1 | 202 | 256 | 839.895 | 374.5848 | 0.44599 | 8.5799 | 1.03
BTM C1 | 1279.9 | 1333.9 | 4376.3123 | 1951.7915 | 0.44599 | 8.5799 | 1.03
C2 | 1279.9 | 1333.9 | 4376.3123 | 1951.7915 | 0.44599 | 8.5799 | 1.03
BTM C2 | 1309 | 1363 | 4471.7848 | 1994.3713 | 0.44599 | 8.5799 | 1.03 | 2962.5127 | 0.66249 | 12.7449 | 1.53
D | 1309 | 1363 | 4471.7848 | 1994.3713 | 0.44599 | 8.5799 | 1.03
BTM C1 | 1316 | 1370 | 4494.7506 | 2004.6138 | 0.44599 | 8.5799 | 1.03
E | 1316 | 1370 | 4494.7506 | 2004.6138 | 0.44599 | 8.5799 | 1.03
BTM E | 2436 | 2490 | 8169.2913 | 4598.4941 | 0.5629 | 10.829 | 1.3
F | 2436 | 2490 | 8169.2913 | 4598.4941 | 0.5629 | 10.829 | 1.3
BTM F | 2553.5 | 2607.5 | 8554.79 | 4815.4913 | 0.5629 | 10.829 | 1.3
G | 2553.5 | 2607.5 | 8554.79 | 4815.4913 | 0.5629 | 10.829 | 1.3 | 6111.9697 | 0.71445 | 13.7445 | 1.65
BTM G | 2741.2 | 2795.2 | 9170.6037 | 4765.0457 | 0.5196 | 9.996 | 1.2
H | 2741.2 | 2795.2 | 9170.6037 | 5162.1328 | 0.5629 | 10.829 | 1.3
BTM H | 2939 | 2993 | 9819.5538 | 5527.4268 | 0.5629 | 10.829 | 1.3
G | 2939 | 2993 | 9819.5538 | 5527.4268 | 0.5629 | 10.829 | 1.3
BTM G | 3084.8 | 3138.8 | 10297.9002 | 5796.688 | 0.5629 | 10.829 | 1.3

## PorePressures
MD | TVD | MD | TVD | Pore Pressure
(m) | (m) | (ft) | (ft) | SG | psi | psi/ft | ppg
1360 | 1303.5599 | 4461.9423 | 4276.7713 | 1.03 | 1907.3972 | 0.44599 | 8.5799
1363 | 1306.3016 | 4471.7848 | 4285.7664 | 1 | 1855.7369 | 0.433 | 8.33
1680 | 1596.0079 | 5511.811 | 5236.2464 | 1.1 | 2494.0242 | 0.4763 | 9.163
1786 | 1692.8813 | 5859.5801 | 5554.0725 | 1.03 | 2477.0608 | 0.44599 | 8.5799
2274 | 2138.8645 | 7460.6299 | 7017.272 | 1.03 | 3129.6331 | 0.44599 | 8.5799
2610 | 2445.9349 | 8562.9921 | 8024.7208 | 1.03 | 3578.9452 | 0.44599 | 8.5799
2626 | 2460.5573 | 8615.4856 | 8072.6946 | 0.88 | 3076.0195 | 0.38104 | 7.3304
2770 | 2592.1589 | 9087.9265 | 8504.4583 | 1.3 | 4787.1596 | 0.5629 | 10.829
3064 | 2860.8455 | 10052.4934 | 9385.976 | 1.2 | 4876.9532 | 0.5196 | 9.996
3195 | 2980.5664 | 10482.2835 | 9778.7612 | 1.28 | 5419.7806 | 0.55424 | 10.6624
3417.5 | 3183.9092 | 11212.2703 | 10445.8962 | 1.08 | 4884.9189 | 0.46764 | 8.9964
3510 | 3268.4449 | 11515.748 | 10723.2444 | 1.08 | 5014.618 | 0.46764 | 8.9964

## MudWeight
MD | TVD | MD | TVD | Mud Weight
(m) | (m) | (ft) | (ft) | SG | psi | psi/ft | ppg
1188 | 1146.3691 | 3897.6378 | 3761.0535 | 1.03 | 1677.3922 | 0.44599 | 8.5799
1360 | 1303.5599 | 4461.9423 | 4276.7713 | 1.4 | 2592.5788 | 0.6062 | 11.662
1531 | 1459.8368 | 5022.9659 | 4789.4908 | 1.39 | 2882.6508 | 0.60187 | 11.5787
1584 | 1508.2735 | 5196.8504 | 4948.4039 | 1.39 | 2978.2958 | 0.60187 | 11.5787
1640 | 1559.4519 | 5380.5774 | 5116.312 | 1.4 | 3101.5083 | 0.6062 | 11.662
1669 | 1585.955 | 5475.7218 | 5203.2644 | 1.4 | 3154.2189 | 0.6062 | 11.662
1750 | 1659.9809 | 5741.4698 | 5446.1316 | 1.4 | 3301.445 | 0.6062 | 11.662
1765 | 1673.6894 | 5790.6824 | 5491.107 | 1.4 | 3328.709 | 0.6062 | 11.662
1867 | 1766.9072 | 6125.3281 | 5796.9396 | 1.4 | 3514.1048 | 0.6062 | 11.662
2025 | 1911.3034 | 6643.7008 | 6270.6804 | 1.4 | 3801.2865 | 0.6062 | 11.662
2111 | 1989.8988 | 6925.853 | 6528.5394 | 1.4 | 3957.6006 | 0.6062 | 11.662
2250 | 2116.9309 | 7381.8898 | 6945.3114 | 1.4 | 4210.2477 | 0.6062 | 11.662
2327 | 2187.3012 | 7634.5144 | 7176.185 | 1.41 | 4381.2763 | 0.61053 | 11.7453
2385 | 2240.3074 | 7824.8031 | 7350.0899 | 1.4 | 4455.6245 | 0.6062 | 11.662
2479 | 2326.214 | 8133.2021 | 7631.9357 | 1.41 | 4659.5257 | 0.61053 | 11.7453
2597 | 2434.0542 | 8520.3412 | 7985.7421 | 1.4 | 4840.9569 | 0.6062 | 11.662
2690 | 2519.0469 | 8825.4593 | 8264.5896 | 1.41 | 5045.7799 | 0.61053 | 11.7453
2752 | 2575.7087 | 9028.8714 | 8450.4879 | 1.4 | 5122.6857 | 0.6062 | 11.662
2765 | 2587.5894 | 9071.5223 | 8489.4665 | 1.41 | 5183.074 | 0.61053 | 11.7453
2770 | 2592.1589 | 9087.9265 | 8504.4583 | 1.4 | 5155.4026 | 0.6062 | 11.662
3005 | 2806.9254 | 9858.9239 | 9209.0728 | 1.45 | 5781.9164 | 0.62785 | 12.0785
3025 | 2825.2034 | 9924.5407 | 9269.04 | 1.45 | 5819.5668 | 0.62785 | 12.0785
3058 | 2855.3621 | 10032.8084 | 9367.9859 | 1.4 | 5678.873 | 0.6062 | 11.662
3103 | 2896.4876 | 10180.4462 | 9502.9121 | 1.45 | 5966.4033 | 0.62785 | 12.0785
3231 | 3013.4668 | 10600.3937 | 9886.7021 | 1.45 | 6207.3659 | 0.62785 | 12.0785
3323 | 3097.5456 | 10902.231 | 10162.5512 | 1.4 | 6160.5385 | 0.6062 | 11.662
3467 | 3229.1472 | 11374.6719 | 10594.315 | 1.45 | 6651.6406 | 0.62785 | 12.0785
3508 | 3266.6171 | 11509.1864 | 10717.2477 | 1.43 | 6636.0126 | 0.61919 | 11.9119
3510 | 3268.4449 | 11515.748 | 10723.2444 | 1.46 | 6779.0207 | 0.63218 | 12.1618

## Drilling Parameters
Depth | TVD | ROP | WOB | Torque | RPm | SPP | Flow pumps | Tot Gas | mW IN | D Exp
m | m | m/hr | tons | kNm | rpm | bar | l/min | % | kg/l | ....
150
155
160
165
170
175
180
185
190
195
200
205
210
215
220
225
230
235
240
245
250
255 | 255 | 101.54 | 6.63 | 1.38 | 150 | 86.4 | 3675 | 0 | 1.03 | 0.66
260 | 260 | 78.68 | 5.52 | 4.8 | 150 | 91.9 | 3675 | 0 | 1.03 | 0.7
265 | 265 | 45.84 | 2.39 | 3.58 | 150 | 90.5 | 3675 | 0 | 1.03 | 0.68
270 | 270 | 37.43 | 2.46 | 4.16 | 150 | 90.9 | 3675 | 0 | 1.03 | 0.72
275 | 275 | 28.63 | 2.47 | 3.4 | 138 | 77.9 | 3278 | 0 | 1.03 | 0.89
280 | 280 | 39.47 | 2.28 | 3.88 | 150 | 89.8 | 3675 | 0 | 1.03 | 0.7
285 | 285 | 33.64 | 2.64 | 4.03 | 150 | 90.2 | 3675 | 0 | 1.03 | 0.75
290 | 290 | 26.07 | 2.07 | 2.3 | 135 | 86.5 | 3627 | 0 | 1.03 | 0.81
295 | 295 | 36.33 | 2.22 | -9.47 | 110 | 89.4 | 3674 | 0 | 1.03 | 0.67
300 | 300 | 48.15 | 3.47 | 7.07 | 110 | 91.4 | 3674 | 0 | 1.03 | 0.67
305 | 305 | 54.88 | 2.77 | 14.96 | 110 | 89.9 | 3674 | 0 | 1.03 | 0.61
310 | 310 | 56.55 | 1.87 | 14.95 | 110 | 88.3 | 3674 | 0 | 1.03 | 0.57
315 | 315 | 59.9 | 2.08 | 8.1 | 132 | 90 | 3674 | 0 | 1.03 | 0.6
320 | 320 | 61.96 | 1.92 | 2.01 | 150 | 88.3 | 3674 | 0 | 1.03 | 0.61
325 | 325 | 59.64 | 1.94 | -0.64 | 129 | 87.9 | 3674 | 0 | 1.03 | 0.59
330 | 330 | 52.5 | 3.64 | -0.51 | 110 | 91.6 | 3674 | 0 | 1.03 | 0.66
335 | 335 | 49.13 | 3.07 | 3.79 | 110 | 90.2 | 3674 | 0 | 1.03 | 0.64
340 | 340 | 48.58 | 1.69 | 3.89 | 131 | 89.6 | 3675 | 0 | 1.03 | 0.62
345 | 345 | 36.32 | 1.57 | 3.39 | 116 | 92.6 | 3674 | 0 | 1.03 | 0.63
350 | 350 | 46.31 | 1 | 5.03 | 110 | 92 | 3674 | 0 | 1.03 | 0.55
355 | 355 | 51.32 | 0.32 | 5.21 | 110 | 89.8 | 3674 | 0 | 1.03 | 0.46
360 | 360 | 51.41 | 0.08 | 5.22 | 110 | 89.1 | 3674 | 0 | 1.03 | 0.39
365 | 365 | 51.86 | 0.01 | 5.28 | 110 | 88.8 | 3674 | 0 | 1.03 | 0.32
370 | 370 | 42.2 | 0.01 | 3.02 | 146 | 86.5 | 3586 | 0 | 1.03 | 0.41
375 | 375 | 49.25 | 0.01 | -1.01 | 121 | 88.9 | 3674 | 0 | 1.03 | 0.33
380 | 380 | 31.31 | 0.04 | 0.11 | 98 | 71.9 | 3251 | 0 | 1.03 | 0.43
385 | 385 | 21.49 | 0.01 | 0.01 | 90 | 61 | 2987 | 0 | 1.03 | 0.38
390 | 390 | 22.86 | 0.01 | 0.01 | 90 | 60.2 | 2987 | 0 | 1.03 | 0.37
395 | 394.99 | 31.71 | 0.01 | 0.01 | 90 | 58.6 | 2988 | 0 | 1.03 | 0.34
400 | 399.99 | 36.14 | 0.01 | 0.01 | 90 | 59 | 2988 | 0 | 1.03 | 0.33
405 | 404.98 | 46.95 | 2.54 | 0.01 | 90 | 59.9 | 2984 | 0 | 1.03 | 0.6
410 | 409.98 | 47.47 | 3.72 | 0.01 | 90 | 62.6 | 2988 | 0 | 1.03 | 0.64
415 | 414.97 | 47.29 | 3.64 | 0.01 | 90 | 61.8 | 2987 | 0 | 1.03 | 0.63
420 | 419.96 | 40.17 | 1.6 | 4.61 | 90 | 63.8 | 2988 | 0 | 1.03 | 0.49
425 | 424.96 | 33.53 | 0.86 | 2.03 | 90 | 64.8 | 2987 | 0 | 1.03 | 0.53
430 | 429.95 | 28.88 | 3.7 | 0.13 | 90 | 66.4 | 2987 | 0 | 1.03 | 0.73
435 | 434.94 | 21.18 | 5.2 | 0.12 | 90 | 68.1 | 2987 | 0 | 1.03 | 0.83
440 | 439.94 | 22.22 | 6.02 | 0.12 | 90 | 68.3 | 2987 | 0 | 1.03 | 0.85
445 | 444.93 | 16.08 | 5.91 | 0.13 | 90 | 68 | 2987 | 0 | 1.03 | 0.91
450 | 449.92 | 16.21 | 5.7 | 0.12 | 90 | 67.8 | 2987 | 0 | 1.03 | 0.9
455 | 454.92 | 15.96 | 5.32 | 0.14 | 90 | 67.5 | 2987 | 0 | 1.03 | 0.89
460 | 459.91 | 29.15 | 3.73 | 3.1 | 135 | 97.3 | 3707 | 0 | 1.03 | 0.81
465 | 464.91 | 34.78 | 4.14 | 5.47 | 175 | 134.3 | 4497 | 0 | 1.03 | 0.83
470 | 469.9 | 30.65 | 4.33 | 5.42 | 175 | 134.8 | 4503 | 0 | 1.03 | 0.86
475 | 474.88 | 25.14 | 4.87 | 5.75 | 142 | 87.1 | 3400 | 0 | 1.03 | 0.88
480 | 479.86 | 16.36 | 4.75 | 2.53 | 90 | 67.7 | 2987 | 0 | 1.03 | 0.86
485 | 484.83 | 16.57 | 4.98 | 2.76 | 90 | 68 | 2987 | 0 | 1.03 | 0.87
490 | 489.8 | 15.77 | 5.27 | 2.76 | 90 | 68.7 | 2987 | 0 | 1.03 | 0.89
495 | 494.77 | 16.49 | 5.08 | 2.76 | 90 | 68.2 | 2987 | 0 | 1.03 | 0.87
500 | 499.74 | 20.88 | 3.61 | 4.97 | 118 | 76.9 | 3200 | 0 | 1.03 | 0.84
505 | 504.71 | 31.12 | 7.84 | 6.81 | 172 | 131.2 | 4414 | 0 | 1.03 | 0.96
510 | 509.68 | 18.33 | 5.15 | 4.58 | 174 | 131 | 4458 | 0 | 1.03 | 0.98
515 | 514.64 | 15.14 | 5.11 | 2.4 | 112 | 82.5 | 3377 | 0 | 1.03 | 0.94
520 | 519.6 | 11.86 | 5.8 | 3.4 | 97 | 75.8 | 3219 | 0 | 1.03 | 0.98
525 | 524.55 | 14.03 | 6 | 3.65 | 105 | 86.9 | 3500 | 0 | 1.03 | 0.96
530 | 529.5 | 27.47 | 6.97 | 6.48 | 171 | 133.3 | 4446 | 0 | 1.03 | 0.96
535 | 534.46 | 29.42 | 6.58 | 6.36 | 175 | 135.9 | 4502 | 0 | 1.03 | 0.94
540 | 539.41 | 23.36 | 6.08 | 5.8 | 172 | 131.1 | 4399 | 0 | 1.03 | 1
545 | 544.37 | 26.77 | 6.35 | 6.37 | 175 | 136.9 | 4502 | 0 | 1.03 | 0.95
550 | 549.32 | 24.58 | 5.91 | 5.65 | 170 | 136.4 | 4502 | 0 | 1.03 | 0.95
555 | 554.28 | 33.27 | 8.4 | 2.92 | 135 | 139.8 | 4502 | 0 | 1.03 | 0.91
560 | 559.25 | 35.79 | 8.84 | 4.36 | 135 | 140.6 | 4502 | 0 | 1.03 | 0.9
565 | 564.21 | 35.78 | 9.87 | 5.12 | 135 | 143 | 4502 | 0 | 1.03 | 0.92
570 | 569.18 | 32.82 | 10.94 | 5.46 | 106 | 101.6 | 3524 | 0 | 1.03 | 0.91
575 | 574.14 | 42.78 | 7.71 | 8.18 | 194 | 140.5 | 4502 | 0 | 1.03 | 0.91
580 | 579.1 | 40.1 | 7.01 | 7.97 | 190 | 135.1 | 4410 | 0 | 1.03 | 1.02
585 | 584.07 | 45.8 | 8.49 | 4.2 | 152 | 142.6 | 4501 | 0 | 1.03 | 0.87
590 | 589.03 | 42.17 | 8.94 | 4.42 | 135 | 142 | 4501 | 0 | 1.03 | 0.87
595 | 594 | 41.28 | 8.89 | 4.44 | 135 | 142.1 | 4501 | 0 | 1.03 | 0.87
600 | 598.98 | 45 | 10 | 5.14 | 135 | 144.2 | 4501 | 0 | 1.03 | 0.87
605 | 603.96 | 44.51 | 7.64 | 7.4 | 168 | 124.5 | 4123 | 0 | 1.03 | 0.89
610 | 608.94 | 48.68 | 8.3 | 9.58 | 197 | 133.4 | 4231 | 0 | 1.03 | 0.9
615 | 613.92 | 41.45 | 8.04 | 4.78 | 176 | 142 | 4501 | 0 | 1.03 | 0.91
620 | 618.9 | 35.21 | 9.33 | 0.59 | 135 | 145.1 | 4501 | 0 | 1.03 | 0.94
625 | 623.88 | 39.03 | 10.49 | 6.27 | 135 | 148.2 | 4501 | 0 | 1.03 | 0.91
630 | 628.85 | 38.36 | 11.3 | 6.57 | 135 | 149.2 | 4501 | 0 | 1.03 | 0.93
635 | 633.83 | 31.9 | 9.91 | 6.32 | 137 | 143.5 | 4408 | 0 | 1.03 | 0.97
640 | 638.81 | 48.18 | 10.03 | 13.22 | 201 | 146.5 | 4376 | 0 | 1.03 | 0.95
645 | 643.79 | 43.49 | 9.81 | 9.16 | 183 | 148.8 | 4501 | 0 | 1.03 | 0.95
650 | 648.76 | 33.93 | 12.06 | 6.69 | 135 | 149.5 | 4501 | 0 | 1.03 | 0.97
655 | 653.74 | 33.43 | 11.81 | 6.7 | 135 | 150.4 | 4501 | 0 | 1.03 | 0.97
660 | 658.72 | 31.41 | 11.17 | 4.38 | 133 | 145.4 | 4425 | 0 | 1.03 | 0.98
665 | 663.7 | 40.2 | 12.64 | 0 | 135 | 152 | 4501 | 0 | 1.03 | 0.95
670 | 668.67 | 40.48 | 12.26 | 0 | 135 | 151.3 | 4501 | 0 | 1.03 | 0.94
675 | 673.65 | 42.45 | 8.52 | 10.1 | 183 | 134.3 | 4168 | 0 | 1.03 | 0.94
680 | 678.62 | 43.5 | 9.02 | 3.19 | 153 | 148.7 | 4501 | 0 | 1.03 | 0.89
685 | 683.59 | 45.65 | 9.59 | 0.12 | 135 | 147 | 4501 | 0 | 1.03 | 0.86
690 | 688.56 | 48.81 | 10.39 | 1.78 | 135 | 149 | 4501 | 0 | 1.03 | 0.86
695 | 693.53 | 46.4 | 9.93 | 5.71 | 135 | 148.7 | 4501 | 0 | 1.03 | 0.87
700 | 698.5 | 38.62 | 9.51 | 4.28 | 133 | 145 | 4433 | 0 | 1.03 | 0.92
705 | 703.46 | 51.24 | 10.45 | 0.53 | 135 | 152.2 | 4501 | 0 | 1.03 | 0.85
710 | 708.43 | 45.2 | 11.05 | 7.03 | 135 | 153.2 | 4501 | 0 | 1.03 | 0.89
715 | 713.4 | 40.31 | 7.28 | 11.33 | 192 | 139.8 | 4317 | 0 | 1.03 | 0.94
720 | 718.37 | 33.12 | 7.96 | 8.95 | 174 | 145.3 | 4412 | 0 | 1.03 | 0.95
725 | 723.33 | 29.76 | 10.94 | 7.58 | 135 | 150.8 | 4501 | 0 | 1.03 | 0.98
730 | 728.3 | 30.45 | 10.96 | 7.12 | 135 | 152.2 | 4501 | 0 | 1.03 | 0.98
735 | 733.26 | 30.23 | 10.87 | 6.92 | 135 | 152.3 | 4501 | 0 | 1.03 | 0.98
740 | 738.23 | 28.34 | 9.43 | 7.87 | 151 | 150.6 | 4499 | 0 | 1.03 | 1.02
745 | 743.19 | 47.43 | 6.64 | 12.01 | 205 | 148.7 | 4501 | 0 | 1.03 | 0.88
750 | 748.16 | 40.16 | 7.13 | 1.87 | 148 | 147.4 | 4501 | 0 | 1.03 | 0.86
755 | 753.12 | 35.27 | 8.76 | 4.13 | 135 | 149.5 | 4501 | 0 | 1.03 | 0.9
760 | 758.06 | 38.14 | 9.14 | 5.68 | 135 | 149.7 | 4501 | 0 | 1.03 | 0.89
765 | 763 | 37.68 | 9.1 | 6.5 | 135 | 150.9 | 4501 | 0 | 1.03 | 0.89
770 | 767.93 | 30.36 | 9.98 | 6.62 | 129 | 143.5 | 4294 | 0 | 1.03 | 0.95
775 | 772.87 | 36.94 | 6.48 | 8.51 | 172 | 148.6 | 4501 | 0 | 1.03 | 0.9
780 | 777.81 | 33.46 | 4.79 | 4.49 | 158 | 145.8 | 4501 | 0 | 1.03 | 0.86
785 | 782.75 | 35.83 | 7.78 | 5.36 | 135 | 151.4 | 4501 | 0 | 1.03 | 0.88
790 | 787.69 | 35.8 | 7.73 | 6.25 | 135 | 152 | 4501 | 0 | 1.03 | 0.88
795 | 792.63 | 39.4 | 7.79 | 5.98 | 135 | 152.1 | 4501 | 0 | 1.03 | 0.86
800 | 797.52 | 39.73 | 8.42 | 6.24 | 135 | 153.9 | 4501 | 0 | 1.03 | 0.87
805 | 802.42 | 47.92 | 7.79 | 5.76 | 135 | 152.9 | 4501 | 0 | 1.03 | 0.82
810 | 807.31 | 43.58 | 6.27 | 8.73 | 165 | 147.7 | 4409 | 0 | 1.03 | 0.86
815 | 812.2 | 33.28 | 8.71 | 8.86 | 167 | 149.8 | 4370 | 0 | 1.03 | 0.97
820 | 817.1 | 26.05 | 8.66 | 6.16 | 133 | 149.2 | 4437 | 0 | 1.03 | 1
825 | 821.99 | 30.23 | 6.5 | 2.32 | 134 | 151.7 | 4454 | 0 | 1.03 | 0.88
830 | 826.88 | 39.2 | 7.48 | 6.62 | 135 | 154.3 | 4501 | 0 | 1.03 | 0.86
835 | 831.78 | 39.66 | 8.39 | 6.59 | 135 | 155.8 | 4501 | 0 | 1.03 | 0.88
840 | 836.63 | 32.52 | 6.46 | 9.35 | 176 | 164 | 4660 | 0 | 1.03 | 0.92
845 | 841.47 | 37.76 | 4.77 | 12.3 | 205 | 154.7 | 4541 | 0 | 1.03 | 0.87
850 | 846.31 | 38.24 | 5.15 | 4.36 | 141 | 164.2 | 4700 | 0 | 1.03 | 0.8
855 | 851.15 | 27.85 | 6.9 | 6.1 | 150 | 185.9 | 5011 | 0 | 1.03 | 0.93
860 | 855.99 | 25.63 | 5.94 | 5.24 | 145 | 173.7 | 4825 | 0 | 1.03 | 0.96
865 | 860.83 | 27.98 | 13.27 | 0.01 | 150 | 187.5 | 5011 | 0 | 1.03 | 1.07
870 | 865.67 | 26.71 | 16.29 | 0.01 | 150 | 187.9 | 5011 | 0 | 1.03 | 1.13
875 | 870.51 | 27.48 | 15.94 | 3.61 | 168 | 188.3 | 5011 | 0 | 1.03 | 1.15
880 | 875.34 | 38.9 | 15.87 | 15.26 | 220 | 189.7 | 5010 | 0 | 1.03 | 1.13
885 | 880.17 | 23.89 | 13.51 | 2.45 | 161 | 183.6 | 5010 | 0 | 1.03 | 1.12
890 | 885 | 71.33 | 9.05 | 0.38 | 136 | 155.1 | 4541 | 0 | 1.03 | 0.91
895 | 889.83 | 68.08 | 10.55 | 1.74 | 101 | 98.1 | 3378 | 0 | 1.03 | 1.04
900 | 894.66 | 21.52 | 12.92 | 6.08 | 150 | 184.2 | 5011 | 0 | 1.03 | 1.14
905 | 899.49 | 92.4 | 0.17 | -0.2 | 110 | 99.1 | 3663 | 0 | 1.03 | 0.4
910 | 904.32 | 156.95 | 1.57 | -0.34 | 100 | 85.2 | 3337 | 0 | 1.03 | 0.38
915 | 909.14 | 124.82 | 5.12 | 1.16 | 100 | 90.2 | 3338 | 0 | 1.03 | 0.59
920 | 913.99 | 125.4 | 0.25 | 0.95 | 100 | 83.2 | 3337 | 0 | 1.03 | 0.32
925 | 918.85 | 165.31 | 6.37 | 0.96 | 100 | 91.6 | 3337 | 0 | 1.03 | 0.48
930 | 923.71 | 201.02 | 4.47 | 1.51 | 100 | 89.5 | 3338 | 0 | 1.03 | 0.41
935 | 928.57 | 172.25 | 10.37 | 3.88 | 100 | 98.8 | 3337 | 0 | 1.03 | 0.52
940 | 933.43 | 154.78 | 11.63 | 4.74 | 100 | 101 | 3338 | 0 | 1.03 | 0.56
945 | 938.3 | 105.43 | 4.12 | 0.08 | 94 | 89.8 | 3095 | 0 | 1.03 | 0.84
950 | 943.16 | 102.75 | 4.98 | -0.66 | 91 | 82.1 | 3040 | 0 | 1.03 | 0.55
955 | 948.02 | 132.24 | 2.41 | 2.67 | 90 | 76.1 | 2982 | 0 | 1.03 | 0.42
960 | 952.87 | 117.96 | 6.11 | 0.83 | 90 | 81.2 | 2981 | 0 | 1.03 | 0.59
965 | 957.71 | 93.72 | 8.23 | 3.93 | 89 | 87.8 | 2981 | 0 | 1.03 | 0.64
970 | 962.55 | 96.37 | 8.15 | 5 | 90 | 86.1 | 2981 | 0 | 1.03 | 0.6
975 | 967.39 | 98.69 | 5.48 | 0.71 | 90 | 80.7 | 2981 | 0 | 1.03 | 0.65
980 | 972.23 | 104.03 | 4.93 | 2.76 | 90 | 80.7 | 2981 | 0 | 1.03 | 0.64
985 | 977.07 | 76.63 | 6.2 | -0.46 | 83 | 79.8 | 2748 | 0 | 1.03 | 0.87
990 | 981.91 | 109.68 | 3.52 | 2.63 | 90 | 81.7 | 2981 | 0 | 1.03 | 0.54
995 | 986.75 | 110.23 | 3.4 | 3.35 | 89 | 81.9 | 2982 | 0 | 1.03 | 0.51
1000 | 991.58 | 123.09 | 2.37 | -0.15 | 90 | 78.9 | 2982 | 0 | 1.03 | 0.43
1005 | 996.4 | 118.99 | 2.74 | -0.32 | 89 | 79 | 2982 | 0 | 1.03 | 0.45
1010 | 1001.22 | 114.94 | 3.8 | 0.15 | 89 | 79.3 | 2982 | 0 | 1.03 | 0.48
1015 | 1006.04 | 56.15 | 8.03 | 3.06 | 90 | 85.8 | 2982 | 0 | 1.03 | 0.91
1020 | 1010.86 | 110.22 | 5.88 | 5.98 | 90 | 81.6 | 2982 | 0 | 1.03 | 0.53
1025 | 1015.68 | 71.59 | 4.11 | 0.82 | 88 | 82.3 | 2936 | 0 | 1.03 | 0.68
1030 | 1020.51 | 115.57 | 4.43 | 0.15 | 89 | 82.4 | 2982 | 0 | 1.03 | 0.49
1035 | 1025.33 | 112.99 | 4.28 | 0.72 | 90 | 82.8 | 2982 | 0 | 1.03 | 0.49
1040 | 1030.16 | 103.33 | 3.07 | 1.23 | 89 | 80.8 | 2982 | 0 | 1.03 | 0.48
1045 | 1035.01 | 68.79 | 3.88 | 1.24 | 89 | 83.1 | 2982 | 0 | 1.03 | 0.64
1050 | 1039.85 | 85.37 | 6.21 | 1.23 | 89 | 88.9 | 2982 | 0 | 1.03 | 0.58
1055 | 1044.7 | 88.97 | 4.05 | 1.69 | 91 | 84.9 | 3020 | 0 | 1.03 | 0.55
1060 | 1049.54 | 104.69 | 2.3 | 0.99 | 100 | 95.4 | 3338 | 0 | 1.03 | 0.48
1065 | 1054.39 | 84.43 | 2.01 | 1.87 | 100 | 95.4 | 3338 | 0 | 1.03 | 0.53
1070 | 1059.23 | 162.68 | 0.26 | 0 | 100 | 91.4 | 3338 | 0 | 1.03 | 0.3
1075 | 1064.08 | 117 | 1.74 | 0 | 100 | 94.1 | 3338 | 0 | 1.03 | 0.46
1080 | 1068.92 | 63.68 | 4.9 | 2.55 | 100 | 98.5 | 3338 | 0 | 1.03 | 0.86
1085 | 1073.78 | 16.27 | 10.96 | 6.24 | 123 | 147.4 | 4105 | 0 | 1.03 | 1.13
1090 | 1078.63 | 24.44 | 13.05 | 6.81 | 154 | 198.3 | 5011 | 0 | 1.03 | 1.1
1095 | 1083.49 | 31.63 | 12.51 | 6.65 | 150 | 197.6 | 5011 | 0 | 1.03 | 1.04
1100 | 1088.34 | 30.19 | 11.89 | 6.14 | 150 | 194.1 | 5011 | 0 | 1.03 | 1.02
1105 | 1093.19 | 26.65 | 10 | 8.12 | 168 | 191.8 | 5011 | 0 | 1.03 | 1.08
1110 | 1098.05 | 32.9 | 2.85 | 11.79 | 203 | 185.2 | 5011 | 0 | 1.03 | 0.89
1115 | 1102.9 | 17.04 | 7.75 | 7.1 | 145 | 177.5 | 4835 | 0 | 1.03 | 1.15
1120 | 1107.73 | 17.11 | 5.3 | 5.69 | 150 | 186 | 5011 | 0 | 1.03 | 1.02
1125 | 1112.54 | 22.98 | 8.76 | 4.32 | 150 | 186 | 5010 | 0 | 1.03 | 1.01
1130 | 1117.34 | 22.36 | 11.85 | 3.79 | 150 | 185.2 | 5004 | 0 | 1.03 | 1.11
1135 | 1122.14 | 22.06 | 12.59 | 4.8 | 136 | 163.7 | 4535 | 0 | 1.03 | 1.09
1140 | 1126.94 | 26.07 | 12.33 | 4.89 | 150 | 189.6 | 5011 | 0 | 1.03 | 1.07
1145 | 1131.75 | 30.03 | 8.69 | 8.54 | 150 | 188.8 | 5011 | 0 | 1.03 | 1.01
1150 | 1136.55 | 35.44 | 9.88 | 6.92 | 141 | 171.8 | 4704 | 0 | 1.03 | 0.96
1155 | 1141.35 | 37.71 | 12.16 | 2.49 | 136 | 163.1 | 4542 | 0 | 1.03 | 0.95
1160 | 1146.1 | 34 | 13.32 | 5.38 | 136 | 164.1 | 4542 | 0 | 1.03 | 1
1165 | 1150.8 | 35.67 | 13.71 | 5.83 | 131 | 157.3 | 4378 | 0 | 1.03 | 0.99
1170 | 1155.51 | 38.56 | 13.69 | 5.61 | 132 | 163.3 | 4412 | 0 | 1.03 | 0.97
1175 | 1160.22 | 39.73 | 12.41 | 6.05 | 136 | 165.1 | 4542 | 0 | 1.03 | 0.97
1180 | 1164.92 | 54.81 | 7.36 | 14.48 | 136 | 166.5 | 4542 | 0 | 1.03 | 0.78
1185 | 1169.63 | 39.06 | 7.56 | 7.44 | 140 | 172.1 | 4655 | 0 | 1.03 | 0.89
1190 | 1174.34 | 37.76 | 9.78 | 0.01 | 150 | 192 | 5011 | 0 | 1.03 | 0.93
1195 | 1179.05 | 38.63 | 9.97 | 2.82 | 150 | 192.2 | 5011 | 0 | 1.03 | 0.93
1200 | 1183.75 | 29.64 | 6.35 | 7.95 | 147 | 187.7 | 4891 | 0 | 1.03 | 0.91
1205 | 1188.46 | 51.89 | 4.15 | 13.92 | 160 | 214.5 | 5345 | 0 | 1.03 | 0.74
1210 | 1193.16 | 55.04 | 6.46 | 14.04 | 160 | 213.7 | 5345 | 0 | 1.03 | 0.79
1215 | 1197.87 | 55.34 | 11.91 | 15.72 | 160 | 216 | 5345 | 0 | 1.03 | 0.9
1220 | 1202.57 | 52.67 | 11.68 | 14.54 | 160 | 215.7 | 5345 | 0 | 1.03 | 0.91
1225 | 1207.27 | 43.97 | 5.13 | 11.11 | 155 | 198.9 | 5178 | 0 | 1.03 | 0.83
1230 | 1211.98 | 61.46 | 7.11 | 13.2 | 160 | 212.8 | 5345 | 0 | 1.03 | 0.79
1235 | 1216.68 | 62.51 | 9 | 14.27 | 160 | 215 | 5344 | 0 | 1.03 | 0.82
1240 | 1221.39 | 46.2 | 8.27 | 12.84 | 143 | 181.7 | 4771 | 0 | 1.03 | 0.93
1245 | 1226.11 | 43.16 | 5.81 | 0.9 | 160 | 205.7 | 5344 | 0 | 1.03 | 0.87
1250 | 1230.83 | 104.59 | 3.01 | 1.69 | 136 | 154.4 | 4521 | 0 | 1.03 | 0.55
1255 | 1235.55 | 13.45 | 10.48 | 2.74 | 120 | 131.4 | 4008 | 0 | 1.03 | 1.12
1260 | 1240.28 | 19.04 | 11.27 | 3.51 | 120 | 131.7 | 4008 | 0 | 1.03 | 1.07
1265 | 1245 | 17.93 | 11.53 | 2.87 | 118 | 128.1 | 3940 | 0 | 1.03 | 1.1
1270 | 1249.72 | 26.62 | 12.2 | 0.2 | 120 | 133.4 | 4008 | 0 | 1.03 | 1.01
1275 | 1254.44 | 31.17 | 13.35 | 4.96 | 120 | 135.1 | 4008 | 0 | 1.03 | 0.99
1280 | 1259.19 | 40.64 | 9.54 | 5.23 | 118 | 128.2 | 3932 | 0 | 1.03 | 0.89
1285 | 1263.94 | 127.05 | 0.03 | 7.64 | 102 | 95.1 | 3387 | 0 | 1.03 | 0.26
1290 | 1268.68 | 79.15 | 1.27 | 5.5 | 104 | 100.8 | 3463 | 0 | 1.03 | 0.51
1295 | 1273.43 | 102.23 | 2.17 | 1.87 | 120 | 124.2 | 4008 | 0 | 1.03 | 0.5
1300 | 1278.18 | 121.69 | 1.85 | 1.88 | 120 | 124.4 | 4008 | 0 | 1.03 | 0.46
1305 | 1282.93 | 96.59 | 1.91 | 0.77 | 120 | 124.8 | 4008 | 0 | 1.03 | 0.55
1310 | 1287.68 | 139.97 | 1.48 | -1.49 | 120 | 125.6 | 4008 | 0 | 1.03 | 0.43
1315 | 1292.43 | 115.14 | 2.09 | -1.51 | 120 | 126.5 | 4008 | 0 | 1.03 | 0.48
1320 | 1297.24 | 126.92 | 1.89 | -1.49 | 120 | 126.9 | 4008 | 0 | 1.03 | 0.46
1325 | 1302.05 | 101.27 | 1.77 | -1.5 | 120 | 127.1 | 4008 | 0 | 1.03 | 0.49
1330 | 1306.86 | 93.62 | 1.94 | -1.5 | 105 | 103.2 | 3485 | 0 | 1.03 | 0.49
1335 | 1311.67 | 38.21 | 6.8 | 0.94 | 105 | 108.3 | 3493 | 0 | 1.03 | 0.99
1340 | 1316.48 | 19.19 | 8.64 | 3 | 120 | 135 | 4008 | 0 | 1.03 | 1.02
1345 | 1321.29 | 42.03 | 7.92 | 2.05 | 120 | 135.8 | 4008 | 0 | 1.03 | 0.95
1350 | 1326.11 | 22.18 | 12.39 | 5.02 | 120 | 140.6 | 4008 | 0 | 1.03 | 1.14
1355 | 1330.92 | 14.04 | 8.76 | 2.45 | 128 | 149.5 | 4258 | 0 | 1.03 | 1.08
1360 | 1335.74 | 13.99 | 9.73 | 2.12 | 150 | 193.7 | 5011 | 0 | 1.03 | 1.15
1365 | 1340.56 | 13.43 | 6.87 | 2.72 | 148 | 186.6 | 4930 | 0 | 1.03 | 1.14
1370 | 1345.37 | 15.55 | 7.07 | 7.58 | 125 | 150.6 | 4008 | 0.07 | 1.16 | 0.85
1375 | 1350.17 | 7.03 | 1.85 | 14.44 | 90 | 140.7 | 3166 | 0.29 | 1.35 | 0.74
1380 | 1354.97 | 15.44 | 1.99 | 15.4 | 110 | 232 | 4539 | 0.28 | 1.36 | 0.63
1385 | 1359.77 | 19.01 | 3.12 | 15 | 119 | 233.6 | 4544 | 0.31 | 1.36 | 0.72
1390 | 1364.57 | 19.88 | 3.65 | 15.75 | 120 | 233.6 | 4544 | 0.22 | 1.36 | 0.68
1395 | 1369.36 | 16.28 | 4.21 | 15.61 | 118 | 233.5 | 4544 | 0.25 | 1.36 | 0.73
1400 | 1374.13 | 45.8 | 7.96 | 20.91 | 112 | 238.5 | 4544 | 0.37 | 1.36 | 0.65
1405 | 1378.9 | 36.32 | 7.21 | 20.43 | 113 | 237.4 | 4544 | 0.18 | 1.36 | 0.68
1410 | 1383.64 | 37.56 | 5.68 | 17.87 | 120 | 235.7 | 4544 | 0.4 | 1.36 | 0.65
1415 | 1388.35 | 28.69 | 3.19 | 16.57 | 120 | 223.5 | 4393 | 0.57 | 1.36 | 0.63
1420 | 1393.06 | 23.2 | 3.21 | 17 | 120 | 217.8 | 4323 | 0.45 | 1.36 | 0.65
1425 | 1397.77 | 38.16 | 2.29 | 16.8 | 115 | 222.6 | 4411 | 0.19 | 1.37 | 0.59
1430 | 1402.47 | 41.23 | 2.38 | 17.86 | 127 | 231.7 | 4544 | 0.14 | 1.37 | 0.54
1435 | 1407.18 | 39.58 | 3.39 | 18.87 | 122 | 231.7 | 4544 | 0.19 | 1.37 | 0.57
1440 | 1411.89 | 20.83 | 2.99 | 17.49 | 117 | 239.1 | 4544 | 0.29 | 1.38 | 0.66
1445 | 1416.6 | 21.31 | 2.33 | 16.12 | 130 | 238.9 | 4544 | 0.43 | 1.38 | 0.62
1450 | 1421.26 | 22.49 | 2.45 | 16.18 | 130 | 238.4 | 4544 | 0.47 | 1.38 | 0.62
1455 | 1425.9 | 23 | 2.56 | 16.36 | 130 | 237.9 | 4544 | 0.52 | 1.38 | 0.62
1460 | 1430.54 | 31.45 | 3.49 | 18.23 | 115 | 239 | 4544 | 0.6 | 1.38 | 0.6
1465 | 1435.18 | 31.52 | 3.6 | 17.99 | 120 | 239.3 | 4544 | 0.35 | 1.38 | 0.61
1470 | 1439.82 | 31.6 | 3.36 | 17.56 | 130 | 239.2 | 4544 | 0.63 | 1.38 | 0.61
1475 | 1444.46 | 34.33 | 3.22 | 17.43 | 142 | 239.5 | 4543 | 0.35 | 1.38 | 0.67
1480 | 1449.1 | 43.37 | 4.45 | 19.17 | 150 | 240.2 | 4544 | 0.39 | 1.38 | 0.62
1485 | 1453.74 | 43.27 | 4.87 | 19.04 | 150 | 240.1 | 4544 | 0.6 | 1.38 | 0.63
1490 | 1458.4 | 42.57 | 4.53 | 19.38 | 150 | 240 | 4544 | 0.8 | 1.38 | 0.62
1495 | 1463.05 | 42.94 | 4.88 | 19.51 | 150 | 239.9 | 4544 | 0.74 | 1.38 | 0.63
1500 | 1467.71 | 41.84 | 5.4 | 19.47 | 150 | 240.4 | 4544 | 0.58 | 1.38 | 0.65
1505 | 1472.36 | 45.32 | 5.04 | 18.48 | 180 | 240.2 | 4544 | 0.25 | 1.38 | 0.65
1510 | 1477.02 | 45.2 | 5.22 | 18.15 | 179 | 239.7 | 4544 | 0.2 | 1.38 | 0.66
1515 | 1481.68 | 37.7 | 4.44 | 16.63 | 175 | 239 | 4544 | 0.22 | 1.38 | 0.7
1520 | 1486.33 | 43.36 | 4.28 | 18.5 | 178 | 239.5 | 4544 | 0.23 | 1.38 | 0.64
1525 | 1490.99 | 42.95 | 4.93 | 19.58 | 179 | 245.2 | 4544 | 0.23 | 1.38 | 0.66
1530 | 1495.65 | 43.38 | 4.32 | 18.7 | 178 | 242.3 | 4544 | 0.23 | 1.39 | 0.64
1535 | 1500.32 | 44.64 | 4.43 | 19.16 | 177 | 242.4 | 4544 | 0.23 | 1.39 | 0.64
1540 | 1504.99 | 44.84 | 4.5 | 19 | 177 | 243.1 | 4544 | 0.23 | 1.39 | 0.64
1545 | 1509.66 | 43.68 | 4.52 | 18.67 | 178 | 242.7 | 4544 | 0.23 | 1.39 | 0.64
1550 | 1514.33 | 22.86 | 2.89 | 16.76 | 124 | 229 | 4298 | 0.18 | 1.39 | 0.7
1555 | 1519 | 18.62 | 2.96 | 15.85 | 139 | 247.3 | 4544 | 0.13 | 1.39 | 0.67
1560 | 1523.67 | 24.55 | 3.28 | 15.49 | 172 | 247.6 | 4544 | 0.22 | 1.39 | 0.71
1565 | 1528.34 | 25.8 | 3.54 | 16.58 | 177 | 247.7 | 4544 | 0.29 | 1.39 | 0.68
1570 | 1533 | 25.06 | 3.42 | 16.01 | 176 | 247.5 | 4543 | 0.33 | 1.39 | 0.68
1575 | 1537.64 | 24.2 | 3.64 | 16.67 | 176 | 247.3 | 4544 | 0.32 | 1.39 | 0.7
1580 | 1542.28 | 24.07 | 3.5 | 16.27 | 176 | 246.7 | 4544 | 0.38 | 1.39 | 0.69
1585 | 1546.92 | 23.96 | 3.6 | 16.59 | 177 | 246.8 | 4544 | 0.34 | 1.39 | 0.7
1590 | 1551.55 | 23.84 | 3.76 | 16.95 | 176 | 247.1 | 4544 | 0.39 | 1.39 | 0.7
1595 | 1556.19 | 23.98 | 3.7 | 16.78 | 177 | 247.8 | 4544 | 0.29 | 1.39 | 0.7
1600 | 1560.83 | 35.06 | 6.16 | 17.92 | 177 | 237.1 | 4466 | 0.33 | 1.4 | 0.78
1605 | 1565.47 | 35.71 | 4.56 | 19.75 | 178 | 235.8 | 4456 | 0.4 | 1.39 | 0.67
1610 | 1570.09 | 34.92 | 4.5 | 18.69 | 178 | 235.6 | 4456 | 0.45 | 1.39 | 0.67
1615 | 1574.7 | 33.02 | 4.06 | 18.44 | 177 | 235.3 | 4456 | 0.5 | 1.39 | 0.67
1620 | 1579.3 | 33.6 | 3.84 | 18.34 | 171 | 235.2 | 4456 | 0.51 | 1.39 | 0.65
1625 | 1583.91 | 33.61 | 4.69 | 19.21 | 173 | 205 | 4119 | 0.55 | 1.38 | 0.68
1630 | 1588.52 | 33.75 | 4.14 | 18.52 | 178 | 209.8 | 4183 | 0.18 | 1.39 | 0.67
1635 | 1593.12 | 33.69 | 3.36 | 17.09 | 177 | 234.1 | 4456 | 0.19 | 1.39 | 0.64
1640 | 1597.73 | 34.98 | 3.6 | 17.28 | 177 | 232.1 | 4456 | 0.34 | 1.39 | 0.66
1645 | 1602.33 | 41.66 | 3.78 | 17.66 | 177 | 230.9 | 4456 | 0.48 | 1.39 | 0.62
1650 | 1606.93 | 40.05 | 3.61 | 18.45 | 177 | 227.4 | 4396 | 0.4 | 1.39 | 0.62
1655 | 1611.52 | 39.36 | 3.81 | 18.28 | 177 | 200.8 | 4061 | 0.41 | 1.39 | 0.63
1660 | 1616.1 | 38.34 | 4.1 | 19.45 | 177 | 212.7 | 4213 | 0.54 | 1.39 | 0.65
1665 | 1620.68 | 38.69 | 4.6 | 19.37 | 177 | 231.4 | 4455 | 0.62 | 1.39 | 0.66
1670 | 1625.27 | 37.84 | 5.43 | 20.6 | 177 | 230.2 | 4455 | 0.59 | 1.39 | 0.69
1675 | 1629.85 | 39.05 | 4.95 | 20.9 | 177 | 227.6 | 4399 | 0.34 | 1.39 | 0.67
1680 | 1634.44 | 44.57 | 4.33 | 18.2 | 176 | 222.5 | 4299 | 0.51 | 1.39 | 0.71
1685 | 1639.02 | 46.65 | 4.95 | 19.71 | 177 | 236.5 | 4456 | 0.65 | 1.4 | 0.64
1690 | 1643.6 | 45.18 | 4.55 | 19.95 | 178 | 236.7 | 4456 | 0.46 | 1.39 | 0.64
1695 | 1648.18 | 43.85 | 4.71 | 20.31 | 178 | 236.5 | 4456 | 0.62 | 1.39 | 0.65
1700 | 1652.76 | 43.32 | 4.77 | 20.05 | 177 | 234.6 | 4455 | 0.71 | 1.39 | 0.65
1705 | 1657.34 | 43.39 | 4.84 | 20.4 | 178 | 234.9 | 4455 | 0.75 | 1.39 | 0.65
1710 | 1661.91 | 43.34 | 5.23 | 20.83 | 177 | 235.7 | 4455 | 0.61 | 1.39 | 0.66
1715 | 1666.49 | 42.81 | 4.77 | 20.15 | 178 | 235.8 | 4455 | 0.37 | 1.39 | 0.65
1720 | 1671.07 | 40.9 | 4.03 | 19.28 | 172 | 235.4 | 4416 | 0.62 | 1.4 | 0.67
1725 | 1675.65 | 52.04 | 5.32 | 22.07 | 178 | 240.2 | 4456 | 0.79 | 1.4 | 0.63
1730 | 1680.22 | 50.93 | 4.18 | 21.4 | 178 | 191.4 | 3773 | 0.82 | 1.4 | 0.6
1735 | 1684.8 | 48 | 4.65 | 21.71 | 178 | 236.3 | 4412 | 0.43 | 1.39 | 0.63
1740 | 1689.38 | 48.84 | 5.2 | 22.51 | 178 | 240.7 | 4456 | 0.28 | 1.38 | 0.65
1745 | 1693.96 | 42.14 | 4.66 | 20.92 | 177 | 236 | 4442 | 0.3 | 1.38 | 0.67
1750 | 1698.54 | 47.48 | 4.67 | 21.84 | 178 | 238.1 | 4456 | 0.41 | 1.39 | 0.63
1755 | 1703.12 | 48.19 | 3.81 | 20.37 | 178 | 237.8 | 4456 | 0.32 | 1.39 | 0.6
1760 | 1707.69 | 50.04 | 4.2 | 20.21 | 178 | 240.1 | 4456 | 0.38 | 1.39 | 0.65
1765 | 1712.27 | 52.03 | 6.04 | 23.39 | 178 | 241.6 | 4456 | 0.59 | 1.39 | 0.65
1770 | 1716.85 | 50.83 | 5.58 | 23.29 | 179 | 241.7 | 4456 | 0.64 | 1.39 | 0.65
1775 | 1721.44 | 49.43 | 5.41 | 22.69 | 178 | 240.2 | 4456 | 0.74 | 1.39 | 0.65
1780 | 1726.02 | 45.83 | 5.52 | 23.87 | 178 | 237 | 4456 | 0.8 | 1.39 | 0.66
1785 | 1730.61 | 45.48 | 5.24 | 22.05 | 178 | 238.8 | 4456 | 0.76 | 1.39 | 0.65
1790 | 1735.19 | 47.2 | 5.27 | 23.24 | 178 | 240.2 | 4456 | 0.52 | 1.39 | 0.65
1795 | 1739.78 | 47.97 | 5.34 | 22.39 | 178 | 240.7 | 4455 | 0.4 | 1.39 | 0.65
1800 | 1744.36 | 43.33 | 4.01 | 20.56 | 178 | 242.7 | 4456 | 0.45 | 1.39 | 0.64
1805 | 1748.95 | 52.12 | 3.06 | 21.98 | 178 | 244.4 | 4456 | 0.64 | 1.39 | 0.57
1810 | 1753.53 | 50.22 | 4.47 | 21.85 | 178 | 245.1 | 4456 | 0.72 | 1.39 | 0.62
1815 | 1758.12 | 49.84 | 3.92 | 20.54 | 178 | 245.1 | 4456 | 0.79 | 1.39 | 0.6
1820 | 1762.71 | 48.34 | 3.69 | 20.95 | 178 | 243.9 | 4456 | 0.86 | 1.39 | 0.6
1825 | 1767.3 | 47.81 | 3.71 | 20.37 | 178 | 244.4 | 4456 | 0.43 | 1.4 | 0.6
1830 | 1771.89 | 48 | 3.98 | 20.33 | 178 | 244.3 | 4456 | 0.33 | 1.4 | 0.61
1835 | 1776.48 | 47.38 | 3.92 | 20.69 | 178 | 244.4 | 4455 | 0.38 | 1.4 | 0.61
1840 | 1781.07 | 39.17 | 3.78 | 18.29 | 178 | 245.9 | 4456 | 0.59 | 1.4 | 0.65
1845 | 1785.66 | 52.33 | 4.14 | 19.88 | 178 | 248.7 | 4456 | 0.49 | 1.4 | 0.6
1850 | 1790.26 | 51.1 | 3.97 | 20.68 | 178 | 248.9 | 4456 | 0.22 | 1.39 | 0.6
1855 | 1794.84 | 47.34 | 4.21 | 20.52 | 178 | 245.6 | 4456 | 0.23 | 1.4 | 0.64
1860 | 1799.43 | 50.49 | 3.52 | 19.4 | 169 | 233.5 | 4263 | 0.29 | 1.39 | 0.59
1865 | 1804.02 | 48.1 | 4.4 | 20.32 | 178 | 243.7 | 4458 | 0.41 | 1.36 | 0.64
1870 | 1808.61 | 48.16 | 4.45 | 20.39 | 178 | 245.1 | 4458 | 0.61 | 1.37 | 0.63
1875 | 1813.19 | 48.13 | 4.42 | 20.64 | 178 | 247.6 | 4458 | 0.74 | 1.37 | 0.63
1880 | 1817.78 | 43.88 | 4.16 | 19.72 | 178 | 249.1 | 4457 | 0.65 | 1.38 | 0.63
1885 | 1822.37 | 50.93 | 3.46 | 20.48 | 178 | 250.4 | 4457 | 0.53 | 1.39 | 0.59
1890 | 1826.96 | 44.42 | 3.41 | 20.51 | 178 | 251.4 | 4456 | 0.61 | 1.39 | 0.61
1895 | 1831.54 | 49.13 | 2.85 | 19.8 | 178 | 251.9 | 4456 | 0.66 | 1.39 | 0.57
1900 | 1836.13 | 43.98 | 3.21 | 20.53 | 178 | 252.2 | 4456 | 0.72 | 1.39 | 0.61
1905 | 1840.71 | 44.75 | 3.21 | 20.65 | 178 | 252.7 | 4456 | 0.69 | 1.39 | 0.6
1910 | 1845.29 | 44.82 | 2.15 | 18.98 | 175 | 250.7 | 4455 | 0.49 | 1.39 | 0.56
1915 | 1849.87 | 43.98 | 2.65 | 19.96 | 178 | 247.4 | 4456 | 0.56 | 1.38 | 0.59
1920 | 1854.46 | 37.91 | 2.09 | 18.43 | 174 | 242.2 | 4456 | 0.49 | 1.38 | 0.69
1925 | 1859.04 | 52.48 | 3.07 | 19.75 | 178 | 253.6 | 4456 | 0.39 | 1.39 | 0.57
1930 | 1863.62 | 50.54 | 3.52 | 20.46 | 178 | 253.5 | 4456 | 0.39 | 1.39 | 0.59
1935 | 1868.21 | 49.9 | 3.34 | 20.56 | 178 | 253.4 | 4456 | 0.46 | 1.38 | 0.59
1940 | 1872.81 | 47.79 | 3.39 | 20.43 | 178 | 253.2 | 4456 | 0.6 | 1.38 | 0.6
1945 | 1877.4 | 48.31 | 3.32 | 20.43 | 178 | 252.2 | 4456 | 0.65 | 1.38 | 0.59
1950 | 1881.99 | 48.01 | 3.69 | 21.18 | 178 | 249.9 | 4456 | 0.7 | 1.38 | 0.61
1955 | 1886.59 | 47.23 | 3.79 | 20.58 | 178 | 246.4 | 4456 | 0.74 | 1.38 | 0.61
1960 | 1891.18 | 42.52 | 2.96 | 19.56 | 176 | 210 | 3992 | 0.61 | 1.38 | 0.62
1965 | 1895.77 | 47.91 | 2.85 | 20.05 | 178 | 132.9 | 2910 | 0.41 | 1.39 | 0.59
1970 | 1900.37 | 47.54 | 4.24 | 22.53 | 179 | 249.5 | 4411 | 0.57 | 1.38 | 0.63
1975 | 1905.02 | 42.07 | 2.1 | 20.14 | 172 | 214.6 | 4061 | 0.41 | 1.38 | 0.61
1980 | 1909.67 | 48.09 | 1.41 | 21.21 | 178 | 238.9 | 4456 | 0.41 | 1.37 | 0.51
1985 | 1914.32 | 21.68 | 0.22 | 17.67 | 178 | 220.4 | 4177 | 0.19 | 1.38 | 0.47
1990 | 1918.97 | 37.61 | 0.55 | 19.52 | 178 | 245.3 | 4407 | 0.38 | 1.38 | 0.48
1995 | 1923.62 | 48.14 | 0.94 | 20.81 | 178 | 217 | 4042 | 0.61 | 1.38 | 0.48
2000 | 1928.27 | 40.13 | 0.95 | 20.09 | 178 | 225.5 | 4146 | 0.52 | 1.38 | 0.51
2005 | 1932.93 | 43.27 | 1.61 | 19.38 | 178 | 245.7 | 4456 | 0.24 | 1.38 | 0.61
2010 | 1937.58 | 51.27 | 1.66 | 21.01 | 178 | 245.5 | 4456 | 0.3 | 1.38 | 0.52
2015 | 1942.3 | 50.16 | 1.44 | 21.56 | 178 | 245.3 | 4455 | 0.38 | 1.38 | 0.51
2020 | 1947.03 | 18.31 | 0.41 | 17.58 | 177 | 230.7 | 4250 | 0.32 | 1.38 | 0.56
2025 | 1951.76 | 11.54 | 0.01 | 16.52 | 177 | 243.5 | 4357 | 0.35 | 1.39 | 0.41
2030 | 1956.5 | 31.54 | 0.69 | 19.74 | 178 | 248.4 | 4455 | 0.17 | 1.38 | 0.51
2035 | 1961.23 | 47.6 | 1.9 | 21.84 | 178 | 247.8 | 4455 | 0.29 | 1.38 | 0.54
2040 | 1965.97 | 45.99 | 1.87 | 22.49 | 178 | 248.3 | 4455 | 0.35 | 1.39 | 0.54
2045 | 1970.7 | 51.79 | 5.09 | 22.23 | 178 | 253.1 | 4456 | 0.25 | 1.39 | 0.63
2050 | 1975.44 | 48.34 | 5.82 | 23.55 | 178 | 252.9 | 4456 | 0.31 | 1.39 | 0.66
2055 | 1980.23 | 45.99 | 5.43 | 23.49 | 179 | 252.9 | 4456 | 0.19 | 1.39 | 0.66
2060 | 1985.04 | 38.47 | 4.74 | 22.35 | 178 | 252.4 | 4455 | 0.29 | 1.39 | 0.67
2065 | 1989.85 | 38.56 | 4.48 | 22.56 | 178 | 251.9 | 4455 | 0.34 | 1.39 | 0.66
2070 | 1994.65 | 35.95 | 5.35 | 23.4 | 179 | 251.9 | 4455 | 0.33 | 1.39 | 0.7
2075 | 1999.46 | 38.27 | 4.76 | 23.16 | 178 | 251.2 | 4455 | 0.34 | 1.39 | 0.67
2080 | 2004.27 | 33.16 | 4.6 | 21.81 | 178 | 249.4 | 4438 | 0.36 | 1.39 | 0.7
2085 | 2009.08 | 17.83 | 2.99 | 17.84 | 177 | 236.9 | 4240 | 0.18 | 1.4 | 0.75
2090 | 2013.89 | 41.05 | 4.05 | 21.03 | 178 | 257 | 4455 | 0.28 | 1.4 | 0.63
2095 | 2018.74 | 40.17 | 3.53 | 22.04 | 178 | 256.6 | 4455 | 0.28 | 1.4 | 0.62
2100 | 2023.61 | 38.47 | 3.51 | 21.72 | 178 | 256.1 | 4455 | 0.21 | 1.39 | 0.63
2105 | 2028.49 | 38.71 | 3.43 | 22.62 | 178 | 255.6 | 4455 | 0.3 | 1.39 | 0.62
2110 | 2033.36 | 37.01 | 3.76 | 22.37 | 178 | 254.7 | 4455 | 0.33 | 1.39 | 0.64
2115 | 2038.23 | 38.56 | 3.37 | 21.85 | 178 | 253 | 4455 | 0.34 | 1.39 | 0.62
2120 | 2043.1 | 38.3 | 3.4 | 22.28 | 178 | 253.1 | 4455 | 0.33 | 1.39 | 0.63
2125 | 2047.98 | 31.13 | 4.52 | 22.9 | 178 | 258.3 | 4465 | 0.29 | 1.4 | 0.72
2130 | 2052.85 | 39.88 | 6.34 | 23.62 | 179 | 259.3 | 4456 | 0.34 | 1.4 | 0.7
2135 | 2057.77 | 38.81 | 5.92 | 23.3 | 179 | 259.4 | 4455 | 0.28 | 1.4 | 0.69
2140 | 2062.72 | 36.75 | 5.73 | 22.66 | 179 | 259.6 | 4455 | 0.35 | 1.4 | 0.7
2145 | 2067.67 | 38.43 | 5.1 | 23.05 | 179 | 258.1 | 4455 | 0.36 | 1.39 | 0.68
2150 | 2072.62 | 26.79 | 3.09 | 20.28 | 157 | 221.1 | 3985 | 0.33 | 1.39 | 0.71
2155 | 2077.57 | 28.63 | 3.21 | 21.53 | 178 | 233.5 | 4149 | 0.2 | 1.39 | 0.66
2160 | 2082.52 | 28.65 | 1.09 | 28.47 | 179 | 242.8 | 4267 | 0.19 | 1.38 | 0.55
2165 | 2087.48 | 44.73 | 5.21 | 37.65 | 172 | 261.1 | 4456 | 0.18 | 1.39 | 0.66
2170 | 2092.43 | 43.76 | 5.06 | 37.61 | 170 | 261.8 | 4456 | 0.14 | 1.39 | 0.65
2175 | 2097.38 | 45.46 | 8.79 | 37.66 | 179 | 263.3 | 4456 | 0.21 | 1.39 | 0.74
2180 | 2102.33 | 46.68 | 8.53 | 38.42 | 179 | 264.9 | 4456 | 0.25 | 1.39 | 0.72
2185 | 2107.28 | 48.72 | 8.04 | 36.36 | 179 | 264.9 | 4456 | 0.23 | 1.39 | 0.71
2190 | 2112.23 | 47.93 | 8.08 | 37.15 | 179 | 264.6 | 4455 | 0.24 | 1.39 | 0.71
2195 | 2117.18 | 47.96 | 8.28 | 37.2 | 179 | 264.9 | 4455 | 0.25 | 1.39 | 0.71
2200 | 2122.13 | 47.79 | 8.37 | 37.35 | 179 | 265.1 | 4455 | 0.24 | 1.4 | 0.71
2205 | 2127.08 | 42.76 | 9.21 | 33.77 | 174 | 262.6 | 4435 | 0.18 | 1.39 | 0.82
2210 | 2132.03 | 52.15 | 9.64 | 36.46 | 179 | 223.1 | 3978 | 0.19 | 1.39 | 0.72
2215 | 2136.97 | 50.34 | 9.5 | 37.41 | 179 | 247.4 | 4262 | 0.23 | 1.4 | 0.73
2220 | 2141.91 | 48.59 | 9.56 | 37.29 | 179 | 266.1 | 4456 | 0.22 | 1.4 | 0.73
2225 | 2146.85 | 38.15 | 10.52 | 31.54 | 179 | 266.3 | 4456 | 0.21 | 1.4 | 0.81
2230 | 2151.78 | 34 | 11.19 | 23.78 | 178 | 264.8 | 4456 | 0.19 | 1.4 | 0.83
2235 | 2156.72 | 35.32 | 11.07 | 24.33 | 179 | 264.6 | 4455 | 0.24 | 1.4 | 0.82
2240 | 2161.66 | 31.56 | 11.42 | 24.2 | 179 | 264.5 | 4455 | 0.24 | 1.4 | 0.9
2245 | 2166.6 | 39.46 | 11.33 | 26.77 | 178 | 265.1 | 4456 | 0.2 | 1.4 | 0.84
2250 | 2171.53 | 52.1 | 8.42 | 23.37 | 179 | 265.5 | 4456 | 0.27 | 1.4 | 0.7
2255 | 2176.47 | 50.07 | 7.99 | 30.7 | 179 | 265.6 | 4478 | 0.36 | 1.4 | 0.69
2260 | 2181.4 | 48.46 | 7.92 | 23.98 | 179 | 266.1 | 4455 | 0.37 | 1.4 | 0.7
2265 | 2186.33 | 35.6 | 10.23 | 24.65 | 179 | 266.1 | 4465 | 0.37 | 1.4 | 0.83
2270 | 2191.26 | 30.74 | 10.24 | 22.54 | 179 | 266.1 | 4455 | 0.28 | 1.4 | 0.84
2275 | 2196.19 | 39.96 | 12.41 | 24.9 | 179 | 265.8 | 4455 | 0.2 | 1.4 | 0.82
2280 | 2201.13 | 12.56 | 10.61 | 21.36 | 178 | 264.1 | 4455 | 0.28 | 1.39 | 1.01
2285 | 2206.06 | 14.43 | 11.56 | 21.45 | 178 | 263.9 | 4455 | 0.18 | 1.39 | 1.01
2290 | 2210.99 | 24.36 | 11.47 | 22.72 | 179 | 265.8 | 4455 | 0.22 | 1.39 | 0.9
2295 | 2215.91 | 29.39 | 11.53 | 22.17 | 178 | 265.3 | 4455 | 0.24 | 1.39 | 0.87
2300 | 2220.83 | 33.74 | 11.77 | 22.8 | 179 | 264.6 | 4455 | 0.17 | 1.39 | 0.84
2305 | 2225.75 | 29.81 | 12.62 | 23.4 | 179 | 263.7 | 4455 | 0.24 | 1.39 | 0.88
2310 | 2230.66 | 37.39 | 13.78 | 23.75 | 179 | 263 | 4455 | 0.25 | 1.39 | 0.86
2315 | 2235.58 | 38.68 | 14.99 | 25.47 | 179 | 262.9 | 4455 | 0.26 | 1.39 | 0.87
2320 | 2240.49 | 38.1 | 14.72 | 26.02 | 179 | 262.9 | 4455 | 0.26 | 1.39 | 0.87
2325 | 2245.41 | 28.49 | 10.4 | 20.26 | 157 | 218 | 3790 | 0.26 | 1.39 | 1.06
2330 | 2250.33 | 37.91 | 14.01 | 25.93 | 179 | 241.6 | 4181 | 0.16 | 1.39 | 0.86
2335 | 2255.24 | 38.58 | 15.52 | 29.18 | 177 | 230.2 | 4054 | 0.18 | 1.39 | 0.88
2340 | 2260.13 | 35.96 | 13.22 | 27.66 | 179 | 265.4 | 4443 | 0.19 | 1.39 | 0.86
2345 | 2265.02 | 26.62 | 11.3 | 24.19 | 179 | 237.9 | 4090 | 0.19 | 1.38 | 0.95
2350 | 2269.91 | 13.95 | 9.42 | 21.95 | 178 | 243.2 | 4210 | 0.25 | 1.39 | 0.96
2355 | 2274.81 | 19.63 | 14.54 | 24.64 | 179 | 266.4 | 4457 | 0.24 | 1.38 | 1
2360 | 2279.7 | 20.93 | 15.39 | 25.49 | 179 | 267.3 | 4456 | 0.28 | 1.38 | 1.01
2365 | 2284.59 | 17.15 | 13.79 | 22.59 | 179 | 269.7 | 4456 | 0.23 | 1.39 | 1.1
2370 | 2289.48 | 18.71 | 14.01 | 23.21 | 179 | 270.7 | 4456 | 0.21 | 1.39 | 0.99
2375 | 2294.35 | 14.41 | 13.75 | 22.67 | 179 | 270.5 | 4456 | 0.24 | 1.39 | 1.05
2380 | 2299.2 | 13.73 | 15.05 | 23.71 | 179 | 271.2 | 4456 | 0.23 | 1.39 | 1.09
2385 | 2304.05 | 11.62 | 13.96 | 21.87 | 179 | 271.7 | 4455 | 0.19 | 1.39 | 1.09
2390 | 2308.91 | 10.33 | 15.88 | 22.43 | 179 | 271.4 | 4455 | 0.18 | 1.39 | 1.16
2395 | 2313.76 | 8.16 | 15.31 | 23.42 | 175 | 270.5 | 4455 | 0.18 | 1.39 | 1.19
2400 | 2318.61 | 5.29 | 13.74 | 21.96 | 179 | 270.7 | 4455 | 0.14 | 1.39 | 1.23
2405 | 2323.46 | 6.82 | 14.8 | 21.43 | 178 | 270.3 | 4441 | 0.14 | 1.4 | 1.22
2410 | 2328.31 | 8.89 | 19.17 | 21.97 | 178 | 252.6 | 4239 | 0.16 | 1.4 | 1.23
2415 | 2333.13 | 7.08 | 15.88 | 21.58 | 175 | 275 | 4477 | 0.16 | 1.4 | 1.22
2420 | 2337.93 | 6.96 | 15.81 | 21.01 | 178 | 275.4 | 4477 | 0.16 | 1.4 | 1.21
2425 | 2342.73 | 6.56 | 15.59 | 21.48 | 179 | 269.9 | 4407 | 0.17 | 1.4 | 1.27
2430 | 2347.53 | 10.24 | 18.84 | 23.43 | 179 | 276.5 | 4451 | 0.2 | 1.4 | 1.2
2435 | 2352.33 | 18.38 | 18.15 | 27.35 | 179 | 276.6 | 4451 | 0.25 | 1.4 | 1.07
2440 | 2357.13 | 7.3 | 16.32 | 22.88 | 178 | 272.3 | 4451 | 0.18 | 1.4 | 1.21
2445 | 2361.93 | 9.02 | 12.83 | 22.75 | 177 | 277.8 | 4450 | 0.22 | 1.41 | 1.1
2450 | 2366.73 | 10.92 | 9.07 | 22.43 | 182 | 277.6 | 4450 | 0.18 | 1.4 | 0.98
2455 | 2371.53 | 9.6 | 11.03 | 23.24 | 186 | 277.5 | 4450 | 0.21 | 1.4 | 1.05
2460 | 2376.3 | 6.56 | 11.69 | 22.21 | 149 | 280.4 | 4444 | 0.15 | 1.4 | 1.1
2465 | 2381.07 | 6.5 | 15.42 | 22.48 | 150 | 278.8 | 4450 | 0.16 | 1.4 | 1.18
2470 | 2385.81 | 5.68 | 15.46 | 23.27 | 150 | 279.5 | 4450 | 0.17 | 1.4 | 1.21
2475 | 2390.55 | 6.32 | 14.7 | 22.97 | 179 | 274.6 | 4450 | 0.17 | 1.4 | 1.21
2480 | 2395.29 | 5.96 | 14.89 | 23.1 | 179 | 275.1 | 4450 | 0.18 | 1.4 | 1.25
2485 | 2400.03 | 12.98 | 12.87 | 24.03 | 179 | 273.6 | 4450 | 0.23 | 1.4 | 1.06
2490 | 2404.77 | 14.59 | 10.46 | 22.56 | 179 | 255.4 | 4168 | 0.17 | 1.4 | 0.97
2495 | 2409.5 | 10.1 | 8.63 | 24.06 | 179 | 283.2 | 4433 | 0.13 | 1.39 | 1
2500 | 2414.2 | 5.94 | 10.3 | 23.63 | 179 | 281.7 | 4432 | 0.1 | 1.39 | 1.12
2505 | 2418.9 | 4.14 | 11.35 | 22.33 | 179 | 282.2 | 4438 | 0.11 | 1.4 | 1.26
2510 | 2423.59 | 2.39 | 15.05 | 20.11 | 180 | 282.1 | 4450 | 0.11 | 1.39 | 1.43
2515 | 2428.29 | 3.32 | 17.04 | 20.15 | 179 | 285.6 | 4420 | 0.14 | 1.4 | 1.46
2520 | 2432.99 | 8.55 | 17.21 | 22.63 | 180 | 289.2 | 4362 | 0.12 | 1.4 | 1.2
2525 | 2437.68 | 9.1 | 11.78 | 21.92 | 179 | 282.7 | 4358 | 0.19 | 1.39 | 1.09
2530 | 2442.38 | 12.5 | 15.87 | 22.18 | 159 | 281.4 | 4390 | 0.11 | 1.4 | 1.08
2535 | 2447.08 | 9.7 | 17.15 | 22.18 | 150 | 282.8 | 4352 | 0.11 | 1.4 | 1.15
2540 | 2451.74 | 10.44 | 18.24 | 22.54 | 150 | 281.2 | 4347 | 0.08 | 1.4 | 1.14
2545 | 2456.4 | 7.35 | 18.81 | 21.84 | 150 | 279.6 | 4395 | 0.07 | 1.4 | 1.23
2550 | 2461.05 | 7.49 | 16.01 | 21.8 | 178 | 279.3 | 4459 | 0.06 | 1.4 | 1.22
2555 | 2465.7 | 11.49 | 18.71 | 23.12 | 180 | 281 | 4476 | 0.06 | 1.4 | 1.17
2560 | 2470.36 | 3.16 | 19.07 | 23.32 | 168 | 281.9 | 4476 | 0.08 | 1.4 | 1.44
2565 | 2475.01 | 5.34 | 16.63 | 23.07 | 180 | 278.7 | 4476 | 0.05 | 1.4 | 1.33
2570 | 2479.67 | 2.38 | 18.12 | 21.26 | 180 | 275.8 | 4476 | 0.04 | 1.4 | 1.52
2575 | 2484.32 | 5.76 | 8.36 | 26.35 | 134 | 226 | 3795 | 0.03 | 1.39 | 1.14
2580 | 2488.92 | 12.96 | 2.09 | 28.8 | 143 | 196.9 | 3366 | 0.02 | 1.39 | 0.78
2585 | 2493.47 | 18.89 | 4.09 | 30.11 | 180 | 194.6 | 3338 | 0.02 | 1.39 | 0.81
2590 | 2498.03 | 19.86 | 3.4 | 29.77 | 180 | 194.6 | 3338 | 0.02 | 1.39 | 0.77
2595 | 2502.58 | 20.07 | 3.42 | 31.06 | 180 | 194.4 | 3338 | 0.02 | 1.4 | 0.77
2600 | 2507.14 | 20.07 | 3.12 | 30.14 | 180 | 193.3 | 3338 | 0.02 | 1.4 | 0.75
2605 | 2511.69 | 19.49 | 3.07 | 30.85 | 180 | 193.7 | 3338 | 0.02 | 1.4 | 0.76
2610 | 2516.25 | 16.24 | 3.96 | 27.31 | 154 | 174.6 | 3009 | 0.03 | 1.4 | 0.94
2615 | 2520.8 | 22.59 | 2.31 | 33.11 | 178 | 194.3 | 3326 | 0.2 | 1.4 | 0.7
2620 | 2525.28 | 17.9 | 1.66 | 30.74 | 180 | 186.7 | 3248 | 0.06 | 1.4 | 0.74
2625 | 2529.67 | 23.67 | 2.4 | 32.31 | 180 | 194.1 | 3307 | 0.07 | 1.4 | 0.7
2630 | 2534.05 | 16.56 | 1.68 | 30.89 | 180 | 191.7 | 3290 | 0.05 | 1.4 | 0.71
2635 | 2538.43 | 20.12 | 2.07 | 30.2 | 180 | 189.5 | 3270 | 0.07 | 1.4 | 0.7
2640 | 2542.82 | 21.06 | 1.51 | 30.07 | 180 | 189.3 | 3270 | 0.08 | 1.4 | 0.65
2645 | 2547.2 | 16.8 | 1.35 | 30 | 180 | 189.2 | 3268 | 0.06 | 1.4 | 0.69
2650 | 2551.58 | 14.48 | 1.67 | 28.92 | 158 | 198.1 | 3347 | 0.07 | 1.41 | 0.73
2655 | 2555.96 | 27.7 | 1.82 | 30.1 | 140 | 191.4 | 3270 | 0.07 | 1.41 | 0.6
2660 | 2560.3 | 25.66 | 2.34 | 31.22 | 140 | 191.4 | 3269 | 0.07 | 1.41 | 0.64
2665 | 2564.53 | 23.79 | 3.38 | 30.58 | 140 | 191.4 | 3269 | 0.07 | 1.41 | 0.7
2670 | 2568.77 | 26.17 | 3.38 | 30.41 | 140 | 192.1 | 3269 | 0.08 | 1.41 | 0.68
2675 | 2573 | 29.85 | 3.27 | 30.29 | 140 | 192.5 | 3270 | 0.06 | 1.41 | 0.71
2680 | 2577.23 | 35 | 2.04 | 31.17 | 140 | 192.8 | 3269 | 0.06 | 1.41 | 0.58
2685 | 2581.47 | 33.47 | 2.54 | 31.74 | 140 | 192.7 | 3270 | 0.06 | 1.41 | 0.62
2690 | 2585.7 | 29.1 | 3.61 | 30.83 | 140 | 193 | 3269 | 0.08 | 1.41 | 0.68
2695 | 2589.94 | 31.37 | 6.61 | 35 | 140 | 194.4 | 3269 | 0.08 | 1.41 | 0.78
2700 | 2594.14 | 23.59 | 7.29 | 34.49 | 137 | 194.4 | 3269 | 0.09 | 1.41 | 0.83
2705 | 2598.23 | 15.74 | 6.44 | 32.84 | 139 | 194.1 | 3269 | 0.06 | 1.41 | 0.88
2710 | 2602.32 | 10.17 | 6.94 | 31.25 | 139 | 193.8 | 3270 | 0.05 | 1.41 | 0.99
2715 | 2606.41 | 11.07 | 4.8 | 32.37 | 144 | 192 | 3269 | 0.05 | 1.41 | 0.88
2720 | 2610.5 | 10.9 | 3.53 | 33.22 | 148 | 191.4 | 3270 | 0.06 | 1.42 | 0.82
2725 | 2614.59 | 9.9 | 4.15 | 32.73 | 148 | 191.7 | 3270 | 0.06 | 1.41 | 0.87
2730 | 2618.68 | 8.24 | 4.98 | 31.76 | 149 | 190.9 | 3269 | 0.05 | 1.41 | 0.93
2735 | 2622.77 | 7.34 | 5.77 | 31.5 | 149 | 217 | 3511 | 0.04 | 1.4 | 0.98
2740 | 2626.81 | 10.57 | 4.9 | 33.1 | 145 | 221.5 | 3559 | 0.05 | 1.4 | 0.88
2745 | 2630.68 | 9.55 | 5.11 | 31.24 | 148 | 213.8 | 3481 | 0.05 | 1.4 | 0.93
2750 | 2634.56 | 9.84 | 6.05 | 32.16 | 148 | 208.2 | 3425 | 0.04 | 1.4 | 0.94
2755 | 2638.43 | 8.91 | 5.77 | 31.04 | 149 | 208.3 | 3426 | 0.05 | 1.4 | 1.03
2760 | 2642.31 | 6.92 | 7.41 | 30.94 | 145 | 207.8 | 3425 | 0.04 | 1.4 | 1.06
2765 | 2646.18 | 7.15 | 7.53 | 30.75 | 147 | 207.7 | 3426 | 0.04 | 1.4 | 1.05
2770 | 2650.06 | 7.41 | 10.44 | 30.71 | 148 | 202.9 | 3381 | 0.04 | 1.4 | 1.12
2775 | 2653.93 | 4.71 | 6.91 | 28.27 | 150 | 213.1 | 3465 | 0.03 | 1.4 | 1.12
2780 | 2657.77 | 5.88 | 7.2 | 29.99 | 151 | 214.5 | 3492 | 0.02 | 1.4 | 1.11
2785 | 2661.39 | 6.73 | 8.13 | 30.66 | 154 | 214 | 3489 | 0.04 | 1.4 | 1.09
2790 | 2665.01 | 7.38 | 8.39 | 32.07 | 147 | 211.5 | 3479 | 0.04 | 1.4 | 1.06
2795 | 2668.63 | 8.56 | 8.02 | 32.65 | 146 | 215.5 | 3508 | 0.05 | 1.4 | 1.02
2800 | 2672.25 | 11.22 | 7.5 | 33.12 | 146 | 217.9 | 3537 | 0.05 | 1.4 | 0.96
2805 | 2675.87 | 10.92 | 7.9 | 33.28 | 146 | 218.5 | 3537 | 0.05 | 1.4 | 0.98
2810 | 2679.49 | 14.53 | 7.44 | 33.7 | 146 | 219.4 | 3537 | 0.05 | 1.4 | 0.91
2815 | 2683.11 | 9.26 | 6.97 | 33.06 | 144 | 214.8 | 3485 | 0.04 | 1.4 | 0.99
2820 | 2686.73 | 11.93 | 7.14 | 34.1 | 146 | 222.8 | 3559 | 0.04 | 1.4 | 0.94
2825 | 2690.11 | 13.77 | 6.96 | 33.74 | 147 | 222.3 | 3559 | 0.04 | 1.4 | 0.91
2830 | 2693.48 | 10 | 8.03 | 33.19 | 148 | 222.5 | 3559 | 0.03 | 1.4 | 1.01
2835 | 2696.86 | 5.77 | 8.42 | 31.89 | 149 | 221.6 | 3559 | 0.03 | 1.4 | 1.11
2840 | 2700.23 | 5.51 | 8.49 | 31.61 | 149 | 221.1 | 3559 | 0.03 | 1.4 | 1.13
2845 | 2703.6 | 5.38 | 8.54 | 31.61 | 149 | 220.4 | 3559 | 0.04 | 1.4 | 1.13
2850 | 2706.98 | 7.14 | 8.54 | 32.41 | 149 | 220.2 | 3559 | 0.04 | 1.4 | 1.07
2855 | 2710.35 | 6.31 | 8.29 | 31.46 | 142 | 222 | 3562 | 0.04 | 1.4 | 1.08
2860 | 2713.72 | 7.25 | 9.05 | 32.6 | 149 | 222.5 | 3565 | 0.04 | 1.4 | 1.09
2865 | 2716.89 | 5.93 | 10.21 | 32.44 | 149 | 217.2 | 3516 | 0.04 | 1.4 | 1.16
2870 | 2720.05 | 4.45 | 10.32 | 31.36 | 150 | 221.7 | 3566 | 0.04 | 1.4 | 1.21
2875 | 2723.21 | 5.13 | 9.85 | 31.99 | 149 | 221.5 | 3565 | 0.04 | 1.4 | 1.17
2880 | 2726.37 | 8.17 | 9.51 | 33.04 | 148 | 221.6 | 3565 | 0.04 | 1.4 | 1.07
2885 | 2729.53 | 8.44 | 9.66 | 33.74 | 148 | 222 | 3565 | 0.04 | 1.4 | 1.07
2890 | 2732.69 | 10.47 | 9.55 | 34.2 | 147 | 212.8 | 3473 | 0.04 | 1.4 | 1.02
2895 | 2735.86 | 12.1 | 10.21 | 34.41 | 143 | 218.8 | 3529 | 0.05 | 1.4 | 1.04
2900 | 2739.02 | 14.22 | 10.19 | 35.45 | 143 | 223.3 | 3565 | 0.06 | 1.4 | 0.98
2905 | 2742.04 | 10.57 | 8.35 | 34.22 | 146 | 223.3 | 3565 | 0.05 | 1.4 | 0.99
2910 | 2745.06 | 9.72 | 8.1 | 33.32 | 148 | 223 | 3565 | 0.04 | 1.4 | 1
2915 | 2748.07 | 8.21 | 7.84 | 32.49 | 149 | 222.9 | 3565 | 0.05 | 1.4 | 1.02
2920 | 2751.09 | 7.93 | 7.88 | 32.13 | 147 | 218.7 | 3526 | 0.04 | 1.4 | 1.04
2925 | 2754.1 | 8.57 | 9.45 | 33.56 | 145 | 220.4 | 3543 | 0.05 | 1.4 | 1.05
2930 | 2757.12 | 9.94 | 8.74 | 33.7 | 144 | 222.7 | 3564 | 0.05 | 1.4 | 1.01
2935 | 2760.13 | 8.28 | 8.83 | 32.47 | 148 | 223.4 | 3565 | 0.04 | 1.4 | 1.05
2940 | 2763.14 | 8.28 | 9.91 | 31.71 | 149 | 224.8 | 3565 | 0.04 | 1.4 | 1.08
2945 | 2766.06 | 8.1 | 10.46 | 32.24 | 148 | 226.5 | 3560 | 0.04 | 1.4 | 1.1
2950 | 2768.99 | 7.48 | 10.67 | 31.67 | 148 | 228.7 | 3559 | 0.04 | 1.4 | 1.13
2955 | 2771.91 | 5.37 | 9.3 | 28.92 | 149 | 228.7 | 3559 | 0.05 | 1.4 | 1.15
2960 | 2774.83 | 4.34 | 9.27 | 30.14 | 150 | 229.3 | 3542 | 0.04 | 1.4 | 1.19
2965 | 2777.76 | 4.03 | 9.43 | 30.65 | 149 | 217.5 | 3399 | 0.04 | 1.4 | 1.22
2970 | 2780.68 | 3.69 | 8.51 | 29.33 | 149 | 215.1 | 3420 | 0.03 | 1.4 | 1.39
2975 | 2783.6 | 2.11 | 7.48 | 28.28 | 148 | 213.1 | 3398 | 0.04 | 1.4 | 1.25
2980 | 2786.53 | 1.98 | 8.26 | 28.43 | 142 | 226.5 | 3515 | 0.04 | 1.4 | 1.3
2985 | 2789.4 | 3.26 | 10.96 | 30.48 | 137 | 228.8 | 3542 | 0.06 | 1.4 | 1.28
2990 | 2792.27 | 3.33 | 9.71 | 30.34 | 138 | 227.4 | 3542 | 0.06 | 1.4 | 1.24
2995 | 2795.15 | 3 | 8.99 | 29.03 | 140 | 226.2 | 3543 | 0.06 | 1.4 | 1.24
3000 | 2798.02 | 5.46 | 8.93 | 30.83 | 137 | 226.9 | 3543 | 0.06 | 1.4 | 1.14
3005 | 2800.89 | 2.75 | 8.8 | 28 | 140 | 226.7 | 3543 | 0.06 | 1.4 | 1.24
3010 | 2803.76 | 3.44 | 8.78 | 27.97 | 140 | 228.4 | 3543 | 0.06 | 1.4 | 1.23
3015 | 2806.62 | 3.29 | 9.9 | 27.98 | 139 | 227.9 | 3529 | 0.06 | 1.4 | 1.27
3020 | 2809.49 | 4.21 | 10.44 | 28.7 | 138 | 231.5 | 3500 | 0.07 | 1.4 | 1.21
3025 | 2812.35 | 3.95 | 10.1 | 27.81 | 140 | 235.2 | 3542 | 0.07 | 1.4 | 1.22
3030 | 2815.22 | 4.95 | 9.62 | 29.41 | 139 | 235 | 3542 | 0.07 | 1.4 | 1.15
3035 | 2818.08 | 6.06 | 8.96 | 28.56 | 140 | 234.5 | 3542 | 0.07 | 1.4 | 1.11
3040 | 2820.95 | 1.95 | 9.53 | 25.97 | 140 | 233.4 | 3542 | 0.29 | 1.4 | 1.33
3045 | 2823.81 | 2.16 | 9.62 | 26.81 | 140 | 231.6 | 3528 | 0.06 | 1.4 | 1.3
3050 | 2826.68 | 1.73 | 9.67 | 26.06 | 140 | 231 | 3542 | 0.05 | 1.4 | 1.34
3055 | 2829.54 | 3.75 | 9.51 | 27.82 | 139 | 232.4 | 3543 | 0.05 | 1.4 | 1.22
3060 | 2832.41 | 5.67 | 9.84 | 29.38 | 140 | 233.9 | 3543 | 0.06 | 1.4 | 1.13
3065 | 2835.3 | 5.19 | 9.63 | 28.99 | 140 | 233.6 | 3543 | 0.06 | 1.4 | 1.13
3070 | 2838.2 | 5.81 | 9.12 | 28.09 | 140 | 227.7 | 3487 | 0.06 | 1.4 | 1.14
3075 | 2841.09 | 4.6 | 9.26 | 28.54 | 140 | 233.6 | 3542 | 0.06 | 1.4 | 1.15
3080 | 2843.99 | 4.54 | 8.97 | 28.37 | 140 | 233.7 | 3542 | 0.06 | 1.4 | 1.13
3085 | 2846.92 | 2.16 | 9.59 | 26.31 | 140 | 233.5 | 3542 | 0.05 | 1.4 | 1.32
3090 | 2849.86 | 5.64 | 9.1 | 28.87 | 140 | 233.9 | 3542 | 0.08 | 1.4 | 1.1
3095 | 2852.8 | 5.47 | 8.62 | 28.7 | 140 | 234.6 | 3543 | 0.08 | 1.4 | 1.09
3100 | 2855.74 | 8.83 | 8.14 | 30.71 | 140 | 235.8 | 3543 | 0.08 | 1.4 | 0.99
3105 | 2858.68 | 8.45 | 7.21 | 28.71 | 140 | 235.5 | 3535 | 0.1 | 1.4 | 0.99
3110 | 2861.62 | 10.31 | 5.71 | 27.12 | 140 | 230 | 3486 | 0.22 | 1.4 | 0.88
3115 | 2864.57 | 8.34 | 5.45 | 24.2 | 123 | 223.1 | 3234 | 0.16 | 1.4 | 0.92
3120 | 2867.53 | 3.94 | 2.4 | 15.33 | 60 | 188.8 | 2106 | 0.1 | 1.4 | 0.82
3125 | 2870.5 | 4.36 | 3.07 | 11.37 | 60 | 207.3 | 2121 | 0.37 | 1.4 | 0.87
3130 | 2873.46 | 6 | 3.69 | 16.14 | 60 | 206.3 | 2228 | 1.04 | 1.4 | 0.83
3135 | 2876.43 | 5.09 | 3.61 | 15.63 | 60 | 204.5 | 2207 | 0.92 | 1.4 | 0.86
3140 | 2879.39 | 5.05 | 3.29 | 15.61 | 60 | 204.7 | 2228 | 0.79 | 1.4 | 0.84
3145 | 2882.34 | 4.56 | 3.84 | 15.43 | 60 | 204.1 | 2227 | 0.5 | 1.4 | 0.89
3150 | 2885.3 | 5.41 | 4.42 | 15.67 | 60 | 202.6 | 2215 | 0.41 | 1.4 | 0.88
3155 | 2888.26 | 6.18 | 4.39 | 15.84 | 60 | 203.4 | 2229 | 0.78 | 1.4 | 0.86
3160 | 2891.22 | 5.53 | 4.39 | 15.97 | 62 | 203.6 | 2228 | 0.87 | 1.4 | 0.89
3165 | 2894.18 | 9.82 | 4.95 | 19.38 | 100 | 202.7 | 2228 | 1.73 | 1.4 | 0.89
3170 | 2897.14 | 9.36 | 5.57 | 19.44 | 105 | 202.7 | 2228 | 2.14 | 1.4 | 0.94
3175 | 2900.09 | 10.07 | 5.33 | 19.49 | 110 | 202.6 | 2228 | 3.14 | 1.4 | 0.92
3180 | 2903.05 | 10.03 | 5.24 | 19.38 | 110 | 202.5 | 2227 | 2.93 | 1.4 | 0.92
3185 | 2906.01 | 10.12 | 5.14 | 19.09 | 116 | 201.7 | 2227 | 2.59 | 1.4 | 0.92
3190 | 2908.97 | 10.41 | 5.09 | 19.4 | 123 | 201 | 2227 | 2.76 | 1.4 | 0.92
3195 | 2911.92 | 10.42 | 4.93 | 19.36 | 130 | 200.7 | 2227 | 2.12 | 1.4 | 0.93
3200 | 2914.88 | 9.66 | 5.19 | 19.41 | 130 | 199.1 | 2214 | 2.03 | 1.4 | 0.96
3205 | 2917.84 | 8.09 | 3.88 | 19.79 | 139 | 197.7 | 2203 | 1.81 | 1.4 | 0.95
3210 | 2920.8 | 9.18 | 5.03 | 19.67 | 140 | 200.8 | 2226 | 2.17 | 1.4 | 0.97
3215 | 2923.76 | 10.05 | 4.93 | 19.18 | 140 | 200.9 | 2226 | 3.02 | 1.4 | 0.94
3220 | 2926.73 | 8.75 | 4.86 | 19.15 | 140 | 188.4 | 2130 | 2.81 | 1.4 | 1
3225 | 2929.7 | 9.81 | 4.51 | 20.17 | 140 | 185.6 | 2132 | 3.36 | 1.4 | 0.93
3230 | 2932.68 | 15.12 | 3.5 | 19.7 | 140 | 200.4 | 2227 | 4.24 | 1.4 | 0.81
3235 | 2935.66 | 15.63 | 3.64 | 20.06 | 140 | 200.8 | 2226 | 4.44 | 1.4 | 0.81
3240 | 2938.64 | 15.65 | 3.44 | 19.6 | 140 | 201.4 | 2226 | 4.64 | 1.4 | 0.8
3245 | 2941.61 | 12.69 | 2.68 | 19.59 | 140 | 201.8 | 2227 | 4.18 | 1.4 | 0.79
3250 | 2944.59 | 14.19 | 2.89 | 19.95 | 140 | 201.4 | 2227 | 5.24 | 1.4 | 0.78
3255 | 2947.57 | 14.35 | 2.45 | 19.57 | 140 | 201.1 | 2226 | 4.83 | 1.4 | 0.75
3260 | 2950.55 | 14.92 | 2.04 | 19.57 | 140 | 201.2 | 2226 | 3.07 | 1.4 | 0.72
3265 | 2953.52 | 15.45 | 2.11 | 19.52 | 140 | 201.1 | 2226 | 2.44 | 1.4 | 0.72
3270 | 2956.5 | 13.93 | 2.18 | 19.63 | 140 | 188.2 | 2136 | 2.28 | 1.4 | 0.75
3275 | 2959.48 | 27.48 | 2.69 | 20.3 | 140 | 174.7 | 2054 | 3.61 | 1.4 | 0.67
3280 | 2962.46 | 28.86 | 3.7 | 20.55 | 140 | 201.8 | 2227 | 3.81 | 1.4 | 0.71
3285 | 2965.44 | 44.69 | 3.25 | 20.57 | 140 | 201.6 | 2227 | 1.58 | 1.4 | 0.65
3290 | 2968.42 | 25.93 | 4.48 | 22.24 | 140 | 202.4 | 2228 | 0.59 | 1.4 | 0.76
3295 | 2971.4 | 27.26 | 3.57 | 21.15 | 140 | 202.6 | 2228 | 0.61 | 1.4 | 0.71
3300 | 2974.38 | 27.21 | 2.84 | 20.72 | 140 | 202.6 | 2228 | 0.9 | 1.4 | 0.68
3305 | 2977.37 | 28.54 | 3.46 | 21.28 | 140 | 202.6 | 2227 | 1.02 | 1.4 | 0.7
3310 | 2980.36 | 29 | 3.28 | 21.38 | 140 | 202.5 | 2227 | 0.87 | 1.4 | 0.69
3315 | 2983.34 | 28.91 | 2.72 | 20.87 | 140 | 203.7 | 2227 | 0.65 | 1.4 | 0.66
3320 | 2986.33 | 25.47 | 4.82 | 21.38 | 140 | 205.1 | 2227 | 0.52 | 1.4 | 0.78
3325 | 2989.32 | 25.06 | 3.63 | 20.51 | 140 | 205.1 | 2227 | 0.42 | 1.4 | 0.73
3330 | 2992.3 | 25.1 | 5.09 | 21.32 | 140 | 204.3 | 2227 | 0.39 | 1.4 | 0.79
3335 | 2995.29 | 26.04 | 6.42 | 22.79 | 140 | 204.1 | 2227 | 0.33 | 1.4 | 0.83
3340 | 2998.29 | 23.29 | 6.6 | 22.28 | 140 | 204.3 | 2227 | 0.31 | 1.4 | 0.86
3345 | 3001.31 | 25.84 | 6.36 | 21.68 | 140 | 205.5 | 2227 | 0.32 | 1.4 | 0.83
3350 | 3004.32 | 27.54 | 6.87 | 22.28 | 140 | 205.9 | 2227 | 0.31 | 1.4 | 0.83
3355 | 3007.34 | 28.22 | 6.48 | 22.25 | 140 | 205.8 | 2227 | 0.31 | 1.4 | 0.81
3360 | 3010.35 | 28.91 | 6.16 | 21.72 | 140 | 207 | 2227 | 0.3 | 1.4 | 0.8
3365 | 3013.37 | 20.86 | 5.35 | 21.58 | 140 | 207.2 | 2227 | 0.26 | 1.4 | 0.88
3370 | 3016.38 | 26.37 | 5.64 | 22.08 | 140 | 206.7 | 2228 | 0.26 | 1.39 | 0.83
3375 | 3019.4 | 24.66 | 5.87 | 22.28 | 140 | 206.4 | 2227 | 0.24 | 1.4 | 0.85
3380 | 3022.41 | 24.06 | 5.94 | 22.26 | 140 | 206.4 | 2227 | 0.24 | 1.4 | 0.86
3385 | 3025.42 | 25.47 | 5.53 | 22.03 | 140 | 206.1 | 2227 | 0.27 | 1.4 | 0.84
3390 | 3028.44 | 28.77 | 4.38 | 21.09 | 140 | 206.2 | 2227 | 0.32 | 1.4 | 0.77
3395 | 3031.45 | 28.79 | 4.32 | 21.26 | 140 | 206.5 | 2227 | 0.33 | 1.4 | 0.76
3400 | 3034.46 | 25.67 | 5.49 | 21.93 | 140 | 206.5 | 2227 | 0.31 | 1.4 | 0.83
3405 | 3037.48 | 14.71 | 6.1 | 22.2 | 140 | 207 | 2227 | 0.23 | 1.39 | 0.99
3410 | 3040.49 | 21.09 | 4.78 | 21.36 | 140 | 206.8 | 2227 | 0.21 | 1.39 | 0.86
3415 | 3043.51 | 26.3 | 4.23 | 21.38 | 140 | 207.3 | 2227 | 0.26 | 1.39 | 0.78
3420 | 3046.52 | 24.68 | 4.18 | 21.49 | 140 | 207 | 2227 | 0.24 | 1.39 | 0.8
3425 | 3049.54 | 15.5 | 3.33 | 21.1 | 140 | 205.2 | 2227 | 0.19 | 1.4 | 0.83
3430 | 3052.55 | 21.05 | 4.2 | 22.04 | 140 | 204.5 | 2227 | 0.19 | 1.4 | 0.81
3435 | 3055.57 | 24.36 | 4.65 | 22.41 | 137 | 204.4 | 2227 | 0.21 | 1.4 | 0.81
3440 | 3058.58 | 27.92 | 4.91 | 22.3 | 140 | 204.4 | 2227 | 0.23 | 1.4 | 0.79
3445 | 3061.6 | 25.84 | 3.3 | 21.76 | 140 | 204.9 | 2227 | 0.23 | 1.39 | 0.75
3450 | 3064.61 | 27.03 | 4.07 | 21.06 | 140 | 204.8 | 2227 | 0.27 | 1.39 | 0.77
3455 | 3067.63 | 27.89 | 2.76 | 21.07 | 140 | 205.4 | 2227 | 0.32 | 1.39 | 0.7
3460 | 3070.65 | 27.83 | 2.33 | 21.04 | 140 | 205.6 | 2227 | 0.31 | 1.4 | 0.67
3465 | 3073.67 | 25.33 | 3.36 | 21.43 | 140 | 204.6 | 2227 | 0.32 | 1.4 | 0.75
3470 | 3076.7 | 28.96 | 2.38 | 21.12 | 140 | 204.4 | 2227 | 0.31 | 1.4 | 0.67
3475 | 3079.72 | 29.03 | 3.13 | 21.72 | 140 | 205.1 | 2227 | 0.26 | 1.4 | 0.71
3480 | 3082.75 | 28.92 | 3.1 | 21.15 | 140 | 205.3 | 2227 | 0.23 | 1.4 | 0.71
3485 | 3085.77 | 20.32 | 3.3 | 22.01 | 140 | 203.5 | 2168 | 0.16 | 1.4 | 0.79
3490 | 3088.79 | 23.62 | 3.28 | 21.21 | 140 | 206.2 | 2207 | 0.25 | 1.4 | 0.8
3495 | 3091.82 | 27.88 | 3.57 | 21.72 | 140 | 209.1 | 2227 | 0.28 | 1.4 | 0.74
3500 | 3094.85 | 27.82 | 3.57 | 21.45 | 140 | 209.9 | 2227 | 0.3 | 1.4 | 0.74
3505 | 3097.87 | 28.21 | 3.6 | 21.62 | 140 | 209.4 | 2227 | 0.27 | 1.4 | 0.74
3510 | 3100.9 | 19.33 | 5.9 | 22.39 | 140 | 209.3 | 2227 | 0.2 | 1.4 | 0.91
3515 | 3103.93 | 20.43 | 6.15 | 22.39 | 140 | 208.9 | 2227 | 0.15 | 1.4 | 0.9

## Bit Summary
Hole Section |  | 36” | 17½ | 12¼” | 8 ½” | 8 ½”
BHA Number |  | 1 | 2 | 3 | 4 | 5
Bit Number |  | 1 | 2 | 3 | 4 | 5
Bit size |  | 17½”x36”HO | 17½” | 12¼” | 8 ½” | 8 ½”
Manufacturer |  | Smith
Bit type |  | GS03BDODGVCPD | XR-ODVC | RSR616M | MDI616LHABPX
Serial number |  | - | MY8926 | 216528 | SCC001
Nozzles (n/32”) |  | 1x15, 3x18 | 4x20 | 3x16, 3x15 | 1x12, 5x11 | 3x12, 3x13
TFA (in2) |  | 0,917 | 1228 | 1107 | 0.575 | 0.721
Motor type |  | - | Powerpack | - | Vortex | -
Motor bend |  | - | 1,5º | - | - | -
MWD Type |  | Powerpulse |  | PowerDrive
Depth in (m) |  | 145 | 256 | 1360 | 2770 | 2993
Depth out (m) |  | 256 | 1360 | 2770 | 2993 | 3510
Metres formation drilled |  | 111 | 1104 | 1410 | 223 | 517
Hours on bottom: |  | 15,1 | 24,7 | 66,6 | 11.58 | 36.6
Hours on bottom: Cement |  | - | 1,5 | 10.1 | 3.8 | -
Circulation hours |  | 20.6 | 47 | 115.4 | 28.1 | 47.9
Total bit revolutions |  | (No signal) | 439 | 1409 | 205 | 402
Average ROP (m/hr) |  | 7,3 | 44,6 | 21,2 | 19.25 | 14.13
min-max Flow (l/min) |  | 720-4550 | 3070 – 4495 | 1650 – 3520 | 1940-2092 | 2070-2226
min-max Pressure (bar) |  | 6 – 85 | 75 – 148 | 159 – 220 | 222-257 | 202-235
min-max WOB (ton) |  | 1 – 7 | 1 – 8 | 1 – 9 | 4.8-9.3 | 3.2-8.3
min-max String RPm |  | 70 – 100 | 90 – 190 | 50 – 170 | 30-41 | 140-181
min-max Bit RPm |  | 70 – 100 | 0 – 55 | 50 – 170 | 181-203 | 140-181
min-max Torque (kNm) |  | 2025-12-05 | 2025-10-02 | 7 – 27 | 14.3-20.4 | 16.8-23.5
Average Torque (kNm) |  | 7 | 7 | 15 | 19.3 | 20.8
Mud Weight (g/cc) |  | 1,03 | 1,03 | 1,40 | 1.4 | 1.40 – 1.45
Mud Type |  | SW with hi-vis pills |  | Enviromul OBM | OBM-Standard | OBM-Standard
Start - end inclination |  | 0.00º – 0.09º | 0.09º – 15.49º | 15,49 – 29.63º | 29.63º - 35.31º | 35.31º - 54.67º
Max inclination |  | 0.28º | 15.49º | 29.63º | 35.31º | 55.23º
Start - end Azimuth |  | 220.00 - 109,43 | 220.00 - 148,23 | 148,23º - 133,70º | 133.7º - 165.62º | 165.62º - 202.72º
Lithology |  | - | - | Clay/Sand/Lim |  | Sandst/Limestone/ Marl
| I | 1 | 1 | 4 | 1 | 1
| O | 1 | 1 | 3 | 1 | 1
| D | BU | WT | CT | NO | WT
Grade | L | A | A | N | A | A
| B | E | E | X | X | X
| G | I | I | IN | In | I
| O | ER | NO | WT | NO | CT
| R | TD | TD | TD | BHA | TD
Reason pulled |  | TD reached | TD reached | TD reached | Stop for start up of production. Change BHA | Section TD

## OperationsSorted
Date | Start time | End time | End Depth mMD | Main - Sub Activity | State | Remark
2007-06-09 | 12:00:00 | 12:30:00 | 0 | drilling -- trip | ok | Held pre-job meeting prior to start operation.
2007-06-11 | 00:00:00 | 03:00:00 | 0 | drilling -- trip | ok | Broke out and laid out 2 single 9 3/4" DC. Attempted to rack back 36" hole opener BHA comprising of 36" hole opener, MWD and 9 3/4" DC - nogo due to exceeded weight on PR
2007-06-11 | 00:00:00 | 03:00:00 | 0 | drilling -- trip | ok | S. Hung off BHA again and broke out 9 3/4" DC. Racked back DC. Racked back hole opener / MWD.
2007-06-11 | 03:00:00 | 04:30:00 | 0 | drilling -- drill | ok | Performed FG inspection on TDS and derrick. Vetco Gray installed inclinometer on CART bracket. Had to place shimm rings on bracket to level out the inclinometer.
2007-06-11 | 04:30:00 | 06:00:00 | 0 | drilling -- casi ng | ok | Removed elevator and bails. Cleared drillfloor. Rigged up for running 30" conductor.
2007-06-11 | 06:00:00 | 07:30:00 | 0 | drilling -- casi ng | ok | Continued rigging up for running 30" conductor. Installed bails and elevator.
2007-06-11 | 07:30:00 | 09:00:00 | 0 | drilling -- casi ng | ok | Performed pre-job meeting at drillfloor prior to start running 30" conductor.
2007-06-11 | 09:00:00 | 10:15:00 | 0 | drilling -- casi ng | ok | Picked up 30" shoe joint. Filled joint with water and observed float opening - ok. Tested and rearranged tongs.
2007-06-13 | 06:00:00 | 07:15:00 | 0 | drilling -- casing | ok | Assessed situation. Conferred with shore. Decided to do remedial cement job through top up pipe. Did circulation test through cement hose / top up pipe, 50 bar / 500 lpm.
2007-06-13 | 06:00:00 | 07:15:00 | 0 | drilling -- casing | ok | Meanwhile, prepared for top up cement job.
2007-06-13 | 07:15:00 | 07:45:00 | 0 | drilling -- casing | ok | Held toolbox talk in mud control room prior to cement top up job.
2007-06-13 | 07:45:00 | 08:00:00 | 0 | drilling -- casing | ok | Lined up and pressure tested cement lines to 200 bar / 5 min - ok.
2007-06-13 | 08:00:00 | 10:15:00 | 0 | drilling -- casing | ok | Performed remedial cement job. Pumped 15 m3 of 1,56 G-cement slurry. Pump pressure during cementing 32 bar. Held pumping rate steady at 350 lpm. Displaced cement d own cement hose and top up pipe with 1,1 m3 SW.
2007-06-13 | 10:15:00 | 12:00:00 | 0 | drilling -- casing | ok | Disconnected hose and dropped release ball. Let ball drop and sheard out release sub on UWG with 176 bar. Flushed cement lines/ hose down to seabed.
2007-06-13 | 12:00:00 | 13:00:00 | 0 | drilling -- casing | ok | Released CART from 30" conductor housing by 5 righthand turns. Pulled CART clear of template.
2007-06-13 | 12:00:00 | 13:00:00 | 0 | drilling -- casing | ok | Reading on inclinometer before releasing CART : Pitch 0,09 / Roll 0,11
2007-06-13 | 13:00:00 | 13:30:00 | 0 | drilling -- casing | ok | Broke out and racked back cementing assembly.
2007-06-13 | 13:30:00 | 14:00:00 | 0 | drilling -- casing | ok | Made up TDS to string and pumped cleaning sponge through the pipe at 2600 lpm.
2007-06-13 | 14:00:00 | 15:00:00 | 0 | drilling -- casing | ok | Removed Inclinometer from CART with ROV. POOH with CART and cement stinger on 5 1/2" HWDP. Installed bowl and bushing for handling 4 3/4" aluminum inner string. B roke 4 1/2" IF connection underneath CART. Racked back CART in derrick.
2007-06-13 | 15:00:00 | 15:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to retrieveng 4 3/4" aluminum inner string.
2007-06-13 | 15:15:00 | 16:15:00 | 0 | drilling -- casing | ok | Broke out and laid down 4 3/4" aluminum inner string. Laid down pipe in doubles.
2007-06-13 | 16:15:00 | 16:30:00 | 0 | drilling -- casing | ok | Cleared rig floor of cement stinger handling equipment.
2007-06-13 | 16:30:00 | 16:45:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to transerferring tension cylinders through wellhead module down to Centralizer deck.
2007-06-13 | 16:45:00 | 18:30:00 | 0 | drilling -- casing | ok | Transfered tension cylinders for F-4 down to Centralizer deck.
2007-06-13 | 18:30:00 | 20:00:00 | 0 | drilling -- casing | ok | Transferred tension cylinders for F-7 down to Centralizer deck.
2007-06-13 | 18:30:00 | 20:00:00 | 0 | drilling -- casing | ok | ****Operations transferred to F-12****
2007-10-12 | 06:00:00 | 07:00:00 | 0 | moving -- skid | ok | Skidded derrick towards port to allign with slot F-4.
2007-10-12 | 07:00:00 | 07:30:00 | 0 | moving -- skid | ok | Held toolbox talk before skidding cantilever in longitudinal direction. Observed buckeled standpipe hose in dragchain.
2007-10-12 | 07:30:00 | 09:30:00 | 0 | interruption -- other | ok | Straightened standpipe hose in dragchain with chainhoists.
2007-10-12 | 09:30:00 | 11:00:00 | 0 | moving -- skid | ok | Skidded cantilever to slot F-4 position.
2007-10-12 | 11:00:00 | 12:30:00 | 0 | moving -- skid | ok | Removed weatherdeck hatch on slot F-4. Installed cantilever access stairs. Made final transverse and longitudinal adjustments to center derrick above F-4. Pre pared for removing support beams on aft PRS.
2007-10-12 | 12:30:00 | 14:15:00 | 0 | interruption -- other | ok | Removed support beams on upper arm on aft PRS. Performed NDT inspection of PRS hoisting carriage.
2007-10-12 | 14:15:00 | 16:00:00 | 0 | moving -- skid | ok | Worked on hatches on Weatherdeck. Removed covers on WH module decks on slot F-4. Built scaffolding/fence around F-4 on all levels. Meanwhile changed to monel dies on PRS gripper head.
2007-10-12 | 16:00:00 | 18:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Rigged up slings for installing diverter. Installed diverter, outer ring and masterbushing. Rigged down slings.
2007-10-12 | 18:30:00 | 21:15:00 | 0 | drilling -- wait | ok | Waited on crane to finish loading/backloading supply boat due to urgent need for supply boat going to shore.
2007-10-12 | 18:30:00 | 21:15:00 | 0 | drilling -- wait | ok | Meanwhile:
2007-10-12 | 18:30:00 | 21:15:00 | 0 | drilling -- wait | ok | -Cleared and tidied drillfloor
2007-10-12 | 18:30:00 | 21:15:00 | 0 | drilling -- wait | ok | -Dressed PS-30 with 5 1/2" die holders/dies
2007-10-12 | 21:15 | 21:30:00 | 0 | drilling -- trip | ok | Held toolbox talk prior to making up 17 1/2" drilling BHA.
2007-10-16 | 01:30:00 | 03:30:00 | 0 | drilling -- trip | ok | Broke out and laid down 17 1/2" drilling BHA. Cleaned and tidied rigfloor.
2007-10-16 | 03:30:00 | 04:30:00 | 0 | drilling -- casin g | ok | PIcked up cement head and made up to 6,69 m 5 1/2" DP pup. Laid down cement head w/pup on deck.
2007-10-16 | 04:30:00 | 06:00:00 | 0 | drilling -- casin g | ok | Rigging for running 13 3/8" casing. Cleared and tidied drillfloor. Removed masterbushing. Rigged up slings for removing diverter.
2007-10-16 | 06:00:00 | 07:00:00 | 0 | drilling -- casin g | ok | Removed diverter. Installed hole cover. Rigged down slings.
2007-10-16 | 07:00:00 | 07:15:00 | 0 | drilling -- casin g | ok | Held tolbox talk prior to rigging casing running equipment.
2007-10-16 | 07:15:00 | 07:45:00 | 0 | drilling -- casin g | ok | Greased and checked TDS visually.
2007-10-16 | 07:45:00 | 12:45:00 | 0 | drilling -- casin g | ok | Rigged up for running 13 3/8" casing. Dressed PS-30 slips for 13 3/8". Moved casing tong to drillfloor and set on rails, hooked up hydraulics and panel. Rigged up circulation pac ker, 500T slip type elevator and slings with single joint elevator. Installed PS-30 slips in rotary.
2007-10-16 | 12:45:00 | 13:15:00 | 0 | drilling -- casin g | ok | Held toolbox talk prior to running 13 3/8" casing.
2007-10-18 | 06:00:00 | 07:00:00 | 0 | drilling -- bop/ wellhead equipment | ok | Installed vinyl guides in Centralizer end Tensioning decks. Installed tension ring on Centeralizer deck. Meanwhile started cleaning and dredging template with ROV.
2007-10-18 | 07:00:00 | 07:15:00 | 0 | drilling -- bop/ wellhead equipment | ok | Held toolbox talk before installing spider.
2007-10-18 | 07:15:00 | 08:00:00 | 0 | drilling -- bop/ wellhead equipment | ok | Moved riser spider to drillfloor and installed same in rotary. Hooked up hydraulics.
2007-10-18 | 08:00:00 | 08:45:00 | 0 | drilling -- bop/ wellhead equipment | ok | Rigged up bolt tensioner equipment on drillfloor. Brought fairrings, bolts, guides and caps to drillflloor.
2007-10-18 | 08:45:00 | 09:30:00 | 0 | drilling -- wait | ok | Waited on crane due to helicopter arrival.
2007-10-18 | 09:30:00 | 09:45:00 | 0 | drilling -- bop/ wellhead equipment | ok | Held toolbox talk prior to picking up the TBC/stress joint/lower pup double E.
2007-10-18 | 09:45:00 | 10:30:00 | 0 | drilling -- bop/ wellhead equipment | ok | Picked up TBC/stress joint/lower pup double E by simultaneous lift with deckcrane and TDS. Landed double in riser spider.
2007-10-18 | 10:30:00 | 11:15:00 | 0 | drilling -- bop/ wellhead equipment | ok | Attempted to perform pre-operational checks on TBC according to Vetco instructions, NEG. Observed leakage on minireel hose for hotstab.
2007-10-19 | 15:45:00 | 17:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed hotstab in TBC receptacle with ROV. Unhooked one guidewire from eagle clamp and pulled to surface. Covered open slot openings in wellhead module with hatches and removed scaffolding.
2007-10-19 | 17:15:00 | 19:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Pressured up through minireel hose to activate TBC connector in steps of 500 psi to 3000 psi. Observed indicator rods with ROV - ok. Performed overpull test on connector to 30 MT - ok. Retrieved minireel hose and 2nd guidewire to surface. Covered open slot openings in wellhead module with hatches and removed scaffolding.
2007-10-19 | 19:00:00 | 20:45:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed hatches on weatherdeck on slot F-5 and F-9.
2007-10-19 | 20:45:00 | 22:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Roped off relevant areas. Built scaffolding around slot F-4 on weatherdeck to access Claxton tool.
2007-10-19 | 22:15:00 | 23:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Adjusted tension to 20 MT overpull. Filled riser with 8,7 m3 seawater from cement unit. Closed lo-torque valve on Claxton tool. Pressure tested riser and TBC connector against the well. Pressured up to 20 bar/5 min-ok. Continued to pressure up to 145 bar - observed leakage over Claxton tool in moonpool.
2007-10-19 | 23:30:00 | 00:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Pressure fell 20 bar over 10 min with a corresponding leakage rate of 10 l/min. Observed for leakage on TBC connector with ROV - no leakage detected. Assessed situation. Decid ed to move ahead with operations and confirm test at a later stage.
2007-10-20 | 00:00:00 | 05:30:00 | 0 | drilling -- b op/wellhead equipment | ok | In parallel with tenison cylinder hook-up activities : Rigged up chainhoists and attached to tension ring. Removed vinyl protector guide. Installed centralizer in Centralizer deck. Removed sc affolding and barriers at Centralizer deck. Installed boat collision stool. Made up contact ring to three lowermost groves on serrated area. Assembled tensioning assembly and made up to te nsion ring. Removed chainhoists. At 05:30 operations had progressed to the point where tension cylinders support was required.
2007-10-20 | 11:00:00 | 14:30:00 | 0 | drilling -- b op/wellhead equipment | ok | Made up tensioning assembly to two pistions and elavated tensioning assembly to contact ring. Applied 2 x 20 MT tension. Made up the two other tension cylinders to tensioning assembly. Installed shimm ring underneath tensioning assembly.
2007-10-20 | 14:30:00 | 15:30:00 | 0 | drilling -- b op/wellhead equipment | ok | Transferred tension from block to tension cylinders. Applied 4 x 20 MT on tension cylinders.
2007-10-20 | 15:30:00 | 17:30:00 | 0 | drilling -- b op/wellhead equipment | ok | Broke out Claxton tool from BOP joint with Hy-torq tool. Pullled 5 1/2" landing stand, broke out same and racked back in derrick.
2007-10-20 | 17:30:00 | 17:45:00 | 0 | drilling -- b op/wellhead equipment | ok | Removed master bushing. Pulled Claxton tool and laid out same. Found 1 O-ring missing on Claxton tool and 1 O-ring bursted.
2007-10-20 | 17:45:00 | 18:00:00 | 0 | drilling -- b op/wellhead equipment | ok | Held toolbox talk prior to skidding BOP.
2007-10-20 | 18:00:00 | 18:15:00 | 0 | drilling -- b op/wellhead equipment | ok | Attempted to break out 4 remaining studs on NT-2 connector - negative, not able to break studs within torque limit.
2007-10-20 | 18:15:00 | 22:45:00 | 0 | interruption | ok | Not able to break studs on NT-2 connector. Attempted to adjust BOP to neutral weight on the NT-2 conncetor - still not able to break studs. Torque tool socket adapter broke, repaired adapt er. Traced new and more powerful adapter and used same for making/breaking. Re-made all studs in attempt to break the jammed studs. Untorqued the 4 studs in question - ok.
2007-10-20 | 18:15:00 | 22:45:00 | 0 | -- other | ok | Continued BOP nippling operation.
2007-10-20 | 18:15:00 | 22:45:00 | 0 | -- other | ok | Meanwhile :
2007-10-20 | 18:15:00 | 22:45:00 | 0 | -- other | ok | -Serviced TDS
2007-10-20 | 18:15:00 | 22:45:00 | 0 | -- other | ok | -Removed support beams on forward PRS
2007-10-20 | 18:15:00 | 22:45:00 | 0 | -- other | ok | -Tested standpipe standpipe manifold 5/10 min 20/345 bar
2007-10-20 | 22:45 | 00:00:00 | 0 | drilling -- b op/wellhead equipment | ok | Untorqued all studs on NT-2 connector. Lifted BOP off test stump and skidded to well centre.
2007-10-21 | 00:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Landed BOP on riser NT-2 profile. Made up NT-2 connector. Made up tension cylinders to BOP.
2007-10-21 | 00:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Meanwhile :
2007-10-21 | 00:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | -Calibrated forward PRS
2007-10-21 | 00:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | -Modified BOP overshot joint
2007-10-21 | 00:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | -Tested cement/kill manifold 5/10 min 20/345 bar
2007-10-21 | 00:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | -Prepared BOP test tool
2007-10-21 | 06:00:00 | 07:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Hooked up tension cylinder to BOP. Closed shear ram an lined up for testing down well from cement unit. Meanwhile finished off testing choke manifold.
2007-10-21 | 07:30:00 | 08:30:00 | 0 | drilling -- casing | ok | Pressure tested 13 3/8" casing using seawater to 20/190 bar 5/10 min - ok. Pumped 1 m3 and bled back 1 m3. Opened shear ram.
2007-10-21 | 08:30:00 | 09:45:00 | 0 | drilling -- bop activities | ok | RIH with BOP testplug on 5 1/2" HWDP. Landed plug at 139 m MD and set down 4 MT on plug.
2007-10-21 | 09:45:00 | 10:30:00 | 0 | drilling -- bop activities | ok | Closed MPR. Pressure tested BOP connector, riser, wellhead and TBC connector to 20/345 bar 5/10 mins - ok.
2007-10-21 | 10:30:00 | 11:00:00 | 0 | drilling -- bop activities | ok | Function tested BOP.
2007-10-21 | 11:00:00 | 12:00:00 | 0 | drilling -- bop activities | ok | POOH with Vetco test plug on 5 1/2" HWDP and laid down same.
2007-10-21 | 12:00:00 | 12:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to removing diverter.
2007-10-21 | 12:15:00 | 12:45:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Removed diverter from rotary.
2007-10-21 | 12:45:00 | 13:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to installing overshot joint and diverter.
2007-10-21 | 13:00:00 | 14:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed overshot and made up to flange on BOP body.
2007-10-21 | 14:30:00 | 15:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed diverter in rotary and locked same in place..
2007-10-21 | 15:00:00 | 15:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held time out for safety meeting with rig crew.
2007-10-21 | 15:30:00 | 17:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Continued to nipple up overshot. Removed diverter bails. Installed bushings for manual slips.
2007-10-21 | 17:15:00 | 17:30:00 | 0 | drilling -- bop activities | ok | Held toolbox talk prior to rigging for and testing IBOP and kelly hose.
2007-10-21 | 17:30:00 | 20:45:00 | 0 | drilling -- bop activities | ok | Rigged up testing swage with weco and hooked up hose. Tested upper and lower IBOP to 20/345 bar 5/10 min. Broke out swage. Checked dies on AFT PRS. Cleared V-door before picking up BHA.
2007-10-21 | 20:45:00 | 21:00:00 | 0 | drilling -- trip | ok | Held toolbox talk prior to picking up 12 1/4" BHA.
2007-10-21 | 21:00:00 | 21:30:00 | 0 | drilling -- trip | ok | Picked up and RIH with powerdrive, hung off in slips.Made up and run in with powerdrive, powerpulse, NMDC and 8" DC double.
2007-10-21 | 21:30:00 | 22:45:00 | 0 | drilling -- trip | ok | Held time out for safety meeting with rig crew for nigthshift.
2007-10-21 | 22:45:00 | 00:00:00 | 0 | drilling -- trip | ok | Made up and ran in with powerdrive, powerpulse, ARCm NMDC and pony. Made up 2 x 8" DC double. Observed leakage on flange between overshot and B OP.
2007-10-22 | 00:00:00 | 01:30:00 | 0 | drilling -- trip | ok | Laid down jar from derrick. Picked up new jar from deck and made up to BHA. Meanwhile worked to repair leaking flange. Observed that flange appeared to be biased towards on e side.
2007-10-22 | 01:30:00 | 02:45:00 | 0 | interruption -- oth er | ok | Broke and thigthened bolts as required whilst levelling BOP
2007-10-29 | 15:45:00 | 22:00:00 | 0 | drilling -- trip | ok | Removed auto-slips from rotary and inserted master bushings. LO 12 1/4" BHA from 90 m to surface.
2007-10-30 | 00:00:00 | 02:30:00 | 0 | drilling -- trip | ok | POOH with wear bushing and LO same.
2007-10-30 | 02:30:00 | 03:30:00 | 0 | drilling -- casing | ok | MU cmt head assembly and RB in derrick.
2007-10-30 | 03:30:00 | 06:00:00 | 0 | drilling -- casing | ok | Cleared and tidied rig floor off excess equipment. RU csg tong, handling equipment and FAC tool. Prepared to run 9 5/8" csg.
2007-10-30 | 06:00:00 | 09:00:00 | 0 | drilling -- casing | ok | RU csg tong and handling equipment. Prepared to run 9 5/8" csg.
2007-10-30 | 09:00:00 | 10:00:00 | 0 | interruption -- other | ok | Sorted out power supply problem for csg. tong.
2007-10-30 | 10:00:00 | 12:00:00 | 0 | drilling -- casing | ok | Installed elevators, flush mounted slips, bails and FAC circulating tool. Prepared to run 9 5/8" csg.
2007-11-02 | 15:00:00 | 17:30:00 | 0 | drilling -- casing | ok | Released PADPRT, LO cement head and 2 jnts of 5 1/2" HWDP. POOH with running tool on 5 1/2" HWDP landing string from 120 m to OOH.
2007-11-03 | 00:00:00 | 01:00:00 | 0 | drilling -- casing | ok | POOH with wear bushing running string.
2007-11-03 | 12:00:00 | 13:15:00 | 0 | drilling -- drill | ok | POOH with RTTS running tool assembly from 348 m.
2007-11-03 | 13:15:00 | 14:00:00 | 0 | drilling -- drill | ok | MU jetting sub and RIH to jet BOP, 2000 lpm / 9 bar / 10 rpm. POOH with jetting tool and LO same.
2007-11-03 | 14:00:00 | 14:45:00 | 0 | drilling -- drill | ok | Took time-out for safety to investigate doghouse being hit by unidentified projectile. Ascertain that dowel pin on dog collar sheared off and struck window at hig h speed.
2007-11-03 | 14:45:00 | 16:30:00 | 0 | drilling -- drill | ok | RIH to 28 m. MU side entry sub and TIW. Closed annular. Pumped air through choke line and displaced riser contents to trip tank. RD side entry sub and TIW. POOH from 28 m.
2007-11-03 | 16:30:00 | 00:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held tool box meeting prior to ND diverter. Removed elevators and RU for pulling diverter. Pulled diverter to rig floor. Removed and secured diverter housing on pipe set-back. ND and pulled slick joint.
2007-11-04 | 00:00:00 | 03:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | Removed BOP tension cylinders and sat BOP on test stump.
2007-11-04 | 03:00:00 | 05:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | RU handling equipment for running Claxton tool and PU tool. Removed master bushing. Run in with Claxton tool and re-inserted master bushing.
2007-11-04 | 05:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | Run in and MU Claxton tool to NT2 connector on HPDR BOP joint. MU claxton tool lock-dogs to min 1000 lf.lbs torque with air-operated tool.
2007-11-04 | 07:00:00 | 19:00:00 | 0 | interruption -- maintain | ok | Performed house-keeping and cleaned drill-fllor, cantiliver, pump room and sack store.
2007-11-04 | 07:00:00 | 19:00:00 | 0 | interruption -- maintain | ok | Meanwhile performed testing of production systems. Experienced black-out from 11:28 to 12:20.
2007-11-04 | 19:00:00 | 19:30:00 | 0 | drilling -- bop/wellhead e quipment | ok | Performed hand-over and held tool box meeting before pulling HPDR BOP joint.
2007-11-04 | 19:30:00 | 20:30:00 | 0 | interruption -- other | ok | Software problems due to black-out. Could not operate break on draw work.
2007-11-04 | 20:30:00 | 22:15:00 | 0 | drilling -- bop/wellhead e quipment | ok | Disconnected HPDR BOP joint. Removed master bushing. POOH with Claxton tool and HPDR BOP joint and re-inserted master bushing. LD claxton tool and ris er joint. Installed protector on BOP riser joint flange.
2007-11-04 | 22:15:00 | 23:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | Installed handling tool/flange on top of HPDR tension joint at X-mas tree deck.
2007-11-04 | 23:00:00 | 00:00:00 | 0 | drilling -- other | ok | Removed scaffolding in moonpool.
2007-11-05 | 00:00:00 | 02:00:00 | 0 | drilling -- other | ok | Continued removing scaffolding in moonpool and on X-mas tree deck. Installed hatch on F-4
2007-11-05 | 02:00:00 | 06:00:00 | 0 | interruption -- maintain | ok | Started changing wires on aft PRS. Meanwhile prepared for skidding rig to F-14.
2007-11-05 | 06:00:00 | 11:00:00 | 0 | interruption -- maintain | ok | Continued changing wires on aft PRS. Meanwhile prepared for skidding rig to F-14 and cleaned pits. Operation continues on F-14
2007-11-05 | 06:00:00 | 11:00:00 | 0 | interruption -- maintain | ok | .
2008-02-04 | 21:00:00 | 00:00:00 | 0 | moving -- skid | ok | Prepared for skidding. Simultaneously pressure tested the rig manifold and changed out riser tension cylinder
2008-02-04 | 21:00:00 | 00:00:00 | 0 | moving -- skid | ok | .
2008-02-05 | 00:00:00 | 01:30:00 | 0 | moving -- skid | ok | Continued preparing for skidding. Simultaneously pressure tested the rig manifold and changed out riser tension cylinder.
2008-02-05 | 01:30:00 | 02:00:00 | 0 | moving -- skid | ok | Held tool box talk prior to skidding of the cantilever.
2008-02-05 | 02:00:00 | 03:00:00 | 0 | moving -- skid | ok | Skidded cantilever from F-12 to F-4.
2008-02-05 | 03:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Continued changing out tension cylinder on riser. Simultaneously pressure tested the rig manifold.
2008-02-05 | 06:00:00 | 15:30:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Changed out the two remaining tension cylinders on F-4 riser. Simultaneously pressure tested stab-in valves to 345 bars. Prepared for slip and cut
2008-02-05 | 06:00:00 | 15:30:00 | 0 | drilling -- bop/wellhead equipm ent | ok | .
2008-02-05 | 15:30:00 | 17:00:00 | 0 | interruption -- maintain | ok | Slipped and cut drill line. Re-calibrated block and checked the crow O-matic. Simultaneously nippled down the riser lifting sub.
2008-02-05 | 17:00:00 | 17:45:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Continued nippling down the riser lifting sub. Checked the torque on the Claxton riser handling tool, prior to lifting in same with the HP riser BOP joi nt attached.
2008-02-05 | 17:45:00 | 18:30:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Held tool box talk prior to remove the master bushing, outer ring and the hatch cover on F-4.
2008-02-05 | 18:30:00 | 19:00:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Retrieved the riser lifting sub, and laid out same. Cleared drill floor. Prepared for picking up the HP riser BOP joint.
2008-02-05 | 19:00:00 | 19:15:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Held tool box talk prior to install the HP riser BOP joint.
2008-02-05 | 19:15:00 | 21:30:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Removed master bushing and ran with the HP riser BOP joint and landed same. Installed master bushing. Made up the HP riser BOP joint.
2008-02-05 | 21:30:00 | 00:00:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Built scaffolding around the HP riser BOP joint in the Moon Pool.
2008-02-06 | 00:00:00 | 00:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Continued building scaffolding around the HP riser BOP joint in the Moon Pool.
2008-02-06 | 00:15:00 | 01:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | Released the Claxton tool. Removed master bushing, pulled the Claxton up to the Drill Floor. Installed the master bushing.
2008-02-06 | 01:30:00 | 03:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Moved the BOP into well centre. Simultaneously prepared the diverter and slick jnt on the Drill Floor.
2008-02-06 | 03:00:00 | 03:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk with new crew prior to continue nippling up the BOP and diverter.
2008-02-06 | 03:15:00 | 06:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Position the BOP and commenced making up the tension cylinders to BOP.
2008-02-06 | 06:00:00 | 07:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Made up BOP tension cylinders.
2008-02-06 | 07:00:00 | 07:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk prior to remove the master bushing and installation of the overshot and landing the diverter.
2008-02-06 | 07:15:00 | 11:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Removed the master bushing and installed the overshot and landed the diverter. Made up the NT2 connector. Meanwhile rigged down the diverter ha ndling equipment.
2008-02-07 | 14:15:00 | 15:30:00 | 0 | drilling -- bop activities | ok | Retrieved the test plug and laid out same.
2008-02-07 | 15:30:00 | 16:00:00 | 0 | drilling -- other | ok | Made up the RTTS retrieving tool.
2008-02-07 | 16:00:00 | 16:15:00 | 0 | drilling -- other | ok | Held tool box talk prior to displacethe well above the RTTS plug to OBM.
2008-02-08 | 02:45:00 | 04:30:00 | 0 | drilling -- other | ok | Laid out the RTTS plug. Found cement on top of the hydraulic slip. The retrieving tool was not fully entered, 5 turns out. Packing element damaged in the bottom p art.
2008-02-08 | 04:30:00 | 05:15:00 | 0 | drilling -- other | ok | Continued POOH with 7 std of 5½" DP below the RTTS plug, from 280 m to surface.
2008-02-08 | 05:15:00 | 06:00:00 | 0 | drilling -- bop activit ies | ok | Cleaned and cleared the drill floor. Simultaneously flushed lines from CMT unit to BOP. Commenced pressure testing of the shear rams to 20/310 bars 5/10 mins.
2008-02-08 | 06:00:00 | 07:00:00 | 0 | drilling -- trip | ok | Cleaned and cleared drill floor and prepared for handling the 8½" drilling BHA. Meanwhile completed the pressure test of the shear rams to 20/310 bars 5/10 mins,
2008-02-08 | 06:00:00 | 07:00:00 | 0 | drilling -- trip | ok | 2.1m³ pumped 2m³ in return.
2008-02-08 | 07:00:00 | 07:15:00 | 0 | drilling -- trip | ok | Held tool box talk prior to pick up and M/U 8½" drill BHA.
2008-02-08 | 07:15:00 | 11:00:00 | 0 | drilling -- trip | ok | M/U 8½" drilling BHA as per Schlumberger DD&MWD. Installed radio active sources.
2008-02-16 | 07:15:00 | 09:45:00 | 0 | drilling -- trip | ok | Broke out and laid down NM HWDP. Removed RA-source. Broke out and laid down Isonic, Telescope, Ecoscope and Powerdrive.
2008-02-16 | 09:45:00 | 10:00:00 | 0 | drilling -- trip | ok | Cleaned and tidied drillfloor.
2008-02-16 | 10:00:00 | 10:15:00 | 0 | drilling -- wait | ok | General muster alarm. Crews mustered according to list. Non critical alarm.
2008-02-16 | 10:15:00 | 10:45:00 | 0 | drilling -- trip | ok | Continued to clean and tidy drillfloor. Meanwhile changed rollers for IBOP actuator on TDS.
2008-02-16 | 10:45:00 | 11:45:00 | 0 | drilling -- trip | ok | Prepared for picking up 5 1/2" DP from deck.
2008-02-16 | 10:45:00 | 11:45:00 | 0 | drilling -- trip | ok | Meanwhile
2008-02-16 | 10:45:00 | 11:45:00 | 0 | drilling -- trip | ok | -Moved power rollers on cantilever
2008-02-16 | 10:45:00 | 11:45:00 | 0 | drilling -- trip | ok | -Prepared for running WL
2008-02-16 | 10:45:00 | 11:45:00 | 0 | drilling -- trip | ok | -Inspected, cleaned and greased PS-21 slips
2008-02-16 | 11:45 | 12:00:00 | 0 | drilling -- trip | ok | Held toolbox talk prior to inspection and service on AFT PRS.
2008-02-16 | 12:00:00 | 12:45:00 | 0 | drilling -- other | ok | Inspected and serviced AFT PRS. Found loose bar (54 cm / 560 g) sitting in hoses/junction box below upper drive.
2008-02-16 | 12:45:00 | 13:15:00 | 0 | interruption -- o ther | ok | Evaluated finding. Suspected drag chain in PRS beam.
2008-02-16 | 13:15:00 | 13:45:00 | 0 | interruption -- o ther | ok | Inspected drag chain in PRS beam. Could not identify bar (FG) comming from PRS beam.
2008-02-16 | 13:45:00 | 14:15:00 | 0 | interruption -- o ther | ok | Performed derrick inspection from PRS to crown block.
2008-02-16 | 14:15:00 | 19:00:00 | 0 | interruption -- o ther | ok | Removed lid and inspected inside PRS upper drive. Found rotational dragchain in AFT PRS upper drive to be damaged. Identified origin of loose bar (FG) to be cross member in rotational dragchain. Assessed damage. Decided to perform repair of dragchain.
2008-02-16 | 19:00:00 | 00:00:00 | 0 | interruption -- o ther | ok | Repaired rotational dragchain in AFT PRS upper drive.
2008-02-16 | 19:00:00 | 00:00:00 | 0 | interruption -- o ther | ok | Meanwhile :
2008-02-16 | 19:00:00 | 00:00:00 | 0 | interruption -- o ther | ok | -Built cable head for WL
2008-02-16 | 19:00:00 | 00:00:00 | 0 | interruption -- o ther | ok | -Laid out MDT tools
2008-02-16 | 19:00:00 | 00:00:00 | 0 | interruption -- o ther | ok | -Rigged load sensors on WL unit
2008-02-17 | 00:00:00 | 01:00:00 | 0 | interruption -- other | ok | Repaired rotational dragchain in AFT PRS upper drive. Meanwhile tested MDT tools
2008-02-17 | 01:00:00 | 02:15:00 | 0 | interruption -- other | ok | Repaired rotational dragchain in AFT PRS upper drive. Temporarily halted testing of MDT tools due to loading of drillpipe onto cantilever/pipe-deck.
2008-02-17 | 02:15:00 | 03:15:00 | 0 | interruption -- other | ok | Repaired rotational dragchain in AFT PRS upper drive. Meanwhile tested MDT tools.
2008-02-17 | 03:15:00 | 06:00:00 | 0 | formation evaluation -- log | ok | Tested MDT tools. Calibrated weight sensor. Brought WL rigging equipment to drillfloor.
2008-02-17 | 06:00:00 | 08:45:00 | 0 | formation evaluation -- log | ok | Rigged up sheaves and cable. Brought logging tools to drillfloor.
2008-02-17 | 08:45:00 | 09:00:00 | 0 | formation evaluation -- log | ok | Held toolbox talk prior to making up logging string.
2008-02-17 | 09:00:00 | 10:00:00 | 0 | formation evaluation -- log | ok | Made up MDT toolstring.
2008-02-17 | 10:00:00 | 10:30:00 | 0 | formation evaluation -- log | ok | Tested MDT tools on surface prior to RIH.
2008-02-17 | 10:30:00 | 10:45:00 | 0 | formation evaluation -- log | ok | Re-positioned lower sheave due to unfavorable cable allignment.
2008-02-17 | 10:45:00 | 11:15:00 | 0 | formation evaluation -- log | ok | RIH with MDT logging string on 7/48 cable. Perfomed shallow test - negative.
2008-02-17 | 11:15:00 | 11:45:00 | 0 | formation evaluation -- log | ok | POOH with MDT logging tools. Performed checks on surface - ok.
2008-02-17 | 17:45:00 | 19:30:00 | 0 | interruption -- repair | ok | POOH with MDT logging string on 7/48 cable from 2671 m MD to surface.
2008-02-17 | 19:30:00 | 23:00:00 | 0 | interruption -- repair | ok | Checked cable, cable head and surface cables - ok.
2008-02-17 | 23:00:00 | 00:00:00 | 0 | interruption -- repair | ok | Isolated and checked MDT string components as required.
2008-02-18 | 00:00:00 | 00:30:00 | 0 | workover -- wai t | ok | General alarm - crews mustered according to list. Announced possible gas in wellhead area. Removed WL toolstring from well - well stable - stood by for securing well. Investiga ted alarm and found fault on gas sensor. Resumed work.
2008-02-18 | 00:30:00 | 03:15:00 | 0 | interruption -- r epair | ok | Continued isolating and checking MDT string components as required.
2008-02-18 | 03:15:00 | 03:30:00 | 0 | interruption -- r epair | ok | Found both MRPO pumps in MDT toolstring to be faulty. Only one back up MRPO pump available on rig. Discussed situation. Decided to run simplified string with only 1 pump.
2008-02-18 | 03:30:00 | 05:45:00 | 0 | interruption -- r epair | ok | Traced tools for simplifed MDT toolstring. Brought tools to drillfloor. Made up and tested simplified MDT toolstring.
2008-02-18 | 05:45:00 | 06:00:00 | 0 | interruption -- r epair | ok | RIH with simplified MDT toolstring on 7/48 cable.
2008-02-19 | 06:00:00 | 08:45:00 | 0 | interruption -- fish | ok | Rigged up for cut and thread fishing. Suspended upper sheave in dedicated sling in derrick. Suspended lower sheave in V-door above HTS, secured same with slings.
2008-02-19 | 08:45:00 | 09:15:00 | 0 | interruption -- fish | ok | Held toolbox talk prior to performing cut and thread.
2008-02-19 | 09:15:00 | 10:00:00 | 0 | interruption -- fish | ok | Picked up singel and made up x-over. Laid out single.
2008-02-19 | 10:00:00 | 11:15:00 | 0 | interruption -- fish | ok | Held toolbox talk prior to inserting PS-30 automatic slips.
2008-02-19 | 11:15:00 | 13:30:00 | 0 | interruption -- fish | ok | Rigged up and changed to PS-30 automatic slips. Slacked off wire and hung off in slips with T-bar.
2008-02-19 | 13:30:00 | 14:00:00 | 0 | interruption -- fish | ok | Pull tested T-bar. Performed toolbox talk for continuation of operations.
2008-02-19 | 14:00:00 | 14:45:00 | 0 | interruption -- fish | ok | Re-set grip on T-bar in order to get more slack on wire and be able to lay grapple/drain sub on the drilfloor. Ran WL up/down to test counter balance weights on wire - ok. Threade d first joint.
2008-02-24 | 16:30:00 | 20:15:00 | 0 | interruption -- fish | ok | POOH with 5 1/2" DP from 2703 m MD to surface.
2008-02-24 | 20:15:00 | 22:15:00 | 0 | interruption -- fish | ok | Installed C-plate in rotary and hung off MDT toolstring. Broke off tool socket sitting in grapple. Parted and pulled toolstring sections using tugger. Broke off grapple and circulatio n sub and set back last stand of 5 1/2" DP.
2008-02-24 | 22:15:00 | 22:30:00 | 0 | drilling -- bop/wellh ead equipment | ok | Held toolbox talk prior to picking up jet sub and BOP test plug.
2008-02-25 | 11:45:00 | 12:00:00 | 0 | drilling -- bop/wellhead equipment | ok | POOH with 5" DP from 160 m MD to surface. Broke out and laid down jet sub.
2008-02-25 | 12:00:00 | 13:30:00 | 0 | formation evaluation -- log | ok | Cleaned and tidied drillfloor prior to bringing in logging tools.
2008-02-25 | 13:30:00 | 13:45:00 | 0 | formation evaluation -- log | ok | Held toolbox talk prior to running MDT toolstring.
2008-02-27 | 21:30:00 | 23:00:00 | 0 | formation evalu ation -- log | ok | Parted and pulled MDT toolstring sections using C-plate and tugger. Found signs of short circuit in bulkhead coupling. Inner rubber packing on quicksilver probe was worn and tor n.
2008-02-27 | 23:00:00 | 00:00:00 | 0 | formation evalu ation -- log | ok | Cleared and tidied drillfloor. Ran stand of 5" DP to help breaking off 5" saver sub.
2008-02-28 | 00:00:00 | 03:45:00 | 0 | formation evalu ation -- log | ok | Changed from 5" to 5 1/2" saver sub in TDS. Changed die holders and dies in TDS torque wrench. Pulled 5" stand and racked back. Broke and laid down 5" pup, 5" x 5 1/2" x-over and AH-3 1/2" x 4 1/2" IF x-over. Meanwhile packed and disconnected MDT and WL containers for backload/removal.
2008-02-28 | 03:45:00 | 06:00:00 | 0 | formation evalu ation -- log | ok | Cleared and tidied drillfloor. Brought casing running equipment to V-door. Removed PS-30 automatic slips. Installed Odfjell FMS in rotary. Positioned Odfjell casing tong on rails in f ront of IR. Prepared for rigging down WL sheave.
2008-02-28 | 06:00:00 | 07:00:00 | 0 | formation evalu ation -- log | ok | RD WL sheave and installed HTS roller section. Drifted pipe on setback.
2008-02-28 | 07:00:00 | 09:30:00 | 0 | drilling -- casin g | ok | Held tool box talk for RU to run 7" liner. Moved HTS rollers to aft end of cantiliver. Changed inserts in elevator and RU Odfjell csg tong.
2008-03-01 | 10:30:00 | 16:45:00 | 0 | drilling -- casi ng | ok | POOH with 7" liner hanger RT on 5 1/2" DP from 1520 m to OOH. Inspected liner hanger RT. Found hydraulic release activated. All items intact on RT.
2008-03-01 | 16:45:00 | 18:00:00 | 0 | drilling -- casi ng | ok | Cleared rig floor and serviced PS21 slips. Installed and function tested PS21 slips.
2008-03-01 | 16:45:00 | 18:00:00 | 0 | drilling -- casi ng | ok | Had approx. 30 min interruption in operation due to 65 knots wind.
2008-03-02 | 06:00:00 | 07:00:00 | 0 | drilling -- trip | ok | LO 5 1/2" DP 24.7 lbs/ft in singles from 309 m to OOH.
2008-03-02 | 07:00:00 | 07:30:00 | 0 | drilling -- trip | ok | Held time-out for safety with day crew. Inspected derrick in daylight due to yesterdays dropped object.
2008-03-02 | 09:00:00 | 10:45:00 | 0 | drilling -- trip | ok | LO 10 stds of 5 1/2" DP 24.7 lbs/ft in singles.
2008-03-02 | 10:45:00 | 16:00:00 | 0 | interruption -- maint ain | ok | Had tool box talk with drill crew. Performd cut and slip of drill line.
2008-03-02 | 16:00:00 | 19:45:00 | 0 | drilling -- trip | ok | Continued to LO stds of 5 1/2" DP 24.7 lbs/ft in singles.
2008-03-02 | 19:45:00 | 20:30:00 | 0 | drilling -- casing | ok | Changed to 3 1/2" handling equipment and installed master bushings to be able to MU spear assembly. Found that pack-off on spear assembly was wrong size. Discussed further action.
2008-03-02 | 20:30:00 | 21:00:00 | 0 | drilling -- casing | ok | Changed back to 5 1/2" handling equipment. Made arrangement with town to mobilize the correct size pack-off with helicopter.
2008-03-02 | 21:00:00 | 22:15:00 | 0 | drilling -- trip | ok | Continued to LO stds of 5 1/2" DP 24.7 lbs/ft in singles.
2008-03-02 | 22:15:00 | 23:00:00 | 0 | drilling -- casing | ok | Changed to 3 1/2" handling equipment and installed master bushings to be able to MU spear assembly.
2008-03-02 | 23:00:00 | 00:00:00 | 0 | drilling -- casing | ok | Held tool box talk prior to picking up spear. MU spear assembly according to Weatherford's instructions.
2008-03-03 | 00:00:00 | 00:30:00 | 0 | drilling -- ca sing | ok | Continued MU spear assembly according to Weatherford's instructions.
2008-03-03 | 00:30:00 | 01:45:00 | 0 | drilling -- ca sing | ok | Re-arranged DP in derrick whilst waiting for new pack-off for spear assembly to arrive with helicopter.
2008-03-03 | 01:45:00 | 03:00:00 | 0 | drilling -- ca sing | ok | Installed and MU new pack-off on spear assembly.
2008-03-05 | 00:00:00 | 05:30:00 | 0 | drilling -- casing | ok | POOH with 7" liner and RB in derrick from 560 m to OOH.
2008-03-05 | 05:30:00 | 06:00:00 | 0 | drilling -- casing | ok | RD Odfjell csg tong and csg handling equipment.
2008-03-05 | 06:00:00 | 08:00:00 | 0 | drilling -- casing | ok | RD Odfjell csg tong and csg handling equipment.
2008-03-07 | 08:30:00 | 11:30:00 | 0 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5" DP from 74 m to 46 m MD. Removed PS21 slips and installed master bushings. LO 8 1/2" wiper trip BHA from 46 m to OOH. Cle aned and cleared rig floor of excess equipment.
2008-03-07 | 11:30:00 | 14:45:00 | 0 | drilling -- casing | ok | Held tool box talk for RU to run 7" liner. Installed HTS rollers. Changed inserts in elevator and RU Odfjell csg tong.
2008-03-07 | 14:45:00 | 16:00:00 | 0 | drilling -- casing | ok | Inspected PRS and TDS for loose items. Greased PRS and TDS.
2008-03-09 | 18:45:00 | 20:30:00 | 0 | drilling -- c asing | ok | POOH with 7" liner hanger RT on HWDP from 112 m to OOH. Removed PS21 auto slips and installed manual slips. Disconnected HTS back rollers. BO and LD 7" liner hanger RT. Found both wiper plugs attached to liner hanger RT and both darts and one sponge ball inside RT.
2008-03-09 | 20:30:00 | 21:45:00 | 0 | drilling -- c asing | ok | Changed to 3 1/2" handling equipment. PU 3 1/2" fishing assembly. Broke connections and LO Mærsk pup joint and XO. Cleaned and cleared rig floor.
2008-03-09 | 21:45:00 | 00:00:00 | 0 | drilling -- c asing | ok | RU 7" csg tong and handling equipment. Inspected PRS dies and rollers.
2008-03-10 | 00:00:00 | 00:30:00 | 0 | drilling -- casing | ok | PU 7" liner shoe track std and attempted to break baker locked connections. Unsucessful. RB in derrick.
2008-03-10 | 06:00:00 | 14:00:00 | 0 | drilling -- casing | ok | POOH and LO 7" liner in singles from 671 m to OOH.
2008-03-10 | 14:00:00 | 14:45:00 | 0 | drilling -- casing | ok | PU 7" liner shoe track std and attempted to break baker locked connections with csg tong without sucess.
2008-03-10 | 14:45:00 | 17:45:00 | 0 | drilling -- casing | ok | RD csg tong and 7" liner handling equipment.
2008-03-10 | 14:45:00 | 17:45:00 | 0 | drilling -- casing | ok | Meanwhile performed csg test. Observed pressure rise to 290 bar before dropping, 2426 ltrs pumped and 1600 ltrs returned.
2008-03-10 | 17:45:00 | 20:00:00 | 0 | drilling -- casing | ok | PU 7" liner shoe track std and broke baker locked connections using manual tongs. Cleaned and cleared rig floor and changed to 5 1/2" handling equipme nt.
2008-03-11 | 06:00:00 | 07:00:00 | 0 | drilling -- bop/wellhead equipment | ok | POOH with jet sub/BOP test plug on 5 1/2" DP from 165 m to OOH. Broke out and LD test plug.
2008-03-11 | 07:00:00 | 08:00:00 | 0 | drilling -- other | ok | RU 3 1/2" handling equipment. MU kelly cock and grey valve assembly for testing.
2008-03-11 | 08:00:00 | 12:30:00 | 0 | drilling -- other | ok | Tested 3 1/2" kelly cock and grey valve. Tested kill and standpipe manifolds. Tested 5 1/2" kelly cock and grey valve.
2008-03-11 | 08:00:00 | 12:30:00 | 0 | drilling -- other | ok | Meanwhile changed out drill line spooler.
2008-03-11 | 12:30:00 | 13:00:00 | 0 | drilling -- other | ok | Took time-out for safety due to dropped bulldog clamps from drill line.
2008-03-11 | 13:00:00 | 16:00:00 | 0 | interruption -- other | ok | Continued to change out drill line spooler.
2008-03-13 | 04:30:00 | 06:00:00 | 0 | drilling -- t rip | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 57 m to OOH. LD 6" PDC bit and scraper assemblies.
2008-03-13 | 06:00:00 | 06:30:00 | 0 | drilling -- t rip | ok | Held tool box talk prior to make up and RIH with EZSV plug and Circ. Sub. Made up EZSV plug and Circ. Sub.
2008-03-14 | 06:00:00 | 07:15:00 | 0 | drilling -- drill | ok | POOH with 3½" DP and EZSV plug RT to surface.
2008-03-14 | 07:15:00 | 07:45:00 | 0 | drilling -- trip | ok | Changed out PS -21 slips to master bushing. L/O EZSV plug RT.
2008-03-14 | 07:45:00 | 08:00:00 | 0 | drilling -- other | ok | Held tool box talk prior to RIH with BOP/riser clean out assy.
2008-03-14 | 11:45:00 | 13:15:00 | 0 | drilling -- other | ok | POOH with clean out assy and laid out same.
2008-03-14 | 13:15:00 | 14:00:00 | 0 | drilling -- other | ok | Cleaned and cleared rig floor. Inspected aft PRS. Performed daily derrick inspection. Simultaneously prepared mule shoe for 7" line clean out assy.
2008-03-15 | 05:30:00 | 06:00:00 | 0 | completion -- circul ating conditioning | ok | Commenced to wash down from 3380m to 3420m. 40 rpm, 1000 lpm, 110 bars.
2008-03-17 | 15:45:00 | 16:15:00 | 0 | completion -- circulating conditioni ng | ok | Broke out the Razor back assy and laid out same.
2008-03-17 | 16:15:00 | 17:00:00 | 0 | plug abandon -- mechanical plug | ok | Changed to 5½" handling equipment and picked up the GTV RT/GTV plug.
2008-03-17 | 17:00:00 | 17:15:00 | 0 | plug abandon -- mechanical plug | ok | Prepared for RIH with the GTV plug on 5½" HWDP.
2008-03-17 | 17:15:00 | 20:30:00 | 0 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
2008-03-18 | 07:00:00 | 07:45:00 | 0 | plug abandon -- mill | ok | Held tool box talk prior to break/lay out the GTV RT.
2008-03-18 | 07:45:00 | 09:00:00 | 0 | plug abandon -- mill | ok | Inspected the aft PRS's dies. POOH with the GTV RT from 612m to above the BOP.
2008-03-18 | 09:00:00 | 09:45:00 | 0 | plug abandon -- mill | ok | Held tool box talk and closed the shear rams and pressure tested the GTV plug from above to 345 bars 10 min., volume pumped 830 litres - return 83 0 litres.
2008-03-18 | 09:45:00 | 10:00:00 | 0 | plug abandon -- mill | ok | Laid out the GTV RT.
2008-03-18 | 10:00:00 | 10:15:00 | 0 | plug abandon -- mill | ok | Cleaned and cleared the rig floor.
2008-03-18 | 11:00:00 | 12:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | POOH with the wear bushing. Laid out wear bushing and RRT. Found metal chip on the wear bushing.
2008-03-18 | 12:30:00 | 12:45:00 | 0 | drilling -- casing | ok | Picked up WH jetting sub.
2008-03-18 | 12:45:00 | 13:15:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor.
2008-03-18 | 13:15:00 | 14:00:00 | 0 | drilling -- casing | ok | RIH with the WH jetting sub from surface to 129m. Discussed forward plan with town.
2008-03-18 | 14:00:00 | 16:45:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor.
2008-03-18 | 16:45:00 | 18:00:00 | 0 | drilling -- casing | ok | Continued RIH to 138m and washed WH area with 5 rpm 2650 lpm 17 bars. POOH and laid out jetting sub.
2008-03-18 | 18:00:00 | 00:00:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor. Meanwhile cleaned the moon pool, pit room and pump room.
2008-03-19 | 00:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor. Meanwhile cleaned the moon pool, pit room and pump room.
2008-03-19 | 06:00:00 | 15:45:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor. Meanwhile cleaned the moon pool, pit room, pump room and general ma intenance.
2008-03-19 | 15:45:00 | 16:30:00 | 0 | completion -- bop/wellhead equipm ent | ok | Held tool box talk and picked/made up the 10 3/4" Lock down sub.
2008-03-19 | 19:00:00 | 21:00:00 | 0 | completion -- bop/wellhead equipm ent | ok | POOH with the 10 3/4" Lock down sub RT and laid out same.
2008-03-19 | 21:00:00 | 22:45:00 | 0 | interruption -- waiting on weather | ok | WOW. Meanwhile inspected and serviced the aft PRS.
2008-03-19 | 22:45:00 | 23:15:00 | 0 | interruption -- waiting on weather | ok | WOW. Held time out due to LTA on main deck.
2008-03-19 | 23:15:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | WOW. Continued servicing the aft PRS.
2008-03-20 | 00:00:00 | 03:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Serviced and inspected the TDS.
2008-03-20 | 03:00:00 | 05:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Changed out the wash pipe.
2008-03-20 | 05:00:00 | 06:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Cleaned and cleared the rig floor
2008-03-20 | 06:00:00 | 07:15:00 | 0 | interruption -- waiting on weath er | ok | WOW. Cleaned and cleared the rig floor.
2008-03-20 | 07:15:00 | 19:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Performed general maintenance. Cleaned kill manifold. Had derrick inspection. Serviced Carrier rollers, spinner and tracks on aft Roughn eck.
2008-03-20 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Cleaned rig floor. Cleaned pit # 7. Performed maintenance on the aft PRS and the TDS.
2008-03-21 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on w eather | ok | WOW. Greased the UPR track on the PRS beam. Functioned main flow line valve 1250 psi. Transported 6 flood light to the finger board level in the derrick.
2008-03-21 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on w eather | ok | WOW prior to retrieve the HP drilling riser. Meanwhile cleaned stand pipe/Choke line manifold. Changed oil on the TDS. Performed general maintenance and PM's. Changed out the cathead wire.
2008-03-21 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | WOW prior to retrieve the HP drilling riser. Meanwhile prepared tools and lifting equipment, for nippling down the Diverter,BOP and the HPDR. Commenced in
2008-03-21 | 19:00:00 | 00:00:00 | 0 | eather | ok | stallation of flood light in derrick.
2008-03-21 | 19:00:00 | 00:00:00 | 0 | eather | ok | Time Wind speed Wind direction Sea Wave direction
2008-03-21 | 19:00:00 | 00:00:00 | 0 | eather | ok | Knots deg m deg
2008-03-21 | 19:00:00 | 00:00:00 | 0 | eather | ok | 22:00 41/47 30° 6.1/9.7 360°
2008-03-21 | 19:00:00 | 00:00:00 | 0 | eather | ok | 23:00 42/47 30° 6.2/9.8 10°
2008-03-21 | 19:00:00 | 00:00:00 | 0 | eather | ok | 00:00 43/48 30° 6.1/9.7 360°
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | WOW prior to retrieve the HP drilling riser. Continued installation of flood light in derrick.
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | 00:30 40/45 30° 6.4/10.1 360°
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | 02:00 42/47 30° 6.1/9.6 10°
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | 03:00 39/43 30° 6.0/9.6 10°
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | 04:30 37/41 20° 5.6/8.8 360°
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | 05:00 35/41 30° 5.3/8.4 10°
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | 06:00 34/38 20° 4.9/7.9 10°
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | WOW prior to retrieve the HP riser. Meanwhile installed flood light in derrick. Commenced changing out the seal assy of BOP door. Cleaned pit # 9 & 11. Perf ormed general maintenance and PM's.
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | Moved CTS funnel from F-9 to F-1. Installed cover in CTS funnel.
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 07:00 24/30 30° 4.4/10 10°
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 09:00 18/26 28° 4/10.4 30°
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 11:00 14/20 24° 3.7/7.8 40°
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 13:00 9/15 7° 3/9.4 340°
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 15:00 15/21 300° 2.8/9.8 225°
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 17:00 20/23 315° 2.9/8.9 250°
2008-03-22 | 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 19:00 19/22 320° 2.6/4.1 340°
2008-03-22 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | WOW prior to retrieve the HP riser. Installed flood light in derrick. Cleaned pit # 6,8 & 10.
2008-03-22 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-22 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | 21:00 18/22 320° 2.6/4.2 320°
2008-03-22 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | 23:00 20/23 340° 2.5/4 340°
2008-03-23 | 00:00:00 | 06:00:00 | 0 | interruption -- | ok | WOW prior to retrieve the HP riser. Completed installation of the flood light in the derrick. House keeping in the moon pool.
2008-03-23 | 00:00:00 | 06:00:00 | 0 | ther | ok | Time Wind speed Wind direction Sea Wave direction
2008-03-23 | 00:00:00 | 06:00:00 | 0 | ther | ok | Knots deg m deg
2008-03-23 | 00:00:00 | 06:00:00 | 0 | ther | ok | 01:00 7/9 360° 2.7/3.9 340°
2008-03-23 | 00:00:00 | 06:00:00 | 0 | ther | ok | 03:00 11/15 340° 2.4/4.1 340°
2008-03-23 | 00:00:00 | 06:00:00 | 0 | ther | ok | 05:00 15/18 350° 2.7/4.3 340°
2008-03-23 | 00:00:00 | 06:00:00 | 0 | ther | ok | 07:00 12/14 350° 2.9/4.6 340°
2008-03-23 | 06:00:00 | 19:00:00 | 0 | interruption -- | ok | WOW prior to retrieve the HP riser. Changed out of BOP door seal assy, greased manual valves on choke/kill line. Cleaned pit. Performed general maintenance and PM's.
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | Time Wind speed Wind direction Sea Wave direction
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | Knots deg m deg
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | 08:00 17/23 330° 2.6/4.1 350°
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | 10:00 2.3/3.6
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | 12:00 1.6/2.6
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | 14:00 1.3/2.1
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | 16:00 21/24 350° 1.8/2.9 330°
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | 18:00 23/26 340° 3.1/5.0 340°
2008-03-23 | 06:00:00 | 19:00:00 | 0 | ther | ok | 14:30-19:00 Not able to work at rig floor, due to exhaust fumes.
2008-03-23 | 19:00:00 | 00:00:00 | 0 | interruption -- | ok | WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Performed general maintenance and PM's. Greased valves on BOP. Disconnected the CRI hose
2008-03-23 | 19:00:00 | 00:00:00 | 0 | waiting on wea | ok | from F-12 and removed the check valve. Connected up the CRI hose again and opened to annulus, annulus pressure 52 bars. Attempted to inject seawater into F-12, stopped pumpin
2008-03-23 | 19:00:00 | 00:00:00 | 0 | ther | ok | g at 190 bars.
2008-03-23 | 19:00:00 | 00:00:00 | 0 | ther | ok | Time Wind speed Wind direction Sea Wave direction
2008-03-23 | 19:00:00 | 00:00:00 | 0 | ther | ok | Knots deg m deg
2008-03-23 | 19:00:00 | 00:00:00 | 0 | ther | ok | 20:00 18/28 330° 3.7/5.9 350°
2008-03-23 | 19:00:00 | 00:00:00 | 0 | ther | ok | 22:00 22/26 330° 3.6/5.7 340°
2008-03-23 | 19:00:00 | 00:00:00 | 0 | ther | ok | 00:00 26/32 320° 3.3/5.7 340°
2008-03-24 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on w | ok | WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Installed CRI check valve on to F-14. Greased valves on BOP. Hous
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | e keeping in the moon pool.
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | Time Wind speed Wind direction Sea Wave direction
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | Knots deg m deg
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | 02:00 17/20 320° 3.6/5.8 340°
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | 04:00 30/34 320° 3.1/5.8 340°
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | 06:00 15/18 340° 2.7/4.3 340°
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | 07:00 29/33 350° 3.6/5.8 340°
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | WOW prior to retrieve the HP riser. Performed general maintenance and PM's.
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | Time Wind speed Wind direction Sea Wave direction
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | Knots deg m deg
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | 08:00 15/17 340° 4.2/6.7 340°
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | 10:00 25/28 340° 3.9/6.3 340°
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | 12:00 26/30 340° 3.6/5.8 340°
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | 14:00 3.7/5.9 350°
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | 07:00-10:30 No access to rig floor, due to exhaust fumes.
2008-03-24 | 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | 12:45-14:00 No access to rig floor, due to exhaust fumes
2008-03-24 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Performed general maintenance and PM's.
2008-03-24 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | Time Wind speed Wind direction Sea Wave direction
2008-03-24 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | Knots deg m deg
2008-03-24 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | 20:00 3.8/6.1 340°
2008-03-24 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | 22:00 20/24 320° 4.0/6.3 340°
2008-03-24 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | 00:00 17/22 320° 3.9/6.3 340°
2008-03-25 | 00:00:00 | 04:00:00 | 0 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Performed general maintenance and PM's.
2008-03-25 | 15:30:00 | 19:00:00 | 0 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. POOH with the test plug assy. Racked back string in derrick and laid out the test plug.
2008-03-25 | 15:30:00 | 19:00:00 | 0 | interruption -- waiting on weat her | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-25 | 15:30:00 | 19:00:00 | 0 | interruption -- waiting on weat her | ok | 16:30 23/25 340° 4.6/7.4 340°
2008-03-25 | 15:30:00 | 19:00:00 | 0 | interruption -- waiting on weat her | ok | 18:30 23/27 340° 4.2/6.6 340°
2008-03-25 | 15:30:00 | 19:00:00 | 0 | interruption -- waiting on weat her | ok | 16:30-18:30 No access to rig floor, due to exhaust fumes
2008-03-25 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. Prepared for N/D diverter. Checked tool for making up the Claxton tool.
2008-03-25 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weat her | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-25 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weat her | ok | 21:00 17/19 330° 4.2/6.7 340°
2008-03-25 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weat her | ok | 22:30 15/17 330° 3.5/5.5 340°
2008-03-25 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weat her | ok | 23:15 15/17 350° 3.1/5.0 340°
2008-03-25 | 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weat her | ok | 19:00-20:30 No access to rig floor, due to exhaust fumes 23:00-00:00 No access to rig floor, due to exhaust fumes
2008-03-26 | 00:00:00 | 00:30:00 | 0 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. No access to rig floor, due to exhaust fumes.
2008-03-26 | 00:30:00 | 03:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and N/D diverter and BOP. Had gas turbines shut down at 01:25 due to exhaust fumes blowing into the rig floor.
2008-03-26 | 03:00:00 | 03:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk prior to M/U the Claxton tool.
2008-03-26 | 03:15:00 | 06:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Landed the Claxton tool on to the HPDR. Made Claxton tool to 1300 ft-lbs.
2008-03-26 | 06:00:00 | 07:00:00 | 0 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser.
2008-03-26 | 06:00:00 | 07:00:00 | 0 | interruption -- waiting on weat her | ok | Time Wind speed Wind direction Knots deg
2008-03-26 | 06:00:00 | 07:00:00 | 0 | interruption -- waiting on weat her | ok | 06:30 22/25 350°
2008-03-26 | 07:00:00 | 11:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Shut in F-12 for production. Simultaneously prepared for retrieving HPDR BOP joint. Moved CRI hose line from F-12 to F-14. Installed hot stab, for rele asing of riser TBC.
2008-03-26 | 07:00:00 | 11:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-26 | 07:00:00 | 11:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | 08:30 13/15 020° 3,5/5,5 340°
2008-03-26 | 11:00:00 | 15:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Loosen BOP/Tension joint flange. At 11:15 confirmed production shut in. Time Wind speed Wind direction Sea Wave direction
2008-03-26 | 11:00:00 | 15:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Knots deg m deg
2008-03-26 | 11:00:00 | 15:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | 11:30 6/11 030* 2,6/4,1 340°
2008-03-26 | 11:00:00 | 15:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | 13:30 4/10 050° 2,2/3,4 340°
2008-03-26 | 11:00:00 | 15:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | 15:00 1/3 110° 2,1/3,4 350°
2008-03-26 | 15:00:00 | 15:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | Removed horizontal tension support for riser in the moon pool.
2008-03-26 | 15:30:00 | 16:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Loosen the remaining 4 bolts on BOP/tension joint flange.
2008-03-26 | 16:00:00 | 16:45:00 | 0 | drilling -- bop/wellhead equip ment | ok | Picked up the BOP joint and racked back one DP stand.
2008-03-26 | 16:45:00 | 17:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | R/U elevator on slings to allow, for laying out the Claxton tool with pup joint attached. Removed master bushing and outer ring.
2008-03-26 | 17:30:00 | 18:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Pulled the BOP joint above the RT. Installed outer ring and the master bushing. Preserved the BOP joint flange. Laid out the BOP joint.
2008-03-26 | 18:15:00 | 18:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | R/D slings on elevator.
2008-03-26 | 18:30:00 | 19:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Made up riser lifting sub on one DP std.
2008-03-27 | 19:15:00 | 21:30:00 | 0 | drilling -- | ok | Pulled HPDR standard joint #1 and placed coupling in working height above riser spider. Removed
2008-03-27 | 19:15:00 | 21:30:00 | 0 | bop/wellhead equipme nt | ok | fairrings. Landed off HPDR standard joint #1 in riser spider. Broke bolts on flange. Observed loose skirt on TBC connector, bolts partly unscrewd and 2 bolts missing. Thi ghtended bolts on TBC skirt.
2008-03-28 | 00:00:00 | 01:30:00 | 0 | drilling -- bop/well head equipment | ok | Broke bolts on flange between lower pup and stress joint.
2008-03-28 | 01:30:00 | 02:30:00 | 0 | drilling -- wait | ok | Due to findings made by production department, halted operation for inspection in wellhead area. A support bracket on the F-12 flowline/piping was found to be ripped off. Mærsk rig management decided not to start production due to the circumstances. Further investigation/assessment needed before starting production.
2008-03-28 | 02:30:00 | 03:30:00 | 0 | drilling -- bop/well head equipment | ok | Landed HPDR lower pup joint on HTS cradle with simultaneous lift by deck crane and block. Removed handling flange. Re-slung HPDR lower pup joint and lifted to basket on mai n deck.
2008-03-28 | 03:30:00 | 05:15:00 | 0 | drilling -- bop/well head equipment | ok | Installed handling flange type C on TBC joint. Pulled out TBC joint and laid down on HTS cradle with simultaneous lift by block and deck crane. Removed handling flange. Lifted TBC joint to basket on main deck.
2008-03-28 | 05:15:00 | 06:00:00 | 0 | interruption -- wait ing on weather | ok | WOW for running production riser.
2008-03-28 | 05:15:00 | 06:00:00 | 0 | interruption -- wait ing on weather | ok | Meanwhile: Cleared and tidied rigfloor. Brought F-4 flexible hose onto HTS. Held toolbox talk prior to transferring flexible hose to XMT deck.
2008-03-28 | 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | Waited on weather.
2008-03-28 | 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | Meanwhile :
2008-03-28 | 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | -Cleared XMT deck for reception of F-4 flexible hose
2008-03-28 | 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | -Transferred F-4 flexible hose to XMT deck
2008-03-28 | 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | -Suspended flexibel hose in roof and jacked to position for hook up
2008-03-28 | 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | -Landed BOP on test stump and made up NT-2 connector
2008-03-28 | 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | -Tested door seal on BOP
2008-03-28 | 19:00:00 | 00:00:00 | 0 | interruption -- wait ing on weather | ok | Waited on weather.
2008-03-28 | 19:00:00 | 00:00:00 | 0 | interruption -- wait ing on weather | ok | Meanwhile :
2008-03-28 | 19:00:00 | 00:00:00 | 0 | interruption -- wait ing on weather | ok | -Worked on hooking up flexible hose
2008-03-28 | 19:00:00 | 00:00:00 | 0 | interruption -- wait ing on weather | ok | -Assisted production in equalizing across DHSV
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | Waited on weather.
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | Meanwhile :
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | -Worked on hooking up flexible hose
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | -Tested BOP - 6 month 15 K test - had lekage on test stump
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | -Changed gasket on test stump and made up NT-2 connecto r
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | -Lifted F-4 XMT to moonpool
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | -Transferred tension cylinders for F-14 to XMT deck
2008-03-29 | 06:00 | 20:00:00 | 0 | interruption -- waiting on weather | ok | Waited on weather for running production riser.
2008-03-29 | 06:00 | 20:00:00 | 0 | interruption -- waiting on weather | ok | Meanwhile :
2008-03-29 | 06:00 | 20:00:00 | 0 | interruption -- waiting on weather | ok | -Performed 6 month BOP test to 15 K
2008-03-29 | 06:00 | 20:00:00 | 0 | interruption -- waiting on weather | ok | -Repaired 10 MT tugger in moonopol
2008-03-29 | 06:00 | 20:00:00 | 0 | interruption -- waiting on weather | ok | -Moved guide funnel to F-4 and installed debris cover
2008-03-29 | 06:00 | 20:00:00 | 0 | interruption -- waiting on weather | ok | -Performed derrick inspection
2008-03-29 | 20:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | Waited on weather for running production riser.
2008-03-29 | 20:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | Meanwhile :
2008-03-29 | 20:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | -Performed repair of BX elevator
2008-03-29 | 20:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | -Lifted TBC joint to drillfllor
2008-03-29 | 20:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | -Performed pre-operational checks on TBC
2008-04-01 | 08:15:00 | 09:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Pulled landing stand and laid out handling flange and riser cut off.
2008-04-01 | 09:00:00 | 09:15:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to lowering WH with dual lift.
2008-04-01 | 09:15:00 | 10:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Lowered WH to tensioner deck and landed same on top of riser.
2008-04-01 | 10:00:00 | 16:30:00 | 0 | drilling -- bo p/wellhead equipment | ok | Orientated WH with valve stack pointing 45 deg relative to PORT/FWD. Pressure tested BT-seals to 35 bar - ok. Energized plastic in upper annd lower BT seal. Tested seals to 207 bar / 1 0 min - ok. Locked in 1000 psi after test. Energized slips with cap srews according to Vetco procedure. Pull tested WH with tugger - ok. Installed valves on A and B annulus outlets. Mean while loosended bolts on BOP NT-2 connector on stump. Made preparations to run BOP riser joint.
2008-04-01 | 16:30:00 | 16:45:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to installing BOP riser joint.
2008-04-01 | 16:45:00 | 17:45:00 | 0 | drilling -- bo p/wellhead equipment | ok | Ran BOP riser joint using block and dedicated slings and landed on wellhead. Made up NT-2 connector. Retrieved lift slings.
2008-04-01 | 17:45:00 | 18:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to nippling BOP.
2008-04-01 | 18:00:00 | 22:30:00 | 0 | drilling -- bo p/wellhead equipment | ok | Nippled up BOP. Meanwhile prepared for installing diverter.
2008-04-01 | 22:30:00 | 22:45:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to installing slick joint and diverter.
2008-04-01 | 22:45:00 | 00:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Installed diverter in housing.
2008-04-02 | 00:00:00 | 00:30:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Installed diverter in housing.
2008-04-02 | 00:30:00 | 02:15:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Ran slickjoint and landed same on top of BOP. Removed running slings from bails and installed elevator.
2008-04-02 | 02:15:00 | 03:30:00 | 0 | drilling -- bop activi ties | ok | Function tested BOP shear ram - ok. RIH with test plug for testing BOP connection. Function tested BOP rams and annular - ok. Landed test plug in surface wellhead. Performed line test an d verified line up by opening HCR with 35 bar - ok.
2008-04-02 | 03:30:00 | 04:15:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Pressured up to 35 bar using cement unit - mismatch pumped vs theoretical volume. Suspected pressuring up against GT plug. Opened B-annulus valves to vent underneath plug and press ure dropped immediatly. Leakage observed across test plug despite steady pressure 35 bar indicating that plug did not vent into pipe when doing pressure test. Discussed situation - decided to re-attempt test while keeping B-annulus valves open.
2008-04-02 | 04:15:00 | 05:15:00 | 0 | drilling -- bop activi ties | ok | Increased pumprate to 50 lpm and put 100 bar differential across plug, leakage decreased and pressure curve indicated that plug was sealing. Achieved steady pressure curve at 100 bar. Ble d off pressure to 35 bar and held test for 5 mins (1,7 bar drop / 5 min). Steady fluid returns observed from B-annulus. Pressured up to 345 bar and tested connectors + inner A annulus valve f or 10 min - 1,3 bar drop - ok. Shifted valves on A annulus. Held pressure and pressure tested outer A annulus valve for 10 min - 0,7 bar drop - ok. Pumped and bled back 43 liter (35=>345 ba r). Still minor fluid returns from B-annulus outlet but gradually decreasing.
2008-04-02 | 05:15:00 | 05:30:00 | 0 | drilling -- bop activi ties | ok | POOH with 5 1/2" DP stand and test plug. Observed dirt/mud residues plug. Found pieces of steel in the mud residues. Strapped pipe and found landing point 20,45 m vs theoretical 20,81 m - but likely that plug landed too shallow.
2008-04-02 | 05:30:00 | 06:00:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Made up bowl protector to running tool and made up to stand of 5 1/2" DP. Meanwhile hooked up tension cylinders on BOP.
2008-04-02 | 08:30:00 | 09:00:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to retrieving annulus insert.
2008-04-02 | 09:00:00 | 09:30:00 | 0 | drilling -- casing | ok | Checked equipment prior to RIH.
2008-04-02 | 09:30:00 | 10:30:00 | 0 | drilling -- casing | ok | Picked up and made up annulus insert J-slot retrieval tool.
2008-04-02 | 16:45:00 | 17:00:00 | 0 | drilling -- casing | ok | Broke out annular insert RT. Worked to free annular insert free from J-slot running tool due to debris jamming the sleeve.
2008-04-02 | 17:00:00 | 17:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to making up Smith 10 3/4" spear.
2008-04-02 | 17:15:00 | 18:15:00 | 0 | drilling -- casing | ok | Made up spear to 5 1/2" HWDP (LS-1), checked serial no - ok. Broke spear and inserted 9,632" nominal grapple. Made up spear using rig tongs.
2008-04-02 | 18:15:00 | 19:45:00 | 0 | drilling -- casing | ok | Made up adjustment sub setting tool to stand of 5 1/2" HWDP (LS-2), checked serial no - ok.
2008-04-02 | 21:30:00 | 22:00:00 | 0 | drilling -- casing | ok | Made up bowl protector RT and RIH on stand of 5 1/2" DP to 20 m. Caught bowl portector and POOH.
2008-04-02 | 22:00:00 | 22:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to rig up 10 3/4" casing running equipment.
2008-04-02 | 22:15:00 | 23:15:00 | 0 | drilling -- casing | ok | Cleared and tidied drillfloor prior to bringing in casing running equipment.
2008-04-02 | 23:15:00 | 00:00:00 | 0 | drilling -- casing | ok | Installed BX-3 elevator, changed inserts and function tested same.
2008-04-03 | 00:00:00 | 02:00:00 | 0 | drilling -- cas ing | ok | Moved Mærsk casing tong from drawwork deck storage and moved in front of IR.
2008-04-03 | 02:00:00 | 05:00:00 | 0 | drilling -- cas ing | ok | Hooked up casing tong. Changed head on PDM to accommodate 10 3/4" casing. Moved HTS rollers from FWD to AFT end of cantilever. Dressed PS-30 casing with 10 3/4" inserts/di es. Removed masterbushing and installed PS-30 in rotary. Hooked up PS-30 slip. Programmed and tested casing tong - negative.
2008-04-03 | 05:30:00 | 06:00:00 | 0 | drilling -- cas ing | ok | Function tested casing tong - ok.
2008-04-04 | 06:00:00 | 09:00:00 | 0 | interrupti on -- oth er | ok | Jammed torque wrench on TDS. Inspected equipment and found that wrong die-holders had been installed. Changed die-holders.
2008-04-04 | 09:00:00 | 09:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to picking up adjustment sub activation tool.
2008-04-04 | 11:00:00 | 11:45:00 | 0 | drilling -- casing | ok | POOH with adjustment sub activation tool and racked back in derrick.
2008-04-04 | 11:45:00 | 12:00:00 | 0 | drilling -- casing | ok | Made up Drillquip straddle cup tester.
2008-04-04 | 16:15:00 | 17:30:00 | 0 | drilling -- casing | ok | POOH with straddle cup tester from 130,5 m MD to surface. Laid out cup tester and inspected same. Found no tears or flaws, but OD reduced significantly (9,85"/9,70" vs originally 10,13")
2008-04-04 | 17:30:00 | 17:45:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to rigging casing running equipment.
2008-04-04 | 17:45:00 | 18:00:00 | 0 | drilling -- casing | ok | Rigged up casing running equipment. Found a yellow sheared allen bolt on walkway along drillfloor. Suspended operation and evaluated situation.
2008-04-04 | 18:00:00 | 20:00:00 | 0 | interrupti on -- oth er | ok | Isolated aft PRS and TDS and inspected same with manrider. Found origin of bolthead to be from backside of aft PRS upper grip head.
2008-04-04 | 20:00:00 | 00:00:00 | 0 | interrupti on -- oth er | ok | Parked aft PRS for repair. Performed repair work on aft PRS. Broke out and re-thightended in total 24 allen/hex bolts with prescribed momentum (600 ft lbs). Replaced broken bolt.
2008-04-04 | 20:00:00 | 00:00:00 | 0 | interrupti on -- oth er | ok | Meanwhile :
2008-04-04 | 20:00:00 | 00:00:00 | 0 | interrupti on -- oth er | ok | -Installed BX3 elevator in bails
2008-04-04 | 20:00:00 | 00:00:00 | 0 | interrupti on -- oth er | ok | -Brought Vetco/BOT equipment to cantilever
2008-04-05 | 00:00:00 | 02:30:00 | 0 | interruption -- other | ok | Repaired aft PRS. Meanwhile prepared for rigging casing running equipment.
2008-04-05 | 02:30:00 | 03:45:00 | 0 | drilling -- casing | ok | Rigged up Odfjell casing tong adn PS-30 slips dressed for 10 3/4" casing.
2008-04-05 | 03:45:00 | 04:00:00 | 0 | drilling -- casing | ok | Held toolbox talk for running 10 3/4" hanger running tool on 10 3/4" casing.
2008-04-05 | 04:00:00 | 05:00:00 | 0 | drilling -- casing | ok | Made up 10 3/4" x 1502 swedge to 8 m 10 3/4" casing joint. Laid out casing joint.
2008-04-05 | 05:00:00 | 05:30:00 | 0 | interruption -- waiting o n weather | ok | Suspended operation due to reported fumes. Wind direction 330. Assessed situation. Decided to resume operation.
2008-04-05 | 05:30:00 | 06:00:00 | 0 | drilling -- casing | ok | Picked up 10 3/4" casing hanger RT and hung off in slips. Picked up joint of 10 3/4" casing and made up to RT. Picked up joint with pre-made swedge.
2008-04-05 | 21:30:00 | 23:45:00 | 0 | drilling -- casing | ok | Resumed work on drillfloor. Broke out casing hanger RT with 10 turns. Unable to latch elevator on 10 3/4" casing, had to use singel joint elevator and tugger. Pulled 10 3/4" landing string. Broke out RT. Broke out 1502 swedge.
2008-04-05 | 23:45:00 | 00:00:00 | 0 | drilling -- casing | ok | Rigged down casing tong.
2008-04-06 | 00:00:00 | 00:30:00 | 0 | drilling -- casing | ok | Rigged down casing tong. Removed PS-30 slips. Observed dropped object on drillfloor - hex/allen bolt head from aft PRS. Suspended operations for investigation. Fenced off drillfloor.
2008-04-06 | 00:30:00 | 03:00:00 | 0 | interruption -- other | ok | Inspected aft PRS. Discussed way forward. Parked and isolated aft PRS. Secured backside of aft PRS gripper head with cover and trailer straps for dropped obje ct prevention.
2008-04-06 | 03:00:00 | 03:45:00 | 0 | drilling -- casing | ok | Resumed operations. Removed BX3 elevator and installed 5 1/2" DP elevator. Cleared drillfloor from casing handing equipment.
2008-04-06 | 03:45:00 | 04:45:00 | 0 | drilling -- casing | ok | Ran 2 x 5 1/2" DP singels and made up to MS-seal running tool. Meanwhile laid out DP singels on deck to cater for continued operations.
2008-04-06 | 04:45:00 | 06:00:00 | 0 | drilling -- casing | ok | Made up control lines to MS-seal RT. Function tested and adjusted dogs and stroke on MS seal RT.
2008-04-06 | 08:15:00 | 09:00:00 | 0 | drilling -- casing | ok | POOH with MS seal RT on 5 1/2" DP stand. Broke RT tool and laid down.
2008-04-06 | 09:00:00 | 09:15:00 | 0 | drilling -- casing | ok | Held toolbx talk before running bowl protector.
2008-04-06 | 10:00:00 | 10:45:00 | 0 | drilling -- casing | ok | Broke out RT and laid down same. Laid out 2 joints of 5 1/2" DP.
2008-04-06 | 10:45:00 | 11:30:00 | 0 | drilling -- casing | ok | Held toolbox talk and prepared for running casing drift. Experienced problems with programming PDM.
2008-04-06 | 11:30:00 | 13:15:00 | 0 | interruption -- other | ok | Troubleshot PDM. Unable to travel to port aft pipe bay.
2008-04-06 | 13:15:00 | 14:00:00 | 0 | drilling -- casing | ok | Tested PDM - ok. Tested stabbing. Discussed issues related to pipe handling.
2008-04-06 | 14:00:00 | 14:15:00 | 0 | drilling -- casing | ok | Picked up 9,567" casing drift and made up to 5 1/2" HWDP single.
2008-04-07 | 00:00:00 | 02:00:00 | 0 | drilling -- casing | ok | POOH with 9,567" drift on 5 1/2" HWDP from 223 m to surface. Laid out singles on deck when pulling out. Observed dropped object on drillfloor - half crest of external lock ring / simmer ring for pin, 70 mm x 2 mm / 10 grammes. Suspended operations for investigation. Fenced off drillfloor.
2008-04-07 | 02:00:00 | 02:45:00 | 0 | interruption -- oth er | ok | Inspected rig equipment. Found source of dropped object to be cherry picker main hydraulic lift cylinder. No risk of larger dropped object from equipment - lock ring served no pur pose.
2008-04-07 | 02:45:00 | 04:00:00 | 0 | drilling -- casing | ok | Resumed operations. Held toolbox talk. Made up GTV pulling tool to stand of drillpipe hanging in block. Ran stand carefully through BOP. RIH to 80 m MD on 5 1/2" HWDP singl es. Observed leakage on BX-elevator.
2008-04-07 | 17:15:00 | 20:15:00 | 0 | drilling -- casing | ok | POOH with GTV plug on 5 1/2 HWDP singles from 145 m MD to surface.
2008-04-07 | 20:15:00 | 20:45:00 | 0 | drilling -- casing | ok | Broke out and laid down GTV plug and pulling tool.
2008-04-07 | 20:45:00 | 22:30:00 | 0 | drilling -- casing | ok | Made up secondary bowl protector pulling tool. RIH and latched secondary bowl protector. Strapped pipe while POOH, measured 20,45 m to tubing hanger landing shoulder. Ma de up kick assembly.
2008-04-07 | 22:30:00 | 22:45:00 | 0 | completion -- co mpletion string | ok | Held toolbox talk for rigging up tubing running equipment.
2008-04-07 | 22:45:00 | 00:00:00 | 0 | completion -- co mpletion string | ok | Positioned HTS and moved rollers on cantilever. Cleared drillfloor. Positioned control line reel on fwd pipe setback. Meanwhile installed NPR plug with ballseat in tailpipe joint.
2008-04-12 | 00:00:00 | 00:30:00 | 0 | completio n -- test s csssv | ok | POOH with running string and LD RT.
2008-04-12 | 00:30:00 | 02:45:00 | 0 | completio n -- compl etion strin g | ok | RD completion handling equipment.
2008-04-12 | 02:45:00 | 03:45:00 | 0 | completio n -- compl etion strin g | ok | PU 2 joints of 5 1/2" HWDP and RIH and drained riser.
2008-04-12 | 03:45:00 | 06:00:00 | 0 | completio n -- compl etion strin g | ok | ND and pulled diverter.
2008-04-12 | 06:00:00 | 10:15:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Continued ND diverter. Went trough SJA and procedure with day crew. Attached slings to slick joint. Prepared barriers, handrails and slings. Lifted out diverter. Installed outer ring and master bushings. Loosened nuts on slick joint.
2008-04-12 | 10:15:00 | 12:00:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Held tool box talk and reviewed SJA and procedures. Disconnected tension cylinders in WH module.
2008-04-12 | 12:00:00 | 13:15:00 | 0 | drilling -- bop/wellh ead equip ment | ok | ND NT2 connection on BOP. Informed production department to shut in well at 12.30.
2008-04-12 | 13:15:00 | 14:00:00 | 0 | interruptio n -- wait | ok | Waited on production to shut in well. Meanwhile removed 2 HP hoses connected to WH.
2008-04-12 | 14:00:00 | 14:45:00 | 0 | drilling -- bop/wellh ead equip ment | ok | ND slick joint and BOP.
2008-04-12 | 14:45:00 | 16:15:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Dismantled scaffolding on NT2 connection in moonpool and installed slings on riser. RU for disconnecting riser NT2 connection and disconnected same.
2008-04-12 | 16:15:00 | 17:30:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Dismantled scaffolding in moonpool. PU riser and terminated control lines on well head. Installed carrier on HTS. Installed hatch on weather deck and master bushings on rig floor. Hoisted ri ser to rig floor and retracted same.
2008-04-12 | 17:30:00 | 19:15:00 | 0 | completio n -- test s csssv | ok | Disconnected control lines from communication collar and hoisted same to rig floor. Installed hatch in moonpool. Installed outer ring and master bushings on rig floor. Installed anti vibration r ing on TH. Removed one control line exit block on multi bowl. Unwrapped required length of CL around TH neck and fed control line through dedicated port on multi bowl. Fed high pressure packings and fittings onto CL and MU fittings to threads in multi bowl. Installed dart in BPV in TH by hand. Installed 137 VG seal ring on top of multi bowl and VG 63 seal ring on top of TH.
2008-04-12 | 19:15:00 | 20:30:00 | 0 | completio n -- test s csssv | ok | Removed hatch to F-4. Lowered spacer spool down from rig floor with TDS until NT2 box connector landed out on top of WH. MU locking dogs until connection leveled out. MU actuation scr ews with 800 ft-lbs. Disconnected slings and removed same.
2008-04-12 | 19:15:00 | 20:30:00 | 0 | completio n -- test s csssv | ok | Pressure tested and energized BT seals through ports 7/8. Tested VG 63 connection trough test port 9/10 to 35 bar/5 min. Tested TH void, grafoil seals and BT seals 35/380 bar for 5/10 min via test port 5/6.
2008-04-12 | 19:15:00 | 20:30:00 | 0 | completio n -- test s csssv | ok | MU ferrule swagelock fittings for CL. Installed seal rings and CL exit block. Installed seal ring on top of spacer spool.
2008-04-12 | 20:30:00 | 00:00:00 | 0 | moving -- skid | ok | Skidded cantiliver 1.5 m starboard and as far aft as possible to be able to possition crane for lifting XMT.
2008-04-13 | 00:00:00 | 02:00:00 | 0 | completion -- bop/well head equipment | ok | Held tool box meeting. Connected crane hook to one of the two chackles in the end of the chain hoist and wire sling. Disconnected transport plate. Lifted XMT to wireline de ck and landed it on wooden beams, where it hung suspended in crane hook and resting on wooden beams with 1 MT.
2008-04-13 | 02:00:00 | 05:15:00 | 0 | moving -- skid | ok | Skidded rig to sea fastening position to gain access for lifting XMT with the port aft deck crane.
2008-04-13 | 05:15:00 | 06:00:00 | 0 | completion -- bop/well head equipment | ok | Held tool box meeting. Attempted to lift XMT from wireline deck to F-4 wellhead. Could not reach F-4. Decided to skid further to starboard.
2008-04-13 | 06:00:00 | 07:00:00 | 0 | moving -- skid | ok | Skidded 0.6 m further starboard and reached max skidded position starboard and fwd (sea fastning position).
2008-04-13 | 07:00:00 | 09:00:00 | 0 | moving -- skid | ok | Unable to reach F-4 and F-5 with port aft deck crane. Evalutated alternative methode for landing of XMT.
2008-04-13 | 07:00:00 | 09:00:00 | 0 | moving -- skid | ok | Meanwhile held toolbox meeting and went through procedures and SJA with day crew.
2008-04-13 | 09:00:00 | 10:30:00 | 0 | moving -- skid | ok | Skidded port and aft out to F-4.
2008-04-13 | 09:00:00 | 10:30:00 | 0 | moving -- skid | ok | Meanwhile lined up from CMT onto F-12 kill valve. Lined up over choke manifold to equalize above TRSCSSV. Tested lines. Equalized TRSCSSV with 84 bar and opened s ame. Started production from F-12.
2008-04-13 | 10:30:00 | 11:00:00 | 0 | moving -- skid | ok | Held time-out for safety. Talked about everyones right to stop the operation if anything is unclear or confusing. Went through operational plan and safety aspects involved.
2008-04-13 | 11:00:00 | 12:00:00 | 0 | moving -- skid | ok | Installed staircase to cantiliver.
2008-04-13 | 12:00:00 | 13:30:00 | 0 | completion -- bop/well head equipment | ok | Removed big moonpool hatch and lowered XMT to moonpool. Re-installed hatch.
2008-04-13 | 13:30:00 | 15:30:00 | 0 | moving -- skid | ok | Transfered XMT from turtle to weather deck and skidded cantiliver to port and fwd to position XMT in center.
2008-04-13 | 15:30:00 | 16:15:00 | 0 | interruption -- wait | ok | Waited on production to shut in well.
2008-04-13 | 16:15:00 | 16:45:00 | 0 | completion -- bop/well head equipment | ok | Attached TDS to XMT. Positioned and disconnected base plate.
2008-04-13 | 16:45:00 | 17:30:00 | 0 | moving -- skid | ok | Skidded rig fwd and port to position XMT over F-4 for final installation.
2008-04-13 | 16:45:00 | 17:30:00 | 0 | moving -- skid | ok | Meanwhile bled down all pressures on F-12 to zero bar.
2008-04-13 | 17:30:00 | 18:45:00 | 0 | completion -- bop/well head equipment | ok | Moved hatch on weather deck to allow XMT to pass through. Lowered XMT until 1 m above F-4 spacer spool.
2008-04-13 | 18:45:00 | 20:15:00 | 0 | completion -- bop/well head equipment | ok | Held tool box meeting. Lowered XMT on to spacer spool with TDS and verified correct orientation.
2008-04-13 | 18:45:00 | 20:15:00 | 0 | completion -- bop/well head equipment | ok | MU graylock connection. Re-built scaffolding around XMT for proper working environment. Checked alignment of flanges between flow hose and XMT. Pressure tested seal ring 35 bar/10 min through test port 3/4 on spacer spool to confirm proper seal.
2008-04-13 | 20:15:00 | 00:00:00 | 0 | completion -- bop/well head equipment | ok | Installed flow line spool. Disconnected lifting wire from TDS. Connected flexible flow line to flow line spool. Re-installed hatch.
2008-04-14 | 00:00:00 | 02:45:00 | 0 | interruption -- wait | ok | Postphoned XMT tests to assist production to start up F-12. Lined up from CMT onto F-12 kill valve. Lined up over choke manifold to equalize above TRSCSSV. Test ed lines. Equalized TRSCSSV and opened same. Started production from F-12.
2008-04-14 | 02:45:00 | 06:00:00 | 0 | completion -- bop/wellhead equipment | ok | Held tool box meeting. Opened HMV with Seawell test pump. Lined up from cmt unit and connected hose on KWV. Performed line test to 20 bar for 5 min.
2008-04-14 | 06:00:00 | 07:30:00 | 0 | completion -- bop/wellhead equipment | ok | Trouble shoot line up from cmt unit through valves and hose from moonpool to KWV due to failing line test. Detected exhaust fumes in WH area.
2008-04-14 | 07:30:00 | 08:15:00 | 0 | interruption -- wait | ok | Exhaust fumes in well head area. Abandoned WH. Shud down on of the gas turbines to reduce exhaust fumes.
2008-04-14 | 08:15:00 | 08:30:00 | 0 | completion -- bop/wellhead equipment | ok | Performed line test to 30/380 bar for 5/10 min against KWV. 2.2 bar drop on high pressure test.
2008-04-14 | 08:30:00 | 10:15:00 | 0 | completion -- bop/wellhead equipment | ok | Attempted to pressure test XMT body and VG 63 ring to 30/380 bar for 5/10 min against dart in BPV. Failed due to leaking dart/BPV.
2008-04-14 | 10:15:00 | 12:30:00 | 0 | completion -- bop/wellhead equipment | ok | Held tool box talk. Removed XMT tree cap. Opened HMV. RIH with retrieving tool for dart on stinger and retrieved dart. POOH with dart. RIH and installed new dart. Flushed XMT. Closed HMV.
2008-04-14 | 12:30:00 | 13:00:00 | 0 | completion -- bop/wellhead equipment | ok | Attempted to pressure test XMT body and VG 63 ring to 30/380 bar for 5/10 min against dart in BPV. Failed due to leaking dart/BPV.
2008-04-14 | 13:00:00 | 14:00:00 | 0 | completion -- bop/wellhead equipment | ok | Pulled dart and BPV. Installed a new BPV and dart. Flushed XMT.
2008-04-14 | 14:00:00 | 14:30:00 | 0 | completion -- bop/wellhead equipment | ok | Pressure tested XMT body and VG 63 ring to 30/380 bar for 5/10 min against dart in BPV. 2.5 bar drop on high pressure test.
2008-04-14 | 14:30:00 | 16:00:00 | 0 | completion -- bop/wellhead equipment | ok | Pressured up to 130 bar against BPV & dart. Close MMV and bled off pressure above MMV to 10 bar. Inflow tested MMV to 120 bar differential pressure for 15 min.
2008-04-14 | 14:30:00 | 16:00:00 | 0 | completion -- bop/wellhead equipment | ok | 1.9 bar drop.
2008-04-14 | 14:30:00 | 16:00:00 | 0 | completion -- bop/wellhead equipment | ok | Equalized pressure above MMV. Opened MMV and closed HMV. Bled of any pressure above HMV to 10 bar. Inflow test HMV to 120 bar differential pressure for 15 min. 2.4 bar drop.
2008-04-14 | 14:30:00 | 16:00:00 | 0 | completion -- bop/wellhead equipment | ok | Equalized pressure across HMV. Opened HMV. Bled off pressure. Closed valves.
2008-04-14 | 16:00:00 | 17:00:00 | 0 | completion -- bop/wellhead equipment | ok | Removed XMT tree cap. Opened HMV. RIH with retrieving tool for dart on stinger and retrieved dart. POOH with dart. Pulled BPV from TH.
2008-04-14 | 17:00:00 | 17:30:00 | 0 | completion -- bop/wellhead equipment | ok | Re-installed XMT tree cap. Close HMV. Test three cap 380 bar/10 min against SV. Bled off pressure.
2008-04-14 | 17:30:00 | 18:00:00 | 0 | completion -- bop/wellhead equipment | ok | Pressure test TRSCSSV CL exit block to 570 bar/15 min, using BOT pump. Test ok. No indication that TRSCSSV opened. Bled off 155 ml on line.
2008-04-14 | 18:00:00 | 19:00:00 | 0 | completion -- bop/wellhead equipment | ok | Evalutated options for flushing flowline and made plan for flowline test. Handover with new crew.
2008-04-14 | 19:00:00 | 20:45:00 | 0 | completion -- bop/wellhead equipment | ok | Held tool box meeting. Hooked up flexible hose and lined up for pressure testing flowline. Flushed through XMT PWV, KWV and lo-torque to cement unit with pot-wat er.
2008-04-14 | 20:45:00 | 21:30:00 | 0 | completion -- bop/wellhead equipment | ok | Attempted to pressure test flow line and XMT to 30/345 bar for 5/10 min. Observed leak at flange on flexible hose.
2008-04-14 | 21:30:00 | 00:00:00 | 0 | completion -- bop/wellhead equipment | ok | Inspected, greased and torqued up flange on flow line flexible hose.
2008-04-14 | 21:30:00 | 00:00:00 | 0 | completion -- bop/wellhead equipment | ok | Meanwhile worked on varco bolts on AFT PRS and installed tension cylinders on F-14.
2008-04-15 | 00:00:00 | 02:15:00 | 0 | completion -- bop/wellhead equipme nt | ok | Inspected, greased and torqued up flange on flow line flexible hose.
2008-04-15 | 00:00:00 | 02:15:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile worked varco bolt on AFT PRS and installed tension cylinders on F-14.
2008-04-15 | 02:15:00 | 04:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Flushed through XMT to cmt unit prior to testing flowline. Pressure tested flow line and XMT to 30/345 bar for 5/10 min. 1.1 bar drop on low pressure test and 1.7 bar drop on high pressure test.
2008-04-15 | 04:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Commisioned XMT.
2008-04-15 | 04:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Meanwhile worked on varco bolts on AFT PRS and installed tension cylinders on F-14.
2008-04-15 | 06:00:00 | 12:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Installed instrumentation on F-4 XMT. Connected umbilical to bulk head plate.
2008-04-15 | 06:00:00 | 12:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile changed out chain on HTS, emptied trip tank and repaired sensor on gate valve shakers. Started to change out one tension cylinder on F-14. Carried out work s cope with climbers in derrick.
2008-04-15 | 12:00:00 | 12:45:00 | 0 | interruption -- wait | ok | Waited on production to restart after production shut-down.
2008-04-15 | 12:45:00 | 16:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Energized instrumentation on XMT.
2008-04-15 | 12:45:00 | 16:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile changed out one tension cylinder on F-14 and cleaned area. lined up from cement unit onto F-12 kill valve. Lined up over choke manifold. Equalized TRSCSSV with 94 bar and opened same. Started production from F-12. Carried out work scope with climbers in derrick.
2008-04-15 | 16:30:00 | 17:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Function tested XMT pressure transmitters.
2008-04-15 | 16:30:00 | 17:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile retrieved base plate from weather deck to moonpool. Carried out work scope with climbers in derrick.
2008-04-15 | 17:00:00 | 19:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Mounted umbilical termination plate on XMT.
2008-04-15 | 17:00:00 | 19:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile performed housekeeping on cantilever. Carried out work scope with climbers in derrick.
2008-04-15 | 19:30:00 | 21:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Tested annulus pressure transmitters on XMT.
2008-04-15 | 19:30:00 | 21:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile worked on Varco bolts on aft PRS. Built suspended scaffolding for repair on fwd PRS. parked and landed BOP on test stump.
2008-04-15 | 21:30:00 | 22:45:00 | 0 | completion -- bop/wellhead equipme nt | ok | Function tested PWV and HMV on XMT with process operator present. Feed back on valve position to process control room read OK.
2008-04-15 | 21:30:00 | 22:45:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile continued building suspended scaffolding for fwd PRS in paralell with securing bolts on aft PRS.
2008-04-15 | 22:45:00 | 00:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Commenced commisioning of XMT. Verified documentation from Vetco Gray and Aibel. Performed pre-commisioning checks.
2008-04-15 | 22:45:00 | 00:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile continued building suspended scaffolding for fwd PRS in paralell with securing bolts on aft PRS. Started to lift parts for fwd PRS onto scaffolding.
2008-04-16 | 00:00:00 | 06:00:00 | 0 | completion -- bop/wellhead equipment | ok | Performed pre-commisioning checks of valves on XMT. Function tested MMV and SV and XMT with process operator present. Feed back on valve pos ition to control room read OK.
2008-04-16 | 00:00:00 | 06:00:00 | 0 | completion -- bop/wellhead equipment | ok | Meanwhile continued building suspended scaffolding for fwd PRS in paralell with securing bolts on aft PRS.
2008-04-16 | 06:00:00 | 07:00:00 | 0 | completion -- bop/wellhead equipment | ok | Performed pre-commisioning checks of valves on XMT. Function tested MMV and SV and XMT with process operator present. Feed back on valve pos ition to control room read OK.
2008-04-16 | 06:00:00 | 07:00:00 | 0 | completion -- bop/wellhead equipment | ok | Meanwhile continued building suspended scaffolding for fwd PRS in parallell with securing bolts on aft PRS.
2008-04-16 | 07:00:00 | 17:00:00 | 0 | completion -- bop/wellhead equipment | ok | Commisioned XMT.
2008-04-16 | 07:00:00 | 17:00:00 | 0 | completion -- bop/wellhead equipment | ok | Meanwhile performed derrick inspection with climbers and worked on BOP.
2008-04-16 | 17:00:00 | 00:00:00 | 0 | workover -- wait | ok | Waiting on WL equipment and personnel to arrive on rig. Completed commisioning of XMT 38 hrs ahead of plan.
2008-04-16 | 17:00:00 | 00:00:00 | 0 | workover -- wait | ok | Meanwhile erected scaffolding platform for fwd PRS and performed 3-montly maintenance on BOP.
2008-04-17 | 00:00:00 | 06:00:00 | 0 | workover -- wait | ok | Waiting on WL equipment and personnel to arrive on rig.
2008-04-17 | 00:00:00 | 06:00:00 | 0 | workover -- wait | ok | Meanwhile erected scaffolding platform for fwd PRS and performed 3-montly maintenance on BOP.
2008-04-17 | 06:00:00 | 11:00:00 | 0 | workover -- wait | ok | Waiting on WL equipment and personnel to arrive on rig.
2008-04-17 | 06:00:00 | 11:00:00 | 0 | workover -- wait | ok | Meanwhile performed derrick inspection with climbers and performed 3-montly maintenace on BOP.
2008-04-17 | 11:00:00 | 12:30:00 | 0 | workover -- rig up/dow n | ok | Prepared for RU wireline equipment and tested dual and trippel BOP's.
2008-04-17 | 11:00:00 | 12:30:00 | 0 | workover -- rig up/dow n | ok | Meanwhile equalized above DHSV on F-12 with cmt unit to re-start production. Observed leak in F-12 XMT. Meanwhile performed derrick inspection with climbers and performed 3-montly maintenace on BOP.
2008-04-17 | 12:30:00 | 19:00:00 | 0 | workover -- rig up/dow n | ok | Prepared for RU wireline equipment and tested dual and trippel BOP's.
2008-04-17 | 12:30:00 | 19:00:00 | 0 | workover -- rig up/dow n | ok | Meanwhile identified leak on F-12 XMT to be in MEG injection valve.
2008-04-17 | 12:30:00 | 19:00:00 | 0 | workover -- rig up/dow n | ok | Meanwhile performed derrick inspection with climbers and performed 3-montly maintenace on BOP.
2008-04-17 | 19:00:00 | 20:45:00 | 0 | workover -- rig up/dow n | ok | Prepared for RU wireline equipment and tested dual and trippel BOP's.
2008-04-17 | 19:00:00 | 20:45:00 | 0 | workover -- rig up/dow n | ok | Meanwhile continued to work on scaffolding platform for fwd PRS.
2008-04-17 | 20:45:00 | 00:00:00 | 0 | workover -- rig up/dow n | ok | Held tool box meeting. Spotted WL equipment on rig floor and hooked up BCU and pump skids. Prepared riser and BOP for lifting down to moonpool are a.
2008-04-17 | 20:45:00 | 00:00:00 | 0 | workover -- rig up/dow n | ok | Meanwhile changed MEG injection valve on F-12 and re-tested valve to 325 bar/30 min.
2008-04-18 | 00:00:00 | 02:15:00 | 0 | workover -- ri g up/down | ok | Spotted WL equipment on rig floor and hooked up BCU and pump skids. Prepared riser and BOP for lifting down to moonpool area.
2008-04-18 | 00:00:00 | 02:15:00 | 0 | workover -- ri g up/down | ok | Meanwhile equalized above DHSV on F-12 with cmt unit to re-start production. Production on F-12 started 02:00. Meanwhile built scaffolding bridge from cantiliver to Schlumberger WL deck (port aft leg).
2008-04-18 | 02:15:00 | 06:00:00 | 0 | workover -- ri g up/down | ok | Held tool box meeting. Hooked up chicksan line in moonpool from cmt unit to both F-12 and F-4 with seperate high pressure hoses. Lifted off hatch on F-4. Leak tested line from cmt unit to XMT KWV with LTV4 closed 30/380 bar for 5/10 min. Dropped 0.75 bar/10 min. Verified no pressure under XMT cap and removed same.
2008-04-18 | 06:00:00 | 11:00:00 | 0 | workover -- ri g up/down | ok | Lowered the assembled XO, pump-in sub and short riser section through the rotary with tugger from drill floor and connected it to XMT. Installed BOP's with dual placed on top of trippl e BOP.
2008-04-18 | 11:00:00 | 12:15:00 | 0 | workover -- ri g up/down | ok | Built scaffolding around BOP's to enabling handling of riser above BOP's.
2008-04-18 | 12:15:00 | 13:30:00 | 0 | workover -- ri g up/down | ok | Installed riser sections to rig floor.
2008-04-18 | 13:30:00 | 17:00:00 | 0 | interruption -- rig up/down | ok | Opened SV. Attempted to pressure test riser sections and BOP's without sucess. Identified leak in FMC drain valve. Bled off pressure. Closed SV. Attempted to rectify the leaking valv e without sucess.
2008-04-18 | 17:00:00 | 21:00:00 | 0 | workover -- ri g up/down | ok | Built grease injection head, with cable head already installed and one lubricator section on rig floor. PU grease injection head and one lubricator section using tugger. Connected two more lubricator sections. Installed sheave wheels.
2008-04-18 | 17:00:00 | 21:00:00 | 0 | workover -- ri g up/down | ok | Meanwhile drained riser and installed new FMC drain valve.
2008-04-18 | 21:00:00 | 22:15:00 | 0 | workover -- ri g up/down | ok | PU and MU WL toolstring for pulling NPR plug and installed in lubricator. Connected lubricator at in-situ sub.
2008-04-18 | 21:00:00 | 22:15:00 | 0 | workover -- ri g up/down | ok | Opened SV partly and flushed and filled lubricator with packer fluid using cement unit through KWV. Attempted to pressure test wireline rig-up. Observed leak in lubricator XO below t ool catcher.
2008-04-18 | 21:00:00 | 22:15:00 | 0 | workover -- ri g up/down | ok | Meanwhile transfered operation of HMV and TRSCSSV to pump skid in moonpool. Production operator was present during the transfer.
2008-04-18 | 22:15:00 | 23:00:00 | 0 | interruption -- rig up/down | ok | BO lubricator and toostring. Changed leaking o-ring in XO. MU toolstring and re-connected lubricator.
2008-04-18 | 23:00:00 | 23:45:00 | 0 | workover -- ri g up/down | ok | Opened SV partly and flushed and filled lubricator with packer fluid using cement unit through KWV. Pressure tested wireline rig-up 30/185 bar for 5/10 min against HMV. Dropped 0.7 5 bar/10 min. Filled lubricator with 700 ltrs. Bled off pressure in lubricator/rig-up to cmt unit. Closed SV.
2008-04-18 | 23:00:00 | 23:45:00 | 0 | workover -- ri g up/down | ok | Pressured up and opened HMV and TRSCSSV using WL pump in moonpool. Observed for leak on well head for 10 min. No leak observed. Opened SV.
2008-04-18 | 23:45:00 | 00:00:00 | 0 | workover -- w ire line | ok | Started RIH WL toolstring for pulling NPR plug. Production shut down at 23:57 and had shut down WL unit. Re-powered up WL unit.
2008-04-19 | 00:00:00 | 01:15:00 | 0 | workover -- wire line | ok | RIH WL toolstring for pulling NPR plug from surface to TRSCSSV at 496 m MDRT. Found that TRSCSSV was closed. Decided not to wait for cmt unit - production needed to equalize and open TRSCSSV on F-12 to re-start production.
2008-04-19 | 00:00:00 | 01:15:00 | 0 | workover -- wire line | ok | Hooked up pump on rig floor to needle valve on lubricator to equalize and open TRSCSSV in F-4. Ran through TRSCSSV at 496 m MDRT and verified that it was fully open.
2008-04-19 | 01:15:00 | 03:00:00 | 0 | workover -- wire line | ok | Continued RIH WL toolstring for pulling NPR plug to 2600 m MDRT using running procedures for new cables. Running speed 40 m/min. Did not bleed off pressure while RIH and had 11-12 bar in well at 2600 m. Up weight 710 kg / Hanging weight 530 kg / RIH weight 422 kg.
2008-04-19 | 03:00:00 | 04:00:00 | 0 | workover -- wire line | ok | RIH and latched GS pulling tool into NPR plug at 2649.7 m. Jared down to equalize ports in the plug. Waited 15 min for pressure across plug to equalize. Pressure dropped to 10 bar. Bleed off pressure. Released NPR plug by jaring up once. Got 150 kg increase in string weight. Waited 30 min to allow elements to retract.
2008-04-19 | 04:00:00 | 06:00:00 | 0 | workover -- wire line | ok | POOH with NPR plug. Observed that weight dropped back to up weight while POOH. RIH and latched GS pulling tool into NPR plug at 2649.7 m. Pressured up well to 10 bar. Jarred d own to equalize ports in the plug. Waited 15 min for pressure across plug to equalize. No pressure drop observed.
2008-04-19 | 04:00:00 | 06:00:00 | 0 | workover -- wire line | ok | Released NPR plug by jaring up 105 hits. Adjusted stress point on cable after 60 hits with jar. Got approx 300 kg increase in string weight. Bleed off pressure. Waited 30 min to allow el ements to retract.
2008-04-19 | 06:00:00 | 09:00:00 | 0 | workover -- wire line | ok | POOH with NPR plug on 7/32 cable, worked through TRSCSSV at 496 m with 200 kg overpull. Closed SV using 42 turns and closed HMV. Bled off pressure in XMT, riser and lubricato r to closed drain.
2008-04-19 | 09:00:00 | 10:30:00 | 0 | workover -- r ig up/down | ok | RD lubricator and cut wireline as per Seawell instructions. LD and inspected BHA and NPR plug. Plug had only small rift on rubber element.
2008-04-19 | 10:30:00 | 11:45:00 | 0 | completion -- test scsssv | ok | Held tool box meeting. Attempted to increase TRSCSSV CL pressure to 570 bar with Seawell pump without sucess. Max pressure of 540 bar with Seawell pump. RU Vetco pump to p ressure up CL to 570 bar.
2008-04-19 | 11:45:00 | 12:45:00 | 0 | completion -- test scsssv | ok | Lined up to test 7" tubing/liner to 380 bar through KWV with cmt pump. Opened LTV1 and LTV2. Pressured up well to test 7" tubing/liner to 35/380 bar for 5/10 min against EZSV plug at 3448 m MDRT. Pumped 1195 ltrs and bled back 1190 ltrs. Dropped 1.6 bar/10 min. Closed HMV. Adjusted TRSCSSV CL pressure to 520 bar.
2008-04-19 | 12:45:00 | 15:00:00 | 0 | workover -- r ig up/down | ok | Installed Check Valve in test line to cmt unit. Performed line test from cmt unit against KWV to 185 bar/10 min. Dropped 0.9 bar/10 min. Bled down to 10 bar on cmt unit to inflow test C heck Valve. Bled down pressure between KWV and Check Valve to closed drain.
2008-04-19 | 12:45:00 | 15:00:00 | 0 | workover -- r ig up/down | ok | Meanwhile RU scaffolding and lubricator to grease head.
2008-04-19 | 15:00:00 | 20:45:00 | 0 | workover -- r ig up/down | ok | RU additional lubricator sections needed for perforation runs. Lifted riser sections to rig floor. Modified scaffolding to a higher level to be able to assemble lubricator. RU to run 7/16" electric line. Prepared grease injection head. MU cable head with PGGT.
2008-04-19 | 20:45:00 | 23:00:00 | 0 | workover -- r ig up/down | ok | Installed cable head and PGGT with bottom nose in riser. Connected WL riser at in-situ sub. Confirmed correct line up from cmt unit. Opened SV and KWV on XMT. Filled up riser and leak tested WL rigup to 30/185 bar for 5/10 min with cmt pump against HMV. Dropped 0.6 bar/10 min. Bled off pressure to closed drain. Closed SV.
2008-04-19 | 23:00:00 | 00:00:00 | 0 | workover -- r ig up/down | ok | Drained lubricator. Broke riser at in-situ sub and LD toolstring. Cleared drill floor. Installed nitrogen rack and regulator on drill floor.
2008-04-20 | 00:00:00 | 02:15:00 | 0 | interruption -- ri g up/down | ok | Discussed method for PU and MU perforation guns due to uncertified lifting cap.
2008-04-20 | 02:15:00 | 02:45:00 | 0 | workover -- rig u p/down | ok | Held tool box meeting prior to PU and MU gun sections.
2008-04-20 | 02:45:00 | 03:15:00 | 0 | workover -- rig u p/down | ok | Checked GR/CCL on rig floor. Shut down power to Schlumberger unit to follow procedure for MU perforation guns. Closed off rig floor, WH and XMT. Made PA announcement.
2008-04-20 | 03:15:00 | 06:00:00 | 0 | workover -- rig u p/down | ok | PU gun sections from cantiliver onto HTS with crane. Connected toolstring and swivel to gun and lifted guns into riser using both tugger and electric line with gooseneck. Conne cted and hung off all three gun sections in C-plate.
2008-04-20 | 06:00:00 | 08:45:00 | 0 | workover -- rig u p/down | ok | MU firing head, PGGT and new swiwel to guns hung off in riser. Connected upper toolstring to guns hanging in riser and armed guns. PU tension on toolstring and took off C-pl ate.
2008-04-20 | 08:45:00 | 09:15:00 | 0 | workover -- rig u p/down | ok | Connected lubricator and tested in-situ sub to 30/185 bar for 5/10 min with Seawell test pump. Ok.
2008-04-20 | 13:30:00 | 15:30:00 | 0 | workover -- wire line | ok | POOH and logged GR/CCL to above production packer. POOH with perforation guns to OOH. Powered down logging unit at 70 m below seabed. Made PA announcement and pulled cable head into tool catcher. Closed SV to verify BHA OOH.
2008-04-20 | 15:30:00 | 20:30:00 | 0 | workover -- rig u p/down | ok | Closed HMV. Observed no WHP. Opened bleed to closed drain as a precaution. Opened needle valve and confirmed that lubricator was empty and that the well was on vacuu m.
2008-04-20 | 15:30:00 | 20:30:00 | 0 | workover -- rig u p/down | ok | Broke lubricator at in-situ sub. BO and LD guns using sertified lifting sub. Observed that all shots had fired.
2008-04-20 | 20:30:00 | 22:00:00 | 0 | workover -- rig u p/down | ok | PU gun sections from cantiliver onto HTS with crane. MU lifting sub and lifted guns into riser. Connected and hung off all three gun sections in C-plate.
2008-04-20 | 22:00:00 | 23:30:00 | 0 | workover -- rig u p/down | ok | Built and tested new cable head. Checked CCL on rig floor. Shut down power to Schlumberger unit according to procedure for MU perforation gun.
2008-04-20 | 23:30:00 | 00:00:00 | 0 | workover -- rig u p/down | ok | MU firing head, CAL-B and new swiwel to guns hung off in riser. Connected upper toolstring to guns hanging in riser and armed guns.
2008-04-21 | 07:45:00 | 13:00:00 | 0 | interrupti on -- rig up/down | ok | Disarmed guns and removed firing head. Found leak in rope socket/cable head which caused short circuit in toolstring. Built and tested new cable head. Checked CCL on rig floor. Shut dow n power to Schlumberger unit according to procedure for MU perforation gun.
2008-04-21 | 13:00:00 | 14:00:00 | 0 | interrupti on -- rig up/down | ok | MU firing head, CAL-B and new swiwel to guns hung off in riser. Connected upper toolstring to guns hanging in riser and armed guns. PU tension on toolstring and took off C-plate. Connecte d lubricator and tested in-situ sub to 30/185 bar for 5/10 min with Seawell test pump. Ok. Opened HMV and observed 0 WHP. Verified TRSCSSV was open. Opened SV.
2008-04-21 | 18:15:00 | 20:30:00 | 0 | interrupti on -- rig up/down | ok | POOH with perforation guns from 3390 m to OOH. Powered down logging unit at 70 m below seabed. Made PA announcement and pulled cable head into tool catcher. Closed SV to verify B HA OOH. Closed HMV. Observed no WHP. Opened bleed to closed drain as a precaution. Opened needle valve and confirmed that lubricator was empty and that the well was on vacuum. Br oke lubricator at in-situ sub. Confirmed that guns had fired.
2008-04-21 | 20:30:00 | 21:45:00 | 0 | workover | ok | Connected lubricator and tested in-situ sub to 30/185 bar for 5/10 min with Seawell test pump. Ok. Opened HMV and observed 0 WHP. Verified TRSCSSV was open. Opened KWV. Pumped
2008-04-21 | 20:30:00 | 21:45:00 | 0 | -- rig up/ down | ok | /bullheaded 3 m3 100% MEG at 180 lpm and 8 bar into well with cmt pump to provide cusion above closed TRSCSSV. Displaced MEG to above TRSCSSV by chasing it with 5.5 m3 packer f luid at 180 lpm and 8-20 bar. WHP started to increase after approx. 3 m3 packer fluid pumped.
2008-04-22 | 00:00:00 | 01:00:00 | 0 | workover -- rig up/ down | ok | BO and LD guns using certified lifting sub. Observed that all shots had fired.
2008-04-22 | 01:00:00 | 03:00:00 | 0 | workover -- rig up/ down | ok | RD lubricatoor on rig floor. Disconnected and pulled riser sections above BOP to rig floor.
2008-04-22 | 03:00:00 | 03:45:00 | 0 | workover -- rig up/ down | ok | Opened HMV and confirmed 0 WHP below. Closed HMV and opened KWV. Leak tested XMT cross to 123 bar / 10 min against closed HMV. Dropped 0.6 bar / 10 min. Bled off pressure to zero bar. Closed KWV.
2008-04-22 | 03:45:00 | 06:00:00 | 0 | workover -- rig up/ down | ok | Held tool box meeting. RD hydraulic BOP hoses. Disconnected WL BOP's and transfered to overhead crane in moonpool. Transported BOP's to main deck. Dismantl ed scaffolding around BOP's.
2008-04-22 | 06:00:00 | 07:00:00 | 0 | workover -- rig up/ down | ok | Installed tree cap and tested same 35/380 bar for 5/10 min against closed SV using Seawell test pump and 100% MEG. Bled off pressure.
2008-04-22 | 07:00:00 | 08:45:00 | 0 | workover -- rig up/ down | ok | RD HP line from XMT KWV to cmt unit. Installed 1502 weco blind cap outside KWV and opened KWV. Leak tested KWV cap to 35/380 bar for 5/10 min aginst closed SV using Seawell test pump and 100% MEG.
2008-04-22 | 08:45:00 | 09:30:00 | 0 | workover -- rig up/ down | ok | Transfered operation of HMV and TRSCSSV to platform system/production. Filled in and signed "Well handover document" and handed over well from Volve D&W to Mærsk Production at 09:00.
2008-04-22 | 08:45:00 | 09:30:00 | 0 | workover -- rig up/ down | ok | Meanwhile RD scaffolding on rig floor and cleared rig floor of excess equipment.
2008-04-22 | 09:30:00 | 10:45:00 | 0 | workover -- rig up/ down | ok | Removed scaffolding around moonpool hatch and installed hatch.
2008-04-22 | 09:30:00 | 10:45:00 | 0 | workover -- rig up/ down | ok | ****************END OF OPERATIONS****************
2010-09-23 | 16:30:00 | 22:30:00 | 0 | workover -- rig up/dow n | ok | Well handed over from production department. Skidded rig in position. Changed to workover hatch. Meanwhile held pre job meeting with involved perso nnel.
2010-09-23 | 22:30:00 | 00:00:00 | 0 | workover -- rig up/dow n | ok | Held tool box meeting on rig floor. Leak tested XMT cross to 20/100 bar for 5/10 min.
2010-09-24 | 00:00:00 | 01:30:00 | 0 | workover -- rig up/d own | ok | Installed chiksan manifold on TKV and leak tested same to 20/100 bar for 5/10 min.
2010-09-24 | 01:30:00 | 05:00:00 | 0 | workover -- rig up/d own | ok | Removed XMT top cap and installed lower riser and BOP. Leak tested lower riser/BOP connections and function tested BOP. Lowered down upper riser from rig flo or and stabbed riser onto BOP.
2010-09-24 | 01:30:00 | 05:00:00 | 0 | workover -- rig up/d own | ok | Meanwhile checked and tested RST toolstring on surface.
2010-09-24 | 05:00:00 | 06:00:00 | 0 | workover -- rig up/d own | ok | Held tool box talk and lifted up lubricator and GIH in elevator. Started to install toolstring into lubricator.
2010-09-24 | 06:00:00 | 07:45:00 | 0 | workover -- rig up/d own | ok | Continued installing toolstring into lubricator.
2010-09-24 | 07:45:00 | 09:15:00 | 0 | workover -- wait | ok | Waited due to broken bolt in the wheel for KWV. Mechanic attempted to chang bolt without success and found a temporary solution.
2010-09-24 | 09:15:00 | 10:00:00 | 0 | workover -- rig up/d own | ok | Leak tested rig up. 20/100 bar for 5/10 min. Opened well. WHP = 7 bar.
2010-09-25 | 08:00:00 | 10:45:00 | 0 | workover -- wire li ne | ok | POOH with BHA #1.
2010-09-25 | 10:45:00 | 13:00:00 | 0 | workover -- rig up/ down | ok | OOH. WHP 37 bar. Closed well and inflow tested HMV. Bled off and flushed lubricator with N2. Held toolbox meeting.
2010-09-25 | 13:00:00 | 14:00:00 | 0 | workover -- rig up/ down | ok | LD RST toolstring and inspected same.
2010-09-25 | 14:00:00 | 14:45:00 | 0 | workover -- rig up/ down | ok | Closed BOP. Flushed riser with N2 through KWV to blow down.
2010-09-25 | 14:45:00 | 16:15:00 | 0 | workover -- rig up/ down | ok | Closed DHSV and bled down to 8 bar. Inflow tested DHSV. Bled off pressure above and closed well. Lined up and leak tested XMT cross.
2010-09-25 | 16:15:00 | 18:30:00 | 0 | workover -- rig up/ down | ok | Held toolbox meeting and LD lubricator onto cat walk machine. Lifted upper riser section to rig floor with top drive. Lifted BOP away in moon pool. RD lower riser.
2010-09-25 | 18:30:00 | 21:00:00 | 0 | workover -- rig up/ down | ok | Removed chiksan manifold on KWV and installed end cap. Installed XMT top cap. Leak tested KWV end cap and XMT top cap to 20/345 bar for 5/10 min. Disconnect ed local control panel for HMV and DHSV.
2010-09-25 | 18:30:00 | 21:00:00 | 0 | workover -- rig up/ down | ok | Handed well over to Production department.
2010-09-25 | 21:00:00 | 00:00:00 | 0 | workover -- rig up/ down | ok | Disassambled riser and lubricator and lifted out riser sections from rig floor.
2010-09-26 | 00:00:00 | 06:00:00 | 0 | workover -- rig up/dow n | ok | Cleared rig floor off remaining WL equipment.Tidied and cleaned rig floor. Skidded rig in parking position. Prepared and packed WL equipment for demobilization.
2010-09-26 | 00:00:00 | 06:00:00 | 0 | workover -- rig up/dow n | ok | END OF OPERATION
2012-09-11 | 07:00:00 | 11:00:00 | 0 | workover -- wire line | ok | Received WL equipment from boat.
2012-09-11 | 11:00:00 | 13:00:00 | 0 | workover -- wire line | ok | Removed containers, tanks, equipment and prepared pipe deck area for spotting wireline equipment.
2012-09-11 | 13:00:00 | 17:00:00 | 0 | workover -- wire line | ok | Started to spot WL equipment on pipe deck.
2012-09-11 | 17:00:00 | 21:00:00 | 0 | workover -- wire line | ok | Leak tested BOP on stump. Started to prepare WL equipment.
2012-09-11 | 21:00:00 | 21:20:00 | 0 | workover -- wire line | ok | Held Mearsk Toolbox Talk together with Maersk personnel prior to build lubricator. Held AWS check card meeting prior to thread the cable through GIH and toolcatcher.
2012-09-11 | 21:20:00 | 00:00:00 | 0 | workover -- wire line | ok | Lifted and spotted Smart skid in front of winch. Lifted toolcatcher and GIH to rig floor. Threaded the cable through GIH and tool catcher, prior to build cable head. Built lubricator with fork lift on main deck.
2012-09-12 | 00:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Waited on Mearsk electrician, prior to hook up all wireline units. Electrician busy with other jobs. Meanwhile lifted BOP down to BOP deck through hatch on drill floor and prepared wireline equipment.
2012-09-12 | 06:00:00 | 09:00:00 | 0 | interruption -- wait | ok | Waited on Mearsk electrician, prior to hook up all wireline units. Electrician busy with other jobs. Meanwhile prepared wireline equipment.
2012-09-12 | 09:00:00 | 12:00:00 | 0 | workover -- wire line | ok | Hooked up wireline units to power and F&G.
2012-09-12 | 12:00:00 | 14:00:00 | 0 | workover -- wire line | ok | Assembled lubricator and riser on rig floor.
2012-09-12 | 14:00:00 | 17:00:00 | 0 | workover -- wire line | ok | Prepared wireline equipment. Meanwhile built cable head.
2012-09-12 | 17:00:00 | 21:00:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile built cable head and megged same. Tried to connect logging unit to internet, no success.
2012-09-12 | 21:00:00 | 21:30:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile held start up meeting with night crew.
2012-09-12 | 21:30:00 | 00:00:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile tested counter system and RST tool.
2012-09-13 | 00:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile tested RST tool.
2012-09-13 | 06:00:00 | 10:30:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile tested RST tool.
2012-09-13 | 10:30:00 | 11:00:00 | 0 | workover -- wire line | ok | Well handed over from production department.
2012-09-13 | 11:00:00 | 11:30:00 | 0 | workover -- wire line | ok | Held DOP#1 meeting prior to R/U on well.
2012-09-13 | 11:30:00 | 13:00:00 | 0 | workover -- wire line | ok | Leak tested XMT cross to 20/120 bar for 5/10 min. Meanwhile prepared to install lower riser and BOP.
2012-09-13 | 13:00:00 | 13:30:00 | 0 | workover -- other | ok | Held brief prior to install lower riser and BOP.
2012-09-13 | 13:30:00 | 16:30:00 | 0 | workover -- wire line | ok | Removed XMT top cap and installed lower riser and BOP. Leak tested lower riser/BOP connections to 20/120 bar for 5/10 min.
2012-09-13 | 16:30:00 | 17:15:00 | 0 | workover -- wire line | ok | Lowered down lower lubricator from rig floor and stabbed lubricator onto BOP.
2012-09-13 | 17:15:00 | 17:30:00 | 0 | workover -- other | ok | Held brief prior to install toolstring into lubricator.
2012-09-13 | 17:30:00 | 19:00:00 | 0 | workover -- wire line | ok | Installed toolstring into lubricator.
2012-09-13 | 19:00:00 | 19:30:00 | 0 | workover -- wire line | ok | Held brief prior to lift up lubricator and GIH in elevator.
2012-09-13 | 19:30:00 | 22:30:00 | 0 | workover -- wire line | ok | Connected hoses and lifted up lubricator and GIH in elevator. Connected toolstring and stabbed upper lubricator unto lower lubricator.
2012-09-13 | 22:30:00 | 23:00:00 | 0 | workover -- other | ok | Held DOP#2 meeting prior to RIH with RST toolstring.
2012-09-13 | 23:00:00 | 00:00:00 | 0 | workover -- wire line | ok | Prepared to leak test R/U.
2012-09-14 | 00:00:00 | 02:00:00 | 0 | workover -- wire line | ok | Leak tested R/U to 20/120 bar for 5/10 min. Opened well. WHP = 42 bar
2012-09-14 | 00:00:00 | 02:00:00 | 0 | workover -- wire line | ok | .
2012-09-14 | 02:00:00 | 02:15:00 | 0 | workover -- other | ok | Held well controll drill prior to RIH.
2012-09-15 | 07:40:00 | 09:30:00 | 0 | workover -- wire line | ok | POOH from 3220 m to surface. WHP:42 bar.
2012-09-15 | 09:30:00 | 11:00:00 | 0 | workover -- test scsssv | ok | OOH. Closed in SWAB and HMV. Inflow tested same. Opened HMV and inflow tested DHSV.
2012-09-15 | 11:00:00 | 12:30:00 | 0 | workover -- wire line | ok | L/D upper lubricator on drill floor and removed BHA#1, RST-D logging tool.
2012-09-15 | 12:30:00 | 13:00:00 | 0 | workover -- oth er | ok | Performed brief prior to rig down.
2012-09-15 | 13:00:00 | 15:10:00 | 0 | workover -- wire line | ok | Lifted lower lubricator to rig floor with top drive. Lifted BOP away in moon pool. R/D lower riser.
2012-09-15 | 15:10:00 | 19:00:00 | 0 | workover -- wire line | ok | Removed chiksan manifold on KWV and installed end cap. Installed XMT top cap. Leak tested KWV end cap and XMT top cap to 20/345 bar for 5/10 min. Disconnected local panal for HMV and DHSV. Handed well over to production department.
2012-09-15 | 15:10:00 | 19:00:00 | 0 | workover -- wire line | ok | END OF OPERATION
2016-10-01 | 15:00:00 | 16:00:00 | 0 | moving -- skid | ok | Reporting continued from F-99.
2016-10-01 | 15:00:00 | 16:00:00 | 0 | moving -- skid | ok | Continued to skid cantilever to F-04 9m inboard/1.25m port. Continued work with Aft PRS
2016-10-01 | 16:00:00 | 16:30:00 | 0 | moving -- skid | ok | Installed covers to skidding system. Meanwhile held TBT for connecting HP hose to F-04 and for removal of well head cover/installation of split cover
2016-10-01 | 16:30:00 | 17:30:00 | 0 | plug abandon -- o ther | ok | Connected HP hose to F-04. Meanwhile tested aft PRS. Prepared subs for pressure testing
2016-10-01 | 17:30:00 | 19:00:00 | 0 | plug abandon -- o ther | ok | Performed line test down to XMT. Performed test of XMT cross 20/345bar for 5/10min. Good test
2016-10-01 | 19:00:00 | 19:15:00 | 0 | plug abandon -- o ther | ok | Performed Pre-job Meeting to remove moonpool hatches
2016-10-01 | 19:15:00 | 20:15:00 | 0 | plug abandon -- o ther | ok | Removed hatches and installed split hatch
2016-10-01 | 20:15:00 | 21:30:00 | 0 | plug abandon -- o ther | ok | Adjusted scaffolding around Xmas tree. Prepared lines and bled off A and B annulus to MGS. Worked to fill A and B annulus with sea water. Bled off pressure and remo ved Tree cap from Xmas tree w/ rigfloor winch
2016-10-01 | 21:30:00 | 23:45:00 | 0 | plug abandon -- o ther | ok | Hooked up hydraulic pump for local control of DHSV an HMV. Meanwhile worked to fill A and B annulus with sea water, carried out TBT for R/U cement head
2016-10-01 | 23:45:00 | 00:00:00 | 0 | plug abandon -- o ther | ok | Worked to P/U cement head in moonpool using overhead crane and transfered to TDS lifting chains
2016-10-02 | 00:00:00 | 00:45:00 | 0 | plug aba ndon -- o ther | ok | Worked to P/U cement head in moonpool using overhead crane and transfered to TDS lifting chains
2016-10-02 | 00:45:00 | 01:45:00 | 0 | plug aba ndon -- o ther | ok | M/U cement head to the Xmas tree, installed split hatch in moonpool
2016-10-02 | 01:45:00 | 03:30:00 | 0 | plug aba ndon -- o ther | ok | Built scaffolding around cement head in moonpool
2016-10-02 | 03:30:00 | 03:45:00 | 0 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to pressure test cement head
2016-10-02 | 03:45:00 | 04:45:00 | 0 | plug aba ndon -- o ther | ok | Confirmed line up, flushed and pressure tested cement head and bleed off manifold to 20/345 bar for 5/10 min
2016-10-02 | 04:45:00 | 05:00:00 | 0 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting before bullheading operation
2016-10-02 | 05:00:00 | 05:30:00 | 0 | plug aba ndon -- o ther | ok | Lined up to pump into the well. Opened HMV. Wellhead pressure went up to 20 bar. Bled off pressure to MGS. Pressured up DHSV control line to 520bar. Pressured up above DHSV to equalize pressure. Observed indecation of DHSV openning on hydraulic pump pressure gauge.
2016-10-02 | 05:30:00 | 06:00:00 | 0 | plug aba ndon -- o ther | ok | Pumped 10m3 of wash pill, 1100 l/min - 134bar
2016-10-02 | 06:00:00 | 08:00:00 | 0 | plug aba ndon -- o ther | ok | Bullheaded sea water into the well, 1300 l/min - 143 bar, totally pumped 140m3. Meanwhile carried out TBT for cement job
2016-10-02 | 08:00:00 | 09:45:00 | 0 | plug aba ndon -- o ther | ok | Lined up valves on the cement head, released bottom dart, mixed and pumped 13.6m3 1,90SG cement, 600l/min. Pressure 130 bar, decreasing to 90bar, indicating cement moving down in t he tubing. Displaced lines w/ 0,9m3 of Hi-vis pill. Released top dart. Pumped 12,2m3 of Hi-vis (totally pumped 13,1m3 of Hi-vis). Displaced w/ 37,7m3 of sea water at initial rate of 1000lpm. I ncreased pumping rate to 1300l/min - 101bar. Reduced pumping rate in the end of displacement to 700l/min - 83bar. Switched to contamination pill. Observed rapid increase in pressure whil e pumping contamination pill indicating cement plugging into perforations. Shut down after having pumped 3,5m3 contamination pill, 111 bar and monitored WH pressure decline. Recorded fi nal stabilized squeeze pressure of 60bar. Closed swab valve.
2016-10-02 | 08:00:00 | 09:45:00 | 0 | plug aba ndon -- o ther | ok | Verified volumes pumped by checking volumes left in the pits and silos. Theoretical top of cement 2755mMD. DHSV was cycled 3 times after 30m3 of sea water displacement was pumped
2016-10-02 | 09:45:00 | 13:00:00 | 0 | plug aba ndon -- o ther | ok | Flushed manifolds after cement job. Worked aloft in derrick to repair crown grease system. Lined up and prepare to pressure test BOP. Meanwhile WOC
2016-10-02 | 13:00:00 | 13:45:00 | 0 | plug aba ndon -- o ther | ok | Performed BOP test No1 20/345 bar 5/10 minutes. Cycleed HMV and MMV. Meanwhile WOC
2016-10-02 | 13:45:00 | 14:45:00 | 0 | plug aba ndon -- o ther | ok | Lined up for BOP test No2, flushed 0.5m3 through kill and choke lines
2016-10-02 | 14:45:00 | 15:45:00 | 0 | plug aba ndon -- o ther | ok | Performed BOP test No2 20/345 bar 5/10 minutes. Cycled HMV and MMV. Meanwhile pumped out dirty side of skimmer tank to mill tank, WOC
2016-10-02 | 15:45:00 | 17:00:00 | 0 | plug aba ndon -- o ther | ok | Lined up and performed BOP test No3 20/345 bar 5/10 minutes. Continued to clear out dirty side of skimmer tank, transfered to mud pits 7.5m3. Lined up to bleed off pressure from XMT 110 bar down to 62bar. Meanwhile WOC
2016-10-02 | 17:00:00 | 17:30:00 | 0 | plug aba ndon -- o ther | ok | Opened all low torque valves on cement head and pressure tested rig up against SV to 310 bar/10 minutes. Meanwhile WOC
2016-10-02 | 17:30:00 | 18:15:00 | 0 | plug aba ndon -- o ther | ok | Closed HMV , bled off pressure above HMV from 72bar to 0. Opened SV, pressured up to 72bar to equalize, opened HMV. Pressured up well against cement plug with cement pump to 310b ar/10min. Pumped 620liters. Good pressure test.
2016-10-02 | 18:15:00 | 19:15:00 | 0 | plug aba ndon -- o ther | ok | Carried out inflow test of cement plug. Bled down pressure in tubing to 10 bar. Monitored pressure pressure for 30 min. Pressure increased 3.6 bar with clear decreasing trend towards the en
2016-10-02 | 18:15:00 | 19:15:00 | 0 | plug aba ndon -- o ther | ok | d. Good inflow test
2016-10-02 | 19:15:00 | 22:00:00 | 0 | plug aba ndon -- o ther | ok | Carried out inflow test of DHSV. Equalized pressure and opened swab valve, applied 310 bar to tubing. 770l pumped. Closed DHSV. Bled off pressure in tubing above DHSV to 240 bar. Monitored pressure above DHSV for 30 min for 70bar LP inflow test. Pressure increased 1.5bar in 30 min with decreasing trend towards the end. Good LP inflow test. Bled down pressure in tubing above DHSV to 10bar. 110l bled off. Monitored pressure above DHSV for 30 min for 300bar HP inflow test. Pressure increased 2,4bar in 30 min with decreasing trend towards the end
2016-10-02 | 19:15:00 | 22:00:00 | 0 | plug aba ndon -- o ther | ok | . Good HP inflow test. Equalized pressure above DHSV, pressured up control line to DHSV to 520bar to open DHSV. Bled off tubing pressure to 20bar. 710l bled off. Closed DHSV. Bled off r emaining pressure from Xmas tree. Meanwhile performed TBT to R/D cement head
2016-10-02 | 22:00:00 | 23:30:00 | 0 | plug aba ndon -- o ther | ok | Closed SV. R/D cement head. Removed hydraulic control hoses to HMV and DHSV. Broke off bleed off manifold from kill wing side
2016-10-02 | 23:30:00 | 00:00:00 | 0 | plug aba ndon -- o ther | ok | Worked to installed BPV plug for drop protection and Xmas tree lifting cap. Meanwhile performed BOP test No4
2016-10-03 | 00:00:00 | 00:15:00 | 0 | plug abandon -- ot her | ok | Continued to install BPV plug for drop protection and Xmas tree lifting cap. Meanwhile worked to perform BOP test No5
2016-10-03 | 00:15:00 | 02:30:00 | 0 | plug abandon -- ot her | ok | Remove scaffolding from around Xmas tree and R/D electric and hydraulic lines from Xmas tree. Meanwhile performed pre-job meeting to N/D Xmas tree, pressure te sted BOP test No5
2016-10-03 | 02:30:00 | 03:15:00 | 0 | plug abandon -- ot her | ok | Removed hatches and beam between slots. Meanwhile worked to pressure test BOP test No6, 7
2016-10-03 | 03:15:00 | 04:00:00 | 0 | plug abandon -- ot her | ok | Removed master bushing and outer ring. Lowered diverter chains on TDS bails to wellhead and attached to X-tree. Meanwhile pressure tested BOP test No7
2016-10-03 | 04:00:00 | 04:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to lift Xmas tree
2016-10-03 | 04:15:00 | 05:15:00 | 0 | plug abandon -- ot her | ok | Took weight as per lifting plan and removed Grayloc clamp. Lifted X-tree to moonpool. Transfered load to gantry crane in moonpool. Attached lifting arrangement fro m TDS to Spacer spool
2016-10-03 | 05:15:00 | 06:30:00 | 0 | plug abandon -- ot her | ok | Released NT-2 connector on wellhead, had difficulties to release 2x tight bolts. Meanwhile prepared HP riser on rig floor
2016-10-03 | 06:30:00 | 08:15:00 | 0 | plug abandon -- ot her | ok | Cut control lines, installed communication collar and dart on BPV, cleaned up seal area. Meanwhile P/U riser from HTS
2016-10-03 | 08:15:00 | 08:45:00 | 0 | plug abandon -- ot her | ok | Installed covers in moonpool using rigfloor winch
2016-10-03 | 08:45:00 | 09:15:00 | 0 | plug abandon -- ot her | ok | P/U and RIH HP riser and M/U NT-2 connector
2016-10-03 | 09:15:00 | 11:00:00 | 0 | plug abandon -- ot her | ok | Removed scaffolding from test stump and built scaffolding around HP Riser. Performed checks prior to skid BOP to well center. Meanwhile worked to M/U TDS test a ssembly
2016-10-03 | 11:00:00 | 11:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to move BOP to well center
2016-10-03 | 11:15:00 | 12:00:00 | 0 | plug abandon -- ot her | ok | Skidded BOP to well center and landed off on HP riser. Meanwhile pressure tested kelly hose to 20/345 bar, 5/10 min
2016-10-03 | 12:00:00 | 12:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to M/U NT-2 connector
2016-10-03 | 12:15:00 | 13:30:00 | 0 | plug abandon -- ot her | ok | M/U NT-2 connector. Meanwhile pressure tested upper/lower IBOPs and 2x FOSVs to 20/345 bar, 5/10 min
2016-10-03 | 13:30:00 | 13:45:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to connect tension cylinders
2016-10-03 | 13:45:00 | 15:00:00 | 0 | plug abandon -- ot her | ok | R/U tension system
2016-10-03 | 15:00:00 | 15:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to handle slick joint
2016-10-03 | 15:15:00 | 16:00:00 | 0 | plug abandon -- ot her | ok | Removed master bushing, RIH with Slick joint and M/U same, measured RKB to top of Annular = 5.78m
2016-10-03 | 16:00:00 | 16:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to handle diverter
2016-10-03 | 16:15:00 | 17:45:00 | 0 | plug abandon -- ot her | ok | P/U and RIH w/ diverter and landed off. Continued M/U slick joint. Meanwhile removed chains from bails and connected overshot hose. Energized overshot, lined up a nd filled hole with 3m3. No leaks observed
2016-10-03 | 17:45:00 | 18:00:00 | 0 | plug abandon -- ot her | ok | Lined up cement unit through kill HCR, closed BSRs. Applied 20 bar to kill HCR valve to confirm line up
2016-10-03 | 18:00:00 | 18:30:00 | 0 | plug abandon -- ot her | ok | With slick joint made up, fine tuned tension cylinders for equal pull
2016-10-03 | 18:30:00 | 19:00:00 | 0 | plug abandon -- ot her | ok | Performed connection test to 20/345 bar 5/10 min, good test
2016-10-03 | 19:00:00 | 19:30:00 | 0 | plug abandon -- ot her | ok | Finished to M/U slick joints, cleaned and cleared rig floor
2016-10-03 | 19:30:00 | 20:00:00 | 0 | plug abandon -- ot her | ok | Changed handling equipment to 3.5in DP
2016-10-03 | 20:00:00 | 20:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to retrieve dart and BPV
2016-10-03 | 20:15:00 | 21:15:00 | 0 | plug abandon -- ot her | ok | Retrieved dart from BPV
2016-10-03 | 21:15:00 | 21:45:00 | 0 | plug abandon -- ot her | ok | Retrieved BPV
2016-10-03 | 21:45:00 | 22:15:00 | 0 | plug abandon -- ot her | ok | R/B 3.5in DP, L/D retrieval tool
2016-10-03 | 22:15:00 | 22:30:00 | 0 | plug abandon -- ot her | ok | Changed handling gear, prepared for running THRT
2016-10-03 | 22:30:00 | 22:45:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to R/U casing tong
2016-10-03 | 22:45:00 | 23:30:00 | 0 | plug abandon -- ot her | ok | R/U casing tong
2016-10-03 | 23:30:00 | 23:45:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to run w/ THRT and landing string
2016-10-03 | 23:45:00 | 00:00:00 | 0 | plug abandon -- ot her | ok | P/U and RIH with tubing hanger running tool (THRT).
2016-10-04 | 00:00:00 | 02:00:00 | 0 | plug aba ndon -- o ther | ok | Continued to P/U and M/U tubingTHRT and landing string. POOH, installed control lines and inspected THRT. RIH and landed off THRT on TH. Observed top box of landing string is too high for casing tong to be able to M/U swedge.
2016-10-04 | 02:00:00 | 02:15:00 | 0 | interrupti on -- rep air | ok | Performed Pre-job Meeting to rearrange landing string to be able to M/U swedge w/ casing tong. Started to position upper pup joint of landing string for casing tong to break off. Observed hy draulic oil leak from elevator
2016-10-04 | 02:15:00 | 03:00:00 | 0 | interrupti on -- rep air | ok | Identified faulty hydraulic hose inside of the elevator and changed same
2016-10-04 | 03:00:00 | 05:30:00 | 0 | interrupti on -- rep air | ok | Broke top 6m pup from landing string. M/U swedge using aft PRS and casing tong. Realized that it is not possible to break swedge while connected to TH with THRT. Broke off swedge using aft PRS and casing tong. Located 4m tubing joint (3m + 1m pups) on the pipe deck. M/U same to landing string, M/U 1m pup joint to landing string. Achieved sufficient stick up to be able to M
2016-10-04 | 03:00:00 | 05:30:00 | 0 | interrupti on -- rep air | ok | /U swedge
2016-10-04 | 05:30:00 | 06:15:00 | 0 | interrupti on -- rep air | ok | Attempted to engage THRT to TH. No success, POOH, checked THRT, observed shear pins sheared prematurely. Repaired THRT
2016-10-04 | 06:15:00 | 07:00:00 | 0 | plug aba ndon -- o ther | ok | RIH and landed off THRT, engaged tool and confirmed w/ 2t overpull. Applied pressure to shear pin and then rotated string 8x turns CCW into communication collar
2016-10-04 | 07:00:00 | 08:00:00 | 0 | plug aba ndon -- o ther | ok | Connected cement hose and LT valve, flushed hose. Pressure tested same to 100 bar. Lined up pumps through cement hose. Applied pressure of 520bar to DHSV control lines. Pressured u p well above DHSV, observed DHSV equalized and opened at 100 bar pressure. No indications of gas below DHSV/in the well observed. Bled off pressure from the well through the cement hose to MGS to 0. Closed DHSV. Verified no pressure in the A-annulus
2016-10-04 | 08:00:00 | 08:15:00 | 0 | plug aba ndon -- o ther | ok | Broke off swedge
2016-10-04 | 08:15:00 | 08:30:00 | 0 | plug aba ndon -- o ther | ok | Released TH and and pulled 180t on hook load. String stretch of 0,75m
2016-10-04 | 08:30:00 | 08:45:00 | 0 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to R/U WL equipment
2016-10-04 | 08:45:00 | 09:30:00 | 0 | plug aba ndon -- o ther | ok | R/U wireline equipment
2016-10-04 | 13:00:00 | 15:00:00 | 0 | plug aba ndon -- o ther | ok | POOH from 2621 m to surface. Average pulling speed 22 m/min. Backflow at rotary gradually decreased and eventually stopped
2016-10-04 | 15:00:00 | 15:30:00 | 0 | plug aba ndon -- o ther | ok | R/D wireline equipment
2016-10-04 | 15:30:00 | 15:45:00 | 0 | plug aba ndon -- o ther | ok | Performed flowcheck. Static
2016-10-06 | 03:15:00 | 05:15:00 | 0 | plug aban don -- oth er | ok | POOH w/ spear and L/D 5.5in DP
2016-10-06 | 05:15:00 | 05:30:00 | 0 | plug aban don -- ce ment plug | ok | Performed Pre-job Meeting to L/D spear BHA
2016-10-06 | 05:30:00 | 05:45:00 | 0 | plug aban don -- ce ment plug | ok | Removed DP slips, installed master bushing
2016-10-06 | 05:45:00 | 06:15:00 | 0 | plug aban don -- ce ment plug | ok | L/D spear BHA
2016-10-06 | 06:15:00 | 06:45:00 | 0 | plug aban don -- ce ment plug | ok | Removed power rollers. Cleaned and cleared rig floor
2016-10-06 | 07:45:00 | 08:00:00 | 0 | plug aban don -- oth er | ok | Performed Pre-job Meeting to P/U MS-T seal retrieval tool
2016-10-06 | 10:00:00 | 10:15:00 | 0 | plug aban don -- cut | ok | Performed Pre-job Meeting to P/U cutter BHA
2016-10-06 | 11:45:00 | 12:00:00 | 0 | plug aban don -- cut | ok | L/D cutter BHA
2016-10-06 | 12:00:00 | 12:15:00 | 0 | plug aban don -- equ ipment rec overy | ok | Performed Pre-job Meeting to R/U casing tong
2016-10-06 | 12:15:00 | 13:15:00 | 0 | plug aban don -- equ ipment rec overy | ok | R/U casing tong on the rig floor
2016-10-06 | 14:30:00 | 16:15:00 | 0 | plug aban don -- equ ipment rec overy | ok | POOH and L/D 10 3/4in caing tieback from 103m to surface
2016-10-06 | 16:15:00 | 17:00:00 | 0 | plug aban don -- equ ipment rec overy | ok | R/D casing tong and changed BX elevators
2016-10-06 | 17:00:00 | 17:15:00 | 0 | plug aban don -- oth er | ok | Performed Pre-job Meeting to change saver sub to left hand one
2016-10-06 | 17:15:00 | 18:30:00 | 0 | plug aban don -- oth er | ok | Placed 3m pup in rotary. Screwed in TDS and broke off saver sub. L/D pup with saver sub on top. RIH 1x stand with left hand DP. M/U left hand saver sub to stand, screwed in TDS and M/ U to saver sub
2016-10-06 | 18:30:00 | 18:45:00 | 0 | plug aban don -- oth er | ok | R/B stand and P/U torque tool
2016-10-06 | 21:45:00 | 22:15:00 | 0 | plug aban don -- oth er | ok | L/D torque tool
2016-10-06 | 22:15:00 | 22:30:00 | 0 | plug aban don -- oth er | ok | L/D 4x singles of LH DP from the stand previously R/B
2016-10-06 | 22:30:00 | 22:45:00 | 0 | plug aban don -- oth er | ok | Removed DP slips, installed master bushing
2016-10-06 | 22:45:00 | 23:00:00 | 0 | plug aban don -- oth er | ok | Performed Pre-job Meeting to change saver sub back to right hand one
2016-10-06 | 23:00:00 | 00:00:00 | 0 | plug aban don -- oth er | ok | Worked to change saver sub back to right hand one
2016-10-07 | 00:00:00 | 00:15:00 | 0 | plug abandon - | ok | Worked to change saver sub back to the right hand one
2016-10-07 | 00:15:00 | 00:30:00 | 0 | plug abandon - | ok | Performed Pre-job Meeting to P/U spear BHA
2016-10-07 | 01:15:00 | 02:00:00 | 0 | plug abandon - | ok | Engaged spear in tieback adapter fish, pulled w/ 6t overpull. POOH w/ fish to surface
2016-10-07 | 02:00:00 | 02:45:00 | 0 | plug abandon - | ok | R/B spear BHA, L/D tieback adapter stump
2016-10-07 | 02:45:00 | 03:00:00 | 0 | plug abandon - | ok | Performed TBT to P/U perforation guns
2016-10-07 | 08:30:00 | 09:00:00 | 0 | plug abandon - | ok | L/D perforation BHA.
2016-10-07 | 09:00:00 | 09:15:00 | 0 | plug abandon - | ok | Performed TBT for cutting 10 3/4" casing
2016-10-07 | 09:15:00 | 09:30:00 | 0 | plug abandon - | ok | Removed master bushing. Installed PS-21 slips.
2016-10-07 | 09:30:00 | 09:45:00 | 0 | plug abandon - | ok | P/U and M/U 10 3/4" cutter BHA.
2016-10-07 | 11:30:00 | 11:45:00 | 0 | plug abandon - | ok | L/D cutter BHA.
2016-10-07 | 11:45:00 | 12:00:00 | 0 | plug abandon - | ok | Cleaned and cleared drill floor.
2016-10-07 | 12:00:00 | 12:15:00 | 0 | plug abandon - | ok | Performed TBT for drops inspection prior to milling 10 3/4" casing hanger.
2016-10-07 | 12:15:00 | 13:00:00 | 0 | plug abandon - | ok | Performed drops inspection of TDS, and both PRSs.
2016-10-07 | 23:00:00 | 00:00:00 | 0 | plug abandon - | ok | R/B 8 1/4" DC.
2016-10-07 | 23:00:00 | 00:00:00 | 0 | - other | ok | B/O and L/O CH milling BHA.
2016-10-08 | 00:00:00 | 00:30:00 | 0 | plug abandon -- mill | ok | Cleaned and cleared drill floor
2016-10-08 | 00:30:00 | 00:45:00 | 0 | plug abandon -- equipm ent recovery | ok | Performed TBT for RIH with spear and retrieve 10 3/4" casing
2016-10-08 | 00:45:00 | 01:00:00 | 0 | plug abandon -- equipm ent recovery | ok | M/U spear BHA
2016-10-08 | 03:00:00 | 06:00:00 | 0 | plug abandon -- equipm ent recovery | ok | L/D casing pup joint.
2016-10-08 | 03:00:00 | 06:00:00 | 0 | plug abandon -- equipm ent recovery | ok | Continued POOH with 10 3/4" casing from 170 m to surface. Average 10 joints/hr.
2016-10-08 | 06:00:00 | 08:15:00 | 0 | plug abandon -- equipm ent recovery | ok | R/D handling equipment.
2016-10-08 | 08:15:00 | 08:30:00 | 0 | plug abandon -- other | ok | Performed TBT for running 13 3/8" EZSV plug
2016-10-08 | 17:15:00 | 17:30:00 | 0 | plug abandon -- cement plug | ok | POOH and L/D the EZSV RT.
2016-10-08 | 17:30:00 | 19:00:00 | 0 | plug abandon -- other | ok | RIH with 3 std 8 1/4" DC. L/O 2 x singles to cantilever.
2016-10-08 | 19:00:00 | 21:15:00 | 0 | plug abandon -- other | ok | Performed TBT with ongoing crew. Performed manual tong training. L/O 7 joints 8 1/4" DC.
2016-10-08 | 21:15:00 | 22:00:00 | 0 | plug abandon -- other | ok | L/O 10 3/4" spear BHA
2016-10-08 | 22:00:00 | 23:15:00 | 0 | plug abandon -- other | ok | L/O 3 joints 6 3/4" DC
2016-10-08 | 23:15:00 | 00:00:00 | 0 | plug abandon -- other | ok | L/O 5 joints over-torqued 5 1/2" DP
2016-10-09 | 00:00:00 | 01:15:00 | 0 | plug abandon -- other | ok | L/O 13 joints 5 1/2" over-torqued DP
2016-10-09 | 01:15:00 | 03:00:00 | 0 | plug abandon -- other | ok | L/O 4 joints over-torqued 5 1/2" HWDP. Used manual tongs to break one of the connections
2016-10-09 | 01:15:00 | 03:00:00 | 0 | plug abandon -- other | ok | .
2016-10-09 | 03:00:00 | 03:15:00 | 0 | plug abandon -- other | ok | Cleaned and cleared drill floor.
2016-10-09 | 03:00:00 | 03:15:00 | 0 | plug abandon -- other | ok | Changed handling equipment for pulling diverter.
2016-10-09 | 03:15:00 | 03:30:00 | 0 | plug abandon -- other | ok | Performed TBT for N/D BOP
2016-10-09 | 03:30:00 | 04:15:00 | 0 | plug abandon -- other | ok | N/D diverter and pulled slickjoint.
2016-10-09 | 04:15:00 | 04:45:00 | 0 | plug abandon -- other | ok | Load shifted weight from tension system to BOP carrier.
2016-10-09 | 04:45:00 | 05:30:00 | 0 | plug abandon -- other | ok | Disconnected BOP tension system. Meanwhile: Disconnected BOP NT2 connector
2016-10-09 | 05:30:00 | 05:45:00 | 0 | plug abandon -- other | ok | Skidded BOP over to test stump
2016-10-09 | 05:45:00 | 06:15:00 | 0 | plug abandon -- other | ok | Removed scaffolding around HP-riser. Meanwhile: Performed TBT for pulling HP-riser
2016-10-09 | 06:15:00 | 07:00:00 | 0 | plug abandon -- other | ok | Pulled HP-riser to drill floor. Installed master bushing.
2016-10-09 | 07:00:00 | 07:15:00 | 0 | plug abandon -- other | ok | Performed TBT for L/O HP-riser to HTS and installing hatches in moonpool
2016-10-09 | 07:15:00 | 07:30:00 | 0 | plug abandon -- other | ok | L/O HP-riser to HTS
2016-10-09 | 07:30:00 | 09:00:00 | 0 | plug abandon -- other | ok | Installed hatches in moonpool.
2016-10-09 | 07:30:00 | 09:00:00 | 0 | plug abandon -- other | ok | Meanwhile: Cleaned and preserved slickjoint
2016-10-10 | 10:45:00 | 13:15:00 | 0 | interruption -- wait | ok | Waited on supply boat with equipment for pulling production riser
2016-10-10 | 10:45:00 | 13:15:00 | 0 | interruption -- wait | ok | Meanwhile:
2016-10-10 | 10:45:00 | 13:15:00 | 0 | interruption -- wait | ok | L/O 3 1/2" DP from set-back. Meanwhile: Performed PMs.
2016-10-10 | 13:15:00 | 15:00:00 | 0 | interruption -- wait | ok | Waited on supply boat with equipment for pulling production riser
2016-10-10 | 13:15:00 | 15:00:00 | 0 | interruption -- wait | ok | Meanwhile:
2016-10-10 | 13:15:00 | 15:00:00 | 0 | interruption -- wait | ok | Canged handling equipment to handle 5 1/2" DP. L/O 5 1/2" DP from set-back.
2016-10-10 | 15:00:00 | 19:00:00 | 0 | plug abandon -- other | ok | Continued L/O 5 1/2" DP from set-back. Meanwhile:
2016-10-10 | 15:00:00 | 19:00:00 | 0 | plug abandon -- other | ok | Removed remaining hoses and electrical cables from WH
2016-10-10 | 19:00:00 | 19:15:00 | 0 | plug abandon -- other | ok | Performed TBT for L/D diverter
2016-10-10 | 19:15:00 | 20:45:00 | 0 | plug abandon -- other | ok | R/U and attached lifting equipment to TDS and diverter. L/O diverter and secured same on main deck.
2016-10-10 | 19:15:00 | 20:45:00 | 0 | plug abandon -- other | ok | Removed diverter lifting equipment from TDS.
2016-10-10 | 19:15:00 | 20:45:00 | 0 | plug abandon -- other | ok | Meanwhile: Performed TBT for building scaffolding around BOP connector on test stump.
2016-10-10 | 20:45:00 | 21:30:00 | 0 | plug abandon -- other | ok | Prepared 1502 hoses/chiksan at WH Built scaffolding around BOP.
2016-10-10 | 21:30:00 | 22:15:00 | 0 | plug abandon -- other | ok | N/U BOP NT2 connector on test stump. Prepared lifting equipment on moonpool hatch. Lifted multibowl NT2 connector to drill floor.
2016-10-10 | 21:30:00 | 22:15:00 | 0 | plug abandon -- other | ok | Lifted PR cutter BHA to HTS
2016-10-10 | 22:15:00 | 23:00:00 | 0 | plug abandon -- other | ok | Continued N/U BOP NT2 connector on test stump
2016-10-10 | 23:00:00 | 00:00:00 | 0 | plug abandon -- other | ok | Removed hatch in moonpool.
2016-10-11 | 00:00:00 | 00:45:00 | 0 | plug abandon -- other | ok | Lowered NT2 connector for multibowl. M/U NT2 connector on multibowl.
2016-10-11 | 00:45:00 | 01:00:00 | 0 | plug abandon -- other | ok | Installed master bushing and removed box ring from rotary.
2016-10-11 | 01:00:00 | 01:15:00 | 0 | plug abandon -- other | ok | Performed TBT for handling PR cutter BHA
2016-10-11 | 04:30:00 | 05:00:00 | 0 | plug abandon -- other | ok | Performed debrief after M/U BHA.
2016-10-11 | 05:00:00 | 05:30:00 | 0 | plug abandon -- other | ok | Performed TBT for R/D tension cylinders on PR
2016-10-11 | 05:30:00 | 07:00:00 | 0 | plug abandon -- other | ok | Bled off pressure in PR tension cylinders, observed 35 ton increase on weight indicator
2016-10-11 | 07:00:00 | 07:15:00 | 0 | plug abandon -- other | ok | Prepared WH/tension ring for removal
2016-10-11 | 07:15:00 | 11:30:00 | 0 | plug abandon -- other | ok | Performed TBT for removing tension cylinders with ongoing crew
2016-10-11 | 07:15:00 | 11:30:00 | 0 | plug abandon -- other | ok | Continued bleeding off tension cylinders.
2016-10-11 | 07:15:00 | 11:30:00 | 0 | plug abandon -- other | ok | R/D tension cylinders, left the cylinders hanging from top mounting point. Secured tension cylinders.
2016-10-11 | 11:30:00 | 12:00:00 | 0 | plug abandon -- other | ok | Meanwhile: Assisted crane with backload. Cleaned shaker pits.
2016-10-11 | 12:00:00 | 15:30:00 | 0 | plug abandon -- other | ok | Performed information meeting with all involved personnel for riser pulling operations.
2016-10-11 | 12:00:00 | 15:30:00 | 0 | plug abandon -- other | ok | R/D boat collision stool and prepared to remove centralizers from centralizer deck. Connected 3 x weco 1502 hoses to WH outlets.
2016-10-11 | 15:30:00 | 19:00:00 | 0 | interruption -- wait | ok | Meanwhile: Assisted crane with backload. Continued cleaning shaker pits.
2016-10-11 | 15:30:00 | 19:00:00 | 0 | interruption -- wait | ok | Waited on supply boat for riser equipment
2016-10-11 | 15:30:00 | 19:00:00 | 0 | interruption -- wait | ok | Meanwhile:
2016-10-11 | 15:30:00 | 19:00:00 | 0 | interruption -- wait | ok | Performed housekeeping on cantilever. Removed pipes and equipment from cantilever to make space for riser joints.
2016-10-11 | 15:30:00 | 19:00:00 | 0 | interruption -- wait | ok | Assisted crane with backload. Continued cleaning shaker pits.
2016-10-11 | 19:00:00 | 19:15:00 | 0 | plug abandon -- other | ok | Performed TBT for R/U riser handling equipment
2016-10-11 | 19:15:00 | 20:30:00 | 0 | plug abandon -- other | ok | R/U tailing arm and saddle on HTS. Continued to clear cantilever.
2016-10-11 | 19:15:00 | 20:30:00 | 0 | plug abandon -- other | ok | Installed beams on cantilever deck for L/O riser joints.
2016-10-11 | 20:30:00 | 21:00:00 | 0 | plug abandon -- other | ok | Performed information meeting with all involved personnel for riser pulling operations.
2016-10-11 | 21:00:00 | 23:45:00 | 0 | plug abandon -- other | ok | Continued to clear cantilever. Installed deck beams on cantilever.
2016-10-11 | 23:45:00 | 00:00:00 | 0 | plug abandon -- other | ok | Spotted riser handling equipment. Meanwhile: Cleared drill floor.
2016-10-12 | 00:00:00 | 01:00:00 | 0 | plug abandon -- other | ok | Continued spotting riser handling equipment. Meanwhile: Cleared drill floor.
2016-10-12 | 01:00:00 | 01:15:00 | 0 | plug abandon -- other | ok | Performed TBT for cutting the production riser and pulling the multibowl to drill floor.
2016-10-12 | 01:15:00 | 01:30:00 | 0 | plug abandon -- other | ok | Took 5 ton overpull.
2016-10-12 | 01:15:00 | 01:30:00 | 0 | plug abandon -- other | ok | Staged up pump rate to 900 lpm, observed water leaking over the top of the multibowl
2016-10-12 | 01:30:00 | 01:45:00 | 0 | plug abandon -- other | ok | Stopped pumping. Checked scribe line to confirm multibowl running tool still engaged to the multibowl.
2016-10-12 | 01:45:00 | 02:00:00 | 0 | plug abandon -- other | ok | Staged up pump rate to 2300 lpm / 87 bar. Continued pumping for approximately 15 min, lost overpull, good indication of cut
2016-10-12 | 01:45:00 | 02:00:00 | 0 | plug abandon -- other | ok | Observed multibowl/riser turned 1/4 turn clockwise at successful cut.
2016-10-12 | 02:00:00 | 02:15:00 | 0 | plug abandon -- other | ok | P/U slowly to confirm successful cut.
2016-10-12 | 02:15:00 | 03:00:00 | 0 | plug abandon -- other | ok | Removed hoses and valves from multibowl.
2016-10-12 | 03:00:00 | 03:30:00 | 0 | plug abandon -- other | ok | Pulled riser and multibowl to drill floor.
2016-10-12 | 03:00:00 | 03:30:00 | 0 | plug abandon -- other | ok | Removed master bushing and installed the big C-plate.
2016-10-12 | 03:30:00 | 03:45:00 | 0 | plug abandon -- other | ok | Disengaged multibowl RT by rotating elevator.
2016-10-12 | 03:45:00 | 04:00:00 | 0 | plug abandon -- other | ok | Installed small C-plate and false rotary.
2016-10-12 | 04:00:00 | 04:45:00 | 0 | plug abandon -- other | ok | B/O and attempted to rack back multibowl RT. Unable to rack back due to too long assebly. Parked AFT PRS with multibowl RT out of the way.
2016-10-12 | 04:45:00 | 06:00:00 | 0 | plug abandon -- other | ok | Pulled inner string and R/B 2 x 5 1/2" DP stands. R/B cutter BHA
2016-10-12 | 06:00:00 | 06:15:00 | 0 | plug abandon -- other | ok | P/U and M/U multibowl RT. Removed C-plate.
2016-10-12 | 06:15:00 | 07:00:00 | 0 | plug abandon -- other | ok | Pulled up riser until first flange at centralizer deck. Cleaned flange for marine growth.
2016-10-12 | 07:00:00 | 07:15:00 | 0 | plug abandon -- other | ok | Performed TBT for pulling and cutting riser
2016-10-12 | 07:15:00 | 07:45:00 | 0 | plug abandon -- other | ok | Pulled tensioner joint above drill floor. Cleaned flange for marine growth on WH deck.
2016-10-12 | 07:45:00 | 08:00:00 | 0 | plug abandon -- other | ok | Installed master bushing and elevator. Landed riser on elevator.
2016-10-12 | 08:00:00 | 09:00:00 | 0 | plug abandon -- other | ok | R/U cutting machine.
2016-10-12 | 08:00:00 | 09:00:00 | 0 | plug abandon -- other | ok | Installed hole cover to collect swarf
2016-10-12 | 09:00:00 | 09:45:00 | 0 | plug abandon -- other | ok | Cut tensioner joint
2016-10-12 | 09:45:00 | 10:00:00 | 0 | plug abandon -- other | ok | Collected swarf.
2016-10-12 | 09:45:00 | 10:00:00 | 0 | plug abandon -- other | ok | R/D cutting machine.
2016-10-12 | 10:00:00 | 11:15:00 | 0 | plug abandon -- other | ok | L/O tensioner joint
2016-10-12 | 11:15:00 | 12:30:00 | 0 | plug abandon -- other | ok | Removed running tool. Changed handling equipment. Installed cradle on HTS
2016-10-12 | 11:15:00 | 12:30:00 | 0 | plug abandon -- other | ok | Cleared drill floor.
2016-10-12 | 12:30:00 | 12:45:00 | 0 | plug abandon -- other | ok | Lifted riser. Removed master bushing
2016-10-12 | 12:45:00 | 13:00:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #2). Cleaned flanges on WH deck
2016-10-12 | 13:00:00 | 13:15:00 | 0 | plug abandon -- other | ok | Installed master bushing and elevator. Removed fairing and landed riser onto elevator
2016-10-12 | 13:15:00 | 14:00:00 | 0 | plug abandon -- other | ok | R/U cutting machine and hole cover. Cut riser
2016-10-12 | 14:00:00 | 14:15:00 | 0 | plug abandon -- other | ok | Collected swarf.
2016-10-12 | 14:00:00 | 14:15:00 | 0 | plug abandon -- other | ok | R/D cutting machine.
2016-10-12 | 14:15:00 | 14:45:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #2).
2016-10-12 | 14:45:00 | 15:15:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #3).
2016-10-12 | 15:15:00 | 15:30:00 | 0 | plug abandon -- other | ok | Removed master bushing. Pulled flange through rotary.
2016-10-12 | 15:15:00 | 15:30:00 | 0 | plug abandon -- other | ok | Installed master bushing and elevator. Landed riser onto elevator.
2016-10-12 | 15:30:00 | 16:00:00 | 0 | plug abandon -- other | ok | R/U cutting maching and cut riser
2016-10-12 | 16:00:00 | 16:15:00 | 0 | plug abandon -- other | ok | R/D cutting maching. Collected swarf
2016-10-12 | 16:15:00 | 16:30:00 | 0 | plug abandon -- other | ok | L/D riser joint (lift #3)
2016-10-12 | 16:30:00 | 17:00:00 | 0 | plug abandon -- other | ok | Pulled riser joint (lift #4).
2016-10-12 | 16:30:00 | 17:00:00 | 0 | plug abandon -- other | ok | Pulled master bushing. Pulled flange through rotary, installed master bushing and elevator. Landed riser onto elevator.
2016-10-12 | 17:00:00 | 17:30:00 | 0 | plug abandon -- other | ok | R/U cutting maching and attempted cut riser. Knifes worn out and broken.
2016-10-12 | 17:30:00 | 19:00:00 | 0 | plug abandon -- other | ok | Changed knifes and continued cutting riser.
2016-10-12 | 17:30:00 | 19:00:00 | 0 | plug abandon -- other | ok | Experienced knifes not cutting evenly due to ovality of riser.
2016-10-12 | 19:00:00 | 19:15:00 | 0 | plug abandon -- other | ok | Continued cutting riser.
2016-10-12 | 19:00:00 | 19:15:00 | 0 | plug abandon -- other | ok | Meanwhile: Performed TBT with ongoing crew.
2016-10-12 | 19:15:00 | 19:30:00 | 0 | plug abandon -- other | ok | R/D cutting maching. Collected swarf
2016-10-12 | 19:30:00 | 20:00:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #4).
2016-10-12 | 20:00:00 | 20:45:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #5)
2016-10-12 | 20:00:00 | 20:45:00 | 0 | plug abandon -- other | ok | Removed master bushing. Pulled flange through rotary, installed master bushing and elevator. Landed riser onto elevator.
2016-10-12 | 20:45:00 | 22:15:00 | 0 | plug abandon -- other | ok | R/U cutting manchine and cut riser.
2016-10-12 | 20:45:00 | 22:15:00 | 0 | plug abandon -- other | ok | Experienced knifes not cutting evenly due to ovality of riser.
2016-10-12 | 22:15:00 | 22:30:00 | 0 | plug abandon -- other | ok | R/D cutting machine. Collected swarf
2016-10-12 | 22:30:00 | 22:45:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #5).
2016-10-12 | 22:45:00 | 23:15:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #6).
2016-10-12 | 22:45:00 | 23:15:00 | 0 | plug abandon -- other | ok | Removed master bushing. Pulled flange through rotary, installed master bushing and elevator. Landed riser onto elevator.
2016-10-12 | 23:15:00 | 23:45:00 | 0 | plug abandon -- other | ok | R/U cutting machine and cut riser.
2016-10-12 | 23:45:00 | 00:00:00 | 0 | plug abandon -- other | ok | R/D cutting machine. Collected swarf.
2016-10-13 | 00:00:00 | 00:15:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #6).
2016-10-13 | 00:15:00 | 00:45:00 | 0 | plug abandon -- other | ok | Lifted riser (lift #7). Removed master bushing. Pulled riser.
2016-10-13 | 00:15:00 | 00:45:00 | 0 | plug abandon -- other | ok | Installed master bushing and hole cover in rotary
2016-10-13 | 00:45:00 | 01:15:00 | 0 | plug abandon -- other | ok | L/O riser joint.
2016-10-13 | 01:15:00 | 02:15:00 | 0 | plug abandon -- other | ok | Installed hole covers and hatches.
2016-10-13 | 02:15:00 | 02:30:00 | 0 | plug abandon -- other | ok | Changed elevator to handle BHA.
2016-10-13 | 02:15:00 | 02:30:00 | 0 | plug abandon -- other | ok | Meanwhile: Removed scaffolding in moonpool.
2008-04-03 | 06:00:00 | 07:00:00 | 3 | drilling -- cas ing | ok | Picked up tie-back adapter and checked seals and acme thread. Installed tie-back adapter in slips. Secured same with dogcollar.
2008-04-03 | 07:00:00 | 08:00:00 | 3 | drilling -- cas ing | ok | Picked up first 10 3/4" joint and stabbed on to tie-back adapter. Had problems with Mærsk casing tong. Not able to get torque/turn curves on computer.
2016-10-06 | 20:45:00 | 21:45:00 | 7 | plug aban don -- oth er | ok | R/B 1x stand of LH DP, L/D 16x joints of LH DP
2016-10-07 | 11:00:00 | 11:30:00 | 9.5 | plug abandon - | ok | POOH w/ 10 3/4" cutter BHA on 5 1/2" DP from 312 m to 9,5 m.
2007-06-09 | 12:30:00 | 14:30:00 | 10 | drilling -- trip | ok | P/U 36" hole opener BHA, hung off in rotary. Installed bushing and slips. Removed safety clamp from centralizer guide bushing. Attempted to calibrate MWD depth sensor
2007-06-09 | 12:30:00 | 14:30:00 | 10 | drilling -- trip | ok | - no sucess - decided to use drillers depth for survey reference.
2007-10-18 | 04:15:00 | 06:00:00 | 10 | drilling -- casin g | ok | POOH with CART on 5 1/2" HWDP landing string. Laid out two singles on way out. Laid out CART tool.
2008-03-17 | 07:00:00 | 11:00:00 | 10 | completion -- circulating conditioni ng | ok | Held tool box talk and continued POOH with 3½" DP and washing string. Laid out 3½" DP in singles.
2008-03-17 | 11:00:00 | 11:15:00 | 10 | completion -- circulating conditioni ng | ok | Commenced to rig up 5½" DP handling equipment, found that the Razor back could not fit into the basket. Rigged back up the 3½" handling equi pment.
2008-03-17 | 11:15:00 | 15:45:00 | 10 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor. Meanwhile held tool box talk prior to installation of the GTV plug. Meanwhile continued making up the flow line at WH for F-7. Prepared for nippling of BOP.
2016-10-06 | 10:15:00 | 10:30:00 | 10 | plug aban don -- cut | ok | P/U and RIH cutter BHA to 9,5m
2016-10-06 | 11:30:00 | 11:45:00 | 10 | plug aban don -- cut | ok | Flowchecked for 5min, stable. POOH to 9,5m
2008-02-19 | 14:45:00 | 16:15:00 | 13 | interruption -- fish | ok | Picked up first joint. Made up grapple and drain sub. RIH with 5 1/2" DP single.
2008-02-19 | 16:15:00 | 19:00:00 | 13 | interruption -- fish | ok | Observed damage on cable due to unfavorable angel when spinning in the drilpipe, wire partly cut through. Suspended WL in C-plate and cut off damaged wire. Fitted spearhead and fishing weights on winch side of wireline.
2008-02-19 | 19:00:00 | 00:00:00 | 13 | interruption -- fish | ok | Rigged down upper sheave. Attached upper sheave in crown block. Removed 5" weco coupling and blind cap on top of TDS. Put on weco nut acting as wear bushing. Threaded WL through topdrive.
2008-03-11 | 16:00:00 | 17:15:00 | 13 | drilling -- trip | ok | Held tool box meeting with involved personnel. MU and RIH with 6" PDC bit and scraper assembly from surface to 13 m.
2008-03-11 | 17:15:00 | 18:00:00 | 13 | interruption -- other | ok | Repaired damaged fittings on HTS rollers.
2016-10-07 | 07:45:00 | 08:15:00 | 14 | plug abandon - | ok | POOH w/ perforation BHA from 148 m to 14 m.
2016-10-07 | 08:15:00 | 08:30:00 | 14 | plug abandon - | ok | Changed to 4 1/2" inserts in BX-elevator.
2007-10-18 | 11:15:00 | 14:15:00 | 15 | drilling -- bop/ wellhead equipment | ok | Observed damaged intervall on minireel hose. Cut back minireel to 150 m and reterminated fittings. Prepared 30 m excess undamaged hose for potential extension. Function tested TB C connector according to Vetco procedures.
2007-11-04 | 06:00:00 | 07:00:00 | 18 | drilling -- bop/wellhead e quipment | ok | Untorqued bolts on HPDR BOP joint at X-mas tree level using Bandak tool, but left bolts in flange.
2008-04-02 | 06:00:00 | 08:30:00 | 20 | drilling -- casing | ok | Installed bowl protector according to Vetco instructions. POOH with 5 1/2" DP stand and laid down RT. Meanwhile hooked up BOP tension cylinerders in moonpool.
2008-04-05 | 06:00:00 | 07:00:00 | 20 | drilling -- casing | ok | Made up pup joint with pre-made 1502 swedge. RIH and landed casing hanger RT at 20 m MD. Set of weight of landing string. Entered hanger RT threads using ch ain tong. Made up RT with 9 lefthand turns using casing tong.
2008-04-05 | 07:00:00 | 07:15:00 | 20 | drilling -- casing | ok | Held toolbox talk prior to pressure testing.
2008-04-05 | 07:15:00 | 08:00:00 | 20 | drilling -- casing | ok | Rigged up 1502 chicksan from swedge to cement hose hub on drillfloor.
2008-04-05 | 08:00:00 | 08:45:00 | 20 | drilling -- casing | ok | Lined up to cement pump and flushed lines. Performed line test to 380 bar - ok. Exhaust fumes detected on drillfloor.
2008-04-05 | 08:45:00 | 09:30:00 | 20 | drilling -- casing | ok | Pressured up on cement unit and tested upper tie-back/adjustment sub/tie-back adapter to 380 bar /10 min - ok. Pumped and bled back 587 litres.
2008-04-05 | 09:30:00 | 21:30:00 | 20 | interruption -- waiting o n weather | ok | Exhaust fumes on drillfoor and drillers cabin. Suspended drillfloor operations. Checked wind and conditions every 30 min. Monitored well from shaker control room.
2008-04-05 | 09:30:00 | 21:30:00 | 20 | interruption -- waiting o n weather | ok | Meanwhile :
2008-04-05 | 09:30:00 | 21:30:00 | 20 | interruption -- waiting o n weather | ok | -Cleaned and tidied in moonpool
2008-04-05 | 09:30:00 | 21:30:00 | 20 | interruption -- waiting o n weather | ok | -Cleaned and tidied in wellhead module
2008-04-05 | 09:30:00 | 21:30:00 | 20 | interruption -- waiting o n weather | ok | -Housekeeping in heavy tool store
2008-04-05 | 09:30:00 | 21:30:00 | 20 | interruption -- waiting o n weather | ok | 21:30 - shut down gas turbines to get working conditions on drillfloor.
2008-04-06 | 06:00:00 | 07:00:00 | 20 | drilling -- casing | ok | Locked MS seal running tool in surface WH, observed 0,4 l return - ok. Performed 10 MT overpull to confirm latch - ok. Set MS seal assembly by applying 4300 p si. Observed 1,62" travel / 3,5 liter returned fluid - ok.
2008-04-06 | 07:00:00 | 07:45:00 | 20 | drilling -- casing | ok | Pressure tested MS seal through test port in surface wellhead to 380 bar / 10 min - ok.
2008-04-06 | 07:45:00 | 08:15:00 | 20 | drilling -- casing | ok | Released dogs in MS seal RT by rotating 5 turns to the right.
2008-04-06 | 09:15:00 | 10:00:00 | 20 | drilling -- casing | ok | Made up bowl protector RT. RIH and set bowl protector at 20,10 m MD.
2016-10-06 | 06:45:00 | 07:45:00 | 20 | plug aban don -- oth er | ok | P/U wash tool. RIH from surface to 20.5 m. Jetted wellhead w/ 2200 l/min, 10 rpm, moved string 1m up/down. POOH, L/D jetting tool
2016-10-06 | 08:00:00 | 10:00:00 | 20 | plug aban don -- oth er | ok | P/U and M/U MS-T seal retrieval tool and tested same RIH to 20.5m and engaged MS-T seal retrieval tool. Pulled seal free with 80t overpull POOH from 20,5m and L/D MS-T seal and retrie val tool
2007-10-18 | 14:15:00 | 17:15:00 | 22 | drilling -- bop/ wellhead equipment | ok | Picked up 2nd double D by simultaneous lift with deckcrane and TDS, brought to vertical postion. Removed handling tool on flange in rotary. Installed guided pins. Stabbed double D o nto flange in rotary. Made up flange according to Bandak procedure. Tested connection to 200 bar on flange. Installed fairrings.
2016-10-08 | 08:30:00 | 09:15:00 | 24 | plug abandon -- mecha nical plug | ok | P/U and M/U EZSV plug and RT. Installed centralizer on RT. L/D double 5 1/2" DP. P/U and M/U 3 pup joints for space out
2007-10-18 | 17:15:00 | 22:30:00 | 26 | drilling -- bop/ wellhead equipment | ok | Prepared guidewires with ROV hooks. Built scaffolding around and removed hatches on all wellhead module levels. Removed weatherdeck hatches on F-5 og F-9. Ran guidewires and prepared wire loops in F-4 Centralizer deck opening. Ran in with riser, hooked up guidewires at Centralizer deck and ran riser and guidwires to sealevel.
2008-04-04 | 09:15:00 | 10:15:00 | 28 | drilling -- casing | ok | RIH with adjustment sub and located same at 28,4 m MD. Checked serial numbers on pipe. Made up TDS.
2008-04-04 | 10:15:00 | 11:00:00 | 28 | drilling -- casing | ok | Pressured up on drillpipe to 140 bar to activate horizontal dogs. Pulled back 0,4 m and confirmed engaged in vertical dog profile by 9 MT overpull. Rotated string with 22 righthand turns. Obs erved colored band through B-annulus outlet to confirm adjustment sub collapsing. Increased overpull to 30 MT and continued rotating until TDS stalled out on 9 kNm and overpull reduced. Slacked off string to 28,4 m MD mark and waited for 2 min. Bleed off pressure on DP. Obtained a total of 17" travel on adjustment sub.
2008-04-04 | 12:00:00 | 12:30:00 | 28 | drilling -- casing | ok | RIH with straddle cup tester and located same at 28,4 m MD across metal seal in adjustment sub. Meanwhile held toolbox talk for pressure testing.
2008-04-04 | 12:30:00 | 13:00:00 | 28 | drilling -- casing | ok | Lined up cement unit on standpipe. Performed line test to 380 bar.
2008-04-04 | 13:00:00 | 14:30:00 | 28 | drilling -- casing | ok | Pressure tested adjustment sub (metal seal) to 380 bar / 10 min - ok. Kept B-annulus open throughout test.
2007-10-12 | 21:30:00 | 00:00:00 | 32 | drilling -- trip | ok | Made up 17 1/2" BHA according to Schlumberger instructions. Gauged bit and stabilizers. Set scribline and measured corrections on GWD and MWD. Adjusted UBHO sub in line with scribeline.
2007-10-16 | 13:15:00 | 14:45:00 | 32 | drilling -- casin g | ok | Picked up, made up and ran 13 3/8" shoe joint, float collar joint and 6 m pup joint. Threadlocked couplings. Filled casing with SW and tested float for flowthrough - ok.
2008-03-14 | 14:00:00 | 15:45:00 | 32 | completion -- circulating conditioning | ok | Held tool box talk and broke out 6" bit and bit sub and made up 3½" mule shoe. Made up Razor Back assy. Installed PS-21 slips
2008-03-14 | 14:00:00 | 15:45:00 | 32 | completion -- circulating conditioning | ok | .
2008-03-07 | 16:00:00 | 18:00:00 | 39 | drilling -- casing | ok | Held tool box talk prior to running 7" liner. MU and RIH with shoe track and landing collar. Checked shoe and float collar for flow-through.
2008-02-08 | 01:15:00 | 02:00:00 | 40 | drilling -- other | ok | Continued POOH with the RTTS plug from 140 m to 40 m, pulled out wet. Displacement over trip tank OK.
2008-02-08 | 02:00:00 | 02:30:00 | 40 | drilling -- other | ok | Made up to TDS, established returns at 38 bars. POOH from 40 m to surface with the RTTS plug.
2008-02-08 | 02:30:00 | 02:45:00 | 40 | drilling -- other | ok | Changed to manual slips.
2008-02-28 | 09:30:00 | 12:30:00 | 40 | drilling -- casin g | ok | Held tool box talk prior to running 7" liner. MU and RIH with shoe track and landing collar. Checked shoe and float collar for flow-through. Thread locked first 4 connections.
2008-02-25 | 13:45:00 | 14:30:00 | 41 | formation evaluation -- log | ok | Ran MDT toolstring in sections to 41 m MD using C-plate and tugger according to Schlumberger instructions.
2008-02-25 | 14:30:00 | 14:45:00 | 41 | formation evaluation -- log | ok | Changed dies in IR. Made up AH-3 1/2" x 4 1/2" IF x-over to 5" DP stand. Made up x-over to MDT logging string.
2008-02-25 | 14:45:00 | 15:15:00 | 41 | formation evaluation -- log | ok | Connected locomotive to docking head. Schlumberger tetsed MDT toolstring. Disconnected locomotive.
2008-02-25 | 15:15:00 | 15:30:00 | 41 | formation evaluation -- log | ok | Held toolbox talk prior to RIH with MDT toolstring on 5" DP.
2008-02-27 | 20:15:00 | 21:30:00 | 41 | formation evalu ation -- log | ok | POOH with MDT toolstring on 5" DP from 334 m to 41 m MD.
2008-03-13 | 06:30:00 | 07:00:00 | 42 | drilling -- d rill | ok | RIH with EZSV plug and Circ. Sub to 42 m.
2008-03-13 | 07:00:00 | 07:15:00 | 42 | drilling -- o ther | ok | Held tool box talk with day shift prior to change to PS -21 slips and RIH with EZSV plug and Circ. Sub on 3½" DP.
2008-03-13 | 07:15:00 | 08:00:00 | 42 | drilling -- o ther | ok | Changed to PS -21 slips and functioned same.
2007-10-16 | 14:45:00 | 15:30:00 | 43 | drilling -- casin g | ok | Ran 1 joint of 13 3/8" casing. Adjusted torque setting on tong. Tong jammed to coupling and could not be released.
2007-10-16 | 15:30:00 | 17:00:00 | 43 | interruption -- other | ok | Casing tong stuck on casing coupling. Removed die carrier to release the grip.
2008-03-10 | 20:00:00 | 21:15:00 | 44 | drilling -- bop/wellhead equi pment | ok | PU and MU jet sub assembly. RIH and washed BOP cavity. Staged up pumps to 3125 lpm / 43 bar and washed through cavity several times.
2008-03-17 | 20:30:00 | 21:00:00 | 44 | plug abandon -- mechanical plug | ok | RIH with the GTV plug on 5½" HWDP from surface to 44m.
2008-03-17 | 21:00:00 | 21:30:00 | 44 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
2008-04-08 | 12:15:00 | 19:00:00 | 48 | interruption | ok | Found casing tong to be programmed with wrong torque values. Optimum torque set to 15660 ft lbs instead of 15660 Nm. Two tubing connections on assy#2 overtorqued. No back-up ass embly available. Discussed situation. Evaluated and discussed further actions with town. Got confirmation that VamTop thread should be good within 30% overtorque. Decided to do drift r un through overtorqued couplings to verify no deformation or restrictions.
2008-04-08 | 12:15:00 | 19:00:00 | 48 | interruption | ok | Meanwhile :
2008-04-08 | 12:15:00 | 19:00:00 | 48 | interruption | ok | -Repaired handrails and kick plates in derrick
2008-04-08 | 12:15:00 | 19:00:00 | 48 | interruption | ok | -Removed 10 allen/hex bolts from fwd PRS
2007-10-18 | 22:30:00 | 22:45:00 | 51 | drilling -- bop/ wellhead equipment | ok | Held toolbox talk prior to picking up 3rd double C.
2007-10-18 | 22:45:00 | 00:00:00 | 51 | drilling -- bop/ wellhead equipment | ok | Picked up 3rd double C by simultaneous lift with deckcrane and TDS, brought to vertical position. Removed handling tool on flange in rotary. Installed guide pins.
2007-10-18 | 22:45:00 | 00:00:00 | 51 | drilling -- bop/ wellhead equipment | ok | Meanwhile ROV attempted to install VX ring on subsea wellhead. Observed grease/shadow on seal surface. Attempted to wash/flush -still visible. Brought ROV to surface in order to m ount brush tooling.
2008-02-16 | 06:00:00 | 07:00:00 | 53 | drilling -- trip | ok | Freed 2 3/4" drift. Racked back jar/HWDP and 1 stand of 5" HWDP.
2008-02-16 | 07:00:00 | 07:15:00 | 53 | drilling -- trip | ok | Held toolbox talk prior to laying out LWD/MWD/drilling assemblies.
2007-10-16 | 17:00:00 | 17:30:00 | 55 | drilling -- casin g | ok | Ran 1 joint of 13 3/8" casing. Still problems with torque setting on casing tong.
2007-10-16 | 17:30:00 | 18:00:00 | 55 | interruption -- other | ok | Repaired casing tong. Changed sensor and cable. Adjusted dump valve setting.
2008-03-13 | 01:30:00 | 02:45:00 | 57 | drilling -- d rill | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 578 m to 57 m.
2008-03-13 | 02:45:00 | 04:30:00 | 57 | interruptio n -- other | ok | Retrieved 3 1/2" DP std that was pulled out of fingerboard by PRS lower arm due to human error. Held time-out for safety. Prepared equipment to be used for retrieving std. Instected finger board. RB 3 1/2" DP std in fingerboard.
2007-06-11 | 10:15:00 | 14:30:00 | 66 | drilling -- casi ng | ok | Ran 30" conductor to 66 m MD.
2016-10-07 | 13:00:00 | 15:15:00 | 72 | plug abandon - | ok | M/U CH milling BHA
2016-10-07 | 22:30:00 | 23:00:00 | 72 | plug abandon - | ok | POOH w/ CH milling BHA on 5 1/2" DP from 110 m to 72 m.
2008-03-07 | 06:00:00 | 07:45:00 | 74 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5" DP from 928 m to 74 m MD.
2008-03-07 | 07:45:00 | 08:15:00 | 74 | drilling -- casing | ok | Flow checked well prior to pulling BHA through BOP. Meanwhile held tool box meeting prior to BHA handling.
2008-03-07 | 08:15:00 | 08:30:00 | 74 | drilling -- casing | ok | Installed net around fwd PRS for prevention of dropped objects.
2008-03-05 | 08:00:00 | 11:30:00 | 75 | drilling -- casing | ok | PU and MU 8 1/2" wiper trip BHA.
2008-04-02 | 10:30:00 | 10:45:00 | 76 | drilling -- casing | ok | RIH with retrieval tool on 5 1/2" HWDP landing string from surface to 76 m MD.
2008-04-02 | 10:45:00 | 11:00:00 | 76 | drilling -- casing | ok | Mærsk crewchange. Held toolbox talk prior to continuing operation.
2007-10-19 | 00:00:00 | 02:15:00 | 80 | drilling -- bop/wellhead eq uipment | ok | Stabbed double C onto flange in rotary. Made up flange according to Bandak procedure. Tested connection to 200 bar on flange. Installed fairrings. Ran STB guidewire to template. Ran port guidewire to 40 m below sealevel. RIH with riser to 80 m MD.
2008-04-07 | 04:00:00 | 05:30:00 | 80 | interruption -- oth er | ok | Fixed BX elevator. Changed 3 ea hydraulic hoses/fittings running from TDS to BX elevator.
2016-10-08 | 15:00:00 | 15:30:00 | 80 | plug abandon -- cement plug | ok | POOH w/ EZSV RT on 5 1/2" DP from 160 m to 80 m. M/U BOP jetting tool and FOSV.
2016-10-08 | 15:30:00 | 17:00:00 | 80 | plug abandon -- cement plug | ok | Jetted BOP 8 x passes up/down, 1450 lpm, 50 rpm. Operated annular preventer and pipe rams. B/O and L/O BOP jetting tool and FOSV.
2016-10-08 | 17:00:00 | 17:15:00 | 80 | plug abandon -- cement plug | ok | Removed PS-21 slips and installed master bushing.
2007-10-29 | 13:15:00 | 15:45:00 | 90 | drilling -- drill | ok | POOH with 12 1/4" BHA from 1330 m to 90 m MD. Performed gyro survey on each stand. Oriented string to confirm toolface every 300 m as instructed by Gyro data.
2008-03-27 | 04:30:00 | 06:00:00 | 95 | drilling -- | ok | Disconnected flange bolt on HPDR flange and picked up double.
2008-03-27 | 04:30:00 | 06:00:00 | 95 | drilling -- | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-27 | 04:30:00 | 06:00:00 | 95 | drilling -- | ok | 05:00 11/15 170° 1,5/2,4 360°
2016-10-06 | 13:45:00 | 14:00:00 | 98 | plug aban don -- equ ipment rec overy | ok | Broke out pup joint and casing hanger, L/D same
2016-10-06 | 14:00:00 | 14:30:00 | 98 | plug aban don -- equ ipment rec overy | ok | Changed BX Elevators to BX-4s and PDM head
2007-06-09 | 14:30:00 | 19:00:00 | 100 | drilling -- trip | ok | Continued making up 36" hole opener BHA.
2007-06-10 | 23:00:00 | 23:30:00 | 100 | drilling -- drill | ok | Continued to POOH with 36" hole opener BHA from 152 m to 100 m MD. Removed automatic slips and replaced master bushing.
2007-06-11 | 14:30:00 | 18:15:00 | 100 | drilling -- casi ng | ok | Ran 30" conductor including ST-2 x RL-4 xover fm 66 m to 100 m MD. Strapped top up pipe along conductor on XMT deck. Filled 30" conductor with SW on way in.
2007-06-11 | 14:30:00 | 18:15:00 | 100 | drilling -- casi ng | ok | Top up pipe cement outlets to be located at : 43,4 m below ML
2007-06-11 | 14:30:00 | 18:15:00 | 100 | drilling -- casi ng | ok | 24,5 m below ML 14,8 m below ML
2007-06-11 | 18:15:00 | 19:00:00 | 100 | drilling -- casi ng | ok | Changed to 5 1/2" handling equipment prior to picking up 30" conductor housing.
2007-06-11 | 19:00:00 | 19:30:00 | 100 | drilling -- casi ng | ok | Held toolbox talk.
2007-06-11 | 19:30:00 | 20:30:00 | 100 | drilling -- casi ng | ok | Picked up 30" conductor housing. Made up RL-4 connection to 36000 ft lbs using rig tongs. Enagaged anti-rotation slots.
2008-03-31 | 00:00:00 | 01:00:00 | 101 | drilling -- b op/wellhea d equipme nt | ok | Held toolbox talk prior to lifting in tension joint. Removed BX-elevator. Installed 2 wire slings between bails and elevator. Picked up tension joint with deck crane and laid same on HTS cradl
2008-03-31 | 00:00:00 | 01:00:00 | 101 | drilling -- b op/wellhea d equipme nt | ok | e. Hooked up aft sling in tugger to get further in on drillfloor. Latched BX elevator around lift sub below 3 m pup joint. Lifted tension joint to upright position with simultaneous lift on deck cran e and block.
2008-03-31 | 01:00:00 | 02:30:00 | 101 | drilling -- b op/wellhea d equipme nt | ok | Removed handling flange type F. Installed guide pins and landed tension joint on 3rd PR double. Made up connection using bolt tensioner tools. Pressure tested connection through test por t 5 min / 345 bar using hand pump. Installed bolt protector caps. Installed fairrings.
2016-10-06 | 13:15:00 | 13:30:00 | 103 | plug aban don -- oth er | ok | RIH w/ spear and engage in 10 3/4in surface casing hanger, pulled casing to surface
2016-10-06 | 13:30:00 | 13:45:00 | 103 | plug aban don -- equ ipment rec overy | ok | Performed Pre-job Meeting to pull and L/D 10 3/4in casing
2008-04-03 | 21:00:00 | 23:00:00 | 108 | drilling -- cas ing | ok | RIH with 10 3/4" tie-back casing from surface to 108 m MD according to tally.
2007-10-15 | 20:45:00 | 22:30:00 | 110 | drilling -- trip | ok | Removed automatic slips and installed masterbushing. Pulled 4 stands. Meanwhile prepared for repairing leakage on TDS.
2007-10-15 | 22:30:00 | 00:00:00 | 110 | interruption -- ot her | ok | Parked TDS and repaired leakage on TDS gear box system.
2007-10-16 | 00:00:00 | 01:30:00 | 110 | interruption -- other | ok | Repaired leakage on TDS gear box system.
2007-10-19 | 02:15:00 | 04:45:00 | 110 | drilling -- bop/wellhead eq uipment | ok | Picked up 4th double B by simultaneous lift with deckcrane and TDS, brought to vertical position. Removed handling tool on flange in rotary. Installed guide pins. Stabbed double B onto flange in rotary. Made up flange according to Bandak procedure. Tested connection to 200 bar on flange. Installed fairrings. RIH with riser to 110 m MD.
2007-10-19 | 02:15:00 | 04:45:00 | 110 | drilling -- bop/wellhead eq uipment | ok | Meanwhile ROV established STB and port guidewires to template eagel clamps. Brushed and cleaned wellhead seal surface with ROV.
2007-10-19 | 04:45:00 | 06:00:00 | 110 | drilling -- bop/wellhead eq uipment | ok | Picked up 5th double A by simultaneous lift with deckcrane and TDS, brought to vertical position. Removed handling tool on flange in rotary. Installed guide pins. Stabbed double A onto flange in rotary. Made up flange according to Bandak procedure.
2007-10-19 | 04:45:00 | 06:00:00 | 110 | drilling -- bop/wellhead eq uipment | ok | Meanwhile brought ROV to surface and installed VX ring installation tooling. Dove ROV.
2008-02-16 | 04:00:00 | 05:30:00 | 110 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5" DP from 1331 m to 110 m MD.
2008-02-16 | 05:30:00 | 06:00:00 | 110 | drilling -- trip | ok | Removed PS-21 slips. Inserted masterbushing and bowls. Worked to free 2 3/4" drift which was stuck in jar.
2016-10-07 | 21:30:00 | 22:00:00 | 110 | plug abandon - | ok | Circulated 2 x B/U w/ 3000 lpm / 22 bar. R/B 1 stand 5 1/2" DP.
2016-10-07 | 22:00:00 | 22:30:00 | 110 | plug abandon - | ok | Performed drops inspection of TDS.
2016-10-07 | 22:00:00 | 22:30:00 | 110 | - mill | ok | Meanwhile: Flowchecked well, static. Performed TBT for L/O milling BHA.
2007-06-11 | 20:30:00 | 21:30:00 | 111 | drilling -- casi ng | ok | Ran in with 30" conductor housing and installed top up pipe on XMT deck.
2007-06-11 | 21:30:00 | 22:00:00 | 111 | drilling -- casi ng | ok | Installed C-plate in rotary and landed 30" conductor housing in same. Broke out and laid down 30" handling CART.
2007-06-11 | 22:00:00 | 22:30:00 | 111 | drilling -- casi ng | ok | Rig up C-plate, bowl and slips for running cement stinger on top of 30" conductor housing.
2007-06-11 | 22:30:00 | 00:00:00 | 111 | drilling -- casi ng | ok | Ran 4 3/4" aluminum cement stinger inside 30 conductor.
2007-06-12 | 00:00:00 | 00:30:00 | 111 | drilling -- casi ng | ok | Continued running 4 3/4" aluminum cement stinger inside 30" conductor. Installed a total of 10 joints adding up to 91 m, i.e. approx 16 m off shoe bottom. Installed centralizers on j oint number 3 and 6.
2007-06-12 | 00:30:00 | 01:30:00 | 111 | drilling -- casi ng | ok | Picked up primary CART. M/U 4 1/2" IF x butress X-over to low end of CART. M/U CART to innerstring. Removed innerstring handling equipment. Made up CART to 30" conducto r housing with 5 lefthand turns. Checked inclinometer -ok. Checked filler valve in open position - ok.
2008-03-09 | 10:15:00 | 18:45:00 | 112 | drilling -- c asing | ok | POOH with 7" liner hanger RT on 5 1/2" DP from 2667 m to 112 m MD.
2008-03-09 | 10:15:00 | 18:45:00 | 112 | drilling -- c asing | ok | RU rollers on HTS and cleared rig floor of excess equipment prior to LO pipe in singles. LO 13 stds of 5 1/2" DP 24.7 lbs/ft in singles. Pumped 3 m3 1.63 sg slug, 1000 lpm / 7 bar at 594 m
2008-03-09 | 10:15:00 | 18:45:00 | 112 | drilling -- c asing | ok | .
2007-10-16 | 18:00:00 | 21:00:00 | 115 | drilling -- casin g | ok | Ran 13 3/8" casing from 55 m to 200 m MD. Filled casing with seawater. Got problems functioning PS-30 slips.
2007-10-16 | 21:00:00 | 21:30:00 | 115 | interruption -- other | ok | Not able to open PS-30 slips. Thightened fitting on hydraulic hose.
2008-04-03 | 23:00:00 | 00:00:00 | 119 | drilling -- cas ing | ok | Picked up and made up 10 3/4" hanger / adjustable sub assy. Landed hanger in slips. Broke off casing hanger handling tool. Checked casing hanger. Changed from BX3 to 5 1/2" BX elevator.
2008-04-04 | 00:00:00 | 00:15:00 | 119 | drilling -- casing | ok | Picked up pre-made 5 1/2" HWDP (LS-1) with 10 3/4" Itco spear with PRS. Attempted to make up stand to TDS - negative - slipped in TDS back up dies.
2008-04-04 | 00:15:00 | 01:15:00 | 119 | interrupti on -- oth er | ok | Broke off TDS from stand. Set down stand in PRS. Lowered TDS and inspected torque wrench dies, removed swarf from dies. Re-attempted make up to stand in TDS - ok.
2008-03-31 | 02:30:00 | 04:00:00 | 120 | drilling -- b op/wellhea d equipme nt | ok | Released BX elevator and removed slings. Installed BX elevator in bails. Re-latched tension joint. Removed spider and installed master bushing. RIH with tensioner joint, installed bowl and hung off riser on 3 m 5 1/2" pup joint.
2008-04-02 | 11:00:00 | 12:00:00 | 120 | drilling -- casing | ok | RIH with retrieval tool on 5 1/2" HWDP landing string from 76 m to 120 m MD. Made up TDS and took torque readings wiith annular closed (200 psi on strip bottle). Torque 0,3-0,6 kNm at 5 r pm.
2016-10-06 | 10:30:00 | 11:00:00 | 123 | plug aban don -- cut | ok | RIH w/ cutter BHA, positioned knives at 123m
2016-10-06 | 11:00:00 | 11:30:00 | 123 | plug aban don -- cut | ok | M/U TDS, took parameters. Cut 10 3/4in surface casing tieback at 123m, 400 l/min - 50bar, 80 rpm, 2-10 kNm. Observed good indications of cut: pressure drop and reduction of torque
2007-10-19 | 06:00:00 | 07:00:00 | 128 | drilling -- bop/wellhead eq uipment | ok | Tested riser connection to 200 bar. Installed fairings. RIH with riser to 128 m MD.
2007-10-19 | 07:00:00 | 07:15:00 | 128 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to removing riser spiser.
2016-10-07 | 00:30:00 | 01:15:00 | 128 | plug abandon - | ok | RIH w/ ITCO spear BHA
2007-10-19 | 07:15:00 | 08:30:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Removed riser spider from rotary and installed master bushing. Installed lo-torque on Claxton tool and confirmed in open position. Ran Claxton tool past rotary and hung off on man ual slips.
2007-10-19 | 08:30:00 | 08:45:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Made up stand of 5 1/2" DP to Claxton tool. Made up TDS to DP.
2007-10-19 | 08:45:00 | 09:00:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to landing riser.
2007-10-19 | 09:00:00 | 09:30:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Placed VX gasket on 18 3/4" subsea wellhead with ROV. Inspected guidewires.
2008-03-19 | 16:30:00 | 17:00:00 | 130 | completion -- bop/wellhead equipm ent | ok | RIH with the 10 3/4" Lock down sub to 130 m took up/down weight 78/74 MT.
2008-04-07 | 05:30:00 | 06:00:00 | 130 | drilling -- casing | ok | RIH with GTV pulling tool from 80 m to 130 m MD on 5 1/2" HWDP singles.
2008-04-04 | 16:00:00 | 16:15:00 | 130.5 | drilling -- casing | ok | Pulled back 10 m to put cuptester in blank pipe to test tool. Pressured up - not able to obtain test - straddle cup test leaking.
2016-10-11 | 01:15:00 | 04:15:00 | 134.9 | plug abandon -- other | ok | P/U and M/U cutter BHA and RIH with same. P/U and M/U mutlibowl RT.
2016-10-11 | 04:15:00 | 04:30:00 | 134.9 | plug abandon -- other | ok | RIH w/ BHA and M/U multibowl RT in WH. Took 20 ton OP to verify RT engaged in WH. M/U TDS
2007-10-22 | 02:45:00 | 04:45:00 | 135 | drilling -- drill | ok | Made up 8" DC stand and x-over. Installed automatic slips in rotary. RIH with 12 1/4" drilling BHA on 4 stands of 5 1/2" HWDP to 135 m MD.
2007-06-12 | 01:30:00 | 03:00:00 | 137 | drilling -- casi ng | ok | Ran in with 30" conductor on 5 1/2" HWDP. Strapped residual top up pipe to the conductor housing on XMT deck. Installed ROV plugs in 30" conductor housing on Centralizer de ck.
2007-06-12 | 03:00:00 | 03:30:00 | 137 | drilling -- casi ng | ok | In order not to damage ROV plugs, inclinometer and filler valve => Used chain hoists / steel slings to center top of housing through the Centralizer deck.
2007-10-19 | 09:30:00 | 11:30:00 | 138 | drilling -- bop/wellhead eq uipment | ok | Ran in with riser. Took up/down weight 137 MT. Attempted to land TBC conncetor on 18 3/4" wellhead - negative. Trashed VX- ring when attempting to land. Inspected wellhead an d installed new VX -ring.
2007-10-19 | 11:30:00 | 13:30:00 | 138 | interruption -- waiting on weath er | ok | Waited on weather for improved landing condition. Meanwhile installed coax cable between ROV unit and drillfloor to improve viewing conditions for driller.
2007-10-19 | 13:30:00 | 15:30:00 | 138 | drilling -- bop/wellhead eq uipment | ok | Made 2 more attempts to land TBC connector on 18 3/4" wellhead - negative. Both times the VX-ring was bounced off the wellhead. Lost attachement for 1 guidewire. Installed ne w VX-ring.
2008-04-02 | 14:30:00 | 15:00:00 | 138 | drilling -- casing | ok | Flowchecked well - well static.
2008-04-02 | 15:00:00 | 15:45:00 | 138 | drilling -- casing | ok | Emptied trip tanks. Displaced well to 1,03 sg completion fluid at 1000 lpm. Pumped a total of 26 m3.
2008-04-02 | 15:45:00 | 16:45:00 | 138 | drilling -- casing | ok | Broke out TDS. POOH with annular insert on 5 1/2" HWDP landing string from 138 m MD to surface.
2007-10-18 | 02:30:00 | 04:00:00 | 138.5 | drilling -- casin g | ok | Picked up CART stinger 0,5 m above wellhead. Installed cover on subsea wellhead with ROV. Washed template through drillpipe and CART tool to remove cuttings. Cavitation in string made it hard for ROV to grab onto pipe. Re-positioned ROV to right below CART stinger. Stepped up rate to 4500 lpm and washed template while moving pipe with ROV. Inspected we llhead cap and template with ROV.
2007-10-18 | 04:00:00 | 04:15:00 | 138.5 | drilling -- casin g | ok | Performed toolbox talk prior to pulling CART.
2007-10-19 | 15:30:00 | 15:45:00 | 139 | drilling -- bop/wellhead eq uipment | ok | Landed TBC connector on 18 3/4" subsea wellhead succesfully. Set down 30 MT weight. Observed loose skirt on TBC connector.
2007-10-29 | 22:00:00 | 00:00:00 | 139 | drilling -- trip | ok | MU up wear bushing RT assembly and RIH with same from surface to 138 m. Tool landed off at 139.05 m. Jetted BOP and wellhead, 1650 lpm / 8 bar.
2007-11-02 | 17:30:00 | 22:00:00 | 139 | drilling -- casing | ok | RIH with BOP test plug to 139 m to test MS seal. Closed upper pipe ram. Attempted to pressure test seal assembly to 35 bar / 5 min without sucess. Closed annular to test upper pipe ram and found that upper pipe ram was leaking. Closed lower pipe ram and pressure tested seal assembly to 35 bar / 5 min and 345 bar / 15 min. 463 ltrs pumped and got 450 ltrs back. POOH with BOP test plug.
2007-11-02 | 22:00:00 | 00:00:00 | 139 | drilling -- casing | ok | RIH and installed wear bushing at 139 m MD.
2008-02-06 | 11:00:00 | 13:45:00 | 139 | drilling -- bop activities | ok | M/U BOP test cup assy. and RIH with same to 139 m.
2008-02-06 | 13:45:00 | 14:30:00 | 139 | drilling -- bop activities | ok | Held tool box talk prior to perform BOP test as MC procedure.
2008-02-06 | 14:30:00 | 20:45:00 | 139 | drilling -- bop activities | ok | Performed BOP test as MC procedure, 20/345 bars 5/10min.
2008-02-06 | 20:45:00 | 22:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | Torqued up slip joint. Fault of middle pipe variable 3½" x 5½" rams pressure test.
2008-02-06 | 22:45:00 | 00:00:00 | 139 | interruption -- repair | ok | Drained the riser. Opened middle variable 3½" x 5½" pipe rams and removed the rubbers.
2008-02-07 | 00:00:00 | 02:00:00 | 139 | completion -- bop/we llhead equipment | ok | Job suspended due to priority F12. Drilling dep. transported production Co-flex hose support frame to X-mas tree deck, through Moon Pool.
2008-02-07 | 02:00:00 | 03:30:00 | 139 | drilling -- bop activities | ok | Installed new variable 3½" x 5½" pipe rams rubbers.
2008-02-07 | 03:30:00 | 04:15:00 | 139 | drilling -- bop/wellhead equipment | ok | Attempted to pressure middle variable 3½" x 5½" pipe rams.
2008-02-07 | 04:15:00 | 06:00:00 | 139 | drilling -- bop/wellhead equipment | ok | Drained and opened middle variable 3½" x 5½" pipe rams. Opened top wear plate .
2008-02-07 | 06:00:00 | 07:00:00 | 139 | drilling -- bop activities | ok | Removed top wear plate and inspected seals. No visible damaged on the seals. Simultaneously serviced aft PRS.
2008-02-07 | 07:00:00 | 11:00:00 | 139 | drilling -- bop activities | ok | Changed out O-ring and top wear plate. Installed rams and closed doors. Simultaneously serviced aft PRS and TDS.
2008-02-07 | 11:00:00 | 11:45:00 | 139 | drilling -- bop activities | ok | Pulled up test plug and laid out 3m pup and one joint. Made up one double and ran in with same and landed of the test cup at 139 m. New test area for the middle pipe rams.
2008-02-07 | 11:45:00 | 12:15:00 | 139 | drilling -- bop activities | ok | Lined up the CMT unit and flushed the lines.
2008-02-07 | 12:15:00 | 12:45:00 | 139 | drilling -- bop activities | ok | Pressure tested the BOP middle pipe rams 20/345 bars 5/10 min.
2008-02-07 | 12:45:00 | 14:15:00 | 139 | drilling -- bop activities | ok | Performed accumulator test.
2008-03-18 | 10:15:00 | 11:00:00 | 139 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and picked the wear bushing RRT. M/U on 5½" RIH and engaged the wear bushing at 139m took 60 MT over pull to free the wear b ushing.
2008-03-19 | 18:45:00 | 19:00:00 | 139 | completion -- bop/wellhead equipm ent | ok | Released the 10 3/4"Lock down sub RT.
2008-03-24 | 14:00:00 | 19:00:00 | 139 | interruption -- waiting on w eather | ok | WOW prior to retrieve the HP riser. Meanwhile RIH with test plug and landed of in sub sea WH. Attempted to pressure test against plug. POOH with test pl ug.
2008-03-24 | 14:00:00 | 19:00:00 | 139 | interruption -- waiting on w eather | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-24 | 14:00:00 | 19:00:00 | 139 | interruption -- waiting on w eather | ok | 16:00 23/26 330° 3.9/6.2 330°
2008-03-24 | 14:00:00 | 19:00:00 | 139 | interruption -- waiting on w eather | ok | 18:00 23/27 360° 3.9/6.2 340°
2008-03-24 | 14:00:00 | 19:00:00 | 139 | interruption -- waiting on w eather | ok | 16:30-19:00 No access to rig floor, due to exhaust fumes
2008-03-25 | 04:00:00 | 06:00:00 | 139 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. Meanwhile re-RIH with test plug with polypack seals and landed of in sub sea WH. Pressure tested plug to 25/345 bars 5/10 min.
2008-03-25 | 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. Pressure tested BOP and TDS 20/345 bars 5/10 min. Performed derrick inspection.
2008-03-25 | 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-25 | 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | 12:30 27/32 320° 4.5/7.2 340°
2008-03-25 | 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | 14:30 24/30 320° 4.6/7.3 340°
2008-03-25 | 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | 16:30 23/25 340° 4.6/7.4 340°
2008-03-25 | 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | 18:30 23/27 340° 4.2/6.6 340°
2008-03-25 | 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | 14:45-15:30 No access to rig floor, due to exhaust fumes
2008-03-26 | 19:00:00 | 20:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and RIH with C-type lifting sub and made up same to Tension joint. Simultaneously disconnected the Claxton tool from the BOP joint.
2008-03-26 | 20:45:00 | 21:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | Installed Spider.
2008-03-26 | 20:45:00 | 21:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | Time Wind speed Wind direction Knots deg
2008-03-26 | 20:45:00 | 21:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | 21:30 4/8 160°
2008-03-26 | 21:45:00 | 00:00:00 | 139 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and applied 130 MT on to the string. Commenced to remove tension cylinders.
2008-03-27 | 00:00:00 | 01:45:00 | 139 | drilling -- | ok | Continued rigging down the tension system.
2008-03-27 | 00:00:00 | 01:45:00 | 139 | drilling -- | ok | Time Wind speed Wind direction Sea Wave direction Knots deg m deg
2008-03-27 | 00:00:00 | 01:45:00 | 139 | drilling -- | ok | 00:20 7/12 160° 1,3/2,1 360°
2008-04-04 | 01:15:00 | 01:30:00 | 139 | drilling -- casing | ok | Ran 10 3/4" Itco spear 3 m into 10 3/4" tie-back casing and latched same. Took up/down weight 82/79 MT. RIH with tie-back casing on 5 1/2" HWDP (LS-1). Put meter marks from casing ha nger landing shoulder. Tagged with 4 MT at ~139,4 m, i.e. 30-40 cm shallow - no colour marks observed in WH B-annulus outlet. Re-attempted tag - same depth.
2008-04-04 | 01:30:00 | 02:30:00 | 139 | drilling -- casing | ok | Evaluated situation. Checked drawings for potential hang-ups. Checked tally and joints left on deck - ok. Made two attempt to index pipe before tagging again - same depth. Sudden overpull of 14 MT observed after pulling some 30 cm above tag depth.
2008-04-04 | 02:30:00 | 03:15:00 | 139 | drilling -- casing | ok | Decided to attempt to screw in 1-2 turn in order to verify tie-back adapter depth. RIH and tagged approx 10 cm deeper than earlier. Observed lower orange and white band in B-annulus outle
2008-04-04 | 02:30:00 | 03:15:00 | 139 | drilling -- casing | ok | t. Measured required distance for adjustment sub travel (15") and decieded to continue according to plan.
2008-04-04 | 03:15:00 | 04:15:00 | 139 | drilling -- casing | ok | Set torqe limit to 2700 Nm. Made 3 attempts to enter tie-back adapter. Entered tie-back adapter on 4th attempt and observed weight increasing about 3-4 MT for each turn. Slacked off to neu tral (80 MT) for each turn achieved. String stalled out at 2700 Nm after 5+ turns achieved. Took 10 MT overpull. Rotated at 1 rpm. Attempted make up to 10 000 Nm (optimum torque) - spear started to slip at 5500 Nm. Re-engaged spear. Adjusted torque setting to minimum torque 6600 Nm -spear started to slip at 5500 Nm. Re-enaged spear. Set torque limit to 10 000 Nm, incre ased rotation to 3 RPM. String stalled out on 10 000 NM (optimum torque) - ok.
2008-04-04 | 04:15:00 | 04:45:00 | 139 | drilling -- casing | ok | Took 30 MT overpull to check pre-tension in casing towards datum. Streched pipe approx 2" and observed lower white band through B-annulus outlet.
2008-04-04 | 04:45:00 | 06:00:00 | 139 | drilling -- casing | ok | Rigged down Odfjell casing tong and removed PS-30 slips. Installed masterbushing and bowl.
2008-03-19 | 17:00:00 | 17:30:00 | 139.3 | completion -- bop/wellhead equipm ent | ok | Installed the 10 3/4" Lock down sub at 139.27m, as per Vetco procedure.
2008-03-19 | 17:30:00 | 17:45:00 | 139.3 | completion -- bop/wellhead equipm ent | ok | Performed line test from CMT unit to the rig floor to 207 bars 5 min.
2008-03-19 | 17:45:00 | 18:45:00 | 139.3 | completion -- bop/wellhead equipm ent | ok | Pressure up to 207 bars 5 min to fully set of the 10 3/4" Lock down sub. Volume pumped 275 litres - 250 litres in return.
2008-04-02 | 12:00:00 | 13:30:00 | 139.7 | drilling -- casing | ok | Tagged annulus insert at 139,68 m MD. Engaged J-slot and confirmed with 1 MT overpull.
2008-04-02 | 13:30:00 | 14:15:00 | 139.7 | drilling -- casing | ok | Closed annnular and backed out insert with 3 lefthand turns. Max torque 5 kNm. Observed for pressure build up - none obeserved. Continued backing out annular insert with another 3 leftha nd turns - observed 6" travel - ok.
2008-04-02 | 14:15:00 | 14:30:00 | 139.7 | drilling -- casing | ok | Opened annular. Attempted to pull free - had 18 MT overpull. Continued rotating left and came free with annular insert.
2016-10-07 | 15:15:00 | 15:45:00 | 139.9 | plug abandon - | ok | RIH w/ CH milling BHA on 5 1/2" DP from 72 m to 110 m.
2016-10-07 | 16:15:00 | 16:45:00 | 139.9 | - mill | ok | M/U TDS and continued RIH, tagged top of 10 3/4" CH at 139,9m. Pulled up and filled string.
2007-10-13 | 00:00:00 | 01:15:00 | 140 | drilling -- d rill | ok | Made up x-over above NM collars. RIH with 17 1/2" drilling BHA on DC/5 1/2" HWDP. Made up and ran hydraulic jar.
2008-02-08 | 00:00:00 | 01:00:00 | 140 | drilling -- other | ok | Continued POOH with RTTS plug from 300 m to 140 m, pulled out wet. As comming out of the sub sea well head, lost 12 MT on the weight.
2008-02-08 | 01:00:00 | 01:15:00 | 140 | drilling -- other | ok | Established levels by filling the well via trip tank.
2008-03-31 | 04:00:00 | 04:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Made up 5 1/2" landing stand. RIH with production riser on 5 1/2" DP. Guided TBC into guide funnel while observing with ROV. Used ROV C-guide for stabbing TBC. Positioned ROV with manipulator camera pointing upwards in guide funnel cut out window. Observed TBC relative to VX ring and top wellhead while comming down with production riser. Stopped riser motion w hen ~10 cm TBC swallow was obtained.
2008-03-31 | 04:45:00 | 05:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Detached lift sling on two points on each side of the hinge of the guide funnel. Unlocked hinge bolts and split guide funnel. Removed guide funnel by means of ROV and tuggers.
2008-03-31 | 05:45:00 | 06:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | RIH with production riser and landed TBC on top of wellhead. Set down 10 MT. Ran hotstab and minireel hose along guidewire.
2008-03-31 | 06:00:00 | 07:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Established hot stab in port A and set valves on ROV lock panel to "lock". Verified TBC fully landed. Locked TBC by pressuring up through minireel to 3000 psi. Observed movement of indic ator rods as prescribed. Maintained pressure for 15 mins. Set valves on ROV lock panel to parking position. Meanwhile assissted production in equalising across F-12 DHSV using cement unit.
2008-03-31 | 07:00:00 | 07:15:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Performed overpull test to 116 MT hookload / 20 MT overpull.
2008-03-31 | 07:15:00 | 08:30:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Removed hotstab and installed dummy stab. Moved hotstab to receptacle on panel B. Set valves to lower dog flush and injected hydraulic fluid / corrosion inhibitor through minireel.
2008-03-31 | 08:30:00 | 09:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Installed bleeder valve on top of tension joint running flange to prepare for pressure test.
2008-03-31 | 09:00:00 | 10:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Flushed and filled riser while venting air through valve on top of tension joint running flange. Closed valve. Lined up cement unit to standpipe and verified line-up by putting 15 bar on IBOP and opening same.
2008-03-31 | 10:00:00 | 11:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Pressure tested production riser to 20/200 bar 5/10 min - ok. Pumped 680 liter and got full return when bleeding back. Observed for leaks around TBC with ROV - ok. Maintained 20 MT ov erpull on TBC while performing pressure test.
2008-03-31 | 11:00:00 | 11:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Reduced hookload to 107 MT / 10 MT overpull on TBC. Took measurement for contact ring relative to Centralizer deck. Meanwhile pumped corrosion inhibitor in TBC upper piston cavity thr ough hotstab port B.
2008-03-31 | 11:45:00 | 13:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Unstabbed hotstab and installed dummy stab in receptacle B. Landed riser guide funnel on F-5 using ROV and tugger support. Installed hatches on all levels in wellhead module for slot F-3 and F-5.
2008-03-31 | 13:45:00 | 14:15:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Held toolbox talk prior to installing tensioner assembly.
2008-03-31 | 14:15:00 | 21:30:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Hoisted tension ring and removed nylon guide in Centralizer deck. Installed centralizer and boat collision stool in Centralizer deck. Placed wooden beams on boat collision stool and landed t ension ring on top. Installed contact ring below mark on riser contact grooves. Installed and assembled tension assy half hubs with shimms and made up tension ring lock plates. Connecte d 2 tension cylinders. Elevated tension assembly with tension cylinders and checked contact ring allignement. Made up contact ring. Connected 2 tension cylinders.
2008-03-31 | 21:30:00 | 22:15:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Pressured up on tension cylinders to 4 x 90 bar (150 MT) and transferred tension from block to tension cylinders on Centralizer deck. Slacked off drillstring to obtain marginal overpull (~1 M T) at cutting height.
2008-03-31 | 22:15:00 | 23:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Installed centralizer assembly in Tensioner deck.
2008-03-31 | 23:00:00 | 00:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Installed Norse cutting equipment on riser. Barriered off Centralizer deck.
2008-04-01 | 00:00:00 | 00:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | Installed Norse cutting equipment on riser.
2008-04-01 | 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | Cut riser according to Norse procedure.
2008-04-01 | 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | Meanwhile :
2008-04-01 | 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | -Installed flood lights in derrick
2008-04-01 | 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | -Varco checked both PRS's with focus on falling objects
2008-04-01 | 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | -Painted tuggerchains and control panels on drillfloor
2008-04-01 | 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | -Tested Gray valve and FOSVs to 345 bar
2008-04-01 | 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | -Brought wellhead to drillfloor
2008-04-01 | 04:30:00 | 05:15:00 | 140 | drilling -- bo p/wellhead equipment | ok | Released top part of riser when cut obtained. Re-configuered cutting jig with 45 deg blades for machining bevel. Put protective ball on top of cut to avoid swarf falling into well.
2008-04-01 | 05:15:00 | 06:00:00 | 140 | drilling -- bo p/wellhead equipment | ok | Cut 45 deg bevel on riser circumference.
2008-04-01 | 06:00:00 | 07:15:00 | 140 | drilling -- bo p/wellhead equipment | ok | Rigged down Norse cutting equipment. Removed swarf and smoothed down cut. Marked deck for wellhead orientation.
2008-04-01 | 07:15:00 | 08:15:00 | 140 | drilling -- bo p/wellhead equipment | ok | Packed and removed cutting equipment. Cleared and tidied wellhead decks.
2008-04-06 | 14:15:00 | 17:15:00 | 140 | drilling -- casing | ok | RIH with 9,567" casing drift from surface to 140 m MD on 5 1/2" HWDP singels. Re-arranged pipe on cantilever deck.
2016-10-06 | 18:45:00 | 19:15:00 | 140 | plug aban don -- oth er | ok | RIH w/ torque tool on LH drill pipe to 140m
2016-10-06 | 19:15:00 | 19:30:00 | 140 | plug aban don -- oth er | ok | Washed profile area 1500l/min - 9bar. Released tieback adapter w/ 38kNm
2016-10-06 | 19:30:00 | 19:45:00 | 140 | plug aban don -- oth er | ok | Performed Pre-job Meeting to change handling gear, L/D 5,5in LH DP
2016-10-06 | 19:45:00 | 20:45:00 | 140 | plug aban don -- oth er | ok | Removed master bushing, installed DP slips. Changed PDM head
2016-10-07 | 15:45:00 | 19:00:00 | 140.1 | plug abandon - | ok | Milled ID in 10 3/4" CH to 12 1/4". 100 rpm / 9-18 kNm, 2000 lpm / 10,8 bar, 4-5 ton WOB. Increased WOB to 8 - 10 ton after milling first 20 cm.
2008-04-02 | 19:45:00 | 21:30:00 | 140.5 | drilling -- casing | ok | Performed extra washing trip in order to clean tie-back adapter. Made up bullnose/jet sub. RIH on 5 1/2" DP from surface to 140 m MD. Stepped up pumps to 3500 lpm / SPP 68 bar. Passed t ie-back adapter and pulled back while pumping and rotating with 5 rpm. Pumped a total of 25 m3. Took returns to separate pit. POOH with jet sub.
2008-04-04 | 14:30:00 | 15:00:00 | 140.5 | drilling -- casing | ok | RIH with straddle cup tester from 28,4 m and located same across tie-back adpater at 140,5 m MD.
2008-04-04 | 15:00:00 | 16:00:00 | 140.5 | drilling -- casing | ok | Filled pipe with approx 1,8 m3 packer fluid prior to testing. Pressured up to 380 bar - observed leakage from B-annulus outlet - not able to obtain test.
2016-10-07 | 19:00:00 | 21:15:00 | 141 | plug abandon - | ok | Continued milling 10 3/4" CH, 100 rpm / 10 - 16 kNm, 2000 lpm / 11 bar, WOB 8 - 10 ton. Stalled out several times
2016-10-07 | 21:15:00 | 21:30:00 | 142 | plug abandon - | ok | Tagged top of 10 3/4" casing 1 m below 10 3/4" CH.
2016-10-07 | 21:15:00 | 21:30:00 | 142 | - mill | ok | Dressed off approximately 5 cm of top of 10 3/4" casing, 120 rpm / 5 - 10 kNm, 2000 lpm / 10 bar.
2008-04-07 | 14:00:00 | 17:15:00 | 145 | drilling -- casing | ok | POOH with GTV plug on 5 1/2" DP singles from 578 m to 145 m MD.
2007-06-09 | 19:00:00 | 22:30:00 | 146 | drilling -- drill | ok | Changed to automatic slips. RIH with 36" hole opener BHA on 5 1/2" HWDP. Dove ROV. Observed stabbing BHA into guide funnel with ROV. Tagged seabed at 145,6 m MD with no flow or rotation.
2016-10-08 | 01:00:00 | 01:30:00 | 147 | plug abandon -- equipm ent recovery | ok | RIH w/ 10 3/4" spear in catch mode on 5 1/2" DP from surface to 147 m
2016-10-07 | 03:00:00 | 05:30:00 | 148 | plug abandon - | ok | M/U and RIH w/ perforation BHA to 148m bottom shot depth
2016-10-07 | 05:30:00 | 06:15:00 | 148 | plug abandon - | ok | Closed UPR, opened choke. Confirmed line up. Filled string. Opened UPR, Broke off TDS and dropped 1 3/8 ball in string. M/U TDS. Closed UPR and opened choke. Fired guns with 160 l/min - 130 bar. Top shot at 145m, bottom shot at 148m. Continued to circulate w/ 160l/min
2016-10-07 | 06:15:00 | 07:00:00 | 148 | plug abandon - | ok | Circulated 1000 lpm / 5 bar. Maximum gas reading 0,41 %.
2016-10-07 | 07:00:00 | 07:30:00 | 148 | plug abandon - | ok | Stopped pumps and closed choke. Monitored well.
2016-10-07 | 07:00:00 | 07:30:00 | 148 | - perforate | ok | Unable to circulate on TT due to contaminated OBM mixed with water. Emptied both TTs and re-filled TTs with clean SW.
2016-10-07 | 07:30:00 | 07:45:00 | 148 | plug abandon - | ok | Opened UPR and choke Flowchecked well for 10 min, static.
2007-06-09 | 22:30:00 | 23:00:00 | 150 | drilling -- drill | ok | Washed down with 36" hole opener BHA with 600 lpm. Observed centralizer guide bushing landing in template guide funnel. Parked ROV in top hat prior to start rotating.
2007-06-10 | 21:00:00 | 23:00:00 | 152 | drilling -- drill | ok | POOH with 36" hole opener BHA from 256,5 m to 152 m MD. Topped up hole with 1,35 sg WBM pumping at 400 lpm.
2007-06-09 | 23:00:00 | 00:00:00 | 157 | drilling -- drill | ok | Drilled 36" hole section from 150 m to 157 m MD. Drilling parameters : Rotation 15-20 rpm / WOB 2 MT/ Flow 900 lpm. Svept hole with 15 m3 hi-vis at 157 m MD.
2008-02-24 | 22:30:00 | 00:00:00 | 160 | drilling -- bop/wellh ead equipment | ok | Cleared and tidied drillfloor. Picked up and made up jet sub. RIH on 5" DP from surface to 160 m MD.
2008-02-25 | 00:00:00 | 01:15:00 | 160 | drilling -- bop/wellhead equipment | ok | Washed accross subsea wellhead with jet sub 4 times pumping at 3000 lpm.
2008-02-25 | 11:00 | 11:45:00 | 160 | drilling -- bop/wellhead equipment | ok | POOH with 5 1/2" DP from 300 m to 160 m MD. Broke out and laid down test plug.
2016-10-08 | 14:00:00 | 14:30:00 | 160 | plug abandon -- cement plug | ok | POOH w/ EZSV RT on 5 1/2" DP from 305 m to 160 m.
2016-10-08 | 14:30:00 | 15:00:00 | 160 | plug abandon -- cement plug | ok | Installed 2x sponge balls. Circulated BU, 2000 lpm.
2008-03-11 | 05:30:00 | 06:00:00 | 165 | drilling -- bop/wellhead equipment | ok | POOH with jet sub/BOP test plug on 5 1/2" DP from 184 m to 165 m MD.
2007-10-30 | 17:00:00 | 22:00:00 | 167 | interruption -- other | ok | Casing torque computer would not work according to set up. Had to continue with modified set-up.
2007-06-10 | 00:00:00 | 02:30:00 | 170 | drilling -- drill | ok | Continued drilling 36" hole section from 157 m to 170 m MD. Drilling parameters : Rotation 70 rpm / WOB 2 MT / Flow 4100 lpm / Torque 6-12 kNm . Performed surv ey on every single - got unreliable data at 157 m and 170 m MD.
2007-06-10 | 02:30:00 | 03:15:00 | 170 | drilling -- drill | ok | Due to unreliable survey data and suspected inclination build up => Performed reaming trip back to 150 m MD.
2007-06-10 | 02:30:00 | 03:15:00 | 170 | drilling -- drill | ok | Meanwhile discussed situation. Found out that surveys had been taken while string was rotating which again gave wrong / unreliable readings.
2007-06-10 | 03:15:00 | 03:30:00 | 170 | drilling -- drill | ok | Repeated survey at 170 m MD. Inclination 0,4 deg - ok.
2016-10-08 | 01:30:00 | 02:30:00 | 170 | plug abandon -- equipm ent recovery | ok | POOH with 10 3/4" casing on 5 1/2" landing string from 147 m to surface.
2016-10-08 | 02:30:00 | 02:45:00 | 170 | plug abandon -- equipm ent recovery | ok | Released spear at surface and R/B spear BHA
2016-10-08 | 02:45:00 | 03:00:00 | 170 | plug abandon -- equipm ent recovery | ok | Performed TBT for R/U casing handling equipment and pulling casing.
2007-10-30 | 12:00:00 | 17:00:00 | 171 | drilling -- casing | ok | Held tool-box meeting before running csg. PU and MU shoe joint, intermediate- and float collar joints. Thread locked first 3 connections. Checked shoe and float co llar for flow-through while PU.
2007-10-30 | 12:00:00 | 17:00:00 | 171 | drilling -- casing | ok | RIH with 9 5/8" csg to 171 m MD. Filled every joint with 1.40 sg mud using FAC tool.
2008-03-10 | 21:15:00 | 22:30:00 | 184 | drilling -- bop/wellhead equi pment | ok | Made up test plug and inspected seals. RIH with same on 5 1/2" DP. Landed test plug in subsea wellhead/wearbushing at 140 m MD. Flushed lines from c ement unit and verified line up.
2008-03-10 | 22:30:00 | 00:00:00 | 184 | drilling -- bop activities | ok | Tested 18 3/4" surface BOP against test plug in subsea wellhead, 20/345 bar 5/10 min.
2008-03-11 | 00:00:00 | 05:30:00 | 184 | drilling -- bop activities | ok | Tested 18 3/4" surface BOP against test plug in subsea wellhead, 20/345 bar 5/10 min.
2008-03-11 | 00:00:00 | 05:30:00 | 184 | drilling -- bop activities | ok | Meanwhile performed derrick inspection, cleaned moonpool area and prepared for greasing manifolds.
2007-06-10 | 03:30:00 | 06:00:00 | 192 | drilling -- drill | ok | Drilled 36" hole section from 170 m to 192 m MD. Drilling parameters : Rotation 70 rpm / WOB 2-3 MT / Flow 4100 lpm / Torque 5-8 kNm. Swept hole with 15 m3 hi- vis every single drilled.
2007-06-10 | 03:30:00 | 06:00:00 | 192 | drilling -- drill | ok | Inclination at 183 m MD 0,06 deg - ok.
2007-06-12 | 03:30:00 | 05:00:00 | 200 | drilling -- casi ng | ok | Ran in with 30" conductor on 5 1/2" HWDP. Observed with ROV when running through template slot.
2008-02-25 | 15:30:00 | 16:00:00 | 200 | formation evaluation -- log | ok | RIH with MDT toolstring on 5" DP from 41 m to 200 m MD. Max running speed 2 min/stand.
2008-02-25 | 16:00:00 | 16:30:00 | 200 | formation evaluation -- log | ok | Removed master bushing and inserted PS-30 automatic slips in rotary.
2007-06-12 | 06:00:00 | 07:45:00 | 210 | drilling -- casi ng | ok | Contiuned to work 30" conductor. Had overpull of 15 MT.
2007-06-12 | 05:00:00 | 06:00:00 | 215 | drilling -- casi ng | ok | Started loosing hook weight at 200 m MD. Worked string up and down trying to release friction in well.
2007-10-13 | 01:15:00 | 02:00:00 | 220 | drilling -- d rill | ok | While observing with ROV, stabbed 17 1/2" BHA into 30" housing/CTS funnel. RIH with 17 1/2" BHA to 220 m MD. ROV took position and started CTS pump. Not able to operate suction v alve from pit#7 when attempting to start pumping.
2007-10-13 | 02:00:00 | 02:30:00 | 220 | interruptio n -- other | ok | Not able to operate suction valve from pit#7. Locked valve open.
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | POOH with 17 1/2" drilling BHA on 5 1/2" DP from 1360 m to 220 m MD.
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | Observed thight spots at :
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | 1345 m MD 20-30 MT overpull
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | 1175 m MD 20 MT overpull
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | 1145 m MD 15 MT overpull
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | 1135 m MD 15 MT overpull
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | 745 m MD 10 MT
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | 690 m MD 10 mT
2007-10-15 | 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | Intervall 580 to 380 m MD 10-12 MT overpull
2007-10-15 | 20:15:00 | 20:30:00 | 220 | drilling -- trip | ok | Topped up well with 40 m3 1,40 WBM. Stopped to investigate for hydraulic leak on top drive.
2007-10-15 | 20:30:00 | 20:45:00 | 220 | interruption -- ot her | ok | Investigated hydraulic leakage on TDS. Found leakage in easy accessible hose fitting. Tightened hose. Further work on TDS needed as a less accessible leakage was observed.
2007-06-10 | 06:00:00 | 10:30:00 | 222 | drilling -- drill | ok | Continued drilling 36" hole section from 192 m to 222 m MD. Drilling parameters : Rotation 70 rpm / WOB 2 MT / Flow 4100 lpm / Torque 8-12 kNm. Swept hole with 15 m3 hi-vis every single drilled.
2007-06-10 | 10:30:00 | 11:00:00 | 222 | interruption -- other | ok | Due to problems with PRS at connection - reciprocated pipe and made extra sweep with hi-vis.
2007-10-13 | 06:30:00 | 07:45:00 | 223 | interruptio n -- other | ok | Had to wait for WL gyro unit to become purged and operational. This was caused by downtime on STB crane during the night, not able to do the lift in due time. Circulated at 3500 lpm and reciprocated pipe. Racked back stand and pulled bit inside conductor shoe to 223 m MD.
2007-10-13 | 07:45:00 | 08:00:00 | 223 | drilling -- d rill | ok | Removed masterbushing and installed automatic slips.
2008-04-06 | 21:45:00 | 00:00:00 | 223 | drilling -- casing | ok | POOH with 9,567" drift on 5 1/2" DP from 580 m to 223 m MD. Laid out singles on deck when pulling out. Performed kick drill.
2007-06-12 | 07:45:00 | 11:30:00 | 237 | drilling -- casi ng | ok | Closed filler valve with ROV. Started circulation with SW at 2300 lpm thorugh 30" conductor. Worked 30" conductor while circulating w/ maximum 12 bar pumppressure and 10 mt downweight. Put datum mark on pipe 112,88 m centralizer deck to top 30" conductor housing.
2008-04-06 | 17:15:00 | 18:15:00 | 245 | drilling -- casing | ok | RIH with 9,567" casing drift from 140 m to 245 m MD on 5 1/2" DP singles. Detected exhaust fumes on drillfloor.
2008-04-06 | 18:15:00 | 19:15:00 | 245 | interruption -- waiting on weather | ok | Exhaust fumes on drillfloor. Made up TDS and spaced out for BOP. Abandoned drillfloor. Shut down one of the gas turbines to reduce exhaust fumes.
2007-10-13 | 11:00:00 | 12:15:00 | 249 | drilling -- d rill | ok | Installed 5 m pup joint and made up TDS for pumping. String free down. Established circulation with 3100 lpm. Swept hole with 20 m3 hi-vis. Pulled 17 1/2" BHA from 262 m to 249 m MD i nside conductor shoe. Got 11 m stick-up.
2007-10-13 | 12:15:00 | 13:15:00 | 249 | drilling -- s urvey | ok | RIH with gyro on WL, located in UBHO and performed survey. Oriented toolface as required. Halted operation due to possible power-shut down during ESD test.
2007-10-13 | 02:30:00 | 03:45:00 | 250 | drilling -- d rill | ok | Commenced pumping at 3500 lpm and tested communication to MWD - ok. Observed severe cavitation in string. Reduced rate to 2000 lpm and washed down to 247 m MD and tagged T OC. Drilled cement inside 30" shoetrack. Drilling parameters : 3500 lpm / SPP 80 bar / 40 RPM / Torque 1-3 kNm / WOB 4 MT.
2007-06-12 | 11:30:00 | 13:30:00 | 251 | drilling -- casi ng | ok | Broke out two joints from 5 1/2" HWDP stand. M/U cement stand with side entry sub and lotorqe valve. Continued to work 30" condcutor while ciruclating SW at 2300 lpm. Reach ed TD and confirmed correct depth by datum mark on pipe towards machined ring on centralizer deck.
2007-06-12 | 13:30:00 | 15:00:00 | 251 | drilling -- casi ng | ok | Hooked up ROV with hydraulic reservoir to hydraulic receptacle on template. Engaged centralization rams in template funnel.
2007-06-12 | 13:30:00 | 15:00:00 | 251 | drilling -- casi ng | ok | Pitch and roll readings :
2007-06-12 | 13:30:00 | 15:00:00 | 251 | drilling -- casi ng | ok | Before engaging rams ; roll 0,04 to 0,3 / pitch 0,01 to 0,2 After engaging rams ; roll static at 0,13 / pitch static at 0,05
2007-06-12 | 15:00:00 | 15:30:00 | 251 | drilling -- casi ng | ok | Circulated at 2300 lpm / SPP 11 bar to confirm no leaks on plugs in conductor housing. No leaks could be observed by the ROV. Meanwhile held cementing prejobmeeting at drill floor.
2007-06-12 | 15:30:00 | 16:15:00 | 251 | drilling -- casi ng | ok | Prepared for cementing conductor. Lined up and tested cement lines to 200 bar / 5 min - ok.
2007-06-12 | 16:15:00 | 17:45:00 | 251 | drilling -- casi ng | ok | Pumped 75 m3 of 1,50 sg X-lite cement slurry with cement unit. Pump pressure during cement displacement 13 bar. Displacement rate 800 lpm.
2007-06-12 | 17:45:00 | 18:00:00 | 251 | drilling -- casi ng | ok | Displaced cement with seawater. Pressure rose from 20 bar to approx 35 bar during displacement indicating cement in annulus and good cement job. Pumped a total of 8,5 m3 le aving theoretical TOC at 247 m MD inside the 30" conductor.
2007-06-12 | 18:00:00 | 18:15:00 | 251 | drilling -- casi ng | ok | Rigged down cement hose and flushed same. Flushed manifold.
2007-06-12 | 18:15:00 | 00:00:00 | 251 | drilling -- casi ng | ok | Waited on cement to set up.
2007-06-12 | 18:15:00 | 00:00:00 | 251 | drilling -- casi ng | ok | Meanwhile :
2007-06-12 | 18:15:00 | 00:00:00 | 251 | drilling -- casi ng | ok | -Cleared and tidied rigfloor
2007-06-12 | 18:15:00 | 00:00:00 | 251 | drilling -- casi ng | ok | -PV on drillfloor equipment
2007-06-12 | 18:15:00 | 00:00:00 | 251 | drilling -- casi ng | ok | -Flushed and cleaned cement unit
2007-06-12 | 18:15:00 | 00:00:00 | 251 | drilling -- casi ng | ok | -Inspected seabed for cement returns - inconcluisve due to poor visiblity
2007-06-13 | 00:00:00 | 04:00:00 | 251 | drilling -- casing | ok | Waited on cement to set up.
2007-06-13 | 00:00:00 | 04:00:00 | 251 | drilling -- casing | ok | Meanwhile :
2007-06-13 | 00:00:00 | 04:00:00 | 251 | drilling -- casing | ok | -PV on drillfloor equipment
2007-06-13 | 00:00:00 | 04:00:00 | 251 | drilling -- casing | ok | -FG inspection on drillfloor
2007-06-13 | 00:00:00 | 04:00:00 | 251 | drilling -- casing | ok | -Grinded down weld seam on LP riser
2007-06-13 | 04:00:00 | 04:30:00 | 251 | drilling -- casing | ok | Held toolbox talk prior to pumping down the top up pipe.
2007-06-13 | 04:30:00 | 05:00:00 | 251 | drilling -- casing | ok | Lined up to pump down top up pipe. Tested line and manifold 100 bar / 5 min.
2007-06-13 | 05:00:00 | 06:00:00 | 251 | drilling -- casing | ok | Stepped up pressure pumping at 50 l/min. Held pressure at predetermined levels :
2007-06-13 | 05:00:00 | 06:00:00 | 251 | drilling -- casing | ok | 24 bar (gauge) - ok 33 bar (gauge) - ok 39 bar (gauge) - ok
2007-06-13 | 05:00:00 | 06:00:00 | 251 | drilling -- casing | ok | At 46 bar gauge, i.e approx 53 bar (770 psi) differential, pressure bled of rapidly indicating burst disk rupture. Indications are that it is the shallowmost disk that ruptured.
2007-06-10 | 11:00:00 | 19:00:00 | 256.5 | drilling -- drill | ok | Continued drilling 36" hole section from 222 to 256,5 m MD. Drilling parameters : Rotation 70 rpm / WOB 2-5 MT / Flow 4100 lpm / Torque 8-12 kNm. Swept hole wit h 15 m 3 hi-vis every single drilled.
2007-06-10 | 19:00:00 | 19:30:00 | 256.5 | drilling -- circulating co nditioning | ok | Circulated well clean with 4400 lpm / SPP 90 bar. Pumped 25 m3 hi-vis. Performed final survey at TD.
2007-06-10 | 19:30:00 | 20:30:00 | 256.5 | drilling -- circulating co nditioning | ok | Displaced well to 1,35 sg WBM at 4000 lpm / SPP 90 bar. Pumped a total of 100 m3.
2007-06-10 | 20:30:00 | 21:00:00 | 256.5 | interruption -- other | ok | Had problems to release torque wrench when attempting to unscrew from topdrive. Troubleshot problem.
2007-10-13 | 03:45:00 | 05:00:00 | 260 | drilling -- d rill | ok | Drilled and opened 36" / 26" / 17 1/2" rathole from 250 m to 260 m MD. Drilling parameters : Flow 3500 lpm / SPP 82 bar / 40 RPM / WOB 1-2 MT / Torque 2-3 KNm. Reamed through sho etrack / rathole 3 times. Pumped 20 m3 hi-vis to clean hole.
2007-10-13 | 08:00:00 | 09:00:00 | 262 | drilling -- d rill | ok | RIH with 17 1/2" BHA from 223 m to 262 m MD to obtain favourable stick up for running WL gyro. Not able to lay out single due to WL unit in V-door. Rigged up for running WL gyro. Held t oolbox talk prior to running gyro.
2007-10-13 | 09:00:00 | 10:00:00 | 262 | drilling -- s urvey | ok | RIH with gyro on WL, located gyro in UBHO and performed survey. Pulled out with gyro and performed survey while pulling out.
2007-10-13 | 10:00:00 | 10:30:00 | 262 | drilling -- d rill | ok | Attempted to orient toolface - negative due to high torque. Pulled string to work out the torque, observed 25 MT overpull.
2007-10-13 | 10:30:00 | 11:00:00 | 262 | drilling -- d rill | ok | Attempted to pull inside shoe, observed 25 MT overpull.
2007-10-13 | 05:00:00 | 06:00:00 | 265 | drilling -- d rill | ok | Drilled new formation from 260 m to 265 m MD. Drilling parameters : Flow 3500 lpm / SPP 83 bar / 40 RPM / WOB 1-3 MT / Torque 2-3 KNm.
2007-10-13 | 06:00:00 | 06:30:00 | 265 | drilling -- d rill | ok | Pumped 15 m3 hi-vis sweep on bottom. Had to wait for WL gyro unit to become operational.
2007-10-13 | 15:15:00 | 15:45:00 | 265 | drilling -- d rill | ok | RIH with 17 1/2" BHA to 265 m MD. Laid out 5 m pup joint and made up stand.
2008-02-20 | 00:00:00 | 06:00:00 | 268 | interruption -- fish | ok | Ran 5 1/2" DP singles over 7/48 wireline from 13 m to 268 m MD according to cut and thread procedure.
2007-10-30 | 22:00:00 | 00:00:00 | 276 | drilling -- casing | ok | RIH with 9 5/8" csg from 171 to 276 m MD. Filled every joint with 1.40 sg mud using FAC tool. First 19 joint was ran with centraliser.
2008-02-28 | 12:30:00 | 18:15:00 | 289 | drilling -- casin g | ok | RIH with 7" liner from 40 m to 289 m MD, filling every 5th joint. Max running speed was 5 joints/hr
2008-02-28 | 12:30:00 | 18:15:00 | 289 | drilling -- casin g | ok | Installed pip-tag 0.34 m below top of collar on 1.92 m pup-joint in RA assembly. Estimated RA depth is 3216.17 m, but final depth will be given when 7" liner is set.
2008-02-07 | 21:45:00 | 23:00:00 | 300 | drilling -- other | ok | POOH from 340 m to 300 m with drag of 12 MT. Pulled out wet.
2008-02-07 | 23:00:00 | 23:45:00 | 300 | drilling -- other | ok | Made up to TDS. Attempted to pump down the DP, w/ 23 bars 400 litres. No returns up annulus.
2008-02-07 | 23:45:00 | 00:00:00 | 300 | drilling -- other | ok | Took time out and evaluated situation.
2008-02-25 | 01:15:00 | 03:00:00 | 300 | drilling -- bop/wellhead equipment | ok | Made up test plug and RIH with same on 5" DP. Landed test plug in subsea wellhead/wearbushing at 140 m MD. Flushed lines from cement unit and verified line up.
2008-02-25 | 03:00:00 | 06:00:00 | 300 | drilling -- bop activities | ok | Tested 18 3/4" surface BOP against tests plug in subsea wellhead, 20/345 bar 5/10 min.
2008-02-25 | 06:00:00 | 11:00:00 | 300 | drilling -- bop activities | ok | Tested 18 3/4" surface BOP against test plug in subsea wellhead, 20/345 bar 5 /10 min.
2008-02-25 | 06:00:00 | 11:00:00 | 300 | drilling -- bop activities | ok | Meanwhile :
2008-02-25 | 06:00:00 | 11:00:00 | 300 | drilling -- bop activities | ok | -Serviced TDS
2008-02-25 | 06:00:00 | 11:00:00 | 300 | drilling -- bop activities | ok | -Removed 7/48 WL sheaves from derrick
2008-02-25 | 06:00:00 | 11:00:00 | 300 | drilling -- bop activities | ok | -Changed elevators
2008-02-25 | 06:00:00 | 11:00:00 | 300 | drilling -- bop activities | ok | -Cleaned and maintained drillfloor equipment
2016-10-08 | 11:15:00 | 12:30:00 | 305 | plug abandon -- cement plug | ok | Pumped 10 m3 wash pill followed by 10 m3 hi-vis pill at 2000 lpm / 9 bar.
2016-10-08 | 11:15:00 | 12:30:00 | 305 | plug abandon -- cement plug | ok | Circulated with clean SW until clean returns. Reduced to 900 lpm when hi-vis at shakers. Increased flow to 2440 lpm when clean SW in returns. Meanwhile: Flushed TTs.
2016-10-08 | 12:30:00 | 12:45:00 | 305 | plug abandon -- cement plug | ok | Performed TBT for cement job
2016-10-08 | 12:45:00 | 13:45:00 | 305 | plug abandon -- cement plug | ok | Closed flow line and opened dump line. R/U cement hose to pump-in sub.
2016-10-08 | 12:45:00 | 13:45:00 | 305 | plug abandon -- cement plug | ok | Applied 20 bar behind FOSV and confirmed line-up. Leak tested surface lines to 100 bar / 3min.
2016-10-08 | 12:45:00 | 13:45:00 | 305 | plug abandon -- cement plug | ok | Balanced OH to surface cement plug in 13 3/8" casing (305 m - 205 m ): Pumped 10 m3 DW at 1000 lpm with cement unit. Mixed and pumped 7,8 m3 1,95sg cement slurry at 600 lpm. Displaced cement with 2 m3 DW at 1000 lpm with cement unit.
2016-10-08 | 13:45:00 | 14:00:00 | 305 | plug abandon -- cement plug | ok | R/D cement hose. B/O and L/O pump-in sub.
2016-10-08 | 09:15:00 | 10:30:00 | 306 | plug abandon -- other | ok | RIH w/ 13 3/8" EZSV plug from 24 m to 306 m.
2016-10-08 | 10:30:00 | 10:45:00 | 306 | plug abandon -- other | ok | P/U and M/U pump-in sub.
2016-10-08 | 10:45:00 | 11:15:00 | 306 | plug abandon -- mecha nical plug | ok | M/U TDS and washed setting area with 560 lpm / 6 bar.
2016-10-08 | 10:45:00 | 11:15:00 | 306 | plug abandon -- mecha nical plug | ok | Set 13 3/8" EZSV plug at 306m. Tagged EZSV plug with 10 ton.
2008-03-02 | 00:00:00 | 06:00:00 | 309 | drilling -- trip | ok | LO 5 1/2" DP 24.7 lbs/ft in singles from 720 m to 309 m.
2016-10-07 | 09:45:00 | 10:15:00 | 312 | plug abandon - | ok | RIH w/ 10 3/4" cutter BHA on 5 1/2" DP from surface to 312 m.
2016-10-07 | 10:15:00 | 10:30:00 | 312 | plug abandon - | ok | M/U TDS. Recorded up/down weight 76 / 71 ton.
2016-10-07 | 10:15:00 | 10:30:00 | 312 | - cut | ok | Filled DP. Initiated circulation 500 lpm / 73 bar, 50 rpm / 0 to 3 kNm.
2016-10-07 | 10:30:00 | 10:45:00 | 312 | plug abandon - | ok | Cut 10 3/4" casing at 312 m, 400 lpm, 50 rpm. SPP dropped, good indication of cut.
2016-10-07 | 10:45:00 | 11:00:00 | 312 | plug abandon - | ok | Lined up to TT and performed flowcheck, well static.
2008-03-14 | 08:00:00 | 11:45:00 | 314 | drilling -- other | ok | Functioned shear rams. Picked up clean out assy and RIH and cleaned BOP, riser and WH. Function tested BOP rams and annular.
2008-02-07 | 17:15:00 | 18:45:00 | 340 | drilling -- other | ok | Displaced the well above the RTTS plug to 1.40 OBM, 1500/1000 lpm.
2008-02-07 | 20:45:00 | 21:00:00 | 340 | drilling -- other | ok | POOH from 350 m to 340 m with drag of 12 MT. Pulled out wet.
2008-02-07 | 21:00:00 | 21:45:00 | 340 | drilling -- other | ok | Changed to PS21 slips.
2008-02-07 | 16:15:00 | 17:15:00 | 342 | drilling -- other | ok | RIH with RTTS retrieving tool and tagged the RTTS plug at 342m, picked up 2m.
2007-11-03 | 08:30:00 | 09:30:00 | 348 | drilling -- circulating conditioning | ok | RIH with RTTS running tool assembly from 332 m to 348 m MD. Circulated 1 x btms up, 2000 lpm / 11 bar.
2007-11-03 | 09:30:00 | 12:00:00 | 348 | drilling -- other | ok | Held pre-job meeting prior to displacing well to SW. Lined up and flushed surface lines and choke & kill hoses. Displaced well above RTTS to SW, 2000 lpm / 12 bar. Used 10 m3 baseoil as spacer.
2007-11-03 | 06:00:00 | 07:30:00 | 349 | drilling -- other | ok | Tested RTTS packer to 180 bar / 10 min from below.
2007-11-03 | 07:30:00 | 08:30:00 | 349 | drilling -- other | ok | Released from RTTS with 22 turns to the left. PU from 349 m to 332 m and spaced out tool joint below LPR. Tested RTTS packer to 180 bar / 10 min from ab ove against closed lower pipe ram.
2007-11-03 | 01:00:00 | 05:15:00 | 350 | drilling -- other | ok | RIH with 7 stds of 5 1/2" DP. MU and RIH with 10 3/4" RTTS with storm valve on 5 1/2" DP to 350 m MD. Up weight 91 MT / Down weight 87 MT. Weight unde r RTTS is 10.2 MT (bouyant).
2007-11-03 | 05:15:00 | 06:00:00 | 350 | drilling -- other | ok | Resiprocated string and circulated with 100 lpm to clean setting area. Installed plug according to Halliburton procedure with element at 350 m MD. Lined up to test RTTS to 180 bar/10 min from below.
2008-02-07 | 18:45:00 | 19:45:00 | 350 | drilling -- other | ok | Took up/down weight 82/79 MT. Stung into the RTTS plug, turned DP 22 turnes and torque up to 2000 ft/lbs, no pressure built up. Lined up to the trip tank. Pressure up DP to 5 bars and confirmed sufficiently engaged to tool. Attempted to release the RTTS plug by pulling 105 MT equivalent to 15 MT over pull.
2008-02-07 | 19:45:00 | 20:15:00 | 350 | drilling -- other | ok | Closed annular and applied 40 bars to the annulus, to collapse the hydraulic slips. Held pressure for 5 min. Bled off pressure in the annulus and opened the annular.
2008-02-07 | 20:15:00 | 20:30:00 | 350 | drilling -- other | ok | Picked up string in 5 MT staged from 81 MT to 115 MT. At 115 MT , equivalent to 25 MT over pull. RTTS plugs mechanical slips disengaged.
2008-02-07 | 20:30:00 | 20:45:00 | 350 | drilling -- other | ok | Waited for element to retract.
2008-04-21 | 15:00:00 | 15:45:00 | 360 | interrupti on -- rig up/down | ok | POOH with perforation guns from 701 m to 360 m MD due to weak CCL signal.
2007-10-16 | 21:30:00 | 00:00:00 | 380 | drilling -- casin g | ok | Ran 13 3/8" casing from 200 m to 380 m MD. Filled casing with 1,40 sg WBM every 5th joint. Average running speed 6 joints/hr.
2016-10-06 | 03:00:00 | 03:15:00 | 389 | plug aban don -- oth er | ok | Performed Pre-job Meeting to L/D 5.5in DP. Meanwhile performed flowcheck. Stable
2007-10-31 | 02:15:00 | 03:00:00 | 393 | interruption -- other | ok | Changed proximity switch on PDM.
2007-10-31 | 00:00:00 | 02:15:00 | 416 | drilling -- casing | ok | RIH with 9 5/8" csg from 276 to 416 m MD. Filled every joint with 1.40 sg mud using FAC tool.
2007-10-13 | 15:45:00 | 00:00:00 | 424 | drilling -- d rill | ok | Drilled 17 1/2" hole section from 265 m to 424 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3500 lpm / SPP 75-90 bar / 100 RPM / WOB 1-9 MT / Torq ue 3-7 kNm. Increaed RPM to 140 during rotary drilling. Pumped 30 m3 hi-vis per stand to clean hole. Average ROP 19 m/hrs. Good correspondance between GWD and MWD obtained at 383 m MD.
2008-03-07 | 18:00:00 | 00:00:00 | 434 | drilling -- casing | ok | RIH with 7" liner from 39 m to 434 m MD, filling every 5th joint. Cleaned and re-doped pin end. Max running speed was 9 joints/hr
2008-03-07 | 18:00:00 | 00:00:00 | 434 | drilling -- casing | ok | Installed pip-tag 0.34 m below top of collar on 2.05 m pup-joint in RA assembly. Estimated RA depth is 3230.76 m, but final depth will be given when 7" liner is set.
2008-03-01 | 18:00:00 | 20:15:00 | 443 | drilling -- trip | ok | RIH with 20 std 5 1/2" DP 24.7 lbs/ft to 443 m.
2008-03-01 | 20:15:00 | 22:15:00 | 443 | drilling -- trip | ok | Stopped RIH and had time-out due to sensor target bracket (570 g) dropped from TDS. Investigated and reported dropped object situation prior to re-commencing operations.
2008-03-02 | 07:30:00 | 09:00:00 | 444 | drilling -- trip | ok | RIH with 5 1/2" DP 24.7 lbs/ft to 444 m.
2008-03-17 | 06:00:00 | 07:00:00 | 474 | interruption -- wait | ok | Continued waiting due to exhaust fumes blowing into the rig floor.
2008-03-17 | 00:00:00 | 03:30:00 | 475 | completion -- circulating conditioni ng | ok | Continued POOH with 3½" DP and laid out in singles from 735m to 475m.
2008-03-17 | 03:30:00 | 06:00:00 | 475 | interruption -- wait | ok | Stopped POOH due to exhaust from the production turbine blowing into the rig floor. Installed safety valve on to the 3½" DP. Monitored well on th e trip tank.
2010-09-24 | 10:00:00 | 10:45:00 | 498 | workover -- wire lin e | ok | RIH with BHA#1, RST. Stopped in DHSV at 498 m.
2010-09-24 | 10:45:00 | 11:15:00 | 498 | workover -- wait | ok | Lined up AWS pump, pumped MEG into well and equalized DHSV at 39 bar.
2008-03-14 | 05:00:00 | 06:00:00 | 525 | drilling -- drill | ok | Continued POOH with 3½" DP EZSV RT from 791m to 525m
2008-03-11 | 18:00:00 | 00:00:00 | 550 | drilling -- drill | ok | RIH with 6" PDC bit and scraper assembly from 13 m to 26 m. Changed to PS21 slips. Continued to RIH with 6" PDC bit and scraper assembly on 3 1/2" DP from 26 m to 550 m. PU 3 1/2" DP in singles. Max running speed was 14 joints/hr.
2008-03-11 | 18:00:00 | 00:00:00 | 550 | drilling -- drill | ok | Meanwhile tested choke manifolds.
2012-09-14 | 02:15:00 | 02:50:00 | 556 | workover -- wire line | ok | RIH with BHA#1, RST to 556 m.
2012-09-14 | 02:50:00 | 03:20:00 | 556 | workover -- wire line | ok | Performed test of RST according to Schlumberger procedure.
2007-10-14 | 00:00:00 | 06:00:00 | 560 | drilling -- d rill | ok | Drilled 17 1/2" hole section from 424 to 560 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3500-3800 lpm / SPP 90-100 bar / 100 RPM / WOB 5-12 MT
2007-10-14 | 00:00:00 | 06:00:00 | 560 | drilling -- d rill | ok | / Torque 4-7 kNm. Increaed RPM to 140 during rotary drilling. Pumped 2 x 15 m3 hi-vis per stand to clean hole. Average ROP 23 m/hrs. Performed cluster shots for SUCOP corrections of MWD data.
2008-03-04 | 20:15:00 | 00:00:00 | 560 | drilling -- casing | ok | POOH with 7" liner and RB in derrick from 844 m to 560 m MD.
2008-04-09 | 00:00:00 | 02:45:00 | 561 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 238 m to 561 m MD. Running speed 30 sec per joint. Checked self filling of tubing - ok.
2008-04-09 | 02:45:00 | 03:15:00 | 561 | completion -- completion string | ok | Handover for short change of Mærsk crew. Held toolbox talk for continued operations. Greased PS-30 and elevator.
2008-03-17 | 21:30:00 | 23:45:00 | 564 | plug abandon -- mechanical plug | ok | RIH with the GTV plug on 5½" HWDP from 44m to 564m
2008-03-17 | 23:45:00 | 00:00:00 | 564 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
2008-03-18 | 00:00:00 | 01:45:00 | 564 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
2008-03-13 | 00:00:00 | 00:30:00 | 578 | drilling -- d rill | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 685 m to 578 m.
2008-03-13 | 00:30:00 | 01:30:00 | 578 | interruptio n -- maintain | ok | Observed yellow UFO flying/falling from derrick and out side/aft of derrick. Inspected PRS, derrick and drillfloor, but were not able to man-ride due to 50 knots wind. Nothing out of the ordi nary was found.
2008-04-07 | 12:30:00 | 14:00:00 | 578 | drilling -- casing | ok | Pulled 3 x 5 1/2" singles while pumping at 200 lpm. Swabbing stopped when plug entered 10 3/4" casing.
2008-04-06 | 19:15:00 | 21:45:00 | 580 | drilling -- casing | ok | Resumed operations. Continued to RIH with 9,567" drift from 245 m to 580 m MD.
2007-10-31 | 03:00:00 | 06:00:00 | 587 | drilling -- casing | ok | RIH with 9 5/8" csg from 416 to 587 m MD. Filled every joint with 1.40 sg mud using FAC tool.
2007-10-22 | 04:45:00 | 06:00:00 | 600 | drilling -- drill | ok | RIH with 12 1/4" drilling BHA from 135 m MD to 600 m MD.
2008-04-07 | 06:00:00 | 09:00:00 | 600 | drilling -- casing | ok | RIH with GTV pulling tool from 130 m to 600 m MD on 5 1/2" singles.
2008-03-18 | 06:00:00 | 07:00:00 | 610 | plug abandon -- mill | ok | Spotted 10m³ of hi-vis on top of GTV plug.
2008-04-07 | 11:15:00 | 12:00:00 | 610 | drilling -- casing | ok | Latched onto plug and confirmed by 10 MT overpull. No pressure observed on standpipe but slight gain in triptank indicating equlized plug. Rotated at 5 rpm righthand while holding 3 MT overpull, released plug with 10 turns, no gain observed. Pulled back 5 m and waited for elastomer element to relax.
2008-04-07 | 12:00:00 | 12:30:00 | 610 | drilling -- casing | ok | RIH with plug to 620 m MD to confirm released. Pulled 5 1/2" single and gained 0,2 m3 in trip tank due to swabbing plug.
2008-04-07 | 09:00:00 | 09:30:00 | 615 | drilling -- casing | ok | Tagged plug with 2 MT at 615 m MD.
2008-04-07 | 09:30:00 | 10:30:00 | 615 | drilling -- casing | ok | Pulled back 1 joint and made up DP to TDS. Displaced his-vis at 2400 lpm. Pumped a total of 37 m3 1,03 sg completion fluid.
2008-04-07 | 10:30:00 | 10:45:00 | 615 | drilling -- casing | ok | Held toolbox talk prior to releasing plug.
2008-04-07 | 10:45:00 | 11:15:00 | 615 | drilling -- casing | ok | Due to unsactisfactory cleanliness of completion fluid, pumped additional 26 m3 at 2400 lpm.
2008-03-18 | 01:45:00 | 02:30:00 | 616 | plug abandon -- mechanical plug | ok | RIH with the GTV plug on 5½" HWDP/DP from 564m to 616m.
2008-03-18 | 02:30:00 | 03:15:00 | 616 | plug abandon -- mechanical plug | ok | Broke out one double and made up TIW, pump in sub and 3m 5½" DP pup. Made up to TDS.
2008-03-18 | 03:15:00 | 03:30:00 | 616 | plug abandon -- mechanical plug | ok | Took up/down weight 98/91 MT. Set GTV plug at per Baker procedure. Bottom of the plug at 617m mid. element 614.5m, slips 615m and top of plug at 612m.
2008-03-18 | 03:30:00 | 04:45:00 | 617 | plug abandon -- mechanical plug | ok | Made 2" 1502 chiksan, flushed lines. Attempted to leak test line, found to much air in the system. Filled up system and leak tested line to TIW and IB OP 380 bars 5 min.
2008-03-18 | 04:45:00 | 05:30:00 | 617 | plug abandon -- mechanical plug | ok | Pressure tested the GTV plug from below to 380 bars 10 min., volume pumped 1.75m³ - 1.73m³ in return.
2008-03-18 | 05:30:00 | 06:00:00 | 617 | plug abandon -- mechanical plug | ok | Rigged down surface lines TIW, pump in sub and 5½" DP pup. Disengaged running tool from plug.
2008-03-10 | 04:30:00 | 06:00:00 | 671 | drilling -- casing | ok | Installed HTS back rollers. POOH and LO 7" liner in singles from 738 m to 671 m MD.
2008-03-12 | 23:00:00 | 00:00:00 | 685 | drilling -- drill | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 807 m to 685 m.
2008-03-03 | 03:00:00 | 06:00:00 | 693 | drilling -- ca sing | ok | RIH with spear assembly. Changed to 5 1/2" handling equipment and installed PS21 slips. RIH with spear assembly on 3 stands of 5 1/2" HWDP from 11 m to 129 m MD. RIH with spea r assembly on 5 1/2" DP from 129 m to 693 m MD.
2008-04-21 | 14:00:00 | 15:00:00 | 701 | interrupti on -- rig up/down | ok | RIH with 4.5" TCP guns on 7/16" electric line from surface to 701 m MD.
2008-03-01 | 23:30:00 | 00:00:00 | 720 | drilling -- trip | ok | LO 5 1/2" DP 24.7 lbs/ft in singles from 806 m to 720 m.
2008-02-25 | 16:30:00 | 17:45:00 | 734 | formation evaluation -- log | ok | RIH with MDT toolstring on 5" DP from 200 m to 734 m MD. Max running speed 2 min/stand.
2008-02-25 | 17:45:00 | 18:00:00 | 734 | formation evaluation -- log | ok | Broke circulation and brought pumps up to 1800 lpm for 5 mins.
2008-02-25 | 18:00:00 | 19:00:00 | 734 | formation evaluation -- log | ok | Installed 5" x 5 1/2" x-over. Changed to 5 1/2" handling equipment.
2008-02-27 | 16:00:00 | 20:00:00 | 734 | formation evalu ation -- log | ok | POOH with MDT toolstring on 5 1/2" DP from 2550 m to 734 m MD.
2008-02-27 | 20:00:00 | 20:15:00 | 734 | formation evalu ation -- log | ok | Changed handling equipment from 5 1/2" to 5". Broke out and laid down 4 1/2" IF x 5 1/2" FH x-over.
2008-02-28 | 18:15:00 | 00:00:00 | 734 | drilling -- casin g | ok | RIH with 7" liner from 289 m to 734 m MD, filling every 5th joint. Max running speed was 9 joints/hr.
2008-03-16 | 23:00:00 | 00:00:00 | 735 | completion -- circulating condi tioning | ok | Changed to 3½" handling equipment. Picked up one std of 3½" from the derrick, continued POOH with 3½" DP and laid out in singles from 770m to 735m.
2008-03-10 | 00:30:00 | 04:30:00 | 738 | drilling -- casing | ok | RIH with 7" liner stds from derrick to 738 m MD. Removed grub screws from top-most centralizer/stop collar on each std.
2008-04-09 | 03:15:00 | 06:00:00 | 750 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 561 m to 750 m MD. Reduced running speed to 1 min per joint in 9 5/8" casing. Checked self filling of tubing - ok.
2008-03-16 | 22:15:00 | 23:00:00 | 760 | completion -- circulating condi tioning | ok | Laid out the Razor back BHA #2.
2008-03-16 | 19:00:00 | 22:15:00 | 770 | completion -- circulating condi tioning | ok | Continued POOH with 5½" DP and wash string, from 2840m to 770m.
2008-03-14 | 15:45:00 | 17:45:00 | 776 | completion -- circulating conditioning | ok | RIH with 3½" mule shoe and Razor Back assy. From 32m to 776m.
2008-03-14 | 17:45:00 | 19:00:00 | 776 | completion -- circulating conditioning | ok | Held tool box talk and picked up Weaterford PBR polish mill.
2008-03-14 | 19:00:00 | 19:15:00 | 778 | completion -- circulating conditioning | ok | Held tool box talk prior to install the 9 5/8" clean out assy.
2008-02-20 | 06:00:00 | 15:15:00 | 780 | interruption -- fish | ok | Ran 5 1/2" DP singles over 7/48 wireline from 268 m to 780 m MD according to cut and thread procedure. Laid out singles #26 and #28 due to stuck protectors.
2008-02-20 | 15:15:00 | 19:00:00 | 780 | interruption -- fish | ok | Laid out 5 1/2" DP singles on pipedeck. Measured and drifted joints. Simultaneoulsy re-arranged stands in derrick.
2008-02-20 | 19:00:00 | 19:30:00 | 780 | interruption -- fish | ok | Held toolbox talk prior to continuing cut and thread.
2008-03-14 | 00:00:00 | 04:30:00 | 791 | drilling -- drill | ok | Pumped slug of 5.5m³ 1.66 SG. Continued POOH with 5½" DP and EZSV RT from 3252m to 791m.
2008-03-14 | 04:30:00 | 05:00:00 | 791 | drilling -- drill | ok | Held tool box talk prior to change over to 3½" surface handling equipment. Performed same.
2008-03-13 | 08:00:00 | 10:45:00 | 792 | drilling -- d rill | ok | Continued RIH with EZSV plug and Circ. Sub on 3½" DP from 42m to 792m at 2 min/std.
2008-03-13 | 10:45:00 | 11:30:00 | 792 | drilling -- o ther | ok | Held tool box talk and changed over to 5½" surface handling equipment.
2007-10-17 | 00:00:00 | 05:45:00 | 800 | drilling -- casin g | ok | Ran 13 3/8" casing from 380 m to 800 m MD. Filled casing with 1,40 sg WBM every 5th joint. Average running speed 6 joints/hr.
2007-10-17 | 05:45:00 | 06:00:00 | 800 | drilling -- casin g | ok | Rearranged catwalk machine to pick casing from fwd STB bay.
2008-03-12 | 00:00:00 | 02:00:00 | 804 | drilling -- drill | ok | RIH with 6" PDC bit and scraper assembly on 3 1/2" DP from 550 m to 804 m. Max running speed was 13 joints/hr.
2008-03-12 | 02:00:00 | 03:45:00 | 804 | drilling -- other | ok | Changed from 3 1/2" handling equipment to 5 1/2" handling equipment.
2008-03-01 | 22:15:00 | 23:30:00 | 806 | drilling -- trip | ok | RIH with 20 std 5 1/2" DP 24.7 lbs/ft from 443 to 806 m.
2008-03-12 | 16:30:00 | 21:15:00 | 807 | drilling -- drill | ok | Pumped slug and continued to POOH with 6" PDC bit and scraper assembly on 5 1/2" DP from 3228 m to 807 m.
2008-03-12 | 21:15:00 | 23:00:00 | 807 | drilling -- other | ok | Changed from 5 1/2" handling equipment to 3 1/2" handling equipment. Serviced foldable fingerboard.
2008-03-12 | 21:15:00 | 23:00:00 | 807 | drilling -- other | ok | Meanwhile flow checked well static. Ok.
2008-03-08 | 00:00:00 | 06:00:00 | 812 | drilling -- casin g | ok | RIH with 7" liner from 434 m to 812 m MD, filling every 5th joint. Cleaned and re-doped pin end. Max running speed was 6 joints/hr.
2008-03-08 | 00:00:00 | 06:00:00 | 812 | drilling -- casin g | ok | LO joint #139 and changed out box on joint #140. Replaced joint #139 with joint #115.
2008-03-14 | 19:15:00 | 20:00:00 | 831 | completion -- circulating conditioning | ok | Changed to 5½" DP handling equipment. Installed the 9 5/8" clean out assy.
2008-03-14 | 20:00:00 | 20:30:00 | 831 | completion -- circulating conditioning | ok | Made up to TDS and broke circulation with 1000 lpm 72 bars. Installed PS-21 slips. Observed hydraulic leak in Aft PRS.
2008-03-14 | 20:30:00 | 21:30:00 | 831 | interruption -- other | ok | Repaired hydraulic leak on Aft PRS.
2008-04-09 | 06:00:00 | 06:45:00 | 834 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 750 m to 834 m MD.
2008-04-09 | 06:45:00 | 08:00:00 | 834 | completion -- completion string | ok | Bad make up on joint #189, laid out same. Broke out box on joint #190. Inspected pin and made up new box on joint #190. Moved mobile cherry picker to aft part of drillfloor for use on aft PRS.
2008-03-08 | 06:00:00 | 07:00:00 | 835 | drilling -- casin g | ok | RIH with 7" liner from 434 m to 812 m MD, filling every 5th joint. Cleaned and re-doped pin end. Filled liner completely before picking up hanger assembly.
2008-02-29 | 00:00:00 | 01:30:00 | 842 | drilling -- casing | ok | RIH with 7" liner from 734 m to 842 m MD, filling every 5th joint. Max running speed was 5 joints/hr. Filled liner completely before picking up hanger assembly.
2008-03-04 | 19:45:00 | 20:15:00 | 844 | drilling -- casing | ok | LO liner hanger.
2008-02-29 | 01:30:00 | 03:30:00 | 850 | drilling -- casing | ok | Changed to 5½" DP elevators. P/U hanger/TSP packer assembly and MU same as per Weatherford procedure. Removed 7" FMS slips, installed master bushing. Filled PBR with Hi-visc mud. Took up/down weight 105/95 MT.
2008-02-29 | 03:30:00 | 05:30:00 | 850 | drilling -- casing | ok | RD Odfjell csg tong. Removed HTS rollers. Cleared and cleaned rig floor.
2008-03-08 | 07:00:00 | 08:45:00 | 850 | drilling -- casin g | ok | Changed to 5½" DP elevators. P/U hanger/TSP packer assembly and MU same as per Weatherford procedure. Removed 7" FMS slips, installed master bushing. Filled PBR w ith drillwater and checked shear pins. Took up/down weight 105/95 MT.
2008-03-08 | 08:45:00 | 10:15:00 | 850 | drilling -- casin g | ok | RD Odfjell csg tong. Removed HTS rollers. BO XO on HWDP and drifted same. Cleared and cleaned rig floor.
2008-03-04 | 14:45:00 | 17:45:00 | 852 | drilling -- casing | ok | LO bumper sub. Held pre-job meeting and SJA. Released spear and LO same.
2008-03-04 | 17:45:00 | 19:45:00 | 852 | drilling -- casing | ok | Held tool box talk with involved personnel. RU Odfjell csg tong with low marking dies and csg handling equipment.
2008-02-29 | 05:30:00 | 06:00:00 | 860 | drilling -- casing | ok | PU 1 std of 5 1/2" HWDP. Changed to PS21 slips. RIH with 7" liner hanger on 5 1/2" HWDP from 850 m to 860 m MD.
2007-10-14 | 06:00:00 | 16:15:00 | 866 | drilling -- d rill | ok | Drilled 17 1/2" hole section from 560 m to 866 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3500-4500 lpm / SPP 90-145 bar / 100 RPM / WOB 5-10 MT / Torque 6-9 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 10 m3 Hi-vis per stand. Reamed one single per stand. Average ROP 30 m/hrs.
2007-10-14 | 16:15:00 | 17:15:00 | 866 | drilling -- d rill | ok | Prepared for driling Utsira formation at 866 m MD. Reamed full stand once. Circulated 1,5 x bottoms up at 4500 lpm. Inclination before entering Utsira was 16,6 deg.
2008-03-04 | 06:00:00 | 14:45:00 | 867 | drilling -- casing | ok | POOH with 7" liner on spear assembly from 2716 m to 867 m MD.
2008-03-04 | 06:00:00 | 14:45:00 | 867 | drilling -- casing | ok | Spaced out inside BOP. Flow checked for 15 min on last joint of 5 1/2" DP. Changed out PS21 with master bushing before POOH with 2 stds of 5 1/2" HWDP.
2008-02-29 | 06:00:00 | 07:15:00 | 925 | drilling -- casing | ok | RIH with 7" liner hanger on 5 1/2" HWDP from 860 m to 925 m MD.
2008-02-29 | 07:15:00 | 09:15:00 | 925 | interruption -- oth er | ok | Changed out 2 stds of 5 1/2" HWDP with 5 1/2" DP.
2008-03-07 | 05:00:00 | 06:00:00 | 928 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5" DP from 1500 m to 928 m MD.
2008-02-08 | 11:00:00 | 13:15:00 | 937 | drilling -- drill | ok | RIH with 8½" drill BHA on 5" DP, from surface to 937m.
2008-02-08 | 13:15:00 | 13:30:00 | 937 | drilling -- drill | ok | Changed over to 5½" handling equipment.
2008-02-08 | 13:30:00 | 13:45:00 | 937 | drilling -- drill | ok | M/U to TDS and tested the MWD at 1500 lpm 138 bars.
2008-03-08 | 10:15:00 | 11:30:00 | 963 | drilling -- casin g | ok | PU 1 std of 5 1/2" HWDP. Changed to PS21 slips. RIH with 7" liner hanger on 5 1/2" HWDP from 850 m to 963 m MD.
2008-04-09 | 08:00:00 | 10:00:00 | 963 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 834 m to 963 m MD.
2008-04-09 | 10:00:00 | 10:45:00 | 963 | completion -- completion string | ok | Bad make up on joint #177, laid out same. Broke out box on joint #178. Inspected pin and made up new box on joint #178.
2007-10-22 | 06:00:00 | 07:15:00 | 1000 | drilling -- drill | ok | Ran in hole with 12 1/4" drilling BHA from 600 m to 1000 m MD. Inspected slips on PRS.
2007-10-22 | 07:15:00 | 07:30:00 | 1000 | drilling -- drill | ok | Held toolbox talk prior to routing SW returns overboard.
2007-10-22 | 07:30:00 | 08:15:00 | 1000 | drilling -- drill | ok | Established circulation rate at 1500 lpm. Tested MWD according to Schlumberger procedure - ok.
2008-03-05 | 11:30:00 | 16:00:00 | 1010 | drilling -- casing | ok | RIH with 8 1/2" wiper trip BHA on 5" DP from 75 m to 1010 m MD.
2008-03-05 | 11:30:00 | 16:00:00 | 1010 | drilling -- casing | ok | Held time-out for safety due to dropped pin from fwd PRS dragchain. Highlighted "red zone" policy.
2008-03-05 | 16:00:00 | 17:15:00 | 1010 | drilling -- casing | ok | MU TDS and tested MWD, 2000 lpm / 146 bar. Changed mud pumps and stand pipes to optimize signal from MWD.
2007-10-14 | 23:00:00 | 00:00:00 | 1077 | drilling -- d rill | ok | Observed negative drilling brake indicating base Utsira encontered at 1077 m MD. Drilled 17 1/2" hole section from 1077 to 1107 m MD. Inclination on base Utsira 12,3 deg.
2008-02-20 | 19:30:00 | 00:00:00 | 1090 | interruption -- fish | ok | Continued running 5 1/2" DP singles over 7/48 wireline from 780 m to 1090 m MD according to cut and thread procedure. Checked wireline and TDS top in coupling for wear every 25 joints.
2007-10-14 | 17:15:00 | 23:00:00 | 1107 | drilling -- d rill | ok | Drilled 17 1/2" hole section from 866 to 1107 m MD. Top Utsira encountered at 890 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3100 lpm / SPP 90-1 00 bar / 100 RPM / WOB 5-12 MT / Torque 4-7 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 15 m3 Hi-vis per stand. Average ROP 37 m/hrs.
2007-10-17 | 06:00:00 | 11:30:00 | 1198 | drilling -- casin g | ok | Ran 13 3/8" casing from 800 m to 1198 m MD. Filled casing with 1,40 sg WBM every 5th joint. Average running speed 6 joints/hr.
2007-10-17 | 11:30:00 | 11:45:00 | 1198 | drilling -- casin g | ok | Held toolbox talk prior to rigging down casing running equipment.
2007-10-17 | 11:45:00 | 14:30:00 | 1198 | drilling -- casin g | ok | Removed PS-30 slips and installed master bushing. Removed 500T slip elevator. Removed FAC circulation tool. Removed casing bails and installed drilling bails and 5 1/2" el evator.
2007-10-17 | 14:30:00 | 14:45:00 | 1198 | drilling -- casin g | ok | Held toolbox talk prior to picking up 13 3/8" x 18 3/4" subsea wellhead.
2007-10-15 | 00:00:00 | 04:15:00 | 1200 | drilling -- drill | ok | Drilled 17 1/2" hole section from 1107 to 1200 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3800 lpm / SPP 110-120 bar / 100 RPM / WOB 6-1 0 MT / Torque 6-8 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 10 m3 Hi-vis per stand. Average ROP 22 m/hrs.
2007-10-15 | 04:15:00 | 05:45:00 | 1200 | drilling -- drill | ok | Prepared for drilling Skade formation at 1200 m MD. Reamed on singel 5 m off bottom. Circulated 1,5 x bottoms up at 4500 lpm. Inclination before entering Skade formation 16,3 d eg.
2007-10-15 | 05:45:00 | 06:00:00 | 1202 | drilling -- drill | ok | Drilled 17 1/2" hole section from 1200 to 1202 m MD.
2007-10-17 | 14:45:00 | 15:30:00 | 1214 | drilling -- casin g | ok | Picked up 13 3/8" x 18 3/4" subsea wellhead and made up to 13 3/8" casing. Ran in with casing and well head to 1214 m MD and hung off in rotary.
2007-10-17 | 15:30:00 | 15:45:00 | 1214 | drilling -- casin g | ok | Held toolbox talk prior to removing casing tong.
2007-10-17 | 15:45:00 | 16:30:00 | 1214 | drilling -- casin g | ok | Rigged down casing tong and panels and removed from drillfloor.
2007-10-22 | 08:15:00 | 09:15:00 | 1300 | drilling -- drill | ok | Ran in hole with 12 1/4" drilling BHA from 1000 m to 1300 m MD. Performed kick drill.
2007-10-29 | 06:00:00 | 12:15:00 | 1330 | drilling -- drill | ok | POOH with 12 1/4" BHA from 2525 m to 1330 m MD. No overpull observed. No obstruction met pulling into 13 3/8" csg shoe. Performed gyro survey on each stand. Oriented string to confirm toolface every 300 m as instructed by Gyro data. Corrected ZMS interlock fault on aft PRS.
2007-10-29 | 12:15:00 | 13:15:00 | 1330 | drilling -- drill | ok | Function tested BOP while circulated through choke and kill lines at 13 3/8" csg shoe. Serviced TDS. Flow checked before POOH with 12 1/4" BHA in casing.
2008-02-16 | 00:45:00 | 03:15:00 | 1331 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5 1/2" DP from 2754 m to 1331 m MD.
2008-02-16 | 03:15:00 | 04:00:00 | 1331 | drilling -- trip | ok | Broke out x-over. Changed from 5 1/2" to 5" handling equipment. Re-inserted 2 3/4" drift into 5" DP as it would not pass the x-over.
2008-04-09 | 15:00:00 | 16:15:00 | 1333 | completion -- completion string | ok | Not able to make up joint #146, laid out same. Inspected box - negative. Laid out joint 145.
2007-10-22 | 09:15:00 | 09:30:00 | 1336.5 | drilling -- drill | ok | Made up TDS and washed down from 1300 m. Tagged cement at 1336,5 with 1500 lpm / SPP 54 bar. Took up/down weights 135/115 MT.
2007-10-22 | 09:30:00 | 10:30:00 | 1336.5 | drilling -- drill | ok | Conducted choke drill.
2007-10-25 | 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | Waiting on Siemens software update. Meanwhile:
2007-10-25 | 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | - Flow checked well before POOH (static).
2007-10-25 | 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | - POOH from 1750 m to 1530 m. Up weight 140 MT / Down weight 124 MT. Monitored well on trip tank at 1530 m. Ok.
2007-10-25 | 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | - POOH from 1530 to inside csg shoe at 1340 m MD.
2007-10-25 | 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | - Continued with PMs and housekeeping/cleaning.
2007-10-25 | 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | - Continued injecting cuttings into F-12 and flushed with 2 x annulus volumes of water.
2007-10-25 | 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | - Repaired Barite hopper B.
2007-10-26 | 00:00:00 | 00:30:00 | 1340 | drilling -- wait | ok | Waiting on Siemens software update.
2007-10-23 | 21:30:00 | 00:00:00 | 1343 | interruption -- ot her | ok | Installed mud bucket. Pulled 12 1/4" drilling BHA from 1585 m MD to 1343 m MD.
2007-10-17 | 16:30:00 | 17:15:00 | 1345 | drilling -- casin g | ok | Ran in hole with casing and wellhead on 5 1/2" HWDP landing string from 1214 m to 1345 m MD. Circulated last stand down with 500 lpm.
2007-10-17 | 17:15:00 | 18:00:00 | 1345 | drilling -- casin g | ok | Picked up cement head with premade pup joint and made up same to landing string and TDS. Took up/down weights 219/144 MT. Broke circulation with 500 lpm and landed 18 3/4" subsea wellhead in 30" conductor housing according to Vetco instructions.
2008-04-09 | 10:45:00 | 15:00:00 | 1345 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 963 m to 1345 m MD.
2007-10-22 | 10:30:00 | 19:00:00 | 1348 | drilling -- drill | ok | Drilled 13 3/8" shoetrack from 1336,5 m to 1348 m MD with seawater. Drilling parameters : Flow 2500 lpm / SPP 50-65 bar / 30-50 RPM / WOB 2-10 MT / Torque 10-27 kNm. Pu mped hi-vis sweeps .
2007-10-22 | 19:00:00 | 21:45:00 | 1350 | drilling -- circulati ng conditioning | ok | Drilled shoetrack from 1348 m to 1350 m MD. Meanwhile held pre-job meeting before displacing well to 1,40 OBM. Emptied slurry holding tank into pit #1 and #5 to obtain more b uffer for cuttings slurry. Pumped hi-vis .Displaced well from seawater to 110 m3 1,40 OBM. Stopped pumping when OBM interface at surface.
2007-10-22 | 21:45:00 | 22:45:00 | 1350 | drilling -- circulati ng conditioning | ok | Pumped 5 m3 seawter/OBM interface to pit #5. Pumped treatable interface of 10 m3 to pit #14. Filled sandtraps and shaker pits with 1,40 sg OBM. Total active volume 185 m3.
2007-10-23 | 03:30:00 | 04:30:00 | 1350 | formation evalu ation -- rft/fit | ok | Pulled bit inside casing shoe at 1350 m MD. Lined up for FIT test to pump down pipe and annulus. Closed annular. Pressured up to 7 bar to fill standpipe and kill line and observed r apid increase in pressure / curve deflection. Pumped 121 liter up to 17 bar. Pressure fell to 13 bar over 15 min, steady leakage rate. Bled back 50 liter.
2007-10-23 | 04:30:00 | 06:00:00 | 1350 | formation evalu ation -- rft/fit | ok | Discussed quality of FIT. Down linked MWD for ESD, got ESD figure of 1,37 sg. Decided to line up for new FIT. Circulated and lined up for new FIT.
2007-10-23 | 06:00:00 | 07:30:00 | 1350 | drilling -- circula ting conditioning | ok | Circulated on well at 3500 lpm to obtain even MW in/out. Leak tested kill line to HCR to 20 bar-ok. Obtained 1,39 sg MW in/out. Racked back 1 stand.
2007-10-23 | 07:30:00 | 08:30:00 | 1350 | formation evalu ation -- rft/fit | ok | Lined up for FIT. Reset pressure to zero bar. Pressured up to 6,5 bar at 50 lpm to fill standpipe and kill line and observed rapid increase in pressure /curve deflection. Continued pum ping at 50 lpm up to FIT pressure of 18 bar. Pumped 100 liter up to 18 bar / 1,53 EMW. Pressure fell to 13 bar after 15 mins with steady leakage rate. Bled back 50 liter.
2007-10-17 | 18:00:00 | 19:45:00 | 1351 | drilling -- casin g | ok | Circulated and condtioned well before cementing. Pumped at 2300 lpm. Standpipe pressure decreased from 37 bar to 20 bar after 200 m3 pumped. Prepared for pumping ce ment. Observed problem with mudpumps.
2007-10-17 | 19:45:00 | 20:45:00 | 1351 | interruption -- o ther | ok | Inspected mudpump#1 and revealed that swab and liner needed to be changed. Questioned if mudpump #3 was ready for operation. Tested mudpump #3 and approved for o peration.
2007-10-17 | 20:45:00 | 23:45:00 | 1351 | drilling -- casin g | ok | Dropped ball to activate lower wiper plug. Mixed and pumped 126 m3 1,56 sg lead cement followed by 20 m3 1,92 sg tail cement. Pump rate 800 to 1200 lpm / pumping press ure 20 bar. Displaced cement line with 890 liter seawater.
2007-10-17 | 23:45:00 | 00:00:00 | 1351 | drilling -- casin g | ok | Released dart in cement head. Pumped 3 m3 seawater with cement unit at 1200 lpm. After pumping approx 1 m3, observed shear of upper wiper plug by 120 bar pressure pe ak. Closed lo-torque on cement head and lined up to pump with mudpumps.
2007-10-18 | 00:00:00 | 01:00:00 | 1351 | drilling -- casin g | ok | Displaced cement with 89,5 m3 / 4080 strokes seawater at 3000 lpm. Slowed down to 1200 lpm / SPP 70 bar prior to bumping plug. Bumped plug with 140 bar and held pressure for 1 0 min - ok. Lined back to cement unit and bled back 940 liter before returns stopped.
2007-10-18 | 01:00:00 | 02:30:00 | 1351 | drilling -- casin g | ok | Disconnected cement line. Released CART with 5 righthand turns according to Vetco instructions. Broke out and laid down cement head with pup. Put in two sponges to clean pipe.
2007-10-22 | 22:45:00 | 00:00:00 | 1351.5 | drilling -- drill | ok | Drilled shoetrack from 1350 m to 1351,5 m MD. Drilling parameters : Flow 2600 lpm / SPP 101 bar / 60 RPM / WOB 5 MT / Torque 6-7 kNm. Hard to make progress at 1351,5 m MD.
2007-10-23 | 00:00:00 | 00:30:00 | 1352 | drilling -- drill | ok | Continued drilling on shoe, hard to make progress. Reduced RPM to 40 and reduced flow to 2200 lpm. Increased WOB steadily from 5 to 7 MT and broke through shoe.
2007-10-15 | 06:00:00 | 11:30:00 | 1360 | drilling -- drill | ok | Drilled 17 1/2" hole from 1202 m MD to TD at 1360 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3100-4500 lpm / SPP 120-165 bar / 100 RPM
2007-10-15 | 06:00:00 | 11:30:00 | 1360 | drilling -- drill | ok | / WOB 6-10 MT / Torque 8-9 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 10 m3 Hi-vis per stand. Average ROP 30 m/hrs.
2007-10-15 | 11:30:00 | 14:15:00 | 1360 | drilling -- circulat ing conditioning | ok | Cleaned hole on TD. Pumped sweeps of 30 m3 hi-vis, 30 m3 seawater and 30 m3 hi-vis. Pumped 3 x bottoms up at 4500 lpm / SPP 150 bar. String RPM 60. Reciprocated full stan d while pumping.
2007-10-15 | 14:15:00 | 15:15:00 | 1360 | drilling -- circulat ing conditioning | ok | Displaced 17 1/2" hole section to 1,40 sg WBM at 4500 lpm / SSP 135-200 bar. Reciprocated full stand while pumping. Pumped a total of 225 m3 1,40 sg WBM.
2007-10-23 | 00:30:00 | 02:00:00 | 1360 | drilling -- drill | ok | Drilled rathole, reamead back to shoe for every 2 m drilled. Flow 2600 lpm / SPP 101 bar / 60 RPM / WOB 5 MT / Torque 6-7 kNm.
2007-10-23 | 02:00:00 | 03:30:00 | 1363 | drilling -- drill | ok | Drilled 3 m new formation prior to FIT. Circulated well to obtain even MW in and out ; 1,39 sg heavy in/out. Used 1,395 sg for FIT calculation.
2007-10-23 | 08:30:00 | 09:45:00 | 1365 | drilling -- drill | ok | Stepped up pumps and RPM. Drilled 2 m of new formation. Took surveys and downlinked tools according to Schlumberger instruction. Downlinked and set powerdrive according to DD instructions.
2008-04-09 | 16:15:00 | 17:45:00 | 1434 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 1333 m to 1434 m MD.
2008-04-09 | 17:45:00 | 18:00:00 | 1434 | completion -- completion string | ok | Inspected threads on joint #134 - negative - laid out joint.
2008-02-21 | 00:00:00 | 04:15:00 | 1438 | interruption -- fish | ok | Ran 5 1/2" DP singles over 7/48 wireline from 1090 m to 1438 m MD according to cut and thread procedure.
2008-02-21 | 04:15:00 | 06:00:00 | 1438 | interruption -- fish | ok | Laid out 5 1/2" DP singles on pipedeck. Measured and drifted joints. Moved weight bars on winch side of wiereline in order to move stress points. Checked rope socket - ok.
2008-02-21 | 06:00:00 | 10:30:00 | 1438 | interruption -- fish | ok | Laid out 5 1/2" singles on pipedeck. Cleaned and checked threads. Measured and drifted joints.
2008-02-21 | 10:30:00 | 10:45:00 | 1438 | interruption -- fish | ok | Held toolbox talk prior to continuing cut and thread operation.
2008-04-09 | 18:00:00 | 18:30:00 | 1455 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 1434 m to 1455 m MD.
2008-04-09 | 18:30:00 | 19:45:00 | 1455 | completion -- completion string | ok | Inspected threads on joint #129 - negative - laid out joint. Mærsk crew change and toolbox talk.
2008-02-21 | 10:45:00 | 11:45:00 | 1500 | interruption -- fish | ok | Ran 5 1/2" singles over 7/48 wireline from 1438 m to 1500 m MD.
2008-02-21 | 11:45:00 | 12:45:00 | 1500 | interruption -- fish | ok | Wireline caught up behind AFT PRS arm. Removed wire and checked for damage - ok.
2008-03-07 | 01:30:00 | 04:30:00 | 1500 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5 1/2" DP from 2748 m to 1500 m MD.
2008-03-07 | 01:30:00 | 04:30:00 | 1500 | drilling -- casing | ok | Torque reading at 7" liner hanger setting depth: 10 rpm / 6-8 kNm, 15 rpm / 6-9 kNm, 20 rpm / 6-9 kNm. At 7" liner hanger setting depth; up weight 147 MT / down weight 125 MT.
2008-03-07 | 04:30:00 | 05:00:00 | 1500 | drilling -- casing | ok | Changed to 5" handling equipment.
2008-03-05 | 17:15:00 | 19:00:00 | 1501 | drilling -- casing | ok | RIH with 8 1/2" wiper trip BHA on 5" DP from 1010 m to 1501 m MD.
2008-03-05 | 19:00:00 | 19:30:00 | 1501 | drilling -- casing | ok | Held time-out for safety due to dropped pin from fwd PRS dragchain. Highlighted "red zone" policy.
2008-03-05 | 19:30:00 | 21:30:00 | 1501 | drilling -- casing | ok | Inspected aft PRS dies. Moved 5 1/2" HWDP from finger board. Installed totco ring in 5" DP. Changed to 5 1/2" handling equipment and installed X-over
2008-03-05 | 19:30:00 | 21:30:00 | 1501 | drilling -- casing | ok | .
2008-03-01 | 06:00:00 | 09:30:00 | 1520 | drilling -- casi ng | ok | POOH with 7" liner hanger RT on 5 1/2" DP from 3340 m to 1520 m MD.
2008-03-01 | 09:30:00 | 10:30:00 | 1520 | interruption -- waiting on we ather | ok | Stopped POOH due to 65 knots wind. Installed TIW and monitored well on trip tank. Performed wind checks.
2007-10-23 | 09:45:00 | 17:30:00 | 1544 | drilling -- drill | ok | Drilled 12 1/4" section from 1365 m to 1544 m MD. Drilling paramters : Flow 3500 lpm / SPP 171-178 bar / 130-170 RPM / WOB 2-4 MT / Torque 1-4 kNm. Average ROP 23 m/hrs. Reamed 1 single before connection. Took SCRs at 1504 m MD.
2007-10-23 | 17:30:00 | 18:00:00 | 1544 | drilling -- drill | ok | Inspected TDS due to excessive noise. Found worn area on upper IBOP actuator sleeve.
2007-10-31 | 06:00:00 | 00:00:00 | 1550 | drilling -- casing | ok | RIH with 9 5/8" csg from 587 to 1550 m MD. Filled every joint with 1.40 sg mud using FAC tool. LO 3 jnts. Running speed 4-7 jnts/hr
2007-10-31 | 06:00:00 | 00:00:00 | 1550 | drilling -- casing | ok | .
2007-10-24 | 17:15:00 | 17:45:00 | 1584 | drilling -- dr ill | ok | Took MWD survey. Stepped up pump and rotation to obtain drilling parameters. Standpipe pressure fell rapidly when reaching 130 bar. Unclear indications. Attempted to pump and obser ved that pop off valve had triggered. Mud returns from pop off ventline went down to pit #15 which overflowed pit and pit room. Halted operation.
2007-10-23 | 18:00:00 | 19:15:00 | 1585 | drilling -- drill | ok | Drilled 1 stand from 1544 m to 1584 m MD while observing / monitoring upper IBOP actuator sleeve. Halted operations for troubleshooting.
2007-10-23 | 19:15:00 | 21:15:00 | 1585 | interruption -- ot her | ok | Decided to pull 12 1/4" drilling BHA into casing shoe for TDS repair. Circulated hole clean with 2-3 bottoms up at 3500 lpm.
2007-10-23 | 21:15:00 | 21:30:00 | 1585 | interruption -- ot her | ok | Flowchecked well for 15 min - well static.
2008-02-21 | 12:45:00 | 14:15:00 | 1640 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1500 m to 1640 m MD.
2008-02-21 | 14:15:00 | 15:45:00 | 1640 | interruption -- fish | ok | Cut back winch side of wireline. Re-built rope socket and fitted spearhead and new weights.
2007-10-24 | 20:00:00 | 23:00:00 | 1640.5 | drilling -- dr ill | ok | Drilled 12 1/4" section from 1585 m to 1640,5 m MD. Drilling parameters : Flow 3500 lpm / SPP 180 bar / 130-170 RPM / WOB 2-3 MT / Torque 10-12 kNm. Average ROP 19 m/hrs. Re amed 1 single before connection. Not able to handle cuttings return from well.
2007-10-25 | 00:30:00 | 06:00:00 | 1706 | drilling -- dr ill | ok | Drilled 12 1/4" section from 1640,5 m to 1706 m MD. Drilling parameters : Flow 3500 lpm / SPP 180 bar / 130-170 RPM / WOB 0-2 MT / Torque 10-12 kNm / ECD 1,42. Average ROP 1 2 m/hrs. Drilled with reduced ROP when going directly to skips. Worked to bring down vicosity in DCI milltank/active before injecting slurry.
2008-04-09 | 19:45:00 | 00:00:00 | 1743 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 1455 m to 1743 m MD.
2007-10-25 | 06:00:00 | 09:00:00 | 1750 | drilling -- dr ill | ok | Drilled 12 1/4" section from 1706 m to 1750 m MD. Drilling parameters : Flow 3500 lpm / SPP 180 bar / 170 RPM / WOB 2-3 MT / Torque 8-12 kNm / ECD 1,42. Average ROP 12 m/hrs. Drilled with reduced ROP when going directly to skips. Worked to bring down vicosity in DCI milltank/active before injecting slurry. Changed out cooling water on MP2.
2007-10-26 | 00:30:00 | 03:30:00 | 1750 | drilling -- wait | ok | Removed TIW valve. RIH with 12 1/4" drilling BHA from 1340 m to 1706 m MD. Made up TDS and washed down from 1706 m to 1750 m MD with 2500 lpm / 98 bar. Took up/down weight 14 3/121 MT.
2007-10-26 | 03:30:00 | 04:00:00 | 1750 | drilling -- drill | ok | Established parameters and downlinked tool as per DD's instruction.
2008-02-21 | 15:45:00 | 18:00:00 | 1750 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1640 m to 1750 m MD. Observed hydraulic leakage from TDS.
2008-02-21 | 18:00:00 | 18:30:00 | 1750 | interruption -- other | ok | Repaired hydraulic leakage on TDS.
2007-10-26 | 04:00:00 | 06:00:00 | 1787 | drilling -- drill | ok | Drilled 12 1/4" section from 1750 m to 1787 m MD. Drilling parameters : Flow 3500 lpm / SPP 187 bar / 170 RPM / WOB 2-3 MT / Torque 9-14 kNm / ECD 1,43. Average ROP 25 m/hrs. Re amed 1 single before connection. Down linked and performed surveys as required.
2008-02-21 | 18:30:00 | 21:15:00 | 1850 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1750 m to planned side entry sub depth of 1850 m MD.
2008-02-21 | 21:15:00 | 22:30:00 | 1850 | interruption -- fish | ok | Held toolbox talk for installing side entry sub. Assessed weather conditions and forecast. High winds > 40 knots and unfavorable forecast. Not able to perform riding belt operations required to re-position upper sheave wheel. Decided to continue running 5 1/2" DP singels over wireline to shoe depth.
2007-11-01 | 00:00:00 | 06:00:00 | 1858 | drilling -- casing | ok | RIH with 9 5/8" csg from 1550 to 1858 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr.
2008-04-10 | 00:00:00 | 01:45:00 | 1938 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing from 1743 m to 1938 m MD.
2008-04-10 | 01:45:00 | 02:30:00 | 1938 | completion -- c ompletion strin g | ok | Bad make up on joint #90, laid out same. Washed and inspected threads on pipedeck. Applied API mod lubeseal dope to pin ends on pipedeck.
2008-03-12 | 03:45:00 | 06:00:00 | 1977 | drilling -- drill | ok | RIH with 6" PDC bit and scraper assembly on 5 1/2" DP from 804 m to 1977 m.
2008-02-21 | 22:30:00 | 00:00:00 | 1989 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1750 m to 1989 m MD.
2016-10-05 | 00:00:00 | 00:30:00 | 2049 | plug abandon -- other | ok | Pulled and L/D the remaining 5x joints of 7in tubing. Average pulling speed 7joints/hour. Totally pulled 45x joints and DHSV assy
2016-10-05 | 00:30:00 | 00:45:00 | 2049 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to M/U swedge
2016-10-05 | 00:45:00 | 01:15:00 | 2049 | plug abandon -- cement plu g | ok | M/U swedge assembly w/ casing tong
2016-10-05 | 01:15:00 | 03:00:00 | 2049 | plug abandon -- other | ok | Removed control line drum. Moved casing tong. Broke off swedge from FOSV. Install 5,5in inserts in BX elevator. M/U 1x std of 5,5in DP. Removed casing slips and installed DP slips. Clear ed rig floor
2016-10-05 | 03:00:00 | 03:30:00 | 2049 | plug abandon -- cement plu g | ok | RIH w/ 7in tubing on 5,5in DP from 2049m to 2291. Average RIH speed 485m/hour
2016-10-05 | 14:45:00 | 15:15:00 | 2049 | plug abandon -- cement plu g | ok | R/U casing tong and broke off swedge from top of tubing string. Meanwhile WOC
2016-10-05 | 15:15:00 | 15:45:00 | 2049 | plug abandon -- cement plu g | ok | R/D casing tong. Meanwhile WOC
2016-10-05 | 12:15:00 | 14:15:00 | 2052 | plug abandon -- other | ok | Installed pipe deck rollers. POOH and L/D singles of 5,5in DP from 2372m to 2052m. Meanwhile WOC
2016-10-05 | 14:15:00 | 14:30:00 | 2052 | plug abandon -- cement plu g | ok | Removed DP slips and installed master bushing. Meanwhile WOC
2016-10-05 | 14:30:00 | 14:45:00 | 2052 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to R/U casing tong. Meanwhile WOC
2008-03-14 | 21:30:00 | 00:00:00 | 2080 | completion -- circulating conditioning | ok | Continued RIH with clean out assy. from 831m to 2080m
2016-10-05 | 15:45:00 | 16:00:00 | 2084 | plug abandon -- cement plu g | ok | P/U spear BHA, set in catch position and engaged into tubing string, RIH to 2084m. Meanwhile WOC
2016-10-04 | 19:30:00 | 00:00:00 | 2109 | plug aba ndon -- o ther | ok | Pull and L/D 7in tubing from 2573m to 2109m, spooled control line. Pulled and L/D DHSV assembly. Average pulling speed 8,5 joints/hour. Totally pulled 39joints and DHSV assy
2008-03-05 | 21:30:00 | 00:00:00 | 2146 | drilling -- casing | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 1501 m to 2146 m MD. Filled pipe every 10 stds.
2007-11-01 | 06:00:00 | 10:45:00 | 2151 | drilling -- casing | ok | RIH with 9 5/8" csg from 1858 to 2151 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr.
2007-11-01 | 10:45:00 | 13:15:00 | 2151 | drilling -- casing | ok | PU and installed 9 5/8" x 10 3/4" XO. Changed to 10 3/4" inserts in elevator and slips.
2008-04-10 | 02:30:00 | 05:15:00 | 2164 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing from 1938 m to 2164 m MD.
2008-04-10 | 05:15:00 | 05:30:00 | 2164 | completion -- c ompletion strin g | ok | Held toolbox talk prior to picking up completion assy#3 DHSV. Counted joints left on deck 84 - ok.
2008-04-10 | 05:30:00 | 06:00:00 | 2164 | completion -- c ompletion strin g | ok | Picked up completion assy#3 DHSV. Made up completion assy#3 and ran through RT. Isolated pipe guides on PS-30 slips.
2008-04-10 | 06:00:00 | 08:00:00 | 2164 | completion -- te st scsssv | ok | PU and installed one tubing joint above TRSCSSV assembly. Flushed control line. Connected control line to TRSCSSV and leak tested to 570 bar/10 min. Bled pressure down to zer
2008-04-10 | 06:00:00 | 08:00:00 | 2164 | completion -- te st scsssv | ok | o. Checked slips alignement. Made guide arrangement for control line from tubing to CL drum. Pressured up control line to 420 bar to keep TRSCSSV open while RIH.
2007-10-26 | 06:00:00 | 00:00:00 | 2178 | drilling -- drill | ok | Drilled 12 1/4" section from 1787 m to 2178 m MD. Drilling parameters : Flow 3500 lpm / SPP 186-194 bar / 170 RPM / WOB 0-5 MT / Torque 11-13 kNm / ECD 1,43-1,44. Average ROP 35 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Observed erratic data on Resestivity log from 2030 mMD (2010 mMD sencor depth). Resistivity sensor non-functional from 2010 mMD at 18:00 hrs. Cuttings return routed to skips due to slurry transfer pump is out of operation.
2007-10-27 | 00:00:00 | 03:00:00 | 2230 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2178 m to 2230 m MD. Drilling parameters : Flow 3500 lpm / SPP 194-197 bar / 170 RPM / WOB 2-7 MT / Torque 13-15 kNm / ECD 1,44. Average ROP 35 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Cuttings return routed to skips due to slurry transfer pump is out of operation.
2008-02-25 | 19:00:00 | 00:00:00 | 2267 | formation evaluation -- log | ok | RIH with MDT toolstring from 734 m to 2267 m MD on 5 1/2" DP. Max running speed 2 min/stand. Circulated 500 lpm / 3 mins every 500 m.
2007-10-27 | 03:30:00 | 06:00:00 | 2275 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2230 m to 2275 m MD. Drilling parameters : Flow 3500 lpm / SPP 197 bar / 170 RPM / WOB 2-7 MT / Torque 14-16 kNm / ECD 1,44. Average ROP 35 m/hr
2007-10-27 | 03:30:00 | 06:00:00 | 2275 | drilling -- dr ill | ok | s. Reamed 1 single before connection. Down linked and performed surveys as required. Cuttings slurry routed to boat due to injection pump is out of operation.
2016-10-05 | 03:30:00 | 03:45:00 | 2291 | plug abandon -- cement plu g | ok | Filled pipe
2007-10-27 | 06:00:00 | 08:00:00 | 2311 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2275 m to 2311 m MD. Drilling parameters : Flow 3500 lpm / SPP 197 bar / 170 RPM / WOB 2-5 MT / Torque 14-15 kNm / ECD 1,44. Average ROP 35 m/hr
2007-10-27 | 06:00:00 | 08:00:00 | 2311 | drilling -- dr ill | ok | s. Reamed 1 stand before connection. Down linked and performed surveys as required.
2007-10-27 | 09:00:00 | 10:00:00 | 2311 | interruption | ok | MP#2 had to be replaced by MP#3 due to leaking swab. MP#3 had been run in test mode and charge pumpe had to be de-isolated.
2007-10-27 | 09:00:00 | 10:00:00 | 2311 | interruption | ok | Meanwhile Picked off bottom and circulated and reciprocated string at 1750 lpm / 55 bar / 20 RPM.
2016-10-05 | 16:00:00 | 17:00:00 | 2365 | plug abandon -- cement plu g | ok | RIH w/ 5,5in DP from 2084m to 2365m. Average tripping speed 612 m/hour. Performed kick drill. Meanwhile WOC
2016-10-05 | 17:00:00 | 19:00:00 | 2365 | plug abandon -- other | ok | Performed maintenance on TDS. Cleared chiksans from wellhead. Worked on PMs on drilling equipment. Tested back up BX elevators, good test. Meanwhile WOC
2016-10-05 | 19:00:00 | 00:00:00 | 2365 | plug abandon -- other | ok | Cleaned in moonpool. Worked to service both PRSs and TDS. Installed drill pipe slips. Meanwhile WOC
2007-11-01 | 13:15:00 | 19:30:00 | 2369 | drilling -- casing | ok | RIH with 10 3/4" csg from 2151 to 2369 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr
2007-11-01 | 13:15:00 | 19:30:00 | 2369 | drilling -- casing | ok | .
2007-11-01 | 19:30:00 | 20:00:00 | 2369 | interruption -- maintain | ok | Performed maintenace on flush joint elevator. Changed dies in csg tong. Meanwhile repaired camera on PDM.
2016-10-05 | 09:30:00 | 10:15:00 | 2372 | plug abandon -- cement plu g | ok | Installed sponge ball. Pumped 10m3 hi-vis at 2400l/min / 43 bar. Circulated out cement at max of 3400 l/min/ 116 bar. Diverted returns overboard. L/D pup joint and R/B 1x stand to 2372m. Meanwhile WOC
2016-10-05 | 10:15:00 | 10:30:00 | 2372 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to wash BOP w/ jetting tool. Meanwhile WOC
2016-10-05 | 10:30:00 | 12:00:00 | 2372 | plug abandon -- cement plu g | ok | Installed closed FOSV and BOP wash tool, made 10x passes in BOP and well head area at 1500 LPM / 12 bar, operated rams and annular once. L/D BOP wash tool. Meanwhile WOC
2016-10-05 | 12:00:00 | 12:15:00 | 2372 | plug abandon -- other | ok | Performed Pre-job Meeting to L/D DP. Meanwhile WOC
2007-10-27 | 10:00:00 | 15:00:00 | 2377 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2311 m to 2377 m MD. Drilling parameters : Flow 3500 lpm / SPP 200-205 bar / 170 RPM / WOB 4-7 MT / Torque 13-15 kNm / ECD 1,43-1,45. Average RO P 10-35 m/hrs. Reamed 1 stand before connection. Down linked and performed surveys as required.
2007-10-27 | 15:00:00 | 16:00:00 | 2377 | interruption | ok | Valve in cutting injection system (CRI) would not open. Hydraulic oil was drained from closing side of automatic valve to make it open. Meanwhile cleaned out cooling water on MP#3.
2007-10-27 | 15:00:00 | 16:00:00 | 2377 | interruption | ok | Meanwhile Picked off bottom and circulated at 1750 lpm / 55 bar / 20 RPM.
2016-10-06 | 02:00:00 | 02:30:00 | 2405 | interruptio n -- wait | ok | Waited for cement, total of 2 hours from 1st tagging attempt
2016-10-05 | 08:00:00 | 09:30:00 | 2416 | plug abandon -- cement plu g | ok | Balanced cement plug (2616 m - 2416 m ): Mixed and pumped 9,4 m3 of 1,9 SG cement slurry, 600 l/min. Displaced the cement to the rig floor with 2900 l of drill water. Zeroed volume coun ters. Displaced the cement with 37 m3 (1670 strokes) of SW, 2900 l/min/ 51 bar. Pulled out of cement to 2416m at 4 min/stand. Theoretical TOC 2416 m MD.
2016-10-06 | 00:00:00 | 02:00:00 | 2436 | plug aban don -- ce ment plug | ok | Initiated circulation and RIH to tag cement. Down weight 129t. Slowly washed down from theoretical TOC of 2416m to 2426m. 500l/min - 11bar. No indication of cement, stable pressure. Co ntinued RIH. Observed increase in pressure to 13-14bar and no change of weight indicating poor cement. Stopped RIH at 2436m, 20m below theoretical TOC. Picked up string 10m and circ ulated well over shackers at max 2000l/min - 100bar. Shackers plugged with cement returns. Diverted returns overboard. Continued circulated until no cement observed in returns. Totally cir culated 108m3. Meanwhile WOC
2016-10-06 | 02:30:00 | 02:45:00 | 2438 | plug aban don -- ce ment plug | ok | Initiated circulation and RIH to tag cement. Down weight 126t. Slowly washed down from 2436m, 500l/min - 10bar, pressure dropped to 8 bar after reaching 2438m. Tagged TOC w/ 10t. Co nfirmed TOC at 2438m (22m below theoretical TOC)
2016-10-06 | 02:45:00 | 03:00:00 | 2438 | plug aban don -- ce ment plug | ok | Released spear from tubing string. Pulled string 2m up, confirmed spear released, up weight of 82t. Top of tubing 389m
2008-03-03 | 06:00:00 | 09:30:00 | 2466 | drilling -- ca sing | ok | RIH with spear assembly on 5 1/2" DP from 693 m to 2466 m MD.
2008-03-03 | 06:00:00 | 09:30:00 | 2466 | drilling -- ca sing | ok | Meanwhile changed out csg tong on fwd iron roughneck.
2008-03-03 | 09:30:00 | 12:00:00 | 2466 | drilling -- ca sing | ok | Broke circulation at 2466 m and pumped 104 m3 1.45 sg mud at 2000 lpm / 88-94 bar. Continued to circulate due to gas peaks at 3.35%. Reduced circulation rate to 1000 lpm / 29,8 bar
2008-03-03 | 09:30:00 | 12:00:00 | 2466 | drilling -- ca sing | ok | , when no gas in returns. Pumped at total of 175 m3. Meanwhile circulating, inspected PRS and dragchain. Found lock nuts loose and missing.
2007-10-27 | 16:00:00 | 00:00:00 | 2497 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2377 m to 2497 m MD. Drilling parameters : Flow 3500 lpm / SPP 200-205 bar / 170 RPM / WOB 4-7 MT / Torque 15-20 kNm / ECD 1,43. Average ROP 35 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Lined over from MP#3 to MP#2 at 21:45.
2007-10-29 | 03:45:00 | 06:00:00 | 2525 | drilling -- drill | ok | Pulled first 5 stnds wet from 2768 to 2550 m MD. No drag observed. Pumped 4,7 m3 1,65 sg slug at 880 lpm / 22 bar. Continued POOH to 2525 m MD. Gyro survey was perf ormed on each stand.
2008-02-27 | 15:00:00 | 15:30:00 | 2550 | formation evalu ation -- log | ok | POOH with MDT toolstring on 5 1/2" DP from 2751 m to 2550 m MD. Got problems with drawwork.
2008-02-27 | 15:30:00 | 16:00:00 | 2550 | interruption -- o ther | ok | Troubleshot problems with drawwork.
2008-03-03 | 18:00:00 | 20:00:00 | 2562 | drilling -- ca sing | ok | RIH with spear assembly on 5 1/2" DP from 2466 m to 2562 m MD while circulating 490 lpm / 18.4 bar. Upweight 152 MT / down weight 130 MT. Observed pressure increasing to 45 bar at 2562 m when sliding string into 7" liner. TOL = 2557 m MD. Stopped pumping and bled off pressure.
2008-03-03 | 20:00:00 | 21:00:00 | 2563 | drilling -- ca sing | ok | Continued to RIH 1.5 m and activated grapple with 3 left hand turns. First attempt to engage grapple failed, but the second attempt was sucessfull. Took 10 MT overpull. Established cir culation at 265 lpm / 32 bar. PU to 191 MT (10 MT above liner weight) and circulated for 15 min. PU to 226 MT (45 MT overpull) and observed 7" liner break free.
2016-10-04 | 18:15:00 | 19:00:00 | 2573 | plug aba ndon -- o ther | ok | Pulled and L/D 2x joints of tubing
2016-10-04 | 19:00:00 | 19:15:00 | 2573 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to pull and L/D 7in tubing w/ new crew
2016-10-04 | 19:15:00 | 19:30:00 | 2573 | plug aba ndon -- o ther | ok | Checked red zone barriers and equipment
2007-11-01 | 20:00:00 | 00:00:00 | 2574 | drilling -- casing | ok | RIH with 10 3/4" csg from 2369 to 2574 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr
2007-11-01 | 20:00:00 | 00:00:00 | 2574 | drilling -- casing | ok | .
2008-02-22 | 00:00:00 | 06:00:00 | 2595 | interruption -- fish | ok | Ran 5 1/2" singles over 7/48 wireline from 1989 m to 2595 m MD. Winds 35- 40 knots.
2016-10-04 | 18:00:00 | 18:15:00 | 2595 | plug aba ndon -- o ther | ok | L/D 3x pup joints
2016-10-04 | 15:45:00 | 17:00:00 | 2600 | plug aba ndon -- o ther | ok | POOH w/ tubing and tubing hanger on landing string. Spooled control line. L/D landing string and TH on deck
2016-10-04 | 17:00:00 | 17:45:00 | 2600 | plug aba ndon -- o ther | ok | Installed casing slips and control line spooler
2016-10-04 | 17:45:00 | 18:00:00 | 2600 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to pull and L/D 7in tubing
2016-10-05 | 06:00:00 | 06:45:00 | 2614 | plug abandon -- cement plu g | ok | R/B 1x stand. Installed side entry sub assembly and connected cement hose, spaced out to 2614m bottom of tubing string
2016-10-05 | 06:45:00 | 07:00:00 | 2614 | plug abandon -- cement plu g | ok | Lined up/prepared to pump wash pill
2016-10-05 | 07:00:00 | 07:15:00 | 2614 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to place pump balance cement plug
2016-10-05 | 07:15:00 | 08:00:00 | 2614 | plug abandon -- cement plu g | ok | Pumped 20m3 wash pill with mud pumps, 2700l/min - 79bar. Applied 20 bar behind IBOP, verified line up
2016-10-04 | 09:30:00 | 11:45:00 | 2616 | plug aba ndon -- o ther | ok | RIH w/ cutter BHA, run #9 from surface 2616 m. Average running speed 20 m/min.
2016-10-05 | 03:45:00 | 04:15:00 | 2616 | plug abandon -- cement plu g | ok | RIH w/ 7in tubing on 5,5in DP from 2291m to 2616m. Average RIH speed 650 m/hour
2016-10-05 | 04:15:00 | 04:30:00 | 2616 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting prior to circulating well to sea water
2016-10-05 | 04:30:00 | 06:00:00 | 2616 | plug abandon -- cement plu g | ok | Started to circulate well to sea water. Staged up pumps to 3000 l/min - 78bar. Observed dirty fluid in returns. OIW reading is above 100ppm. No gas. After 50m3 pumped pulled 3m above c ombination wiper plug. Continued circulating. Shakers overflowed, reduced the rate to 2200l/min - 56bar. Circulated additional 112 m3. Observed clear returns after total of 162 m3 pumped. OIW content less than 30 ppm. Stopped pumps. Installed pump in sub w/ LT valve.
2007-11-02 | 00:00:00 | 00:45:00 | 2617 | drilling -- casing | ok | RIH with 10 3/4" csg from 2574 to 2617 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr. Up weight 261 MT / Down weight 193 MT.
2007-11-02 | 00:45:00 | 02:45:00 | 2617 | drilling -- casing | ok | RD FAC tool and changed bails. Changed to 5 1/2" HWDP hadling equipment.
2008-02-08 | 13:45:00 | 17:45:00 | 2619 | drilling -- drill | ok | Continued RIH with 8½" drill BHA on 5½" DP, from 937m to 2619m, filled every 1000m. Average RIH speed 420 m/hr.
2016-10-04 | 11:45:00 | 13:00:00 | 2621 | plug aba ndon -- o ther | ok | Correlated across interval 2616 - 2638 . Positioned cutter at 2621 m . Performed cut. Observed backflow from pipe after tubing was cut
2007-10-28 | 00:00:00 | 06:00:00 | 2626 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2497 m to 2626 m MD. Drilling parameters : Flow 3500 lpm / SPP 205 bar / 170 RPM / WOB 4-7 MT / Torque 16-18 kNm / ECD 1,44. Average ROP 35 m/hr
2007-10-28 | 00:00:00 | 06:00:00 | 2626 | drilling -- dr ill | ok | s. Reamed 1 single before connection. Down linked and performed surveys as required. Started injecting cuttings slurry into F-12 annulus at 03:30.
2007-10-28 | 00:00:00 | 06:00:00 | 2626 | drilling -- dr ill | ok | Turned back time 1 hour at 03:00 due "winter-time" in Norway.
2007-11-02 | 02:45:00 | 05:30:00 | 2626 | drilling -- casing | ok | PU and MU 10 3/4" casing hanger / PADPRT assembly. Marked running tool to make sure it is not backing out. Took out master bushing and ran hanger assy through rotary. Re-installed m aster bushing. Removed csg tong.
2008-02-08 | 17:45:00 | 18:15:00 | 2632 | drilling -- drill | ok | Took weight at 2619m. M/U to TDS and washed down to 2632m, 10 rpm, 10kNm, 1500 lpm, 139 bars.
2008-02-08 | 18:15:00 | 19:00:00 | 2632 | drilling -- other | ok | Performed choke drill with day shift.
2008-02-08 | 19:00:00 | 19:45:00 | 2632 | drilling -- other | ok | Performed choke drill with night shift. Observed saver sub required change out
2008-02-08 | 19:45:00 | 20:00:00 | 2632 | interruption -- maint ain | ok | Held tool box talk prior to change out the saver sub.
2008-02-08 | 20:00:00 | 22:45:00 | 2632 | interruption -- maint ain | ok | Changed out the saver sub.
2008-02-08 | 22:45:00 | 23:15:00 | 2632 | drilling -- drill | ok | P/U one 5½" DP std. and prepared for drilling. Found discrepancy in depth.
2008-02-08 | 23:15:00 | 23:30:00 | 2632 | drilling -- trip | ok | Counted the 5½" DP in derrick. Changed depth from 2671m to 2632m.
2008-04-10 | 08:00:00 | 16:30:00 | 2645 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing with CL and clamps from 2164 m to 2645 m MD.
2008-04-10 | 08:00:00 | 16:30:00 | 2645 | completion -- c ompletion strin g | ok | Up weight 172 MT / down weight 141 MT. Distance between up and down weight was 0.3 m.
2008-04-10 | 16:30:00 | 17:00:00 | 2645 | completion -- c ompletion strin g | ok | Held tool box talk before entering 7" liner.
2008-04-10 | 17:00:00 | 17:45:00 | 2645 | completion -- c ompletion strin g | ok | Lined up to pump down kill line and to be able to observe overflow from top of tubing. Verified line up with 15 bar.
2008-03-15 | 00:00:00 | 01:15:00 | 2646 | completion -- circul ating conditioning | ok | Continued RIH with clean out assy. from 2080m to 2646m.
2008-03-15 | 01:15:00 | 02:15:00 | 2646 | completion -- circul ating conditioning | ok | Circulated 50m³ OBM at 2100 lpm 295 bars. Took up/down weight zero/20 rpm. 144/123 MT - 137/129 MT.
2008-04-11 | 08:15:00 | 09:15:00 | 2647 | completion | ok | Installed communication collar onto hanger and made 5 right hand turns until it shouldered out on TH. Wrapped CL 3 times around hanger neck. Connected TRSCSSV CL to 1/4" communi cation port at btm of communication collar.
2008-04-11 | 08:15:00 | 09:15:00 | 2647 | completion | ok | PU tubing hanger RT with 7" #29 pup joint. Backed out THRT piston retaining screws and MU THRT to communication collar with 8 turns left hand rotation. Connected TRSCSSV CL to 1/ 4" communication ports on top of THRT.
2008-04-10 | 17:45:00 | 18:30:00 | 2649 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing with CL and clamps from 2645 m to 2649 m MD.
2008-04-10 | 17:45:00 | 18:30:00 | 2649 | completion -- c ompletion strin g | ok | Closed annular BOP at 280 psi. Attempted to reverse circulate, neg. Leaked through annular. Closed annular BOP at 580 psi. Reverse circulated using clean brine at 50 lpm / 3 bar a nd 100 lpm / 3.5 bar to get a reference. Observed returns. Stopped circulating and opened annular BOP.
2008-03-12 | 06:00:00 | 08:00:00 | 2650 | drilling -- drill | ok | RIH with 6" PDC bit and scraper assembly on 5 1/2" DP from 1977 m to 2650 m.
2008-03-12 | 08:00:00 | 09:30:00 | 2650 | drilling -- circulating conditioning | ok | Broke circulation with rotation and circulated btms up, 1824 lpm / 290 bar, 20 rpm / 7 kNm. Up weight 141 MT / down weight 122 MT / rotating weight 130 MT.
2008-04-10 | 18:30:00 | 21:00:00 | 2662.2 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing with CL and clamps from 2649 m to 2659.8 m MD.
2008-04-10 | 18:30:00 | 21:00:00 | 2662.2 | completion -- c ompletion strin g | ok | Performed reverse circulation exercise 50-100 lpm / 3.5 bar. Moved string down in 30 cm increments from 2659.8 m to 2662.2 m and repeated reverse circulation exercise with sam e pressure response (50-100 lpm / 3.5 bar).
2008-04-10 | 21:00:00 | 23:15:00 | 2662.2 | completion -- c ompletion strin g | ok | POOH with 7" 29# S13%Cr tubing with CL and clamps from 2662.2 m to 2644 m MD. PU 2.89 m pup joint to space out to be able to close annular without a coupling or a clamp in th e interval. RIH with 7" 29# S13%Cr tubing from 2644 m to 2662.2 m MD.
2008-04-10 | 23:15:00 | 00:00:00 | 2662.8 | completion -- c ompletion strin g | ok | Performed reverse circulation exercise 50-100 lpm / 3.5 bar. Moved string down in 20 cm increments from 2662.2 m to 2662.8 m.
2008-04-11 | 10:30:00 | 13:00:00 | 2665 | completion | ok | Removed C-plate. Ran in with THRT below rotary. Installed bowls. PU and MU joints for landing string. Up weight 173 MT / down weight 144 MT. RIH with 7" 29# S13%Cr tubing, TH and THRT on landing string from 2647 m to 2665,2 m MD. Got indications when ratcheting muleshoe and seals entered 7" liner PBR. Landed TH on no-go shoulder in surface tubing head. SO weight.
2008-04-11 | 10:30:00 | 13:00:00 | 2665 | completion | ok | Leak tested TH in port 1 and 2 on surface well head to 70 bar/5 min to verify that TH had landed correctly. Engaged TH lock down ring by applying 207 bar. Performed pull test with 15 MT overpull to verify TH lock down. SO weight.
2008-04-11 | 16:00:00 | 17:00:00 | 2665 | completion | ok | Pressured up tubing against NPR plug at 2648 m MDRT to 30 bar / 10 min to check tubing integrity before initiating packer setting. 70 ltrs pumped. Kept 570 bar on TRSCSSV CL. Observ ed 0.3 bar drop.
2008-04-11 | 16:00:00 | 17:00:00 | 2665 | completion | ok | Closed TRSCSSV. Bled down to 5 bar above TRSCSSV and function tested TRSCSSV for 10 min. Bled back 36 ltrs. Observed 0.2 bar drop. Equalized and opened TRSCSSV.
2008-04-11 | 17:30:00 | 19:00:00 | 2665 | completion | ok | Bled down pressure to 320 bar. 60 ltrs bled back. Closed TRSCSSV and bled off pressure above to 250 bar. Bled back 35 ltrs. Inflow tested TRSCSSV with 70 bar diff / 30 min. Inflow test OK.
2008-04-11 | 17:30:00 | 19:00:00 | 2665 | completion | ok | Bled off pressure above TRSCSSV to 10 bar. Bled back 120 ltrs. Inflow tested TRSCSSV with 310 bar diff / 30 min. Inflow test OK. Equalized and opened TRSCSSV using 157 ltrs. Bled of f pressure in tubing to zero. Bled back 800 ltrs.
2008-04-11 | 20:00:00 | 21:00:00 | 2665 | completion | ok | Pressured up A-annulus to leak test packer from below and TH from below to 35/380 bar for 5/10 min pumping brine at 70 lpm. Kept tubing open on drill floor and 570 bar on TRSCSSV C
2008-04-11 | 20:00:00 | 21:00:00 | 2665 | -- test scss sv | ok | L. Pumped 125 ltrs and observed 0.2 bar drop on low pressure test. Pumped 1130 ltrs (total) and observed 2.1 bar (0.5%) drop on high pressure test. Had flow on both tubing and B- annulus while pressuring up A-annulus due to ballooning effect. No flow observed when pumps was shut in. Bled pressure down to zero and had 1100 ltrs in return. Closed TRSCSSV.
2008-02-08 | 23:30:00 | 00:00:00 | 2670 | drilling -- drill | ok | Washed down from 2632m to 2670m. Washing parameters : Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 146. ROP 30-40 m/hr.
2008-02-17 | 16:30:00 | 17:45:00 | 2671 | interruption -- repair | ok | Pulled MDT tool from 3245 m to 2671 m MD inside 9 5/8" casing shoe. Troubleshot tool failure - negative.
2007-11-02 | 05:30:00 | 06:00:00 | 2698 | drilling -- casing | ok | RIH with 10 3/4" x 9 5/8" csg on 5 1/2" HWDP landing string from 2626 to 2698 m MD.
2008-02-18 | 06:00:00 | 07:30:00 | 2700 | interruption -- r epair | ok | RIH witth MDT toolstring on 7/48 cable from surface to 2700 m MD inside 9 5/8" shoe. Rested MDT toolstring for 30 min to allow for temperature adaption.
2008-02-24 | 16:00:00 | 16:30:00 | 2703 | interruption -- fish | ok | Broke out and and laid down 5" x 5 1/2" x-over with 5" pup joint.
2008-02-22 | 06:00:00 | 07:30:00 | 2704 | interruption -- fish | ok | Ran 5 1/2" singles over 7/48 wireline from 2595 m to 2704 m MD.
2008-02-22 | 07:30:00 | 07:45:00 | 2704 | interruption -- fish | ok | Held toolbox talk prior to rigging TDS work platform.
2008-02-22 | 07:45:00 | 08:00:00 | 2704 | interruption -- fish | ok | Lowered and positioned TDS work platform.
2008-02-22 | 08:00:00 | 08:30:00 | 2704 | interruption -- fish | ok | Pulled wireline through TDS and secured same. Installed 5" weco blind plug in TDS top-in coupling.
2008-02-22 | 08:30:00 | 08:45:00 | 2704 | interruption -- fish | ok | Retracted and secured TDS work platform.
2008-02-22 | 08:45:00 | 09:15:00 | 2704 | interruption -- fish | ok | Performed derrick inspection due to period of high winds.
2008-02-22 | 09:15:00 | 10:00:00 | 2704 | interruption -- fish | ok | Pressure tested TDS 5" weco blind plug and K5 manifold valve 5/10 min 20/345 bar. Re-routed wireline over TDS.
2008-02-22 | 10:00:00 | 10:15:00 | 2704 | interruption -- fish | ok | Made up 4 m 5" pup joint to 5" x 5 1/2" x-over, threaded wireline through same.
2008-02-22 | 10:15:00 | 10:45:00 | 2704 | interruption -- fish | ok | Changed to 5" inserts in elevator. Picked up 5" pup/x-over and made up same to string.
2008-02-22 | 10:45:00 | 11:00:00 | 2704 | interruption -- fish | ok | Held toolbox talk prior to removeing PS-30 automatic slips.
2008-02-22 | 11:00:00 | 11:30:00 | 2707 | interruption -- fish | ok | Removed PS-30 automatic slips, dressed same for 5" DP and re-installed in rotary. Ran in on 5" DP to 2707 m MD.
2008-02-22 | 11:30:00 | 12:00:00 | 2707 | interruption -- fish | ok | Took 9000 lbs tension on WL. Fitted T-bar to wireline and hung off on 5" DP.
2008-02-22 | 12:00:00 | 19:00:00 | 2707 | interruption -- fish | ok | Fitted WL in sideentry sub. Cut WL and built rope sockets on winch and well ends according to Schlumberger procedure. Built WL torpedo. Changed from 5 1/2" to 5" saver sub on TDS.
2008-02-22 | 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | Waited on weather. Winds 60-70 knots.
2008-02-22 | 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | Meanwhile :
2008-02-22 | 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | -Inspected and greased PDM, HTS, IR, PS-21 and DP elevators
2008-02-22 | 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | -Inspected TDS torque wrench
2008-02-22 | 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | -Repaired trip tank pump
2008-02-22 | 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | -Installed drag chain guide on AFT PRS
2008-02-22 | 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | -Pressure tested standpipe and kill manifolds
2008-02-23 | 00:00 | 04:15:00 | 2707 | interruption -- w aiting on weathe r | ok | Waited on weather. Winds 50-60 knots.
2008-02-23 | 00:00 | 04:15:00 | 2707 | interruption -- w aiting on weathe r | ok | Meanwhile :
2008-02-23 | 00:00 | 04:15:00 | 2707 | interruption -- w aiting on weathe r | ok | -Installed drag chain guide on AFT PRS
2008-02-23 | 00:00 | 04:15:00 | 2707 | interruption -- w aiting on weathe r | ok | -Pressure tested standpipe and kill manifolds
2008-02-23 | 04:15 | 05:15:00 | 2707 | interruption -- fi sh | ok | Wind down to 45 knots. Performed derrick inspection after period of high winds. Assessed rigging alternatives for removal of upper sheave wheel in crown block.
2008-02-23 | 05:15:00 | 05:30:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk prior to removing upper sheave wheel.
2008-02-23 | 05:30:00 | 06:00:00 | 2707 | interruption -- fi sh | ok | Barriered off drilfloor for aloft work. Brought rigging equipment to derrick. Rigged down upper sheave wheel.
2008-02-23 | 06:00:00 | 08:15:00 | 2707 | interruption -- fi sh | ok | Rigged down WL sheave wheel from crown block. Lowered sheave wheel to drillfloor. Re-made torpedo due to tangeled wires in derrick. Powered up WL. Cleared and tidied drillfloo r.
2008-02-23 | 08:15:00 | 08:30:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk for repositioning WL sheave.
2008-02-23 | 08:30:00 | 09:30:00 | 2707 | interruption -- fi sh | ok | Repositioned WL sheave in derrick. Attached wireline over sheave.
2008-02-23 | 09:30:00 | 09:45:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk prior to making up side entry sub.
2008-02-23 | 09:45:00 | 10:30:00 | 2707 | interruption -- fi sh | ok | Made up side entry sub to toolstring according to Schlumberger instructions.
2008-02-23 | 10:30:00 | 10:45:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk prior to testing IBOPs on TDS.
2008-02-23 | 10:45:00 | 11:45:00 | 2707 | interruption -- fi sh | ok | Rigged up swage with 1502 weco to TDS. Hooked up cement hose. Stopped for ESD test.
2008-02-23 | 11:45:00 | 15:00:00 | 2707 | interruption -- ot her | ok | Halted operation for ongoing ESD test.
2008-02-23 | 11:45:00 | 15:00:00 | 2707 | interruption -- ot her | ok | Meanwhile :
2008-02-23 | 11:45:00 | 15:00:00 | 2707 | interruption -- ot her | ok | -Cleaned and tidied drillfloor and shaker areas
2008-02-23 | 11:45:00 | 15:00:00 | 2707 | interruption -- ot her | ok | -Changed die holders and dies on TDS torque wrench
2008-02-23 | 11:45:00 | 15:00:00 | 2707 | interruption -- ot her | ok | -Continued installation of dragchain guide on AFT PRS
2008-02-23 | 15:00:00 | 16:00:00 | 2707 | interruption -- fi sh | ok | Pressure tested upper/lower IBOP to 30/345 bar 5 /10 min. Meanwhile continued ESD testing.
2008-02-23 | 16:00:00 | 16:30:00 | 2707 | interruption -- fi sh | ok | Picked up stand of 5" DP and made up to side entry sub. Inserted rubber seals in side entry sub. Clamped 7/48 cable in side entry sub cut out.
2008-02-24 | 14:45:00 | 15:30:00 | 2707 | interruption -- fish | ok | Broke out side entry sub and laid down same. Cut loose WL from side entry sub. Rigged down lower sheave and secured upper sheave above V-door.
2008-02-24 | 15:30:00 | 15:45:00 | 2707 | interruption -- fish | ok | Held toolbox talk prior to changing handling equipment.
2008-02-24 | 15:45:00 | 16:00:00 | 2707 | interruption -- fish | ok | Changed slips segments. Re-activated guides in PS-30 automatic slips.
2008-02-24 | 06:00:00 | 09:00:00 | 2710 | interruption -- fish | ok | POOH wet with 5" DP from 3167 m to 2710 m MD. Maintained ~5000 lbs tension in wirieline while spooling in.
2008-02-24 | 09:00:00 | 09:45:00 | 2710 | interruption -- fish | ok | Flowchecked well - well static - ok. Removed snatch block from wireline.
2008-02-24 | 09:45:00 | 10:30:00 | 2710 | interruption -- fish | ok | Pumped 5 m3 1,65 sg slug at 700 lpm and chased to drillfloor.
2008-02-24 | 10:30:00 | 11:45:00 | 2710 | interruption -- fish | ok | Released electrical weakpoint. Powered down logging unit.
2008-02-24 | 11:45:00 | 14:45:00 | 2710 | interruption -- fish | ok | POOH with WL inside 5 1/2" DP from 2710 m MD to surface.
2008-03-04 | 05:30:00 | 06:00:00 | 2716 | drilling -- casing | ok | Pumped slug and POOH with 7" liner on 5 1/2" DP from 2755 m to 2716 m MD.
2008-02-09 | 00:00:00 | 01:30:00 | 2733 | drilling -- drill | ok | Continued washing down from 2670m to 2733m. Washing parameters : Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 146. ROP 30-40 m/hr.
2008-02-09 | 01:30:00 | 04:30:00 | 2734 | drilling -- drill | ok | Drilled out float. From 2733m to 2734m. Drilling parameters : Flow 1500 lpm / SPP 140 bar / String RPM 10-30 / Bit RPM 125-145. ROP 1-40 m/hr, WOB 1-9 MT. Recovered rubber at the shakers.
2007-11-02 | 06:00:00 | 06:30:00 | 2740 | drilling -- casing | ok | RIH with 10 3/4" x 9 5/8" csg on 5 1/2" HWDP landing string from 2698 to 2740 m MD.
2007-11-02 | 06:30:00 | 07:15:00 | 2740 | drilling -- casing | ok | PU cement head and broke circulation in steps up to 2000 lpm, 500 lpm=20 bar and 2000 lpm=56 bar
2008-02-16 | 00:00:00 | 00:15:00 | 2740 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5 1/2" DP from 2780 m to 2740 m MD inside 9 5/8" casing shoe. Recorded up down weight 163/137 MT. Recorded torque at 20 RPM - 7 kN m.
2008-03-07 | 00:00:00 | 01:00:00 | 2748 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3114 m to 2748 m MD.
2008-03-07 | 01:00:00 | 01:30:00 | 2748 | drilling -- casing | ok | Flow checked well inside shoe. Static. Dropped 2 3/4" rabbit.
2008-02-23 | 16:30:00 | 16:45:00 | 2750 | interruption -- fi sh | ok | RIH with 5" DP from 2707 to 2750 m MD, held wireline tension contant at ~7000 lbs.
2008-02-23 | 16:45:00 | 20:00:00 | 2750 | interruption -- fi sh | ok | Broke circulation at 9 5/8" shoe and stepped up rate to 700 lpm as limited by erosion figures for side entry sub. Circulated bottoms up. Standpipe pressure rose from 10 bar to 30 bar throughout circulation. Mud weight out 1,39 sg rising to 1,43 sg towards the end. Mud weight in 1,45 sg. Gas peaked at 7% and levelled out on 0,3% towards end of circulation.
2008-02-23 | 20:00:00 | 21:00:00 | 2750 | interruption -- fi sh | ok | Held toolbox talk prior to running into open hole. Meanwhile flowchecked well and allowed well to equalize due to pipe/annulus imbalance.
2008-02-09 | 04:30:00 | 06:00:00 | 2751 | drilling -- drill | ok | Drilled shoe track from 2734m to 2751m. Drilling parameters : Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 146 / ROP 30-40 m/hr / WOB 1 MT / TQ 10-12 kNm. MUD weight 1.4 SG. Back reamed to float with 1500 lpm, RIH and made connection at 2751m, volume pumped prior to connection 26m³.
2008-02-26 | 00:00:00 | 02:00:00 | 2751 | formation evalua tion -- log | ok | RIH with MDT toolstring from 2267 m to 2751 m MD on 5 1/2" DP. Max running speed 2 min/stand. Circulated 500 lpm / 3 mins every 500 m.
2008-02-27 | 14:00:00 | 15:00:00 | 2751 | formation evalu ation -- log | ok | Held toolbox talk. Changed inserts in PS-30 automaitic slips. Broke out and laid down 5" pup joint and 4 1/2" IF x 5 1/2" FH x-over.
2008-03-06 | 00:00:00 | 02:15:00 | 2751 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 2146 m to 2751 m MD. Filled pipe every 10 stds.
2008-03-06 | 02:15:00 | 04:00:00 | 2751 | drilling -- casi ng | ok | MU TDS and filled pipe and broke circulation at 9 5/8" csg shoe with 500 lpm / 21 bar. Up weight 149 MT / down weight 122 MT. Circulated btms up at 2000 lpm / 164 bar. Max ga s 2.2%. ECD = 1.58 sg.
2008-02-16 | 00:15:00 | 00:45:00 | 2754 | drilling -- trip | ok | Flowchecked well -well static. Meanwhile inspected and serviced TDS. Dropped 2 3/4" drift with pigtail in drillpipe.
2008-02-26 | 02:00:00 | 02:30:00 | 2755 | formation evalua tion -- log | ok | Installed and made up 5 1/2" x 5" x-over and 5" pup joint for circulation.
2008-02-26 | 02:30:00 | 04:15:00 | 2755 | formation evalua tion -- log | ok | Circulated 2 x bottoms up pumping at 2000 lpm / SPP 93 bar. Gas peaked at 6,6% on 1st bottom up and levelled out on 0,2% after 2nd bottom up. MW in/out 1,44/1,44 sg. Te sted rheology and found mud to be in good condition.
2008-02-26 | 04:15:00 | 06:00:00 | 2755 | formation evalua tion -- log | ok | Rigged upper and lower sheave wheels. Deactivated guides in PS-30 automatic slips. Lifted side entry sub with tugger and put locomotive into pipe. Spooled out approx 100 m on WL. Stabbed on side entry sub and lowered upper sheave wheel to centre position.
2008-02-27 | 10:15:00 | 10:45:00 | 2755 | interruption -- r epair | ok | Broke out side entry sub and laid down locomotive.
2008-02-27 | 10:45:00 | 11:30:00 | 2755 | interruption -- r epair | ok | Checked locomotive and cable - ok. Cut cable loose from side entry sub.
2008-02-27 | 11:30:00 | 13:00:00 | 2755 | formation evalu ation -- log | ok | Circulated bottoms up at 2000 lpm / 82-95 bar SPP. Gas peaked at 6,6% at bottoms up. MW in/out 1,45 sg.
2008-02-27 | 13:00:00 | 13:30:00 | 2755 | formation evalu ation -- log | ok | Flow checked well - well static - ok.
2008-02-27 | 13:30:00 | 14:00:00 | 2755 | formation evalu ation -- log | ok | Pumped 6 m3 1,62 sg slug and chased to drillfloor. Allowed active to stabilize.
2008-03-04 | 00:00:00 | 02:45:00 | 2755 | drilling -- casing | ok | Pumped OOH 265 lpm / 32 bar with 7" liner on 5 1/2" DP from 3122 m to 2755 m MD.
2008-03-04 | 02:45:00 | 05:30:00 | 2755 | drilling -- casing | ok | Circulated btms up at csg shoe to clear passage around 7" liner and liner hanger, 1000 lpm / 59 bar. Continued to circulate due to gas peaks at 6.8%. Pumped at total of 113 m3. Flow checked well prior to POOH.
2008-02-27 | 06:00:00 | 08:15:00 | 2757 | interruption -- r epair | ok | POOH with 5" DP from 3244 m to 2757 m MD. Hole in good condtion - no significant drag observed.
2008-02-27 | 08:15:00 | 10:15:00 | 2757 | interruption -- r epair | ok | Removed clamps from side entry sub. Took overpull on wireline and released locomotive from docking head.
2008-02-26 | 06:00:00 | 10:00:00 | 2759 | formation evalua tion -- log | ok | Made up side entry sub. Made up 5" stand for pumping down locomotive. Pumped down locomotive while spooling out wireline. Pumpe rate 420-510 lpm / SPP 15-18 bar.
2008-02-26 | 10:00:00 | 10:15:00 | 2759 | formation evalua tion -- log | ok | Increased pump rate to 1000 lpm / SPP 37 bar before latching locomotive in docking head. Observed 7 bar pressure increase when docking.
2008-02-26 | 10:15:00 | 10:30:00 | 2759 | formation evalua tion -- log | ok | Powered up logging tools. Schlumberger tested MDT toolstring.
2008-02-26 | 10:30:00 | 11:00:00 | 2759 | formation evalua tion -- log | ok | Clamped 7/46 cable in side entry cut out. Tested cable docking by applying 3500 lbs overpull on wireline for 5 mins - ok.
2008-02-26 | 11:00:00 | 11:30:00 | 2759 | formation evalua tion -- log | ok | Held toolbox talk prior to RIH with MDT toolstring on 5" DP / 7/46 cable. Went through well control contingencies. Function tested hydraulic wireline cutter - ok.
2008-02-09 | 06:00:00 | 06:30:00 | 2760 | drilling -- drill | ok | Drilled shoe track from 2751m to 2760m. Drilling parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / ROP 30-40 m/hr / WOB 1-4 MT / TQ 10-12 kNm. MUD weight 1.4 SG.
2008-02-09 | 08:00:00 | 09:00:00 | 2760 | formation evalu ation -- rft/fit | ok | Pulled back into the shoe. Racked back one std. Installed side entry sub and CMT hose. Confirmed line up from CMT unit to drill floor. Leak tested line to 100 bars 10 min.
2008-02-09 | 09:00:00 | 10:00:00 | 2760 | formation evalu ation -- rft/fit | ok | Performed FIT test. Closed annular. Applied 64 bars down DP and ANN equivalent to 1.65 SG. Rigged down CMT hose and side entry sub.
2007-11-02 | 07:15:00 | 07:45:00 | 2760.5 | drilling -- casing | ok | RIH slowly and landed off hanger. Observed 10 MT drag prior to landing off. Pumped 500 lpm and observed weight dropped off.
2007-11-02 | 07:45:00 | 09:00:00 | 2760.5 | drilling -- casing | ok | Circulated 1 csg volume with 1.40 sg OBM at 200 lpm / 57 bar. Meanwhile hed pre-job meeting for cmt job.
2007-11-02 | 09:00:00 | 09:30:00 | 2760.5 | drilling -- casing | ok | Lined up and pressure tested cmt line 245 bar / 5 min. Verified correct line-up by holding and releasing 10 bar through low torque.
2007-11-02 | 09:30:00 | 10:15:00 | 2760.5 | drilling -- casing | ok | Pumped 10 m3 base oil and 20 m3 spacer at 2000 lpm / 48 bar. Mixed and pumped 17,3 m3 1.90 sg cement slurry at 800 lpm / 40-45 bar.
2007-11-02 | 10:15:00 | 12:15:00 | 2760.5 | drilling -- casing | ok | Pumped 490 ltrs water, released dart and continued pumping 400 ltrs water behind cement with cmt unit, to displace surface line volume to rig floor.
2007-11-02 | 10:15:00 | 12:15:00 | 2760.5 | drilling -- casing | ok | Zeroed stroke counters for mud pumps. Displaced and sheared wiper plug by pumping OBM at 1200 lpm using rig pumps. Wiper plug sheared at 138 bar / 886 ltr.
2007-11-02 | 10:15:00 | 12:15:00 | 2760.5 | drilling -- casing | ok | Continued displacing cement with 102.8 m3 OBM at 2000 lpm using mud pumps. Slowed down rate to 1000 lpm / 33 bar (FCP) approx 4 m3 prior to bump. Bumped plug with 110 bar after pumping 4718 strokes, which gives a pump efficiency of 95.3%.
2007-11-02 | 12:15:00 | 13:45:00 | 2760.5 | drilling -- casing | ok | Bled off pressure to 20 bar and closed IBOP. Equalized pressure and opened lo-torque valve. Pressured up well to 310 bar / 10 min through lo-torque valve to test casing. 1300 ltrs pumped and got 1350 ltrs back. Bleed off and checked for back flow to cmt unit. Disconnected cmt hoses and flushed lines.
2007-11-02 | 13:45:00 | 14:30:00 | 2760.5 | drilling -- casing | ok | Lined up top drive to trip tank to monitor returns. Tested surface lines against fail safe valve to 207 bar / 10 min. Closed upper pipe ram and applied 207 bar to set seal assembly.
2007-11-02 | 14:30:00 | 15:00:00 | 2760.5 | drilling -- casing | ok | Took 40 MT overpull. Attempted to pressure test seal assembly without sucess.
2008-02-09 | 06:30:00 | 06:45:00 | 2761 | drilling -- drill | ok | Drilled shoe from 2760m to 2761m. Drilling parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / WOB 1-6 MT / TQ 10-12 kNm.
2007-10-28 | 06:00:00 | 00:00:00 | 2768 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2626 m to 2770 m MD. Drilling parameters : Flow 3500 lpm / SPP 209-211 bar / 160-180 RPM / WOB 4-10 MT / Torque 15-22 kNm / ECD 1,43-1,44. Averag e ROP 1-10 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Started injecting cuttings slurry into F-12 annulus at 20:10.
2007-10-29 | 00:30:00 | 02:30:00 | 2768 | drilling -- circulating conditio ning | ok | Circulated 2 btms up at 2770 m MD, 3500 lpm / 200 bar / 170 rpm / 13-15 kNm to clean well. Took one roadmap measurement, 200 lpm and 60 rpm. Up weight 175 MT. Dow n weight 156 MT.
2007-10-29 | 02:30:00 | 03:30:00 | 2768 | drilling -- survey | ok | BO one std, RU and dropped gyro. Pumped down tool, 550 lpm / 7 bar / 15 rpm and landet off on totco ring on top off jar in BHA.
2007-10-29 | 03:30:00 | 03:45:00 | 2768 | drilling -- drill | ok | Flow checked well while rotating with 10 rpm. Sat tool face on drop gyro.
2007-10-29 | 00:00:00 | 00:30:00 | 2770 | drilling -- drill | ok | Drilled 12 1/4" section from 2768 m to 2770 m MD. Drilling parameters : Flow 3500 lpm / SPP 203 bar / 170 RPM / WOB 7 MT / Torque 15-20 kNm / ECD 1,43. Average RO P 1-4 m/hrs.
2008-02-09 | 06:45:00 | 07:15:00 | 2771 | drilling -- drill | ok | Cleaned out rat hole from 2765m to 2771m. Cleaning parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / WOB 1-3 MT.
2008-02-09 | 07:15:00 | 08:00:00 | 2774 | drilling -- drill | ok | Drilled new formation from 2771m to 2774m. Drilling parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / WOB 5-7 MT / TQ 12-14 kNm. MUD weight 1.4 S G.
2008-02-15 | 22:15:00 | 00:00:00 | 2780 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5 1/2" DP from 3307 m to 2780 m MD.
2008-03-16 | 18:30:00 | 19:00:00 | 2840 | completion -- circulating condi tioning | ok | Laid out the Razor back BHA # 3.
2008-03-16 | 16:15:00 | 18:30:00 | 2846 | completion -- circulating condi tioning | ok | Held tool box and changed to PS-21 slips. POOH from 3420m to 2846m.
2008-03-15 | 02:15:00 | 03:00:00 | 2848 | completion -- circul ating conditioning | ok | Entered the 7" liner. Continued RIH with clean out assy. from 2646m to 2848m
2008-03-15 | 03:00:00 | 03:30:00 | 2848 | completion -- circul ating conditioning | ok | Made up the 10 3/4" casing scraper assy.
2008-02-09 | 10:00:00 | 19:00:00 | 2854 | drilling -- drill | ok | Linked down the Power Drive. Drilled new formation from 2774m to 2854m. Drilling parameters: Flow 2070 lpm / SPP 250 bar / String RPM 30 / Bit RPM 190 / WOB 7-9 MT / TQ 1 6-19 kNm. ECD 1.51 SG. MUD weight 1.4 SG. Took survey before connection.
2008-02-09 | 19:00:00 | 00:00:00 | 2917 | drilling -- drill | ok | Drilled new formation from 2854m to 2917m. Drilling parameters : Flow 2070-2090 lpm / SPP 245-250 bar / String RPM 40 / Bit RPM 203 / ROP 16-20 m/hr / WOB 7-9 MT / TQ 18- 19 kNm. ECD 1.51 SG MUD weight 1.4 SG. Took survey before connection.
2008-02-10 | 04:30:00 | 06:00:00 | 2992 | drilling -- circulating co nditioning | ok | Cleaned out well reciprocating the pipe, flow 2090 lpm / SPP 215 bar / String RPM 50 / Bit RPM 213. Operations transferred to F-99.
2008-02-10 | 00:00:00 | 04:15:00 | 2993 | drilling -- drill | ok | Drilled new formation from 2917m to 2993m. Drilling parameters : Flow 2070 lpm / SPP 245-255 bar / String RPM 40 / Bit RPM 203 / ROP 21-23 m/hr / WOB 6-11 MT / TQ 18-21 kNm. ECD 1.51 SG MUD weight 1.4 SG.
2008-02-10 | 04:15:00 | 04:30:00 | 2993 | drilling -- survey | ok | Took survey at 2993 m MD equivalent to 2795 m TVD. Stopped drilling for further instruction in conjunction with F12 perforation and start production.
2008-02-23 | 21:00:00 | 00:00:00 | 2996 | interruption -- fi sh | ok | RIH with 5" DP from 2750 m to 2996 m MD, held wireline tension contant at ~7000 lbs. Made up TDS to each stand to limit backflow. At 2835 m MD, got indications on downhole ten sion that WL and fish were free, attempted to pull fish free with 12000 lbs WL tension - negative - WL still stuck.
2008-02-13 | 16:00:00 | 00:00:00 | 3035 | drilling -- dril l | ok | Tagged bottom at 2993m. Drilled from 2993m to 3035m. Increased mudweight from 1.40 sg to 1.45 sg . Drilling parameters: Flow 2090-2225 lpm / SPP 200-220 bar / String RPM 180 / ROP 2.5-8,5 m/hr / WOB 4-6 MT / TQ 15-20 kNm / ECD 1.59 SG. Had heavy stick slip with 10 MT WOB to start with, reduced WOB to 5 MT.
2008-02-14 | 00:00:00 | 01:00:00 | 3040 | drilling -- d rill | ok | Continued drilling from 3035m to 3040m. Drilling parameters: Flow 2225 lpm / SPP 220 bar / String RPM 180 / ROP 5-6.5 m/hr / WOB 4-6 MT / TQ 18 kNm / ECD 1.59 SG. Hidra started at 3040m.
2008-02-14 | 01:00:00 | 06:00:00 | 3064 | drilling -- d rill | ok | Continued drilling from 3040m to 3064m. Drilling parameters: Flow 2225 lpm / SPP 220 bar / String RPM 180 / ROP 3-6.5 m/hr / WOB 4-6 MT / TQ 15-18 kNm / ECD 1.59 SG. Held pit drill.
2008-02-14 | 06:00:00 | 07:30:00 | 3070 | drilling -- d rill | ok | Drilled 8 1/2" hole section from 3064 m to 3070 m MD. Drilling parameters : Flow 2200 lpm / SPP 220 bar / String RPM 180 / WOB 3-8 MT / Torque 11-22 kNm / ECD 1,59-1,60 sg. Contro lled WOB and ROP due to stick slip tendencies. Observed drilling break at 3070 m MD.
2008-02-14 | 07:30:00 | 08:00:00 | 3070 | drilling -- d rill | ok | Observed drilling break at 3070 m MD, ROP increased from 5 to 30 m/hr. Flowchecked well - ok - well static.
2008-02-14 | 08:00:00 | 11:15:00 | 3095 | drilling -- d rill | ok | Continued drilling 8 1/2" hole section from 3070 m to 3095 m MD. Drilling parameters : Flow 2200 lpm / SPP 220 bar / String RPM 180 / WOB 3-8 MT / Torque 15-20 kNm / ECD 1,59-1,60 sg. Controlled WOB and ROP due to stick slip tendencies.
2008-02-14 | 11:15:00 | 11:45:00 | 3095 | drilling -- d rill | ok | Observed drilling break at 3095 m MD, ROP increased from 5 to 35 m/hr. Flowchecked well - ok - well static.
2008-02-14 | 11:45:00 | 12:45:00 | 3103 | drilling -- d rill | ok | Continued drilling 8 1/2" section from 3095 to 3103 m MD. Drilling parameters : Flow 2200 lpm / SPP 222 bar / String RPM 180 / WOB 4-8 MT / Torque 16-24 kNm / ECD 1,60 sg.
2008-02-14 | 12:45:00 | 13:00:00 | 3103 | drilling -- d rill | ok | Performed SCR's.
2008-03-06 | 21:00:00 | 00:00:00 | 3114 | drilling -- casi ng | ok | POOH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3508 m to 3271 m MD wet. No obstruction encountered. Pumped slug. Continued to POOH from 3271 m to 3114 m MD. Pulled through tight spot at 3237 m with 25 MT overpull. Worked pipe several times to pass tight spot.
2008-03-03 | 21:00:00 | 00:00:00 | 3122 | drilling -- ca sing | ok | Changed bit depth to include 7" liner. Pumped OOH 265 lpm / 32 bar with 7" liner on 5 1/2" DP from 3414 m to 3122 m MD.
2008-02-24 | 03:00:00 | 06:00:00 | 3167 | interruption -- fish | ok | Pulled 5" DP while feeding torpedo through upper and lower sheaves. Had to dismantle wire guides on lower sheave for torpedo to pass. Fitted T-bar and hung off wire in rotary. Slacked off wire and removed from depth counters on WL unit. Spooled torpedo onto WL drum and inserted WL back in depth counters.
2012-09-15 | 00:00:00 | 06:00:00 | 3180 | workover -- wire line | ok | Logged RST-D in IC mode pass#3 from 3380 to 3250 m at 0,5 m/min.
2008-02-24 | 02:45:00 | 03:00:00 | 3192 | interruption -- fish | ok | Picked up 10 m while allowing wireline to slack off - observed surface and downhole WL tension decreasing.
2008-02-24 | 00:00:00 | 02:00:00 | 3202 | interruption -- fish | ok | RIH with 5" DP from 2996 m to 3202 m MD, held wireline tension contant at ~7000 lbs. Made up TDS to each stand to limit backflow. Hole condtions good - no significant drag observed.
2008-02-24 | 02:00:00 | 02:15:00 | 3202 | interruption -- fish | ok | Broke circulation and cleaned grapple pumping 300 strokes at 1000 lpm. Observed imbalance pipe/annulus when stopped pumping - SPP 5 bar. Good corrspondance with dow nhole pressure of 430 bar read from log and 1,47 sg mudweight in annulus.
2008-02-24 | 02:15:00 | 02:45:00 | 3202 | interruption -- fish | ok | RIH with 5" DP from 3202 m MD and caught fish at 3221 m MD. Set down ~5 MT on fish and observed indication of succesful catch on surface and downhole WL tension.
2012-09-14 | 06:00:00 | 07:05:00 | 3210 | workover -- wire line | ok | Logged RST-D in Sigma mode from 3400 to 3210 m at 4,5 m/min.
2012-09-14 | 07:30:00 | 14:20:00 | 3215 | workover -- wire line | ok | Logged RST-D in IC mode pass#1 from 3410 to 3215 m at 0,5 m/min.
2012-09-14 | 15:00:00 | 23:00:00 | 3215 | workover -- wire line | ok | Logged RST-D in IC mode pass#2 from 3410 to 3215 m at 0,5 m/min.
2012-09-15 | 06:00:00 | 07:40:00 | 3220 | workover -- wire line | ok | Continued logging RST-D in IC mode pass#3 from 3250 to 3220 m at 0,5 m/min.
2008-03-12 | 15:30:00 | 16:30:00 | 3228 | drilling -- drill | ok | POOH with 6" PDC bit and scraper assembly on 5 stds of 5 1/2" DP wet from 3430 m to 3228 m. Flow checked well static. Ok.
2010-09-24 | 14:00:00 | 21:15:00 | 3230 | workover -- wire lin e | ok | Logged RST-D in IC mode from 3390 to 3230 m at 0.5 m/min.
2010-09-24 | 21:45:00 | 22:30:00 | 3230 | workover -- wire lin e | ok | Logged RST in Sigma mode from 3390 to 3230 m at 4,5 m/min.
2010-09-25 | 06:00:00 | 08:00:00 | 3230 | workover -- wire li ne | ok | Continued logging RST-D in IC mode from 3260 to 3230 m at 0.5 m/min.
2008-02-27 | 05:15:00 | 06:00:00 | 3244 | interruption -- r epair | ok | Pulled logging tool free with ~5 MT overpull on block. Got overpull alarm 18 000 lbs on downhole tension. Communication with logging tools ok, but still unable to function high v oltage circuit. POOH with 5" DP from 3412,5 m to 3244 m MD. Maintained 2500 lbs pull in wireline while pulling out.
2008-02-17 | 11:45:00 | 16:30:00 | 3245 | formation evaluation -- log | ok | RIH with MDT logging string on 7/48 cable from surface to station #1 at 3245 m MD. Correlated MDT tool. Attempted to activate MDT probe - negativ e.
2008-02-18 | 08:00:00 | 08:15:00 | 3245 | interruption -- r epair | ok | Correlated toolstring and placed MDT probe at 3245 m MD sample point in Heather.
2008-02-18 | 08:15:00 | 09:30:00 | 3245 | formation evalu ation -- log | ok | Obatined pressure point sample at 3245 m MD in Heather. Attmepted to RIH - cable stuck with MDT at 3345 m MD.
2008-02-18 | 09:30:00 | 10:15:00 | 3245 | formation evalu ation -- log | ok | Worked MDT toolstring and found string to be stuck. No tension on cable head observed when pulling surface tension of max pull 12000 llbs - wire probably stuck/keyseated in f ormation. Depth on mechanical counter 3233 m MD.
2008-02-18 | 10:15:00 | 12:00:00 | 3245 | interruption -- fi sh | ok | Continued to work WL with max 12000 lbs pull. Observed movement of WL unit. Secured WL unit with chains. Checked sheave wheels on drillfloor.
2008-02-18 | 12:00:00 | 14:30:00 | 3245 | interruption -- fi sh | ok | Put 12000 lbs tension in WL and put on brake. Depth on mechancial counter 3232 m MD with 12000 lbs tension.
2008-02-18 | 14:30:00 | 22:00:00 | 3245 | interruption -- fi sh | ok | Worked WL several times. Slacked off to 5000 lbs and picked up to max tension 12000 lbs several tiems - not able to make progress. Prepared for doing cut and thread fishing o n drillpipe. Prepared fishing procedure. Decided to do fluid sampling at stuck point in Heather prior to fishing.
2008-02-18 | 22:00:00 | 23:00:00 | 3245 | formation evalu ation -- log | ok | Pumped to clear tool of mud. Activated MDT probe.
2008-02-18 | 23:00:00 | 00:00:00 | 3245 | formation evalu ation -- log | ok | Stepped up MDT pump in increments. Performed MDT sampling at 3245 m MD according to Schlumberger procedure.
2008-02-19 | 00:00:00 | 02:30:00 | 3245 | formation eval uation -- log | ok | Perfomed MDT sampling at 3245 m MD. Observed 170 bar diff pressure over probe. Filled 2 ea 450 cc bottles with formation fluid. Contamination ~13%. Total volume pumped ~3 0 litres.
2008-02-19 | 02:30:00 | 03:00:00 | 3245 | interruption -- fish | ok | Worked WL up and down in attempt to get free - negativ. Ran probe out/in and re-attempted freeing WL - negative. Slacked off WL to 3000 lbs tension => depth on mechanical co unter 3245 m MD.
2008-02-19 | 03:00:00 | 03:15:00 | 3245 | interruption -- fish | ok | Held pre-job meeting prior to rigging up for cut and thread fishing.
2008-02-19 | 03:15:00 | 06:00:00 | 3245 | interruption -- fish | ok | Put 7200 lbs tension on WL. Fitted T-clamp on 7/48 cable and slacked off WL. Cut 7/48 cable with 5-6 m loose end and fitted spear on same. Fitted spearhead overshot and 2 x fis hing weights to winch side of wireline. Removed sheave wheel from TDS. Removed sheave wheel from aft samson post.
2008-03-13 | 23:00:00 | 00:00:00 | 3252 | drilling -- d rill | ok | POOH wet with 5 std to 3252m.
2010-09-25 | 00:00:00 | 06:00:00 | 3260 | workover -- wire li ne | ok | Continued logging RST-D in IC mode from 3370 to 3260 m at 0.5 m/min.
2008-02-14 | 13:00:00 | 00:00:00 | 3265 | drilling -- d rill | ok | Continued drilling 8 1/2" hole section from 3103 m to 3265 m MD. Added LCM materials to mud prior to entering reservoir. Drilling parameters : Flow 2200 lpm / SPP 220-231 bar / String RPM 180 / WOB 3-8 MT / Torque 11-20 kNm / ECD 1,61-1,62 sg. ROP 10-30 m/hrs. Observed top of Hugin reservoir on logs 3250 m MD / 2987 m TVD. Max gas at top reservoir lag dept h 5 %.
2008-02-14 | 13:00:00 | 00:00:00 | 3265 | drilling -- d rill | ok | Performed pit drill at 16:25 hrs. Good response from loggers and driller.
2008-02-18 | 07:30:00 | 08:00:00 | 3270 | interruption -- r epair | ok | RIH with MDT toolstring on 7/48" cable from 2700 m to 3270 m MD.
2008-04-21 | 01:00:00 | 04:00:00 | 3300 | workover | ok | RIH with 4.5" TCP guns on 7/16" electric line from surface to 3300 m MD.
2008-04-21 | 01:00:00 | 04:00:00 | 3300 | workover | ok | Meanwhile worked on synergi report for derrick, performed general maintenace and prepared BOP for pressure test.
2008-02-15 | 00:00:00 | 01:30:00 | 3302 | drilling -- drill | ok | Drilled 8 1/2" hole section from 3265 m to 3302 m MD. Drilling parameters : Flow 2200 lpm / SPP 220-231 bar / String RPM 180 / WOB 3-8 MT / Torque 11-20 kNm / ECD 1,62-1,63 sg. ROP 30 m/hrs. Max gas 6%
2008-02-15 | 01:30:00 | 02:00:00 | 3302 | drilling -- drill | ok | Observed increase in active of ~1 m3 over 5 mins. Flowcheked well on trip tanks - ok - well static. Found that degassers had been started - volume from sandtraps overflowed into a ctive.
2008-02-15 | 21:00:00 | 21:45:00 | 3307 | drilling -- trip | ok | Pulled 5 stand wet from 3507 m to 3307 m MD. Pulling speed ~10 m/min. No overpull observed.
2008-02-15 | 21:45:00 | 22:15:00 | 3307 | drilling -- trip | ok | Flowchecked well - well static. Pumped 5 m3 1,65 sg slug.
2008-03-06 | 04:00:00 | 06:00:00 | 3320 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 2751 m to 3320 m MD. Filled pipe every 10 stds.
2008-02-15 | 02:00:00 | 04:45:00 | 3327 | drilling -- drill | ok | Continued drilling 8 1/2" hole section from 3302 m to 3327 m MD. Drilling parameters : Flow 2100-2200 lpm / SPP 216-238 bar / String RPM 180 / WOB 3-8 MT / Torque 11-20 kNm / ECD 1,61-1,63 sg. Limited ROP to and cut back flowrate to 2100 lpm due to increasing ECD. Downlinked powerdrive to stop build. Got problems with mudpump#2 and mudpump#3.
2008-02-15 | 04:45:00 | 05:15:00 | 3327 | interruption -- o ther | ok | Troubleshot mudpumps. Not able to start mudpump #3. Mudpump #2 gave wrong output on stroke setting. Decided to drill ahead using mudpump #1 only.
2008-03-01 | 04:30:00 | 06:00:00 | 3340 | drilling -- casi ng | ok | POOH with 7" liner hanger RT on 5 1/2" DP from 3399 m to 3340 m MD.
2008-02-15 | 05:15:00 | 06:00:00 | 3346 | drilling -- drill | ok | Continued drilling 8 1/2" hole section from 3327 m to 3346 m MD. Drilling parameters : Flow 2100 lpm / SPP 214 bar / String RPM 180 / WOB 3-6 MT / Torque 21 kNm / ECD 1,61 sg
2008-02-15 | 05:15:00 | 06:00:00 | 3346 | drilling -- drill | ok | . ROP 30 m/hrs.
2010-09-24 | 22:45:00 | 00:00:00 | 3370 | workover -- wire lin e | ok | Logged RST-D in IC mode from 3390 to 3370 m at 0.5 m/min.
2008-03-15 | 03:30:00 | 05:30:00 | 3380 | completion -- circul ating conditioning | ok | Continued RIH with clean out assy. from 2857m to 3380m
2012-09-14 | 23:30:00 | 00:00:00 | 3380 | workover -- wire line | ok | Logged RST-D in IC mode pass#3 from 3410 to 3380 m at 0,5 m/min.
2008-02-15 | 06:00:00 | 08:15:00 | 3385 | drilling -- drill | ok | Drilled 8 1/2" hole section from 3346 m to 3385 m MD. Drilling parameters : Flow 2100 lpm / SPP 220 bar / String RPM 180 / WOB 2-5 MT / Torque 20-23 kNm / ECD 1,61-1,62 sg / ROP 20-30 m/hrs.
2008-02-15 | 08:15:00 | 08:30:00 | 3385 | drilling -- drill | ok | Performed SCR's.
2008-03-06 | 13:00:00 | 17:45:00 | 3387 | drilling -- casi ng | ok | RB 1 std from 3510 m to 3478 m. No obstruction encountered.
2008-03-06 | 13:00:00 | 17:45:00 | 3387 | drilling -- casi ng | ok | Worked 1 std from 3478 m to 3437 m, 2200 lpm / 201 bar, 150 rpm / 12-15 kNm.
2008-03-06 | 13:00:00 | 17:45:00 | 3387 | drilling -- casi ng | ok | RB and reamed 1 std from 3437 m to 3397 m. Observed tight spots at 3428 m and 3423 m. Reamed through tigh spots with reduced flow of 1500 lpm due to packing off. Staged up parameteres to 2200 lpm / 200 bar while working through tight spots.
2008-03-06 | 13:00:00 | 17:45:00 | 3387 | drilling -- casi ng | ok | RB 1 std and circulated btms up whilst rotation and reciprocating pipe from 3397 m to 3357 m, 2200 lpm / 198 bar, 100 rpm / 12-14 kNm.
2008-04-21 | 04:30:00 | 05:15:00 | 3390.3 | workover | ok | RIH with guns to shooting depth. No WHP. Up weight 2985 kg / Running weight 1540 kg. Hanging weight 2330 kg. Fired guns and perforated interval #2 from 3395.0 m to 3408.5 m MD.
2008-04-21 | 04:30:00 | 05:15:00 | 3390.3 | workover | ok | No obvious indication that guns has fired, but observed short circuit in string and CCL stopped working. Observed no increase in WHP. PU weight increased with 100 kg (3100 kg).
2008-04-21 | 17:30:00 | 18:15:00 | 3390.3 | interrupti on -- rig up/down | ok | Correlated depth to 2 m pup-joint in 7" liner at 3228.38-3230.42 m tally depth / 3229.5 -3231.5 m WL dept correlated with GR on reservoar log using CCL. RIH with guns to shooting depth. No WHP. Fired guns and perforated interval #2 from 3395.0 m to 3408.5 m MD. Positiv indication that guns fired.
2008-02-29 | 09:15:00 | 00:00:00 | 3392 | drilling -- casing | ok | RIH with 7" liner from 925 m to 3392 m MD, filling every 5th stds. Max running speed was 8 stds/hr in cased hole and 5 stds/hr in open hole. Broke circulation at shoe at 2750 m, 1000 lpm / 53 bar.
2008-03-01 | 00:00:00 | 00:45:00 | 3392 | drilling -- casi ng | ok | Took 15 MT weight at 3392 m MD. MU TDS and attempted to work past tight spot with 20-30 MT. Up weight 181 MT / down weight 141 MT. Applied 9400 Nm RH torque when working s tring up. Released torque when working down.
2008-03-01 | 00:45:00 | 01:30:00 | 3392 | drilling -- casi ng | ok | Broke circulation, 230 lpm / 37 bar and established rate at 530 lpm / 49 bar. Washed down to tight spot applying max 20 MT. Observed pressure increasing to 60 bar. Shut down pumpe. Recorded 22 bar back pressure trapped below shoe. Applied 9400 Nm RH torque and worked string up. Recorded up weight of 151 MT, 30 MT upweight less than previous. Liner hang er RT most likely released from 7" liner.
2008-03-01 | 01:30:00 | 02:30:00 | 3392 | drilling -- casi ng | ok | Discussed further action and monitored well on trip tank.
2008-03-01 | 02:30:00 | 02:45:00 | 3392 | drilling -- casi ng | ok | Attempted to break circulation, negativ. Stopped pump at 45 bar after 243 ltrs pumped. Bleed off pressure to zero.
2008-03-01 | 02:45:00 | 03:30:00 | 3392 | drilling -- casi ng | ok | Discussed further action with town and monitored well on trip tank.
2008-03-08 | 11:30:00 | 20:30:00 | 3392 | drilling -- casin g | ok | RIH with 7" liner from 963 m to 3392 m MD, filling every 5th stds. Broke circulation at shoe at 2756 m for 5 min, 500 lpm / 17 bar. Worked past tight spot at 3358 and turned pip e 1/2 turn. Max running speed was 10 stds/hr in cased hole and 6 stds/hr in open hole.
2008-03-01 | 03:30:00 | 04:30:00 | 3399 | drilling -- casi ng | ok | PU and established up weight at 151 MT. Slacked off weight at 130 MT and observed no drag. Unable to tag liner. Broke circulation 220 lpm / 22 bar which indicated that we were circula ting through 5 1/2" DP and liner hanger RT. 7" liner most likely dropped further down.
2010-09-24 | 21:15:00 | 21:45:00 | 3400 | workover -- wire lin e | ok | RIH to 3400 m.
2010-09-24 | 22:30:00 | 22:45:00 | 3400 | workover -- wire lin e | ok | RIH to 3400 m.
2008-04-21 | 15:45:00 | 17:30:00 | 3408 | interrupti on -- rig up/down | ok | Schlumberger discussed with town and confirmed that CCL was ok. RIH with 4.5" TCP guns on 7/16" electric line from 360 m to 3408 m MD.
2008-02-27 | 00:45:00 | 02:45:00 | 3412.5 | formation evalu ation -- log | ok | Pumped 6 m3 slug and allowed active to stabilize. Correlated and took station at 3412,5 m MD.
2008-02-27 | 02:45:00 | 04:30:00 | 3412.5 | formation evalu ation -- log | ok | Performed fluid sampling at 3412,5 m MD. Monitored well on trip tank. Observed downhole tool failure. Adequate sample not obtained from this station.
2008-02-27 | 04:30:00 | 05:15:00 | 3412.5 | interruption -- r epair | ok | Troubleshot tool failure. Not able to function probe and pumps indicating problems with high voltage circuit. Checked surface equipment and confirmed ok. Discussed situation. D ecided to start pulling out of hole.
2008-02-26 | 20:15:00 | 00:00:00 | 3417.5 | formation evalua tion -- log | ok | Correlated and took station at 3417,5 for fluid sampling. Performed fluid sampling. Lined up to trip tank and monitored well continously while performing sampling.
2008-02-27 | 00:00:00 | 00:45:00 | 3417.5 | formation evalu ation -- log | ok | Performed fluid sampling at 3417,5 m MD. Obtained 2 ea 450 cc samples. Monitored well on trip tank.
2008-03-06 | 06:00:00 | 07:00:00 | 3420 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3320 m to 3395 m MD. Worked pipe to pass tight spot at 3395 m. MU TDS and rotated pipe 1/2 turn. Worked past tight spot and continued RIH to 3420 m.
2008-03-16 | 03:30:00 | 04:00:00 | 3420 | completion -- circulating condi tioning | ok | Racked back one std in derrick. Held tool box talk prior to pressure testing the 7" liner/liner lap.
2008-03-16 | 04:00:00 | 04:45:00 | 3420 | completion -- circulating condi tioning | ok | Lined up to the trip tank observed unstable gain. Closed in the well, investigated instability. No pressure built up. Checked the trip tank equipment, found t hat foaming was the reason.
2008-03-16 | 04:45:00 | 05:30:00 | 3420 | completion -- circulating condi tioning | ok | Performed manually flow check of the well, static.
2008-03-16 | 05:30:00 | 06:00:00 | 3420 | completion -- circulating condi tioning | ok | Made CMT hose and leak tested same to 345 bars for 5min. Commenced pressure test of well to 345 bars.
2008-03-16 | 06:00:00 | 06:45:00 | 3420 | completion -- circulating condi tioning | ok | Pressure tested the well to 345 bars 10 min. Pumped 2.2m³ - return 2.2m³. Rigged down surface equipment.
2008-03-16 | 06:45:00 | 07:45:00 | 3420 | completion -- circulating condi tioning | ok | Installed TIW valve & flow checked well. Added de-foamer to trip tank.
2008-03-16 | 07:45:00 | 08:00:00 | 3420 | interruption -- maintain | ok | Held tool box talk prior to slip and cut of drill line.
2008-03-16 | 08:00:00 | 11:00:00 | 3420 | interruption -- maintain | ok | Commenced to slip and cut drill line. Found threads in deadman anchor block damaged. Simultaneously monitored well over the trip tank.
2008-03-16 | 11:00:00 | 15:30:00 | 3420 | interruption -- maintain | ok | Re-cut the threads in the deadman anchor block. Simultaneously installed the Fairings on F-12 for the PR TBC using the ROV.
2008-03-16 | 15:30:00 | 16:15:00 | 3420 | interruption -- maintain | ok | Disconnected the hang of line & re-calibrated the main block/TDS. Functioned Crown-O-matic, set at 54.4 m. Simultaneously installed the Fairings on F-7 for the PR TBC using the ROV.
2010-09-24 | 11:15:00 | 13:30:00 | 3420 | workover -- wire lin e | ok | Continued RIH with BHA#2, RST to 3420 m.
2010-09-24 | 13:30:00 | 14:00:00 | 3420 | workover -- wire lin e | ok | Ran correlation passes. Adjusted the depth according to reference log.
2012-09-14 | 03:20:00 | 05:20:00 | 3420 | workover -- wire line | ok | Continued RIH with BHA#1, RST to 3420 m.
2012-09-14 | 05:20:00 | 06:00:00 | 3420 | workover -- wire line | ok | Ran correlation passes. Adjusted the depth according to reference log.
2012-09-14 | 07:05:00 | 07:30:00 | 3420 | workover -- wire line | ok | RIH to 3420 m.
2012-09-14 | 14:20:00 | 15:00:00 | 3420 | workover -- wire line | ok | RIH to 3420 m.
2012-09-14 | 23:00:00 | 23:30:00 | 3420 | workover -- wire line | ok | RIH to 3420 m.
2008-02-26 | 11:30:00 | 20:15:00 | 3421 | formation evalua tion -- log | ok | RIH with 5" DP and 7/46 cable. Pumped 650 lpm when moving string downwards. Performed pressure point sampling in Hugin formation from 3252 m to 3412 m MD accordin g to instructions from geologist. Hole condition good - no significant drag observed.
2008-04-20 | 13:00:00 | 13:30:00 | 3426 | workover -- perf orate | ok | Bled 50 bar WHP down to zero through closed drain. Correlated guns to shooting depth using GR. Hanging weight 2570 kg. Fired guns and perforated interval #1 from 3408.5 m to 3422.0 m MD. Positiv confirmation that guns had fired, but observed no increase in WHP.
2008-03-12 | 09:30:00 | 13:00:00 | 3430 | drilling -- drill | ok | Entered 7" liner PBR with reduced flow, 400 lpm / 45 bar. Observed no drag. Continued RIH with 6" PDC bit and scraper assembly on 5 1/2" DP from 2650 m to 3430 m.
2008-03-12 | 13:00:00 | 15:30:00 | 3430 | completion -- circulat ing conditioning | ok | MU TDS and washed down with scraper string from 3430 m to 3460 m, 1110 lpm / 143 bar. Up weight 159 MT. Pulled back and scraped liner interval 3440-3450 m, 1790 lpm
2008-03-12 | 13:00:00 | 15:30:00 | 3430 | completion -- circulat ing conditioning | ok | / 300 bar, 60 rpm / 10 kNM. Circulated 1 1/2" btms up at 1790 lpm / 300 bar. RB one std and flow checked well static. Ok.
2008-03-15 | 07:30:00 | 10:45:00 | 3435 | completion -- circul ating conditioning | ok | Scraped 7"/9 5/8"/10 3/4" casing, dressed/polished 7" liner top. Pulled back to 3435m, increased pump rate to 1960 lpm, 292 bars and conditioned mud.
2008-03-13 | 20:15:00 | 20:30:00 | 3440 | drilling -- o ther | ok | Held tool box talk prior to R/U for pressure testing of the EZSV plug and the 7" liner.
2008-03-13 | 20:30:00 | 22:15:00 | 3440 | drilling -- o ther | ok | Rigged up surface lines, flushed lines and tested same to 300 bars 5 min. Closed upper pipe rams and tested the EZSV plug and 7" liner to 300 bars 10 min. 2023 litres pumped and same in return.
2008-03-13 | 22:15:00 | 22:45:00 | 3440 | drilling -- o ther | ok | Rigged down surface test lines.
2008-03-13 | 22:45:00 | 23:00:00 | 3440 | drilling -- o ther | ok | Flow checked prior to POOH with the EZSV plug RT and the circ sub.
2008-04-20 | 09:15:00 | 13:00:00 | 3442 | workover -- wire line | ok | Opened HMV and observed 2 bar WHP. Verified TRSCSSV was open. Opened SV and RIH with 4.5" TCP guns on 7/16" electric line from surface to 3442 m MD. Up weight 28 50 kg / Running weight 1500 kg.
2008-03-15 | 18:30:00 | 18:45:00 | 3444 | completion -- circul ating conditioning | ok | Picked up 150 MT and let Well Commissioner relax. Picked up 6m. Equalized CMT unit and bled down CMT lines. Ran back in to 3444m.
2008-03-15 | 18:45:00 | 19:00:00 | 3444 | completion -- circul ating conditioning | ok | Emptied trip tank.
2008-03-15 | 19:00:00 | 19:45:00 | 3444 | completion -- circul ating conditioning | ok | Held tool box talk prior to pumping the washing train.
2008-03-15 | 19:45:00 | 00:00:00 | 3444 | completion -- circul ating conditioning | ok | Pumped washing train as per Halliburton program: 10 m3 dope cleaner pill, 30 m3 hivis push pill, 15 m3 hivis soap pill, 10 m3 seawater, 15 m3 hivis soap pill, 3200 lpm, 300 bar
2008-03-15 | 19:45:00 | 00:00:00 | 3444 | completion -- circul ating conditioning | ok | s. Chased wash train with 209m³ of completion fluid, 2200 lpm, 155 bars. Checked packer fluid after displacement: < 0.01% solids.
2008-03-16 | 00:00:00 | 03:30:00 | 3444 | completion -- circulating condi tioning | ok | Cleaned all surface lines, kill-, choke-line and manifold. Circulated well and checked packer fluid for solids, only trace of solids.
2008-03-15 | 06:00:00 | 07:30:00 | 3445 | completion -- circul ating conditioning | ok | Continued RIH washing down from 3420m, tagged the PBR 1,5 m deep (at 2662,3 m) with 2 MT, with mule shoe at 3445m, and polished at 500 lpm, 40 bars and 13 kNm.
2008-03-15 | 10:45:00 | 12:30:00 | 3445 | completion -- circul ating conditioning | ok | Set the Well Commissioner as per SPS instruction. Up/down weight with out pumping 167/137 MT, RIH and set down 13 MT on PBR. Closed upper pipe rams and pressured up the Well Commissioner in steps to 70 bars and monitored. Simultaneously held tool box talk prior to perform inflow test of the 7" liner and liner lap.
2008-03-15 | 10:45:00 | 12:30:00 | 3445 | completion -- circul ating conditioning | ok | Opened BOP. PU, relaxed well commisioner element.
2008-03-15 | 12:30:00 | 13:45:00 | 3445 | completion -- circul ating conditioning | ok | Displaced choke & kill line to Base oil, then soap mix to fill lines.
2008-03-15 | 13:45:00 | 16:00:00 | 3445 | completion -- circul ating conditioning | ok | Pumped 26 m³ Base oil + STP volume with 320 lpm, final pump pressure 147 bars (first 5m³ pumped at ~1000 lpm to clean lines). Final static pressure equaled = 134 bars, monitored same for 30 min. Re-set packer with 13.5 MT. New up/down weight 153/125 MT. Lined up to cement unit and equalised pressure across IBOP.
2008-03-15 | 16:00:00 | 18:00:00 | 3445 | completion -- circul ating conditioning | ok | Bled down the drill pipe pressure in stages to 10 bars prior to performing inflow test. 680 liters bled back. Inflow tested the 7" liner and liner lap.
2008-03-15 | 18:00:00 | 18:30:00 | 3445 | completion -- circul ating conditioning | ok | Pressured up DP to 138 bars with cement unit to equalize pressure across the Well Commissioner, 633 litres pumped.
2008-03-13 | 11:30:00 | 19:00:00 | 3448 | drilling -- d rill | ok | Continued RIH with EZSV plug and Circ. Sub on 5½" DP from 792m to 2625m at 2 min/std. Reduced RIH speed as entering the 7" line at 2661m, continue to RIH to 3448m EZSV plug se tting depth.
2008-03-13 | 19:00:00 | 20:15:00 | 3448 | drilling -- o ther | ok | Took up/down weight 168/136 MT. Established circulation at 220 lpm 12 bars. Reciprocated the string, increased rate in stages to 670 lpm 53 bars. Stopped circulation and positioned EZ SV plug at setting depth at 3448m up stroke. Installed the EZSV plug as per Halliburton procedure. Picked up 20 MT to shear the tension sleeve. Set down 10 MT on EZSV plug. Picked u p to 3440m.
2008-03-06 | 07:00:00 | 09:15:00 | 3478 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3420 m to 3478 m MD. Worked pipe to pass tight spot. MU TDS and applied 30 rpm and pumped 500 lpm / 38 bar. Worked past t ight spot and reamed up to 3420 m. Came down from 3420 m to 3478 m with no rotation and no flow.
2008-02-15 | 17:30:00 | 20:15:00 | 3507 | drilling -- circul ating conditioni ng | ok | Circulated hole clean with 3 x bottoms up. Reciprocated stand while pumping. Parameters : Flow 2100 lpm / SPP 212 bar / String RPM 150-180. Observed clean shakers after 3 x bo ttoms up.
2008-02-15 | 20:15:00 | 20:45:00 | 3507 | drilling -- trip | ok | Took up down weight 195/149 MT. Recorded off bottom torque at 10/15/20 RPM - 14-16 kNm. Sent downlink to set LWD tools according to Schlumberger instructions.
2008-02-15 | 20:45:00 | 21:00:00 | 3507 | drilling -- trip | ok | Flowchecked well - well static. Meanwhile held toolbox meeting prior to POOH.
2008-03-06 | 20:30:00 | 21:00:00 | 3508 | drilling -- casi ng | ok | Flow checked well. Static.
2008-03-08 | 22:30:00 | 23:00:00 | 3508 | drilling -- casin g | ok | Installed and MU cmt head. Spaced out liner to 3508 m / top liner hanger at 2665,6 m.
2008-03-08 | 23:00:00 | 00:00:00 | 3508 | drilling -- casin g | ok | Established circulation and increased pump rate in steps to 1140 lpm / 78 bar. Circulated 1 1/2 open hole volume (45 m3). Meanwhile pressure tested cmt line to 345 bar.
2008-03-09 | 00:00:00 | 00:15:00 | 3508 | drilling -- c asing | ok | Continued to circulate 1 1/2 open hole volume, 1140 lpm / 78 bar.
2008-03-09 | 00:15:00 | 01:30:00 | 3508 | drilling -- c asing | ok | Reduced pump rate to 200 lpm. Dropped the ball from the cmt head with liner in tension and chased the ball with 500 lpm / 30.6 bar. Landed ball after 653 stks pumped. Pressured up to 1 35 bar. Held 2 min. Bled down to 70 bar. Sat down 25 MT of drill pipe weight to verify that hanger was set. OK.
2008-03-09 | 00:15:00 | 01:30:00 | 3508 | drilling -- c asing | ok | Continued to pressure up to 175 bar to relese setting tool. Held 1 min. Continued to pressure up to shear out ball seat. Sheared at 228 bar. PU to verify that liner was released. Up weight 158 MT / down weight 134 MT.
2008-03-09 | 01:30:00 | 03:00:00 | 3508 | drilling -- c asing | ok | Sat down weight to 130 MT. Established circulation while rotating and increased pump rate in steps up to 1200 lpm / 74 bar, 20 rpm / 10-12 kNm. Pumped 95 m3. Meanwhile held pre-job meeting for cmt job.
2008-03-09 | 03:00:00 | 05:30:00 | 3508 | drilling -- c asing | ok | Pumped 10 m3 base oil, 780 lpm / 80 bar and 15 m3 of 1.65 sg tuned spacer E+ at 665 lpm / 80 bar with mud pumps while rotating liner 15 rpm / 12 kNm. Lined up to cmt unit through cmt hose. Dropped dart to release bottom wiper plug.
2008-03-09 | 03:00:00 | 05:30:00 | 3508 | drilling -- c asing | ok | Mixed and pumped 15.9 m3 1.90 sg cement slurry at 680 lpm / 80 bar and displaced cement with 0.9 m3 freshwater to rig floor. Dropped dart to release top wiper plug.
2008-03-09 | 03:00:00 | 05:30:00 | 3508 | drilling -- c asing | ok | Lined up to rig pumps and pumped 19 stks before flag indicated dart had dropped. Displaced cement with 45 m3 OBM at 1200 lpm, 15 rpm / 15-18 kNm with full returns. Slowed down pu mp rate to 500 lpm after 1930 strks. FCP = 42 bar. Stopped pumping after 2052 + 19 = 2071 strks pumped. Observed torque increased to 26 kNm after 2071 strks pumped, but had no bu mp.
2008-03-09 | 05:30:00 | 06:00:00 | 3508 | drilling -- c asing | ok | Checked for back flow. Ok. RD cmt hose.
2008-03-09 | 06:00:00 | 08:00:00 | 3508 | drilling -- c asing | ok | Sat TSP packer according to Weatherford procedure. Closed annular and pressured up to 300 bar. Pressure tested TSP packer to 300 bar / 10 min with 1.45 sg OBM.
2008-03-09 | 08:00:00 | 09:15:00 | 3508 | drilling -- c asing | ok | Released liner hanger RT by pressuring up to 70 bar. Pulled and measured RT out of PBR. Increased rate to 1000 lpm when pressure dropped. Dropped 2 sponge balls and circulated DP clean. Circulated out excess cmt, 2000 lpm / 80 bar. Observed cmt and spacer in returns. Circulation pressure increased to 98 bar and then level out.
2008-03-09 | 09:15:00 | 10:15:00 | 3508 | drilling -- c asing | ok | LO cmt head and 10 ft pup joint.
2008-02-15 | 08:30:00 | 17:30:00 | 3510 | drilling -- drill | ok | Continued drilling 8 1/2" hole section from 3385 m to section TD at 3510 m MD. Drilling parameters : Flow 2100 lpm / SPP 220 bar / String RPM 180 / WOB 3-12 MT / Torque 13-23 kNm / ECD 1,59-1,60 sg / ROP 10-30 m/hrs. Racked back one stand of drillpipe.
2008-03-06 | 09:15:00 | 09:30:00 | 3510 | drilling -- casi ng | ok | Washed down with 8 1/2" wiper trip BHA on 5 1/2" DP from 3478 m to 3510 m MD, 1400 lpm / 128 bar, 50 rpm / 13-14 kNm.
2008-03-06 | 09:30:00 | 13:00:00 | 3510 | drilling -- casi ng | ok | Circulated 3 x btms up and conditioned mud at 3510 m whilst rotating and reciprocating string. Increased flow in steps up to 2200 lpm / 206 bar, 150 rpm / 13-17 kNm to be able t o control ECD. Max MW out of hole 1.56 sg. Final ECD 1.57 sg. Max gas 9.3%.
2008-03-06 | 17:45:00 | 18:45:00 | 3510 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3387 m to 3508 m MD. No obstruction encountered. Observed 1.5 m fill at TD.
2008-03-06 | 18:45:00 | 20:30:00 | 3510 | drilling -- casi ng | ok | Circulated btms up at 3510 m, 2200 lpm / 196 bar, 100 rpm / 12-14 kNm. Up weight 178 MT / down weight 134 MT.
2008-03-06 | 18:45:00 | 20:30:00 | 3510 | drilling -- casi ng | ok | Readings to give comparison for liner running:
2008-03-06 | 18:45:00 | 20:30:00 | 3510 | drilling -- casi ng | ok | Rotating 10 rpm / 11-12 kNm, 15 rpm / 11-13 kNm, 20 rpm / 10-13 kNm. Rotating upweight 172 MT / rotating down weight 137 MT.
2008-03-06 | 18:45:00 | 20:30:00 | 3510 | drilling -- casi ng | ok | Pumping 500 lpm / 19 bar, 1000 lpm / 54 bar, 1500 lpm / 102 bar. Distance from neutral to up weight is 0.6 m.
2008-03-08 | 20:30:00 | 22:30:00 | 3510 | drilling -- casin g | ok | RIH with 7" liner from 3392 m to 3468 m MD, filling every 5th stds. MU last std and broke circulation. Staged up pumps to 340 lpm / 23 bar and washed down. Tagged TD at 35 10 m MD. Up weight 190 MT / down weight 142 MT.

## OperationsByDay
Date | Start time | End time | End Depth mMD | Main - Sub Activity | State | Remark
2007-06-09 | 12:00:00 | 12:30:00 | 0 | drilling -- trip | ok | Held pre-job meeting prior to start operation.
| 12:30:00 | 14:30:00 | 10 | drilling -- trip | ok | - no sucess - decided to use drillers depth for survey reference.
P/U 36" hole opener BHA, hung off in rotary. Installed bushing and slips. Removed safety clamp from centralizer guide bushing. Attempted to calibrate MWD depth sensor
| 14:30:00 | 19:00:00 | 100 | drilling -- trip | ok | Continued making up 36" hole opener BHA.
| 19:00:00 | 22:30:00 | 146 | drilling -- drill | ok | Changed to automatic slips. RIH with 36" hole opener BHA on 5 1/2" HWDP. Dove ROV. Observed stabbing BHA into guide funnel with ROV. Tagged seabed at 145,6 m MD with no flow or rotation.
| 22:30:00 | 23:00:00 | 150 | drilling -- drill | ok | Washed down with 36" hole opener BHA with 600 lpm. Observed centralizer guide bushing landing in template guide funnel. Parked ROV in top hat prior to start rotating.
| 23:00:00 | 00:00:00 | 157 | drilling -- drill | ok | Drilled 36" hole section from 150 m to 157 m MD. Drilling parameters : Rotation 15-20 rpm / WOB 2 MT/ Flow 900 lpm. Svept hole with 15 m3 hi-vis at 157 m MD.
2007-06-10 | 00:00:00 | 02:30:00 | 170 | drilling -- drill | ok | Continued drilling 36" hole section from 157 m to 170 m MD. Drilling parameters : Rotation 70 rpm / WOB 2 MT / Flow 4100 lpm / Torque 6-12 kNm . Performed surv ey on every single - got unreliable data at 157 m and 170 m MD.
| 02:30:00 | 03:15:00 | 170 | drilling -- drill | ok | Due to unreliable survey data and suspected inclination build up => Performed reaming trip back to 150 m MD.
Meanwhile discussed situation. Found out that surveys had been taken while string was rotating which again gave wrong / unreliable readings.
| 03:15:00 | 03:30:00 | 170 | drilling -- drill | ok | Repeated survey at 170 m MD. Inclination 0,4 deg - ok.
| 03:30:00 | 06:00:00 | 192 | drilling -- drill | ok | Drilled 36" hole section from 170 m to 192 m MD. Drilling parameters : Rotation 70 rpm / WOB 2-3 MT / Flow 4100 lpm / Torque 5-8 kNm. Swept hole with 15 m3 hi- vis every single drilled.
Inclination at 183 m MD 0,06 deg - ok.
| 06:00:00 | 10:30:00 | 222 | drilling -- drill | ok | Continued drilling 36" hole section from 192 m to 222 m MD. Drilling parameters : Rotation 70 rpm / WOB 2 MT / Flow 4100 lpm / Torque 8-12 kNm. Swept hole with 15 m3 hi-vis every single drilled.
| 10:30:00 | 11:00:00 | 222 | interruption -- other | ok | Due to problems with PRS at connection - reciprocated pipe and made extra sweep with hi-vis.
| 11:00:00 | 19:00:00 | 256.5 | drilling -- drill | ok | Continued drilling 36" hole section from 222 to 256,5 m MD. Drilling parameters : Rotation 70 rpm / WOB 2-5 MT / Flow 4100 lpm / Torque 8-12 kNm. Swept hole wit h 15 m 3 hi-vis every single drilled.
| 19:00:00 | 19:30:00 | 256.5 | drilling -- circulating co nditioning | ok | Circulated well clean with 4400 lpm / SPP 90 bar. Pumped 25 m3 hi-vis. Performed final survey at TD.
| 19:30:00 | 20:30:00 | 256.5 | drilling -- circulating co nditioning | ok | Displaced well to 1,35 sg WBM at 4000 lpm / SPP 90 bar. Pumped a total of 100 m3.
| 20:30:00 | 21:00:00 | 256.5 | interruption -- other | ok | Had problems to release torque wrench when attempting to unscrew from topdrive. Troubleshot problem.
| 21:00:00 | 23:00:00 | 152 | drilling -- drill | ok | POOH with 36" hole opener BHA from 256,5 m to 152 m MD. Topped up hole with 1,35 sg WBM pumping at 400 lpm.
| 23:00:00 | 23:30:00 | 100 | drilling -- drill | ok | Continued to POOH with 36" hole opener BHA from 152 m to 100 m MD. Removed automatic slips and replaced master bushing.
2007-06-11 | 00:00:00 | 03:00:00 | 0 | drilling -- trip | ok | Broke out and laid out 2 single 9 3/4" DC. Attempted to rack back 36" hole opener BHA comprising of 36" hole opener, MWD and 9 3/4" DC - nogo due to exceeded weight on PR
S. Hung off BHA again and broke out 9 3/4" DC. Racked back DC. Racked back hole opener / MWD.
| 03:00:00 | 04:30:00 | 0 | drilling -- drill | ok | Performed FG inspection on TDS and derrick. Vetco Gray installed inclinometer on CART bracket. Had to place shimm rings on bracket to level out the inclinometer.
| 04:30:00 | 06:00:00 | 0 | drilling -- casi ng | ok | Removed elevator and bails. Cleared drillfloor. Rigged up for running 30" conductor.
| 06:00:00 | 07:30:00 | 0 | drilling -- casi ng | ok | Continued rigging up for running 30" conductor. Installed bails and elevator.
| 07:30:00 | 09:00:00 | 0 | drilling -- casi ng | ok | Performed pre-job meeting at drillfloor prior to start running 30" conductor.
| 09:00:00 | 10:15:00 | 0 | drilling -- casi ng | ok | Picked up 30" shoe joint. Filled joint with water and observed float opening - ok. Tested and rearranged tongs.
| 10:15:00 | 14:30:00 | 66 | drilling -- casi ng | ok | Ran 30" conductor to 66 m MD.
| 14:30:00 | 18:15:00 | 100 | drilling -- casi ng | ok | 24,5 m below ML 14,8 m below ML
Ran 30" conductor including ST-2 x RL-4 xover fm 66 m to 100 m MD. Strapped top up pipe along conductor on XMT deck. Filled 30" conductor with SW on way in.
Top up pipe cement outlets to be located at : 43,4 m below ML
| 18:15:00 | 19:00:00 | 100 | drilling -- casi ng | ok | Changed to 5 1/2" handling equipment prior to picking up 30" conductor housing.
| 19:00:00 | 19:30:00 | 100 | drilling -- casi ng | ok | Held toolbox talk.
| 19:30:00 | 20:30:00 | 100 | drilling -- casi ng | ok | Picked up 30" conductor housing. Made up RL-4 connection to 36000 ft lbs using rig tongs. Enagaged anti-rotation slots.
| 20:30:00 | 21:30:00 | 111 | drilling -- casi ng | ok | Ran in with 30" conductor housing and installed top up pipe on XMT deck.
| 21:30:00 | 22:00:00 | 111 | drilling -- casi ng | ok | Installed C-plate in rotary and landed 30" conductor housing in same. Broke out and laid down 30" handling CART.
| 22:00:00 | 22:30:00 | 111 | drilling -- casi ng | ok | Rig up C-plate, bowl and slips for running cement stinger on top of 30" conductor housing.
| 22:30:00 | 00:00:00 | 111 | drilling -- casi ng | ok | Ran 4 3/4" aluminum cement stinger inside 30 conductor.
2007-06-12 | 00:00:00 | 00:30:00 | 111 | drilling -- casi ng | ok | Continued running 4 3/4" aluminum cement stinger inside 30" conductor. Installed a total of 10 joints adding up to 91 m, i.e. approx 16 m off shoe bottom. Installed centralizers on j oint number 3 and 6.
| 00:30:00 | 01:30:00 | 111 | drilling -- casi ng | ok | Picked up primary CART. M/U 4 1/2" IF x butress X-over to low end of CART. M/U CART to innerstring. Removed innerstring handling equipment. Made up CART to 30" conducto r housing with 5 lefthand turns. Checked inclinometer -ok. Checked filler valve in open position - ok.
| 01:30:00 | 03:00:00 | 137 | drilling -- casi ng | ok | Ran in with 30" conductor on 5 1/2" HWDP. Strapped residual top up pipe to the conductor housing on XMT deck. Installed ROV plugs in 30" conductor housing on Centralizer de ck.
| 03:00:00 | 03:30:00 | 137 | drilling -- casi ng | ok | In order not to damage ROV plugs, inclinometer and filler valve => Used chain hoists / steel slings to center top of housing through the Centralizer deck.
| 03:30:00 | 05:00:00 | 200 | drilling -- casi ng | ok | Ran in with 30" conductor on 5 1/2" HWDP. Observed with ROV when running through template slot.
| 05:00:00 | 06:00:00 | 215 | drilling -- casi ng | ok | Started loosing hook weight at 200 m MD. Worked string up and down trying to release friction in well.
| 06:00:00 | 07:45:00 | 210 | drilling -- casi ng | ok | Contiuned to work 30" conductor. Had overpull of 15 MT.
| 07:45:00 | 11:30:00 | 237 | drilling -- casi ng | ok | Closed filler valve with ROV. Started circulation with SW at 2300 lpm thorugh 30" conductor. Worked 30" conductor while circulating w/ maximum 12 bar pumppressure and 10 mt downweight. Put datum mark on pipe 112,88 m centralizer deck to top 30" conductor housing.
| 11:30:00 | 13:30:00 | 251 | drilling -- casi ng | ok | Broke out two joints from 5 1/2" HWDP stand. M/U cement stand with side entry sub and lotorqe valve. Continued to work 30" condcutor while ciruclating SW at 2300 lpm. Reach ed TD and confirmed correct depth by datum mark on pipe towards machined ring on centralizer deck.
| 13:30:00 | 15:00:00 | 251 | drilling -- casi ng | ok | Before engaging rams ; roll 0,04 to 0,3 / pitch 0,01 to 0,2 After engaging rams ; roll static at 0,13 / pitch static at 0,05
Hooked up ROV with hydraulic reservoir to hydraulic receptacle on template. Engaged centralization rams in template funnel.
Pitch and roll readings :
| 15:00:00 | 15:30:00 | 251 | drilling -- casi ng | ok | Circulated at 2300 lpm / SPP 11 bar to confirm no leaks on plugs in conductor housing. No leaks could be observed by the ROV. Meanwhile held cementing prejobmeeting at drill floor.
| 15:30:00 | 16:15:00 | 251 | drilling -- casi ng | ok | Prepared for cementing conductor. Lined up and tested cement lines to 200 bar / 5 min - ok.
| 16:15:00 | 17:45:00 | 251 | drilling -- casi ng | ok | Pumped 75 m3 of 1,50 sg X-lite cement slurry with cement unit. Pump pressure during cement displacement 13 bar. Displacement rate 800 lpm.
| 17:45:00 | 18:00:00 | 251 | drilling -- casi ng | ok | Displaced cement with seawater. Pressure rose from 20 bar to approx 35 bar during displacement indicating cement in annulus and good cement job. Pumped a total of 8,5 m3 le aving theoretical TOC at 247 m MD inside the 30" conductor.
| 18:00:00 | 18:15:00 | 251 | drilling -- casi ng | ok | Rigged down cement hose and flushed same. Flushed manifold.
| 18:15:00 | 00:00:00 | 251 | drilling -- casi ng | ok | -Cleared and tidied rigfloor
-Flushed and cleaned cement unit
-Inspected seabed for cement returns - inconcluisve due to poor visiblity
-PV on drillfloor equipment
Meanwhile :
Waited on cement to set up.
2007-06-13 | 00:00:00 | 04:00:00 | 251 | drilling -- casing | ok | -FG inspection on drillfloor
-Grinded down weld seam on LP riser
-PV on drillfloor equipment
Meanwhile :
Waited on cement to set up.
| 04:00:00 | 04:30:00 | 251 | drilling -- casing | ok | Held toolbox talk prior to pumping down the top up pipe.
| 04:30:00 | 05:00:00 | 251 | drilling -- casing | ok | Lined up to pump down top up pipe. Tested line and manifold 100 bar / 5 min.
| 05:00:00 | 06:00:00 | 251 | drilling -- casing | ok | 24 bar (gauge) - ok 33 bar (gauge) - ok 39 bar (gauge) - ok
At 46 bar gauge, i.e approx 53 bar (770 psi) differential, pressure bled of rapidly indicating burst disk rupture. Indications are that it is the shallowmost disk that ruptured.
Stepped up pressure pumping at 50 l/min. Held pressure at predetermined levels :
| 06:00:00 | 07:15:00 | 0 | drilling -- casing | ok | Assessed situation. Conferred with shore. Decided to do remedial cement job through top up pipe. Did circulation test through cement hose / top up pipe, 50 bar / 500 lpm.
Meanwhile, prepared for top up cement job.
| 07:15:00 | 07:45:00 | 0 | drilling -- casing | ok | Held toolbox talk in mud control room prior to cement top up job.
| 07:45:00 | 08:00:00 | 0 | drilling -- casing | ok | Lined up and pressure tested cement lines to 200 bar / 5 min - ok.
| 08:00:00 | 10:15:00 | 0 | drilling -- casing | ok | Performed remedial cement job. Pumped 15 m3 of 1,56 G-cement slurry. Pump pressure during cementing 32 bar. Held pumping rate steady at 350 lpm. Displaced cement d own cement hose and top up pipe with 1,1 m3 SW.
| 10:15:00 | 12:00:00 | 0 | drilling -- casing | ok | Disconnected hose and dropped release ball. Let ball drop and sheard out release sub on UWG with 176 bar. Flushed cement lines/ hose down to seabed.
| 12:00:00 | 13:00:00 | 0 | drilling -- casing | ok | Reading on inclinometer before releasing CART : Pitch 0,09 / Roll 0,11
Released CART from 30" conductor housing by 5 righthand turns. Pulled CART clear of template.
| 13:00:00 | 13:30:00 | 0 | drilling -- casing | ok | Broke out and racked back cementing assembly.
| 13:30:00 | 14:00:00 | 0 | drilling -- casing | ok | Made up TDS to string and pumped cleaning sponge through the pipe at 2600 lpm.
| 14:00:00 | 15:00:00 | 0 | drilling -- casing | ok | Removed Inclinometer from CART with ROV. POOH with CART and cement stinger on 5 1/2" HWDP. Installed bowl and bushing for handling 4 3/4" aluminum inner string. B roke 4 1/2" IF connection underneath CART. Racked back CART in derrick.
| 15:00:00 | 15:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to retrieveng 4 3/4" aluminum inner string.
| 15:15:00 | 16:15:00 | 0 | drilling -- casing | ok | Broke out and laid down 4 3/4" aluminum inner string. Laid down pipe in doubles.
| 16:15:00 | 16:30:00 | 0 | drilling -- casing | ok | Cleared rig floor of cement stinger handling equipment.
| 16:30:00 | 16:45:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to transerferring tension cylinders through wellhead module down to Centralizer deck.
| 16:45:00 | 18:30:00 | 0 | drilling -- casing | ok | Transfered tension cylinders for F-4 down to Centralizer deck.
| 18:30:00 | 20:00:00 | 0 | drilling -- casing | ok | ****Operations transferred to F-12****
Transferred tension cylinders for F-7 down to Centralizer deck.
2007-10-12 | 06:00:00 | 07:00:00 | 0 | moving -- skid | ok | Skidded derrick towards port to allign with slot F-4.
| 07:00:00 | 07:30:00 | 0 | moving -- skid | ok | Held toolbox talk before skidding cantilever in longitudinal direction. Observed buckeled standpipe hose in dragchain.
| 07:30:00 | 09:30:00 | 0 | interruption -- other | ok | Straightened standpipe hose in dragchain with chainhoists.
| 09:30:00 | 11:00:00 | 0 | moving -- skid | ok | Skidded cantilever to slot F-4 position.
| 11:00:00 | 12:30:00 | 0 | moving -- skid | ok | Removed weatherdeck hatch on slot F-4. Installed cantilever access stairs. Made final transverse and longitudinal adjustments to center derrick above F-4. Pre pared for removing support beams on aft PRS.
| 12:30:00 | 14:15:00 | 0 | interruption -- other | ok | Removed support beams on upper arm on aft PRS. Performed NDT inspection of PRS hoisting carriage.
| 14:15:00 | 16:00:00 | 0 | moving -- skid | ok | Worked on hatches on Weatherdeck. Removed covers on WH module decks on slot F-4. Built scaffolding/fence around F-4 on all levels. Meanwhile changed to monel dies on PRS gripper head.
| 16:00:00 | 18:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Rigged up slings for installing diverter. Installed diverter, outer ring and masterbushing. Rigged down slings.
| 18:30:00 | 21:15:00 | 0 | drilling -- wait | ok | -Cleared and tidied drillfloor
-Dressed PS-30 with 5 1/2" die holders/dies
Meanwhile:
Waited on crane to finish loading/backloading supply boat due to urgent need for supply boat going to shore.
| 21:15 | 21:30:00 | 0 | drilling -- trip | ok | Held toolbox talk prior to making up 17 1/2" drilling BHA.
| 21:30:00 | 00:00:00 | 32 | drilling -- trip | ok | Made up 17 1/2" BHA according to Schlumberger instructions. Gauged bit and stabilizers. Set scribline and measured corrections on GWD and MWD. Adjusted UBHO sub in line with scribeline.
2007-10-13 | 00:00:00 | 01:15:00 | 140 | drilling -- d rill | ok | Made up x-over above NM collars. RIH with 17 1/2" drilling BHA on DC/5 1/2" HWDP. Made up and ran hydraulic jar.
| 01:15:00 | 02:00:00 | 220 | drilling -- d rill | ok | While observing with ROV, stabbed 17 1/2" BHA into 30" housing/CTS funnel. RIH with 17 1/2" BHA to 220 m MD. ROV took position and started CTS pump. Not able to operate suction v alve from pit#7 when attempting to start pumping.
| 02:00:00 | 02:30:00 | 220 | interruptio n -- other | ok | Not able to operate suction valve from pit#7. Locked valve open.
| 02:30:00 | 03:45:00 | 250 | drilling -- d rill | ok | Commenced pumping at 3500 lpm and tested communication to MWD - ok. Observed severe cavitation in string. Reduced rate to 2000 lpm and washed down to 247 m MD and tagged T OC. Drilled cement inside 30" shoetrack. Drilling parameters : 3500 lpm / SPP 80 bar / 40 RPM / Torque 1-3 kNm / WOB 4 MT.
| 03:45:00 | 05:00:00 | 260 | drilling -- d rill | ok | Drilled and opened 36" / 26" / 17 1/2" rathole from 250 m to 260 m MD. Drilling parameters : Flow 3500 lpm / SPP 82 bar / 40 RPM / WOB 1-2 MT / Torque 2-3 KNm. Reamed through sho etrack / rathole 3 times. Pumped 20 m3 hi-vis to clean hole.
| 05:00:00 | 06:00:00 | 265 | drilling -- d rill | ok | Drilled new formation from 260 m to 265 m MD. Drilling parameters : Flow 3500 lpm / SPP 83 bar / 40 RPM / WOB 1-3 MT / Torque 2-3 KNm.
| 06:00:00 | 06:30:00 | 265 | drilling -- d rill | ok | Pumped 15 m3 hi-vis sweep on bottom. Had to wait for WL gyro unit to become operational.
| 06:30:00 | 07:45:00 | 223 | interruptio n -- other | ok | Had to wait for WL gyro unit to become purged and operational. This was caused by downtime on STB crane during the night, not able to do the lift in due time. Circulated at 3500 lpm and reciprocated pipe. Racked back stand and pulled bit inside conductor shoe to 223 m MD.
| 07:45:00 | 08:00:00 | 223 | drilling -- d rill | ok | Removed masterbushing and installed automatic slips.
| 08:00:00 | 09:00:00 | 262 | drilling -- d rill | ok | RIH with 17 1/2" BHA from 223 m to 262 m MD to obtain favourable stick up for running WL gyro. Not able to lay out single due to WL unit in V-door. Rigged up for running WL gyro. Held t oolbox talk prior to running gyro.
| 09:00:00 | 10:00:00 | 262 | drilling -- s urvey | ok | RIH with gyro on WL, located gyro in UBHO and performed survey. Pulled out with gyro and performed survey while pulling out.
| 10:00:00 | 10:30:00 | 262 | drilling -- d rill | ok | Attempted to orient toolface - negative due to high torque. Pulled string to work out the torque, observed 25 MT overpull.
| 10:30:00 | 11:00:00 | 262 | drilling -- d rill | ok | Attempted to pull inside shoe, observed 25 MT overpull.
| 11:00:00 | 12:15:00 | 249 | drilling -- d rill | ok | Installed 5 m pup joint and made up TDS for pumping. String free down. Established circulation with 3100 lpm. Swept hole with 20 m3 hi-vis. Pulled 17 1/2" BHA from 262 m to 249 m MD i nside conductor shoe. Got 11 m stick-up.
| 12:15:00 | 13:15:00 | 249 | drilling -- s urvey | ok | RIH with gyro on WL, located in UBHO and performed survey. Oriented toolface as required. Halted operation due to possible power-shut down during ESD test.
| 15:15:00 | 15:45:00 | 265 | drilling -- d rill | ok | RIH with 17 1/2" BHA to 265 m MD. Laid out 5 m pup joint and made up stand.
| 15:45:00 | 00:00:00 | 424 | drilling -- d rill | ok | Drilled 17 1/2" hole section from 265 m to 424 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3500 lpm / SPP 75-90 bar / 100 RPM / WOB 1-9 MT / Torq ue 3-7 kNm. Increaed RPM to 140 during rotary drilling. Pumped 30 m3 hi-vis per stand to clean hole. Average ROP 19 m/hrs. Good correspondance between GWD and MWD obtained at 383 m MD.
2007-10-14 | 00:00:00 | 06:00:00 | 560 | drilling -- d rill | ok | / Torque 4-7 kNm. Increaed RPM to 140 during rotary drilling. Pumped 2 x 15 m3 hi-vis per stand to clean hole. Average ROP 23 m/hrs. Performed cluster shots for SUCOP corrections of MWD data.
Drilled 17 1/2" hole section from 424 to 560 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3500-3800 lpm / SPP 90-100 bar / 100 RPM / WOB 5-12 MT
| 06:00:00 | 16:15:00 | 866 | drilling -- d rill | ok | Drilled 17 1/2" hole section from 560 m to 866 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3500-4500 lpm / SPP 90-145 bar / 100 RPM / WOB 5-10 MT / Torque 6-9 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 10 m3 Hi-vis per stand. Reamed one single per stand. Average ROP 30 m/hrs.
| 16:15:00 | 17:15:00 | 866 | drilling -- d rill | ok | Prepared for driling Utsira formation at 866 m MD. Reamed full stand once. Circulated 1,5 x bottoms up at 4500 lpm. Inclination before entering Utsira was 16,6 deg.
| 17:15:00 | 23:00:00 | 1107 | drilling -- d rill | ok | Drilled 17 1/2" hole section from 866 to 1107 m MD. Top Utsira encountered at 890 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3100 lpm / SPP 90-1 00 bar / 100 RPM / WOB 5-12 MT / Torque 4-7 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 15 m3 Hi-vis per stand. Average ROP 37 m/hrs.
| 23:00:00 | 00:00:00 | 1077 | drilling -- d rill | ok | Observed negative drilling brake indicating base Utsira encontered at 1077 m MD. Drilled 17 1/2" hole section from 1077 to 1107 m MD. Inclination on base Utsira 12,3 deg.
2007-10-15 | 00:00:00 | 04:15:00 | 1200 | drilling -- drill | ok | Drilled 17 1/2" hole section from 1107 to 1200 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3800 lpm / SPP 110-120 bar / 100 RPM / WOB 6-1 0 MT / Torque 6-8 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 10 m3 Hi-vis per stand. Average ROP 22 m/hrs.
| 04:15:00 | 05:45:00 | 1200 | drilling -- drill | ok | Prepared for drilling Skade formation at 1200 m MD. Reamed on singel 5 m off bottom. Circulated 1,5 x bottoms up at 4500 lpm. Inclination before entering Skade formation 16,3 d eg.
| 05:45:00 | 06:00:00 | 1202 | drilling -- drill | ok | Drilled 17 1/2" hole section from 1200 to 1202 m MD.
| 06:00:00 | 11:30:00 | 1360 | drilling -- drill | ok | / WOB 6-10 MT / Torque 8-9 kNm. Increased RPM to 140 during rotary drilling (string RPM 55). Pumped 3 x 10 m3 Hi-vis per stand. Average ROP 30 m/hrs.
Drilled 17 1/2" hole from 1202 m MD to TD at 1360 m MD. Slided and rotated according to instructions from DD. Drilling parameters : 3100-4500 lpm / SPP 120-165 bar / 100 RPM
| 11:30:00 | 14:15:00 | 1360 | drilling -- circulat ing conditioning | ok | Cleaned hole on TD. Pumped sweeps of 30 m3 hi-vis, 30 m3 seawater and 30 m3 hi-vis. Pumped 3 x bottoms up at 4500 lpm / SPP 150 bar. String RPM 60. Reciprocated full stan d while pumping.
| 14:15:00 | 15:15:00 | 1360 | drilling -- circulat ing conditioning | ok | Displaced 17 1/2" hole section to 1,40 sg WBM at 4500 lpm / SSP 135-200 bar. Reciprocated full stand while pumping. Pumped a total of 225 m3 1,40 sg WBM.
| 15:15:00 | 20:15:00 | 220 | drilling -- trip | ok | 1135 m MD 15 MT overpull
1145 m MD 15 MT overpull
1175 m MD 20 MT overpull
1345 m MD 20-30 MT overpull
690 m MD 10 mT
745 m MD 10 MT
Intervall 580 to 380 m MD 10-12 MT overpull
Observed thight spots at :
POOH with 17 1/2" drilling BHA on 5 1/2" DP from 1360 m to 220 m MD.
| 20:15:00 | 20:30:00 | 220 | drilling -- trip | ok | Topped up well with 40 m3 1,40 WBM. Stopped to investigate for hydraulic leak on top drive.
| 20:30:00 | 20:45:00 | 220 | interruption -- ot her | ok | Investigated hydraulic leakage on TDS. Found leakage in easy accessible hose fitting. Tightened hose. Further work on TDS needed as a less accessible leakage was observed.
| 20:45:00 | 22:30:00 | 110 | drilling -- trip | ok | Removed automatic slips and installed masterbushing. Pulled 4 stands. Meanwhile prepared for repairing leakage on TDS.
| 22:30:00 | 00:00:00 | 110 | interruption -- ot her | ok | Parked TDS and repaired leakage on TDS gear box system.
2007-10-16 | 00:00:00 | 01:30:00 | 110 | interruption -- other | ok | Repaired leakage on TDS gear box system.
| 01:30:00 | 03:30:00 | 0 | drilling -- trip | ok | Broke out and laid down 17 1/2" drilling BHA. Cleaned and tidied rigfloor.
| 03:30:00 | 04:30:00 | 0 | drilling -- casin g | ok | PIcked up cement head and made up to 6,69 m 5 1/2" DP pup. Laid down cement head w/pup on deck.
| 04:30:00 | 06:00:00 | 0 | drilling -- casin g | ok | Rigging for running 13 3/8" casing. Cleared and tidied drillfloor. Removed masterbushing. Rigged up slings for removing diverter.
| 06:00:00 | 07:00:00 | 0 | drilling -- casin g | ok | Removed diverter. Installed hole cover. Rigged down slings.
| 07:00:00 | 07:15:00 | 0 | drilling -- casin g | ok | Held tolbox talk prior to rigging casing running equipment.
| 07:15:00 | 07:45:00 | 0 | drilling -- casin g | ok | Greased and checked TDS visually.
| 07:45:00 | 12:45:00 | 0 | drilling -- casin g | ok | Rigged up for running 13 3/8" casing. Dressed PS-30 slips for 13 3/8". Moved casing tong to drillfloor and set on rails, hooked up hydraulics and panel. Rigged up circulation pac ker, 500T slip type elevator and slings with single joint elevator. Installed PS-30 slips in rotary.
| 12:45:00 | 13:15:00 | 0 | drilling -- casin g | ok | Held toolbox talk prior to running 13 3/8" casing.
| 13:15:00 | 14:45:00 | 32 | drilling -- casin g | ok | Picked up, made up and ran 13 3/8" shoe joint, float collar joint and 6 m pup joint. Threadlocked couplings. Filled casing with SW and tested float for flowthrough - ok.
| 14:45:00 | 15:30:00 | 43 | drilling -- casin g | ok | Ran 1 joint of 13 3/8" casing. Adjusted torque setting on tong. Tong jammed to coupling and could not be released.
| 15:30:00 | 17:00:00 | 43 | interruption -- other | ok | Casing tong stuck on casing coupling. Removed die carrier to release the grip.
| 17:00:00 | 17:30:00 | 55 | drilling -- casin g | ok | Ran 1 joint of 13 3/8" casing. Still problems with torque setting on casing tong.
| 17:30:00 | 18:00:00 | 55 | interruption -- other | ok | Repaired casing tong. Changed sensor and cable. Adjusted dump valve setting.
| 18:00:00 | 21:00:00 | 115 | drilling -- casin g | ok | Ran 13 3/8" casing from 55 m to 200 m MD. Filled casing with seawater. Got problems functioning PS-30 slips.
| 21:00:00 | 21:30:00 | 115 | interruption -- other | ok | Not able to open PS-30 slips. Thightened fitting on hydraulic hose.
| 21:30:00 | 00:00:00 | 380 | drilling -- casin g | ok | Ran 13 3/8" casing from 200 m to 380 m MD. Filled casing with 1,40 sg WBM every 5th joint. Average running speed 6 joints/hr.
2007-10-17 | 00:00:00 | 05:45:00 | 800 | drilling -- casin g | ok | Ran 13 3/8" casing from 380 m to 800 m MD. Filled casing with 1,40 sg WBM every 5th joint. Average running speed 6 joints/hr.
| 05:45:00 | 06:00:00 | 800 | drilling -- casin g | ok | Rearranged catwalk machine to pick casing from fwd STB bay.
| 06:00:00 | 11:30:00 | 1198 | drilling -- casin g | ok | Ran 13 3/8" casing from 800 m to 1198 m MD. Filled casing with 1,40 sg WBM every 5th joint. Average running speed 6 joints/hr.
| 11:30:00 | 11:45:00 | 1198 | drilling -- casin g | ok | Held toolbox talk prior to rigging down casing running equipment.
| 11:45:00 | 14:30:00 | 1198 | drilling -- casin g | ok | Removed PS-30 slips and installed master bushing. Removed 500T slip elevator. Removed FAC circulation tool. Removed casing bails and installed drilling bails and 5 1/2" el evator.
| 14:30:00 | 14:45:00 | 1198 | drilling -- casin g | ok | Held toolbox talk prior to picking up 13 3/8" x 18 3/4" subsea wellhead.
| 14:45:00 | 15:30:00 | 1214 | drilling -- casin g | ok | Picked up 13 3/8" x 18 3/4" subsea wellhead and made up to 13 3/8" casing. Ran in with casing and well head to 1214 m MD and hung off in rotary.
| 15:30:00 | 15:45:00 | 1214 | drilling -- casin g | ok | Held toolbox talk prior to removing casing tong.
| 15:45:00 | 16:30:00 | 1214 | drilling -- casin g | ok | Rigged down casing tong and panels and removed from drillfloor.
| 16:30:00 | 17:15:00 | 1345 | drilling -- casin g | ok | Ran in hole with casing and wellhead on 5 1/2" HWDP landing string from 1214 m to 1345 m MD. Circulated last stand down with 500 lpm.
| 17:15:00 | 18:00:00 | 1345 | drilling -- casin g | ok | Picked up cement head with premade pup joint and made up same to landing string and TDS. Took up/down weights 219/144 MT. Broke circulation with 500 lpm and landed 18 3/4" subsea wellhead in 30" conductor housing according to Vetco instructions.
| 18:00:00 | 19:45:00 | 1351 | drilling -- casin g | ok | Circulated and condtioned well before cementing. Pumped at 2300 lpm. Standpipe pressure decreased from 37 bar to 20 bar after 200 m3 pumped. Prepared for pumping ce ment. Observed problem with mudpumps.
| 19:45:00 | 20:45:00 | 1351 | interruption -- o ther | ok | Inspected mudpump#1 and revealed that swab and liner needed to be changed. Questioned if mudpump #3 was ready for operation. Tested mudpump #3 and approved for o peration.
| 20:45:00 | 23:45:00 | 1351 | drilling -- casin g | ok | Dropped ball to activate lower wiper plug. Mixed and pumped 126 m3 1,56 sg lead cement followed by 20 m3 1,92 sg tail cement. Pump rate 800 to 1200 lpm / pumping press ure 20 bar. Displaced cement line with 890 liter seawater.
| 23:45:00 | 00:00:00 | 1351 | drilling -- casin g | ok | Released dart in cement head. Pumped 3 m3 seawater with cement unit at 1200 lpm. After pumping approx 1 m3, observed shear of upper wiper plug by 120 bar pressure pe ak. Closed lo-torque on cement head and lined up to pump with mudpumps.
2007-10-18 | 00:00:00 | 01:00:00 | 1351 | drilling -- casin g | ok | Displaced cement with 89,5 m3 / 4080 strokes seawater at 3000 lpm. Slowed down to 1200 lpm / SPP 70 bar prior to bumping plug. Bumped plug with 140 bar and held pressure for 1 0 min - ok. Lined back to cement unit and bled back 940 liter before returns stopped.
| 01:00:00 | 02:30:00 | 1351 | drilling -- casin g | ok | Disconnected cement line. Released CART with 5 righthand turns according to Vetco instructions. Broke out and laid down cement head with pup. Put in two sponges to clean pipe.
| 02:30:00 | 04:00:00 | 138.5 | drilling -- casin g | ok | Picked up CART stinger 0,5 m above wellhead. Installed cover on subsea wellhead with ROV. Washed template through drillpipe and CART tool to remove cuttings. Cavitation in string made it hard for ROV to grab onto pipe. Re-positioned ROV to right below CART stinger. Stepped up rate to 4500 lpm and washed template while moving pipe with ROV. Inspected we llhead cap and template with ROV.
| 04:00:00 | 04:15:00 | 138.5 | drilling -- casin g | ok | Performed toolbox talk prior to pulling CART.
| 04:15:00 | 06:00:00 | 10 | drilling -- casin g | ok | POOH with CART on 5 1/2" HWDP landing string. Laid out two singles on way out. Laid out CART tool.
| 06:00:00 | 07:00:00 | 0 | drilling -- bop/ wellhead equipment | ok | Installed vinyl guides in Centralizer end Tensioning decks. Installed tension ring on Centeralizer deck. Meanwhile started cleaning and dredging template with ROV.
| 07:00:00 | 07:15:00 | 0 | drilling -- bop/ wellhead equipment | ok | Held toolbox talk before installing spider.
| 07:15:00 | 08:00:00 | 0 | drilling -- bop/ wellhead equipment | ok | Moved riser spider to drillfloor and installed same in rotary. Hooked up hydraulics.
| 08:00:00 | 08:45:00 | 0 | drilling -- bop/ wellhead equipment | ok | Rigged up bolt tensioner equipment on drillfloor. Brought fairrings, bolts, guides and caps to drillflloor.
| 08:45:00 | 09:30:00 | 0 | drilling -- wait | ok | Waited on crane due to helicopter arrival.
| 09:30:00 | 09:45:00 | 0 | drilling -- bop/ wellhead equipment | ok | Held toolbox talk prior to picking up the TBC/stress joint/lower pup double E.
| 09:45:00 | 10:30:00 | 0 | drilling -- bop/ wellhead equipment | ok | Picked up TBC/stress joint/lower pup double E by simultaneous lift with deckcrane and TDS. Landed double in riser spider.
| 10:30:00 | 11:15:00 | 0 | drilling -- bop/ wellhead equipment | ok | Attempted to perform pre-operational checks on TBC according to Vetco instructions, NEG. Observed leakage on minireel hose for hotstab.
| 11:15:00 | 14:15:00 | 15 | drilling -- bop/ wellhead equipment | ok | Observed damaged intervall on minireel hose. Cut back minireel to 150 m and reterminated fittings. Prepared 30 m excess undamaged hose for potential extension. Function tested TB C connector according to Vetco procedures.
| 14:15:00 | 17:15:00 | 22 | drilling -- bop/ wellhead equipment | ok | Picked up 2nd double D by simultaneous lift with deckcrane and TDS, brought to vertical postion. Removed handling tool on flange in rotary. Installed guided pins. Stabbed double D o nto flange in rotary. Made up flange according to Bandak procedure. Tested connection to 200 bar on flange. Installed fairrings.
| 17:15:00 | 22:30:00 | 26 | drilling -- bop/ wellhead equipment | ok | Prepared guidewires with ROV hooks. Built scaffolding around and removed hatches on all wellhead module levels. Removed weatherdeck hatches on F-5 og F-9. Ran guidewires and prepared wire loops in F-4 Centralizer deck opening. Ran in with riser, hooked up guidewires at Centralizer deck and ran riser and guidwires to sealevel.
| 22:30:00 | 22:45:00 | 51 | drilling -- bop/ wellhead equipment | ok | Held toolbox talk prior to picking up 3rd double C.
| 22:45:00 | 00:00:00 | 51 | drilling -- bop/ wellhead equipment | ok | Meanwhile ROV attempted to install VX ring on subsea wellhead. Observed grease/shadow on seal surface. Attempted to wash/flush -still visible. Brought ROV to surface in order to m ount brush tooling.
Picked up 3rd double C by simultaneous lift with deckcrane and TDS, brought to vertical position. Removed handling tool on flange in rotary. Installed guide pins.
2007-10-19 | 00:00:00 | 02:15:00 | 80 | drilling -- bop/wellhead eq uipment | ok | Stabbed double C onto flange in rotary. Made up flange according to Bandak procedure. Tested connection to 200 bar on flange. Installed fairrings. Ran STB guidewire to template. Ran port guidewire to 40 m below sealevel. RIH with riser to 80 m MD.
| 02:15:00 | 04:45:00 | 110 | drilling -- bop/wellhead eq uipment | ok | Meanwhile ROV established STB and port guidewires to template eagel clamps. Brushed and cleaned wellhead seal surface with ROV.
Picked up 4th double B by simultaneous lift with deckcrane and TDS, brought to vertical position. Removed handling tool on flange in rotary. Installed guide pins. Stabbed double B onto flange in rotary. Made up flange according to Bandak procedure. Tested connection to 200 bar on flange. Installed fairrings. RIH with riser to 110 m MD.
| 04:45:00 | 06:00:00 | 110 | drilling -- bop/wellhead eq uipment | ok | Meanwhile brought ROV to surface and installed VX ring installation tooling. Dove ROV.
Picked up 5th double A by simultaneous lift with deckcrane and TDS, brought to vertical position. Removed handling tool on flange in rotary. Installed guide pins. Stabbed double A onto flange in rotary. Made up flange according to Bandak procedure.
| 06:00:00 | 07:00:00 | 128 | drilling -- bop/wellhead eq uipment | ok | Tested riser connection to 200 bar. Installed fairings. RIH with riser to 128 m MD.
| 07:00:00 | 07:15:00 | 128 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to removing riser spiser.
| 07:15:00 | 08:30:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Removed riser spider from rotary and installed master bushing. Installed lo-torque on Claxton tool and confirmed in open position. Ran Claxton tool past rotary and hung off on man ual slips.
| 08:30:00 | 08:45:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Made up stand of 5 1/2" DP to Claxton tool. Made up TDS to DP.
| 08:45:00 | 09:00:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to landing riser.
| 09:00:00 | 09:30:00 | 130 | drilling -- bop/wellhead eq uipment | ok | Placed VX gasket on 18 3/4" subsea wellhead with ROV. Inspected guidewires.
| 09:30:00 | 11:30:00 | 138 | drilling -- bop/wellhead eq uipment | ok | Ran in with riser. Took up/down weight 137 MT. Attempted to land TBC conncetor on 18 3/4" wellhead - negative. Trashed VX- ring when attempting to land. Inspected wellhead an d installed new VX -ring.
| 11:30:00 | 13:30:00 | 138 | interruption -- waiting on weath er | ok | Waited on weather for improved landing condition. Meanwhile installed coax cable between ROV unit and drillfloor to improve viewing conditions for driller.
| 13:30:00 | 15:30:00 | 138 | drilling -- bop/wellhead eq uipment | ok | Made 2 more attempts to land TBC connector on 18 3/4" wellhead - negative. Both times the VX-ring was bounced off the wellhead. Lost attachement for 1 guidewire. Installed ne w VX-ring.
| 15:30:00 | 15:45:00 | 139 | drilling -- bop/wellhead eq uipment | ok | Landed TBC connector on 18 3/4" subsea wellhead succesfully. Set down 30 MT weight. Observed loose skirt on TBC connector.
| 15:45:00 | 17:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed hotstab in TBC receptacle with ROV. Unhooked one guidewire from eagle clamp and pulled to surface. Covered open slot openings in wellhead module with hatches and removed scaffolding.
| 17:15:00 | 19:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Pressured up through minireel hose to activate TBC connector in steps of 500 psi to 3000 psi. Observed indicator rods with ROV - ok. Performed overpull test on connector to 30 MT - ok. Retrieved minireel hose and 2nd guidewire to surface. Covered open slot openings in wellhead module with hatches and removed scaffolding.
| 19:00:00 | 20:45:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed hatches on weatherdeck on slot F-5 and F-9.
| 20:45:00 | 22:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Roped off relevant areas. Built scaffolding around slot F-4 on weatherdeck to access Claxton tool.
| 22:15:00 | 23:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Adjusted tension to 20 MT overpull. Filled riser with 8,7 m3 seawater from cement unit. Closed lo-torque valve on Claxton tool. Pressure tested riser and TBC connector against the well. Pressured up to 20 bar/5 min-ok. Continued to pressure up to 145 bar - observed leakage over Claxton tool in moonpool.
| 23:30:00 | 00:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Pressure fell 20 bar over 10 min with a corresponding leakage rate of 10 l/min. Observed for leakage on TBC connector with ROV - no leakage detected. Assessed situation. Decid ed to move ahead with operations and confirm test at a later stage.
2007-10-20 | 00:00:00 | 05:30:00 | 0 | drilling -- b op/wellhead equipment | ok | In parallel with tenison cylinder hook-up activities : Rigged up chainhoists and attached to tension ring. Removed vinyl protector guide. Installed centralizer in Centralizer deck. Removed sc affolding and barriers at Centralizer deck. Installed boat collision stool. Made up contact ring to three lowermost groves on serrated area. Assembled tensioning assembly and made up to te nsion ring. Removed chainhoists. At 05:30 operations had progressed to the point where tension cylinders support was required.
| 11:00:00 | 14:30:00 | 0 | drilling -- b op/wellhead equipment | ok | Made up tensioning assembly to two pistions and elavated tensioning assembly to contact ring. Applied 2 x 20 MT tension. Made up the two other tension cylinders to tensioning assembly. Installed shimm ring underneath tensioning assembly.
| 14:30:00 | 15:30:00 | 0 | drilling -- b op/wellhead equipment | ok | Transferred tension from block to tension cylinders. Applied 4 x 20 MT on tension cylinders.
| 15:30:00 | 17:30:00 | 0 | drilling -- b op/wellhead equipment | ok | Broke out Claxton tool from BOP joint with Hy-torq tool. Pullled 5 1/2" landing stand, broke out same and racked back in derrick.
| 17:30:00 | 17:45:00 | 0 | drilling -- b op/wellhead equipment | ok | Removed master bushing. Pulled Claxton tool and laid out same. Found 1 O-ring missing on Claxton tool and 1 O-ring bursted.
| 17:45:00 | 18:00:00 | 0 | drilling -- b op/wellhead equipment | ok | Held toolbox talk prior to skidding BOP.
| 18:00:00 | 18:15:00 | 0 | drilling -- b op/wellhead equipment | ok | Attempted to break out 4 remaining studs on NT-2 connector - negative, not able to break studs within torque limit.
| 18:15:00 | 22:45:00 | 0 | -- other | ok | -Removed support beams on forward PRS
-Serviced TDS
-Tested standpipe standpipe manifold 5/10 min 20/345 bar
Continued BOP nippling operation.
Meanwhile :
|  |  |  | interruption | ok | Not able to break studs on NT-2 connector. Attempted to adjust BOP to neutral weight on the NT-2 conncetor - still not able to break studs. Torque tool socket adapter broke, repaired adapt er. Traced new and more powerful adapter and used same for making/breaking. Re-made all studs in attempt to break the jammed studs. Untorqued the 4 studs in question - ok.
| 22:45 | 00:00:00 | 0 | drilling -- b op/wellhead equipment | ok | Untorqued all studs on NT-2 connector. Lifted BOP off test stump and skidded to well centre.
2007-10-21 | 00:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | -Calibrated forward PRS
-Modified BOP overshot joint
-Prepared BOP test tool
-Tested cement/kill manifold 5/10 min 20/345 bar
Landed BOP on riser NT-2 profile. Made up NT-2 connector. Made up tension cylinders to BOP.
Meanwhile :
| 06:00:00 | 07:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Hooked up tension cylinder to BOP. Closed shear ram an lined up for testing down well from cement unit. Meanwhile finished off testing choke manifold.
| 07:30:00 | 08:30:00 | 0 | drilling -- casing | ok | Pressure tested 13 3/8" casing using seawater to 20/190 bar 5/10 min - ok. Pumped 1 m3 and bled back 1 m3. Opened shear ram.
| 08:30:00 | 09:45:00 | 0 | drilling -- bop activities | ok | RIH with BOP testplug on 5 1/2" HWDP. Landed plug at 139 m MD and set down 4 MT on plug.
| 09:45:00 | 10:30:00 | 0 | drilling -- bop activities | ok | Closed MPR. Pressure tested BOP connector, riser, wellhead and TBC connector to 20/345 bar 5/10 mins - ok.
| 10:30:00 | 11:00:00 | 0 | drilling -- bop activities | ok | Function tested BOP.
| 11:00:00 | 12:00:00 | 0 | drilling -- bop activities | ok | POOH with Vetco test plug on 5 1/2" HWDP and laid down same.
| 12:00:00 | 12:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to removing diverter.
| 12:15:00 | 12:45:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Removed diverter from rotary.
| 12:45:00 | 13:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held toolbox talk prior to installing overshot joint and diverter.
| 13:00:00 | 14:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed overshot and made up to flange on BOP body.
| 14:30:00 | 15:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Installed diverter in rotary and locked same in place..
| 15:00:00 | 15:30:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held time out for safety meeting with rig crew.
| 15:30:00 | 17:15:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Continued to nipple up overshot. Removed diverter bails. Installed bushings for manual slips.
| 17:15:00 | 17:30:00 | 0 | drilling -- bop activities | ok | Held toolbox talk prior to rigging for and testing IBOP and kelly hose.
| 17:30:00 | 20:45:00 | 0 | drilling -- bop activities | ok | Rigged up testing swage with weco and hooked up hose. Tested upper and lower IBOP to 20/345 bar 5/10 min. Broke out swage. Checked dies on AFT PRS. Cleared V-door before picking up BHA.
| 20:45:00 | 21:00:00 | 0 | drilling -- trip | ok | Held toolbox talk prior to picking up 12 1/4" BHA.
| 21:00:00 | 21:30:00 | 0 | drilling -- trip | ok | Picked up and RIH with powerdrive, hung off in slips.Made up and run in with powerdrive, powerpulse, NMDC and 8" DC double.
| 21:30:00 | 22:45:00 | 0 | drilling -- trip | ok | Held time out for safety meeting with rig crew for nigthshift.
| 22:45:00 | 00:00:00 | 0 | drilling -- trip | ok | Made up and ran in with powerdrive, powerpulse, ARCm NMDC and pony. Made up 2 x 8" DC double. Observed leakage on flange between overshot and B OP.
2007-10-22 | 00:00:00 | 01:30:00 | 0 | drilling -- trip | ok | Laid down jar from derrick. Picked up new jar from deck and made up to BHA. Meanwhile worked to repair leaking flange. Observed that flange appeared to be biased towards on e side.
| 01:30:00 | 02:45:00 | 0 | interruption -- oth er | ok | Broke and thigthened bolts as required whilst levelling BOP
| 02:45:00 | 04:45:00 | 135 | drilling -- drill | ok | Made up 8" DC stand and x-over. Installed automatic slips in rotary. RIH with 12 1/4" drilling BHA on 4 stands of 5 1/2" HWDP to 135 m MD.
| 04:45:00 | 06:00:00 | 600 | drilling -- drill | ok | RIH with 12 1/4" drilling BHA from 135 m MD to 600 m MD.
| 06:00:00 | 07:15:00 | 1000 | drilling -- drill | ok | Ran in hole with 12 1/4" drilling BHA from 600 m to 1000 m MD. Inspected slips on PRS.
| 07:15:00 | 07:30:00 | 1000 | drilling -- drill | ok | Held toolbox talk prior to routing SW returns overboard.
| 07:30:00 | 08:15:00 | 1000 | drilling -- drill | ok | Established circulation rate at 1500 lpm. Tested MWD according to Schlumberger procedure - ok.
| 08:15:00 | 09:15:00 | 1300 | drilling -- drill | ok | Ran in hole with 12 1/4" drilling BHA from 1000 m to 1300 m MD. Performed kick drill.
| 09:15:00 | 09:30:00 | 1336.5 | drilling -- drill | ok | Made up TDS and washed down from 1300 m. Tagged cement at 1336,5 with 1500 lpm / SPP 54 bar. Took up/down weights 135/115 MT.
| 09:30:00 | 10:30:00 | 1336.5 | drilling -- drill | ok | Conducted choke drill.
| 10:30:00 | 19:00:00 | 1348 | drilling -- drill | ok | Drilled 13 3/8" shoetrack from 1336,5 m to 1348 m MD with seawater. Drilling parameters : Flow 2500 lpm / SPP 50-65 bar / 30-50 RPM / WOB 2-10 MT / Torque 10-27 kNm. Pu mped hi-vis sweeps .
| 19:00:00 | 21:45:00 | 1350 | drilling -- circulati ng conditioning | ok | Drilled shoetrack from 1348 m to 1350 m MD. Meanwhile held pre-job meeting before displacing well to 1,40 OBM. Emptied slurry holding tank into pit #1 and #5 to obtain more b uffer for cuttings slurry. Pumped hi-vis .Displaced well from seawater to 110 m3 1,40 OBM. Stopped pumping when OBM interface at surface.
| 21:45:00 | 22:45:00 | 1350 | drilling -- circulati ng conditioning | ok | Pumped 5 m3 seawter/OBM interface to pit #5. Pumped treatable interface of 10 m3 to pit #14. Filled sandtraps and shaker pits with 1,40 sg OBM. Total active volume 185 m3.
| 22:45:00 | 00:00:00 | 1351.5 | drilling -- drill | ok | Drilled shoetrack from 1350 m to 1351,5 m MD. Drilling parameters : Flow 2600 lpm / SPP 101 bar / 60 RPM / WOB 5 MT / Torque 6-7 kNm. Hard to make progress at 1351,5 m MD.
2007-10-23 | 00:00:00 | 00:30:00 | 1352 | drilling -- drill | ok | Continued drilling on shoe, hard to make progress. Reduced RPM to 40 and reduced flow to 2200 lpm. Increased WOB steadily from 5 to 7 MT and broke through shoe.
| 00:30:00 | 02:00:00 | 1360 | drilling -- drill | ok | Drilled rathole, reamead back to shoe for every 2 m drilled. Flow 2600 lpm / SPP 101 bar / 60 RPM / WOB 5 MT / Torque 6-7 kNm.
| 02:00:00 | 03:30:00 | 1363 | drilling -- drill | ok | Drilled 3 m new formation prior to FIT. Circulated well to obtain even MW in and out ; 1,39 sg heavy in/out. Used 1,395 sg for FIT calculation.
| 03:30:00 | 04:30:00 | 1350 | formation evalu ation -- rft/fit | ok | Pulled bit inside casing shoe at 1350 m MD. Lined up for FIT test to pump down pipe and annulus. Closed annular. Pressured up to 7 bar to fill standpipe and kill line and observed r apid increase in pressure / curve deflection. Pumped 121 liter up to 17 bar. Pressure fell to 13 bar over 15 min, steady leakage rate. Bled back 50 liter.
| 04:30:00 | 06:00:00 | 1350 | formation evalu ation -- rft/fit | ok | Discussed quality of FIT. Down linked MWD for ESD, got ESD figure of 1,37 sg. Decided to line up for new FIT. Circulated and lined up for new FIT.
| 06:00:00 | 07:30:00 | 1350 | drilling -- circula ting conditioning | ok | Circulated on well at 3500 lpm to obtain even MW in/out. Leak tested kill line to HCR to 20 bar-ok. Obtained 1,39 sg MW in/out. Racked back 1 stand.
| 07:30:00 | 08:30:00 | 1350 | formation evalu ation -- rft/fit | ok | Lined up for FIT. Reset pressure to zero bar. Pressured up to 6,5 bar at 50 lpm to fill standpipe and kill line and observed rapid increase in pressure /curve deflection. Continued pum ping at 50 lpm up to FIT pressure of 18 bar. Pumped 100 liter up to 18 bar / 1,53 EMW. Pressure fell to 13 bar after 15 mins with steady leakage rate. Bled back 50 liter.
| 08:30:00 | 09:45:00 | 1365 | drilling -- drill | ok | Stepped up pumps and RPM. Drilled 2 m of new formation. Took surveys and downlinked tools according to Schlumberger instruction. Downlinked and set powerdrive according to DD instructions.
| 09:45:00 | 17:30:00 | 1544 | drilling -- drill | ok | Drilled 12 1/4" section from 1365 m to 1544 m MD. Drilling paramters : Flow 3500 lpm / SPP 171-178 bar / 130-170 RPM / WOB 2-4 MT / Torque 1-4 kNm. Average ROP 23 m/hrs. Reamed 1 single before connection. Took SCRs at 1504 m MD.
| 17:30:00 | 18:00:00 | 1544 | drilling -- drill | ok | Inspected TDS due to excessive noise. Found worn area on upper IBOP actuator sleeve.
| 18:00:00 | 19:15:00 | 1585 | drilling -- drill | ok | Drilled 1 stand from 1544 m to 1584 m MD while observing / monitoring upper IBOP actuator sleeve. Halted operations for troubleshooting.
| 19:15:00 | 21:15:00 | 1585 | interruption -- ot her | ok | Decided to pull 12 1/4" drilling BHA into casing shoe for TDS repair. Circulated hole clean with 2-3 bottoms up at 3500 lpm.
| 21:15:00 | 21:30:00 | 1585 | interruption -- ot her | ok | Flowchecked well for 15 min - well static.
| 21:30:00 | 00:00:00 | 1343 | interruption -- ot her | ok | Installed mud bucket. Pulled 12 1/4" drilling BHA from 1585 m MD to 1343 m MD.
2007-10-24 | 17:15:00 | 17:45:00 | 1584 | drilling -- dr ill | ok | Took MWD survey. Stepped up pump and rotation to obtain drilling parameters. Standpipe pressure fell rapidly when reaching 130 bar. Unclear indications. Attempted to pump and obser ved that pop off valve had triggered. Mud returns from pop off ventline went down to pit #15 which overflowed pit and pit room. Halted operation.
| 20:00:00 | 23:00:00 | 1640.5 | drilling -- dr ill | ok | Drilled 12 1/4" section from 1585 m to 1640,5 m MD. Drilling parameters : Flow 3500 lpm / SPP 180 bar / 130-170 RPM / WOB 2-3 MT / Torque 10-12 kNm. Average ROP 19 m/hrs. Re amed 1 single before connection. Not able to handle cuttings return from well.
2007-10-25 | 00:30:00 | 06:00:00 | 1706 | drilling -- dr ill | ok | Drilled 12 1/4" section from 1640,5 m to 1706 m MD. Drilling parameters : Flow 3500 lpm / SPP 180 bar / 130-170 RPM / WOB 0-2 MT / Torque 10-12 kNm / ECD 1,42. Average ROP 1 2 m/hrs. Drilled with reduced ROP when going directly to skips. Worked to bring down vicosity in DCI milltank/active before injecting slurry.
| 06:00:00 | 09:00:00 | 1750 | drilling -- dr ill | ok | Drilled 12 1/4" section from 1706 m to 1750 m MD. Drilling parameters : Flow 3500 lpm / SPP 180 bar / 170 RPM / WOB 2-3 MT / Torque 8-12 kNm / ECD 1,42. Average ROP 12 m/hrs. Drilled with reduced ROP when going directly to skips. Worked to bring down vicosity in DCI milltank/active before injecting slurry. Changed out cooling water on MP2.
| 12:00:00 | 00:00:00 | 1340 | drilling -- w ait | ok | - Continued injecting cuttings into F-12 and flushed with 2 x annulus volumes of water.
- Continued with PMs and housekeeping/cleaning.
- Flow checked well before POOH (static).
- POOH from 1530 to inside csg shoe at 1340 m MD.
- POOH from 1750 m to 1530 m. Up weight 140 MT / Down weight 124 MT. Monitored well on trip tank at 1530 m. Ok.
- Repaired Barite hopper B.
Waiting on Siemens software update. Meanwhile:
2007-10-26 | 00:00:00 | 00:30:00 | 1340 | drilling -- wait | ok | Waiting on Siemens software update.
| 00:30:00 | 03:30:00 | 1750 | drilling -- wait | ok | Removed TIW valve. RIH with 12 1/4" drilling BHA from 1340 m to 1706 m MD. Made up TDS and washed down from 1706 m to 1750 m MD with 2500 lpm / 98 bar. Took up/down weight 14 3/121 MT.
| 03:30:00 | 04:00:00 | 1750 | drilling -- drill | ok | Established parameters and downlinked tool as per DD's instruction.
| 04:00:00 | 06:00:00 | 1787 | drilling -- drill | ok | Drilled 12 1/4" section from 1750 m to 1787 m MD. Drilling parameters : Flow 3500 lpm / SPP 187 bar / 170 RPM / WOB 2-3 MT / Torque 9-14 kNm / ECD 1,43. Average ROP 25 m/hrs. Re amed 1 single before connection. Down linked and performed surveys as required.
| 06:00:00 | 00:00:00 | 2178 | drilling -- drill | ok | Drilled 12 1/4" section from 1787 m to 2178 m MD. Drilling parameters : Flow 3500 lpm / SPP 186-194 bar / 170 RPM / WOB 0-5 MT / Torque 11-13 kNm / ECD 1,43-1,44. Average ROP 35 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Observed erratic data on Resestivity log from 2030 mMD (2010 mMD sencor depth). Resistivity sensor non-functional from 2010 mMD at 18:00 hrs. Cuttings return routed to skips due to slurry transfer pump is out of operation.
2007-10-27 | 00:00:00 | 03:00:00 | 2230 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2178 m to 2230 m MD. Drilling parameters : Flow 3500 lpm / SPP 194-197 bar / 170 RPM / WOB 2-7 MT / Torque 13-15 kNm / ECD 1,44. Average ROP 35 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Cuttings return routed to skips due to slurry transfer pump is out of operation.
| 03:30:00 | 06:00:00 | 2275 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2230 m to 2275 m MD. Drilling parameters : Flow 3500 lpm / SPP 197 bar / 170 RPM / WOB 2-7 MT / Torque 14-16 kNm / ECD 1,44. Average ROP 35 m/hr
s. Reamed 1 single before connection. Down linked and performed surveys as required. Cuttings slurry routed to boat due to injection pump is out of operation.
| 06:00:00 | 08:00:00 | 2311 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2275 m to 2311 m MD. Drilling parameters : Flow 3500 lpm / SPP 197 bar / 170 RPM / WOB 2-5 MT / Torque 14-15 kNm / ECD 1,44. Average ROP 35 m/hr
s. Reamed 1 stand before connection. Down linked and performed surveys as required.
| 09:00:00 | 10:00:00 | 2311 | interruption | ok | MP#2 had to be replaced by MP#3 due to leaking swab. MP#3 had been run in test mode and charge pumpe had to be de-isolated.
Meanwhile Picked off bottom and circulated and reciprocated string at 1750 lpm / 55 bar / 20 RPM.
| 10:00:00 | 15:00:00 | 2377 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2311 m to 2377 m MD. Drilling parameters : Flow 3500 lpm / SPP 200-205 bar / 170 RPM / WOB 4-7 MT / Torque 13-15 kNm / ECD 1,43-1,45. Average RO P 10-35 m/hrs. Reamed 1 stand before connection. Down linked and performed surveys as required.
| 15:00:00 | 16:00:00 | 2377 | interruption | ok | Meanwhile Picked off bottom and circulated at 1750 lpm / 55 bar / 20 RPM.
Valve in cutting injection system (CRI) would not open. Hydraulic oil was drained from closing side of automatic valve to make it open. Meanwhile cleaned out cooling water on MP#3.
| 16:00:00 | 00:00:00 | 2497 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2377 m to 2497 m MD. Drilling parameters : Flow 3500 lpm / SPP 200-205 bar / 170 RPM / WOB 4-7 MT / Torque 15-20 kNm / ECD 1,43. Average ROP 35 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Lined over from MP#3 to MP#2 at 21:45.
2007-10-28 | 00:00:00 | 06:00:00 | 2626 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2497 m to 2626 m MD. Drilling parameters : Flow 3500 lpm / SPP 205 bar / 170 RPM / WOB 4-7 MT / Torque 16-18 kNm / ECD 1,44. Average ROP 35 m/hr
Turned back time 1 hour at 03:00 due "winter-time" in Norway.
s. Reamed 1 single before connection. Down linked and performed surveys as required. Started injecting cuttings slurry into F-12 annulus at 03:30.
| 06:00:00 | 00:00:00 | 2768 | drilling -- dr ill | ok | Drilled 12 1/4" section from 2626 m to 2770 m MD. Drilling parameters : Flow 3500 lpm / SPP 209-211 bar / 160-180 RPM / WOB 4-10 MT / Torque 15-22 kNm / ECD 1,43-1,44. Averag e ROP 1-10 m/hrs. Reamed 1 single before connection. Down linked and performed surveys as required. Started injecting cuttings slurry into F-12 annulus at 20:10.
2007-10-29 | 00:00:00 | 00:30:00 | 2770 | drilling -- drill | ok | Drilled 12 1/4" section from 2768 m to 2770 m MD. Drilling parameters : Flow 3500 lpm / SPP 203 bar / 170 RPM / WOB 7 MT / Torque 15-20 kNm / ECD 1,43. Average RO P 1-4 m/hrs.
| 00:30:00 | 02:30:00 | 2768 | drilling -- circulating conditio ning | ok | Circulated 2 btms up at 2770 m MD, 3500 lpm / 200 bar / 170 rpm / 13-15 kNm to clean well. Took one roadmap measurement, 200 lpm and 60 rpm. Up weight 175 MT. Dow n weight 156 MT.
| 02:30:00 | 03:30:00 | 2768 | drilling -- survey | ok | BO one std, RU and dropped gyro. Pumped down tool, 550 lpm / 7 bar / 15 rpm and landet off on totco ring on top off jar in BHA.
| 03:30:00 | 03:45:00 | 2768 | drilling -- drill | ok | Flow checked well while rotating with 10 rpm. Sat tool face on drop gyro.
| 03:45:00 | 06:00:00 | 2525 | drilling -- drill | ok | Pulled first 5 stnds wet from 2768 to 2550 m MD. No drag observed. Pumped 4,7 m3 1,65 sg slug at 880 lpm / 22 bar. Continued POOH to 2525 m MD. Gyro survey was perf ormed on each stand.
| 06:00:00 | 12:15:00 | 1330 | drilling -- drill | ok | POOH with 12 1/4" BHA from 2525 m to 1330 m MD. No overpull observed. No obstruction met pulling into 13 3/8" csg shoe. Performed gyro survey on each stand. Oriented string to confirm toolface every 300 m as instructed by Gyro data. Corrected ZMS interlock fault on aft PRS.
| 12:15:00 | 13:15:00 | 1330 | drilling -- drill | ok | Function tested BOP while circulated through choke and kill lines at 13 3/8" csg shoe. Serviced TDS. Flow checked before POOH with 12 1/4" BHA in casing.
| 13:15:00 | 15:45:00 | 90 | drilling -- drill | ok | POOH with 12 1/4" BHA from 1330 m to 90 m MD. Performed gyro survey on each stand. Oriented string to confirm toolface every 300 m as instructed by Gyro data.
| 15:45:00 | 22:00:00 | 0 | drilling -- trip | ok | Removed auto-slips from rotary and inserted master bushings. LO 12 1/4" BHA from 90 m to surface.
| 22:00:00 | 00:00:00 | 139 | drilling -- trip | ok | MU up wear bushing RT assembly and RIH with same from surface to 138 m. Tool landed off at 139.05 m. Jetted BOP and wellhead, 1650 lpm / 8 bar.
2007-10-30 | 00:00:00 | 02:30:00 | 0 | drilling -- trip | ok | POOH with wear bushing and LO same.
| 02:30:00 | 03:30:00 | 0 | drilling -- casing | ok | MU cmt head assembly and RB in derrick.
| 03:30:00 | 06:00:00 | 0 | drilling -- casing | ok | Cleared and tidied rig floor off excess equipment. RU csg tong, handling equipment and FAC tool. Prepared to run 9 5/8" csg.
| 06:00:00 | 09:00:00 | 0 | drilling -- casing | ok | RU csg tong and handling equipment. Prepared to run 9 5/8" csg.
| 09:00:00 | 10:00:00 | 0 | interruption -- other | ok | Sorted out power supply problem for csg. tong.
| 10:00:00 | 12:00:00 | 0 | drilling -- casing | ok | Installed elevators, flush mounted slips, bails and FAC circulating tool. Prepared to run 9 5/8" csg.
| 12:00:00 | 17:00:00 | 171 | drilling -- casing | ok | Held tool-box meeting before running csg. PU and MU shoe joint, intermediate- and float collar joints. Thread locked first 3 connections. Checked shoe and float co llar for flow-through while PU.
RIH with 9 5/8" csg to 171 m MD. Filled every joint with 1.40 sg mud using FAC tool.
| 17:00:00 | 22:00:00 | 167 | interruption -- other | ok | Casing torque computer would not work according to set up. Had to continue with modified set-up.
| 22:00:00 | 00:00:00 | 276 | drilling -- casing | ok | RIH with 9 5/8" csg from 171 to 276 m MD. Filled every joint with 1.40 sg mud using FAC tool. First 19 joint was ran with centraliser.
2007-10-31 | 00:00:00 | 02:15:00 | 416 | drilling -- casing | ok | RIH with 9 5/8" csg from 276 to 416 m MD. Filled every joint with 1.40 sg mud using FAC tool.
| 02:15:00 | 03:00:00 | 393 | interruption -- other | ok | Changed proximity switch on PDM.
| 03:00:00 | 06:00:00 | 587 | drilling -- casing | ok | RIH with 9 5/8" csg from 416 to 587 m MD. Filled every joint with 1.40 sg mud using FAC tool.
| 06:00:00 | 00:00:00 | 1550 | drilling -- casing | ok | .
RIH with 9 5/8" csg from 587 to 1550 m MD. Filled every joint with 1.40 sg mud using FAC tool. LO 3 jnts. Running speed 4-7 jnts/hr
2007-11-01 | 00:00:00 | 06:00:00 | 1858 | drilling -- casing | ok | RIH with 9 5/8" csg from 1550 to 1858 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr.
| 06:00:00 | 10:45:00 | 2151 | drilling -- casing | ok | RIH with 9 5/8" csg from 1858 to 2151 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr.
| 10:45:00 | 13:15:00 | 2151 | drilling -- casing | ok | PU and installed 9 5/8" x 10 3/4" XO. Changed to 10 3/4" inserts in elevator and slips.
| 13:15:00 | 19:30:00 | 2369 | drilling -- casing | ok | .
RIH with 10 3/4" csg from 2151 to 2369 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr
| 19:30:00 | 20:00:00 | 2369 | interruption -- maintain | ok | Performed maintenace on flush joint elevator. Changed dies in csg tong. Meanwhile repaired camera on PDM.
| 20:00:00 | 00:00:00 | 2574 | drilling -- casing | ok | .
RIH with 10 3/4" csg from 2369 to 2574 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr
2007-11-02 | 00:00:00 | 00:45:00 | 2617 | drilling -- casing | ok | RIH with 10 3/4" csg from 2574 to 2617 m MD. Filled every joint with 1.40 sg mud using FAC tool. Average running speed 4-5 jnts/hr. Up weight 261 MT / Down weight 193 MT.
| 00:45:00 | 02:45:00 | 2617 | drilling -- casing | ok | RD FAC tool and changed bails. Changed to 5 1/2" HWDP hadling equipment.
| 02:45:00 | 05:30:00 | 2626 | drilling -- casing | ok | PU and MU 10 3/4" casing hanger / PADPRT assembly. Marked running tool to make sure it is not backing out. Took out master bushing and ran hanger assy through rotary. Re-installed m aster bushing. Removed csg tong.
| 05:30:00 | 06:00:00 | 2698 | drilling -- casing | ok | RIH with 10 3/4" x 9 5/8" csg on 5 1/2" HWDP landing string from 2626 to 2698 m MD.
| 06:00:00 | 06:30:00 | 2740 | drilling -- casing | ok | RIH with 10 3/4" x 9 5/8" csg on 5 1/2" HWDP landing string from 2698 to 2740 m MD.
| 06:30:00 | 07:15:00 | 2740 | drilling -- casing | ok | PU cement head and broke circulation in steps up to 2000 lpm, 500 lpm=20 bar and 2000 lpm=56 bar
| 07:15:00 | 07:45:00 | 2760.5 | drilling -- casing | ok | RIH slowly and landed off hanger. Observed 10 MT drag prior to landing off. Pumped 500 lpm and observed weight dropped off.
| 07:45:00 | 09:00:00 | 2760.5 | drilling -- casing | ok | Circulated 1 csg volume with 1.40 sg OBM at 200 lpm / 57 bar. Meanwhile hed pre-job meeting for cmt job.
| 09:00:00 | 09:30:00 | 2760.5 | drilling -- casing | ok | Lined up and pressure tested cmt line 245 bar / 5 min. Verified correct line-up by holding and releasing 10 bar through low torque.
| 09:30:00 | 10:15:00 | 2760.5 | drilling -- casing | ok | Pumped 10 m3 base oil and 20 m3 spacer at 2000 lpm / 48 bar. Mixed and pumped 17,3 m3 1.90 sg cement slurry at 800 lpm / 40-45 bar.
| 10:15:00 | 12:15:00 | 2760.5 | drilling -- casing | ok | Continued displacing cement with 102.8 m3 OBM at 2000 lpm using mud pumps. Slowed down rate to 1000 lpm / 33 bar (FCP) approx 4 m3 prior to bump. Bumped plug with 110 bar after pumping 4718 strokes, which gives a pump efficiency of 95.3%.
Pumped 490 ltrs water, released dart and continued pumping 400 ltrs water behind cement with cmt unit, to displace surface line volume to rig floor.
Zeroed stroke counters for mud pumps. Displaced and sheared wiper plug by pumping OBM at 1200 lpm using rig pumps. Wiper plug sheared at 138 bar / 886 ltr.
| 12:15:00 | 13:45:00 | 2760.5 | drilling -- casing | ok | Bled off pressure to 20 bar and closed IBOP. Equalized pressure and opened lo-torque valve. Pressured up well to 310 bar / 10 min through lo-torque valve to test casing. 1300 ltrs pumped and got 1350 ltrs back. Bleed off and checked for back flow to cmt unit. Disconnected cmt hoses and flushed lines.
| 13:45:00 | 14:30:00 | 2760.5 | drilling -- casing | ok | Lined up top drive to trip tank to monitor returns. Tested surface lines against fail safe valve to 207 bar / 10 min. Closed upper pipe ram and applied 207 bar to set seal assembly.
| 14:30:00 | 15:00:00 | 2760.5 | drilling -- casing | ok | Took 40 MT overpull. Attempted to pressure test seal assembly without sucess.
| 15:00:00 | 17:30:00 | 0 | drilling -- casing | ok | Released PADPRT, LO cement head and 2 jnts of 5 1/2" HWDP. POOH with running tool on 5 1/2" HWDP landing string from 120 m to OOH.
| 17:30:00 | 22:00:00 | 139 | drilling -- casing | ok | RIH with BOP test plug to 139 m to test MS seal. Closed upper pipe ram. Attempted to pressure test seal assembly to 35 bar / 5 min without sucess. Closed annular to test upper pipe ram and found that upper pipe ram was leaking. Closed lower pipe ram and pressure tested seal assembly to 35 bar / 5 min and 345 bar / 15 min. 463 ltrs pumped and got 450 ltrs back. POOH with BOP test plug.
| 22:00:00 | 00:00:00 | 139 | drilling -- casing | ok | RIH and installed wear bushing at 139 m MD.
2007-11-03 | 00:00:00 | 01:00:00 | 0 | drilling -- casing | ok | POOH with wear bushing running string.
| 01:00:00 | 05:15:00 | 350 | drilling -- other | ok | RIH with 7 stds of 5 1/2" DP. MU and RIH with 10 3/4" RTTS with storm valve on 5 1/2" DP to 350 m MD. Up weight 91 MT / Down weight 87 MT. Weight unde r RTTS is 10.2 MT (bouyant).
| 05:15:00 | 06:00:00 | 350 | drilling -- other | ok | Resiprocated string and circulated with 100 lpm to clean setting area. Installed plug according to Halliburton procedure with element at 350 m MD. Lined up to test RTTS to 180 bar/10 min from below.
| 06:00:00 | 07:30:00 | 349 | drilling -- other | ok | Tested RTTS packer to 180 bar / 10 min from below.
| 07:30:00 | 08:30:00 | 349 | drilling -- other | ok | Released from RTTS with 22 turns to the left. PU from 349 m to 332 m and spaced out tool joint below LPR. Tested RTTS packer to 180 bar / 10 min from ab ove against closed lower pipe ram.
| 08:30:00 | 09:30:00 | 348 | drilling -- circulating conditioning | ok | RIH with RTTS running tool assembly from 332 m to 348 m MD. Circulated 1 x btms up, 2000 lpm / 11 bar.
| 09:30:00 | 12:00:00 | 348 | drilling -- other | ok | Held pre-job meeting prior to displacing well to SW. Lined up and flushed surface lines and choke & kill hoses. Displaced well above RTTS to SW, 2000 lpm / 12 bar. Used 10 m3 baseoil as spacer.
| 12:00:00 | 13:15:00 | 0 | drilling -- drill | ok | POOH with RTTS running tool assembly from 348 m.
| 13:15:00 | 14:00:00 | 0 | drilling -- drill | ok | MU jetting sub and RIH to jet BOP, 2000 lpm / 9 bar / 10 rpm. POOH with jetting tool and LO same.
| 14:00:00 | 14:45:00 | 0 | drilling -- drill | ok | Took time-out for safety to investigate doghouse being hit by unidentified projectile. Ascertain that dowel pin on dog collar sheared off and struck window at hig h speed.
| 14:45:00 | 16:30:00 | 0 | drilling -- drill | ok | RIH to 28 m. MU side entry sub and TIW. Closed annular. Pumped air through choke line and displaced riser contents to trip tank. RD side entry sub and TIW. POOH from 28 m.
| 16:30:00 | 00:00:00 | 0 | drilling -- bop/wellhead eq uipment | ok | Held tool box meeting prior to ND diverter. Removed elevators and RU for pulling diverter. Pulled diverter to rig floor. Removed and secured diverter housing on pipe set-back. ND and pulled slick joint.
2007-11-04 | 00:00:00 | 03:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | Removed BOP tension cylinders and sat BOP on test stump.
| 03:00:00 | 05:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | RU handling equipment for running Claxton tool and PU tool. Removed master bushing. Run in with Claxton tool and re-inserted master bushing.
| 05:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | Run in and MU Claxton tool to NT2 connector on HPDR BOP joint. MU claxton tool lock-dogs to min 1000 lf.lbs torque with air-operated tool.
| 06:00:00 | 07:00:00 | 18 | drilling -- bop/wellhead e quipment | ok | Untorqued bolts on HPDR BOP joint at X-mas tree level using Bandak tool, but left bolts in flange.
| 07:00:00 | 19:00:00 | 0 | interruption -- maintain | ok | Meanwhile performed testing of production systems. Experienced black-out from 11:28 to 12:20.
Performed house-keeping and cleaned drill-fllor, cantiliver, pump room and sack store.
| 19:00:00 | 19:30:00 | 0 | drilling -- bop/wellhead e quipment | ok | Performed hand-over and held tool box meeting before pulling HPDR BOP joint.
| 19:30:00 | 20:30:00 | 0 | interruption -- other | ok | Software problems due to black-out. Could not operate break on draw work.
| 20:30:00 | 22:15:00 | 0 | drilling -- bop/wellhead e quipment | ok | Disconnected HPDR BOP joint. Removed master bushing. POOH with Claxton tool and HPDR BOP joint and re-inserted master bushing. LD claxton tool and ris er joint. Installed protector on BOP riser joint flange.
| 22:15:00 | 23:00:00 | 0 | drilling -- bop/wellhead e quipment | ok | Installed handling tool/flange on top of HPDR tension joint at X-mas tree deck.
| 23:00:00 | 00:00:00 | 0 | drilling -- other | ok | Removed scaffolding in moonpool.
2007-11-05 | 00:00:00 | 02:00:00 | 0 | drilling -- other | ok | Continued removing scaffolding in moonpool and on X-mas tree deck. Installed hatch on F-4
| 02:00:00 | 06:00:00 | 0 | interruption -- maintain | ok | Started changing wires on aft PRS. Meanwhile prepared for skidding rig to F-14.
| 06:00:00 | 11:00:00 | 0 | interruption -- maintain | ok | .
Continued changing wires on aft PRS. Meanwhile prepared for skidding rig to F-14 and cleaned pits. Operation continues on F-14
2008-02-04 | 21:00:00 | 00:00:00 | 0 | moving -- skid | ok | .
Prepared for skidding. Simultaneously pressure tested the rig manifold and changed out riser tension cylinder
2008-02-05 | 00:00:00 | 01:30:00 | 0 | moving -- skid | ok | Continued preparing for skidding. Simultaneously pressure tested the rig manifold and changed out riser tension cylinder.
| 01:30:00 | 02:00:00 | 0 | moving -- skid | ok | Held tool box talk prior to skidding of the cantilever.
| 02:00:00 | 03:00:00 | 0 | moving -- skid | ok | Skidded cantilever from F-12 to F-4.
| 03:00:00 | 06:00:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Continued changing out tension cylinder on riser. Simultaneously pressure tested the rig manifold.
| 06:00:00 | 15:30:00 | 0 | drilling -- bop/wellhead equipm ent | ok | .
Changed out the two remaining tension cylinders on F-4 riser. Simultaneously pressure tested stab-in valves to 345 bars. Prepared for slip and cut
| 15:30:00 | 17:00:00 | 0 | interruption -- maintain | ok | Slipped and cut drill line. Re-calibrated block and checked the crow O-matic. Simultaneously nippled down the riser lifting sub.
| 17:00:00 | 17:45:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Continued nippling down the riser lifting sub. Checked the torque on the Claxton riser handling tool, prior to lifting in same with the HP riser BOP joi nt attached.
| 17:45:00 | 18:30:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Held tool box talk prior to remove the master bushing, outer ring and the hatch cover on F-4.
| 18:30:00 | 19:00:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Retrieved the riser lifting sub, and laid out same. Cleared drill floor. Prepared for picking up the HP riser BOP joint.
| 19:00:00 | 19:15:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Held tool box talk prior to install the HP riser BOP joint.
| 19:15:00 | 21:30:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Removed master bushing and ran with the HP riser BOP joint and landed same. Installed master bushing. Made up the HP riser BOP joint.
| 21:30:00 | 00:00:00 | 0 | drilling -- bop/wellhead equipm ent | ok | Built scaffolding around the HP riser BOP joint in the Moon Pool.
2008-02-06 | 00:00:00 | 00:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Continued building scaffolding around the HP riser BOP joint in the Moon Pool.
| 00:15:00 | 01:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | Released the Claxton tool. Removed master bushing, pulled the Claxton up to the Drill Floor. Installed the master bushing.
| 01:30:00 | 03:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Moved the BOP into well centre. Simultaneously prepared the diverter and slick jnt on the Drill Floor.
| 03:00:00 | 03:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk with new crew prior to continue nippling up the BOP and diverter.
| 03:15:00 | 06:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Position the BOP and commenced making up the tension cylinders to BOP.
| 06:00:00 | 07:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Made up BOP tension cylinders.
| 07:00:00 | 07:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk prior to remove the master bushing and installation of the overshot and landing the diverter.
| 07:15:00 | 11:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Removed the master bushing and installed the overshot and landed the diverter. Made up the NT2 connector. Meanwhile rigged down the diverter ha ndling equipment.
| 11:00:00 | 13:45:00 | 139 | drilling -- bop activities | ok | M/U BOP test cup assy. and RIH with same to 139 m.
| 13:45:00 | 14:30:00 | 139 | drilling -- bop activities | ok | Held tool box talk prior to perform BOP test as MC procedure.
| 14:30:00 | 20:45:00 | 139 | drilling -- bop activities | ok | Performed BOP test as MC procedure, 20/345 bars 5/10min.
| 20:45:00 | 22:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | Torqued up slip joint. Fault of middle pipe variable 3½" x 5½" rams pressure test.
| 22:45:00 | 00:00:00 | 139 | interruption -- repair | ok | Drained the riser. Opened middle variable 3½" x 5½" pipe rams and removed the rubbers.
2008-02-07 | 00:00:00 | 02:00:00 | 139 | completion -- bop/we llhead equipment | ok | Job suspended due to priority F12. Drilling dep. transported production Co-flex hose support frame to X-mas tree deck, through Moon Pool.
| 02:00:00 | 03:30:00 | 139 | drilling -- bop activities | ok | Installed new variable 3½" x 5½" pipe rams rubbers.
| 03:30:00 | 04:15:00 | 139 | drilling -- bop/wellhead equipment | ok | Attempted to pressure middle variable 3½" x 5½" pipe rams.
| 04:15:00 | 06:00:00 | 139 | drilling -- bop/wellhead equipment | ok | Drained and opened middle variable 3½" x 5½" pipe rams. Opened top wear plate .
| 06:00:00 | 07:00:00 | 139 | drilling -- bop activities | ok | Removed top wear plate and inspected seals. No visible damaged on the seals. Simultaneously serviced aft PRS.
| 07:00:00 | 11:00:00 | 139 | drilling -- bop activities | ok | Changed out O-ring and top wear plate. Installed rams and closed doors. Simultaneously serviced aft PRS and TDS.
| 11:00:00 | 11:45:00 | 139 | drilling -- bop activities | ok | Pulled up test plug and laid out 3m pup and one joint. Made up one double and ran in with same and landed of the test cup at 139 m. New test area for the middle pipe rams.
| 11:45:00 | 12:15:00 | 139 | drilling -- bop activities | ok | Lined up the CMT unit and flushed the lines.
| 12:15:00 | 12:45:00 | 139 | drilling -- bop activities | ok | Pressure tested the BOP middle pipe rams 20/345 bars 5/10 min.
| 12:45:00 | 14:15:00 | 139 | drilling -- bop activities | ok | Performed accumulator test.
| 14:15:00 | 15:30:00 | 0 | drilling -- bop activities | ok | Retrieved the test plug and laid out same.
| 15:30:00 | 16:00:00 | 0 | drilling -- other | ok | Made up the RTTS retrieving tool.
| 16:00:00 | 16:15:00 | 0 | drilling -- other | ok | Held tool box talk prior to displacethe well above the RTTS plug to OBM.
| 16:15:00 | 17:15:00 | 342 | drilling -- other | ok | RIH with RTTS retrieving tool and tagged the RTTS plug at 342m, picked up 2m.
| 17:15:00 | 18:45:00 | 340 | drilling -- other | ok | Displaced the well above the RTTS plug to 1.40 OBM, 1500/1000 lpm.
| 18:45:00 | 19:45:00 | 350 | drilling -- other | ok | Took up/down weight 82/79 MT. Stung into the RTTS plug, turned DP 22 turnes and torque up to 2000 ft/lbs, no pressure built up. Lined up to the trip tank. Pressure up DP to 5 bars and confirmed sufficiently engaged to tool. Attempted to release the RTTS plug by pulling 105 MT equivalent to 15 MT over pull.
| 19:45:00 | 20:15:00 | 350 | drilling -- other | ok | Closed annular and applied 40 bars to the annulus, to collapse the hydraulic slips. Held pressure for 5 min. Bled off pressure in the annulus and opened the annular.
| 20:15:00 | 20:30:00 | 350 | drilling -- other | ok | Picked up string in 5 MT staged from 81 MT to 115 MT. At 115 MT , equivalent to 25 MT over pull. RTTS plugs mechanical slips disengaged.
| 20:30:00 | 20:45:00 | 350 | drilling -- other | ok | Waited for element to retract.
| 20:45:00 | 21:00:00 | 340 | drilling -- other | ok | POOH from 350 m to 340 m with drag of 12 MT. Pulled out wet.
| 21:00:00 | 21:45:00 | 340 | drilling -- other | ok | Changed to PS21 slips.
| 21:45:00 | 23:00:00 | 300 | drilling -- other | ok | POOH from 340 m to 300 m with drag of 12 MT. Pulled out wet.
| 23:00:00 | 23:45:00 | 300 | drilling -- other | ok | Made up to TDS. Attempted to pump down the DP, w/ 23 bars 400 litres. No returns up annulus.
| 23:45:00 | 00:00:00 | 300 | drilling -- other | ok | Took time out and evaluated situation.
2008-02-08 | 00:00:00 | 01:00:00 | 140 | drilling -- other | ok | Continued POOH with RTTS plug from 300 m to 140 m, pulled out wet. As comming out of the sub sea well head, lost 12 MT on the weight.
| 01:00:00 | 01:15:00 | 140 | drilling -- other | ok | Established levels by filling the well via trip tank.
| 01:15:00 | 02:00:00 | 40 | drilling -- other | ok | Continued POOH with the RTTS plug from 140 m to 40 m, pulled out wet. Displacement over trip tank OK.
| 02:00:00 | 02:30:00 | 40 | drilling -- other | ok | Made up to TDS, established returns at 38 bars. POOH from 40 m to surface with the RTTS plug.
| 02:30:00 | 02:45:00 | 40 | drilling -- other | ok | Changed to manual slips.
| 02:45:00 | 04:30:00 | 0 | drilling -- other | ok | Laid out the RTTS plug. Found cement on top of the hydraulic slip. The retrieving tool was not fully entered, 5 turns out. Packing element damaged in the bottom p art.
| 04:30:00 | 05:15:00 | 0 | drilling -- other | ok | Continued POOH with 7 std of 5½" DP below the RTTS plug, from 280 m to surface.
| 05:15:00 | 06:00:00 | 0 | drilling -- bop activit ies | ok | Cleaned and cleared the drill floor. Simultaneously flushed lines from CMT unit to BOP. Commenced pressure testing of the shear rams to 20/310 bars 5/10 mins.
| 06:00:00 | 07:00:00 | 0 | drilling -- trip | ok | 2.1m³ pumped 2m³ in return.
Cleaned and cleared drill floor and prepared for handling the 8½" drilling BHA. Meanwhile completed the pressure test of the shear rams to 20/310 bars 5/10 mins,
| 07:00:00 | 07:15:00 | 0 | drilling -- trip | ok | Held tool box talk prior to pick up and M/U 8½" drill BHA.
| 07:15:00 | 11:00:00 | 0 | drilling -- trip | ok | M/U 8½" drilling BHA as per Schlumberger DD&MWD. Installed radio active sources.
| 11:00:00 | 13:15:00 | 937 | drilling -- drill | ok | RIH with 8½" drill BHA on 5" DP, from surface to 937m.
| 13:15:00 | 13:30:00 | 937 | drilling -- drill | ok | Changed over to 5½" handling equipment.
| 13:30:00 | 13:45:00 | 937 | drilling -- drill | ok | M/U to TDS and tested the MWD at 1500 lpm 138 bars.
| 13:45:00 | 17:45:00 | 2619 | drilling -- drill | ok | Continued RIH with 8½" drill BHA on 5½" DP, from 937m to 2619m, filled every 1000m. Average RIH speed 420 m/hr.
| 17:45:00 | 18:15:00 | 2632 | drilling -- drill | ok | Took weight at 2619m. M/U to TDS and washed down to 2632m, 10 rpm, 10kNm, 1500 lpm, 139 bars.
| 18:15:00 | 19:00:00 | 2632 | drilling -- other | ok | Performed choke drill with day shift.
| 19:00:00 | 19:45:00 | 2632 | drilling -- other | ok | Performed choke drill with night shift. Observed saver sub required change out
| 19:45:00 | 20:00:00 | 2632 | interruption -- maint ain | ok | Held tool box talk prior to change out the saver sub.
| 20:00:00 | 22:45:00 | 2632 | interruption -- maint ain | ok | Changed out the saver sub.
| 22:45:00 | 23:15:00 | 2632 | drilling -- drill | ok | P/U one 5½" DP std. and prepared for drilling. Found discrepancy in depth.
| 23:15:00 | 23:30:00 | 2632 | drilling -- trip | ok | Counted the 5½" DP in derrick. Changed depth from 2671m to 2632m.
| 23:30:00 | 00:00:00 | 2670 | drilling -- drill | ok | Washed down from 2632m to 2670m. Washing parameters : Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 146. ROP 30-40 m/hr.
2008-02-09 | 00:00:00 | 01:30:00 | 2733 | drilling -- drill | ok | Continued washing down from 2670m to 2733m. Washing parameters : Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 146. ROP 30-40 m/hr.
| 01:30:00 | 04:30:00 | 2734 | drilling -- drill | ok | Drilled out float. From 2733m to 2734m. Drilling parameters : Flow 1500 lpm / SPP 140 bar / String RPM 10-30 / Bit RPM 125-145. ROP 1-40 m/hr, WOB 1-9 MT. Recovered rubber at the shakers.
| 04:30:00 | 06:00:00 | 2751 | drilling -- drill | ok | Drilled shoe track from 2734m to 2751m. Drilling parameters : Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 146 / ROP 30-40 m/hr / WOB 1 MT / TQ 10-12 kNm. MUD weight 1.4 SG. Back reamed to float with 1500 lpm, RIH and made connection at 2751m, volume pumped prior to connection 26m³.
| 06:00:00 | 06:30:00 | 2760 | drilling -- drill | ok | Drilled shoe track from 2751m to 2760m. Drilling parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / ROP 30-40 m/hr / WOB 1-4 MT / TQ 10-12 kNm. MUD weight 1.4 SG.
| 06:30:00 | 06:45:00 | 2761 | drilling -- drill | ok | Drilled shoe from 2760m to 2761m. Drilling parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / WOB 1-6 MT / TQ 10-12 kNm.
| 06:45:00 | 07:15:00 | 2771 | drilling -- drill | ok | Cleaned out rat hole from 2765m to 2771m. Cleaning parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / WOB 1-3 MT.
| 07:15:00 | 08:00:00 | 2774 | drilling -- drill | ok | Drilled new formation from 2771m to 2774m. Drilling parameters: Flow 1500 lpm / SPP 140 bar / String RPM 30 / Bit RPM 145 / WOB 5-7 MT / TQ 12-14 kNm. MUD weight 1.4 S G.
| 08:00:00 | 09:00:00 | 2760 | formation evalu ation -- rft/fit | ok | Pulled back into the shoe. Racked back one std. Installed side entry sub and CMT hose. Confirmed line up from CMT unit to drill floor. Leak tested line to 100 bars 10 min.
| 09:00:00 | 10:00:00 | 2760 | formation evalu ation -- rft/fit | ok | Performed FIT test. Closed annular. Applied 64 bars down DP and ANN equivalent to 1.65 SG. Rigged down CMT hose and side entry sub.
| 10:00:00 | 19:00:00 | 2854 | drilling -- drill | ok | Linked down the Power Drive. Drilled new formation from 2774m to 2854m. Drilling parameters: Flow 2070 lpm / SPP 250 bar / String RPM 30 / Bit RPM 190 / WOB 7-9 MT / TQ 1 6-19 kNm. ECD 1.51 SG. MUD weight 1.4 SG. Took survey before connection.
| 19:00:00 | 00:00:00 | 2917 | drilling -- drill | ok | Drilled new formation from 2854m to 2917m. Drilling parameters : Flow 2070-2090 lpm / SPP 245-250 bar / String RPM 40 / Bit RPM 203 / ROP 16-20 m/hr / WOB 7-9 MT / TQ 18- 19 kNm. ECD 1.51 SG MUD weight 1.4 SG. Took survey before connection.
2008-02-10 | 00:00:00 | 04:15:00 | 2993 | drilling -- drill | ok | Drilled new formation from 2917m to 2993m. Drilling parameters : Flow 2070 lpm / SPP 245-255 bar / String RPM 40 / Bit RPM 203 / ROP 21-23 m/hr / WOB 6-11 MT / TQ 18-21 kNm. ECD 1.51 SG MUD weight 1.4 SG.
| 04:15:00 | 04:30:00 | 2993 | drilling -- survey | ok | Took survey at 2993 m MD equivalent to 2795 m TVD. Stopped drilling for further instruction in conjunction with F12 perforation and start production.
| 04:30:00 | 06:00:00 | 2992 | drilling -- circulating co nditioning | ok | Cleaned out well reciprocating the pipe, flow 2090 lpm / SPP 215 bar / String RPM 50 / Bit RPM 213. Operations transferred to F-99.
2008-02-13 | 16:00:00 | 00:00:00 | 3035 | drilling -- dril l | ok | Tagged bottom at 2993m. Drilled from 2993m to 3035m. Increased mudweight from 1.40 sg to 1.45 sg . Drilling parameters: Flow 2090-2225 lpm / SPP 200-220 bar / String RPM 180 / ROP 2.5-8,5 m/hr / WOB 4-6 MT / TQ 15-20 kNm / ECD 1.59 SG. Had heavy stick slip with 10 MT WOB to start with, reduced WOB to 5 MT.
2008-02-14 | 00:00:00 | 01:00:00 | 3040 | drilling -- d rill | ok | Continued drilling from 3035m to 3040m. Drilling parameters: Flow 2225 lpm / SPP 220 bar / String RPM 180 / ROP 5-6.5 m/hr / WOB 4-6 MT / TQ 18 kNm / ECD 1.59 SG. Hidra started at 3040m.
| 01:00:00 | 06:00:00 | 3064 | drilling -- d rill | ok | Continued drilling from 3040m to 3064m. Drilling parameters: Flow 2225 lpm / SPP 220 bar / String RPM 180 / ROP 3-6.5 m/hr / WOB 4-6 MT / TQ 15-18 kNm / ECD 1.59 SG. Held pit drill.
| 06:00:00 | 07:30:00 | 3070 | drilling -- d rill | ok | Drilled 8 1/2" hole section from 3064 m to 3070 m MD. Drilling parameters : Flow 2200 lpm / SPP 220 bar / String RPM 180 / WOB 3-8 MT / Torque 11-22 kNm / ECD 1,59-1,60 sg. Contro lled WOB and ROP due to stick slip tendencies. Observed drilling break at 3070 m MD.
| 07:30:00 | 08:00:00 | 3070 | drilling -- d rill | ok | Observed drilling break at 3070 m MD, ROP increased from 5 to 30 m/hr. Flowchecked well - ok - well static.
| 08:00:00 | 11:15:00 | 3095 | drilling -- d rill | ok | Continued drilling 8 1/2" hole section from 3070 m to 3095 m MD. Drilling parameters : Flow 2200 lpm / SPP 220 bar / String RPM 180 / WOB 3-8 MT / Torque 15-20 kNm / ECD 1,59-1,60 sg. Controlled WOB and ROP due to stick slip tendencies.
| 11:15:00 | 11:45:00 | 3095 | drilling -- d rill | ok | Observed drilling break at 3095 m MD, ROP increased from 5 to 35 m/hr. Flowchecked well - ok - well static.
| 11:45:00 | 12:45:00 | 3103 | drilling -- d rill | ok | Continued drilling 8 1/2" section from 3095 to 3103 m MD. Drilling parameters : Flow 2200 lpm / SPP 222 bar / String RPM 180 / WOB 4-8 MT / Torque 16-24 kNm / ECD 1,60 sg.
| 12:45:00 | 13:00:00 | 3103 | drilling -- d rill | ok | Performed SCR's.
| 13:00:00 | 00:00:00 | 3265 | drilling -- d rill | ok | Continued drilling 8 1/2" hole section from 3103 m to 3265 m MD. Added LCM materials to mud prior to entering reservoir. Drilling parameters : Flow 2200 lpm / SPP 220-231 bar / String RPM 180 / WOB 3-8 MT / Torque 11-20 kNm / ECD 1,61-1,62 sg. ROP 10-30 m/hrs. Observed top of Hugin reservoir on logs 3250 m MD / 2987 m TVD. Max gas at top reservoir lag dept h 5 %.
Performed pit drill at 16:25 hrs. Good response from loggers and driller.
2008-02-15 | 00:00:00 | 01:30:00 | 3302 | drilling -- drill | ok | Drilled 8 1/2" hole section from 3265 m to 3302 m MD. Drilling parameters : Flow 2200 lpm / SPP 220-231 bar / String RPM 180 / WOB 3-8 MT / Torque 11-20 kNm / ECD 1,62-1,63 sg. ROP 30 m/hrs. Max gas 6%
| 01:30:00 | 02:00:00 | 3302 | drilling -- drill | ok | Observed increase in active of ~1 m3 over 5 mins. Flowcheked well on trip tanks - ok - well static. Found that degassers had been started - volume from sandtraps overflowed into a ctive.
| 02:00:00 | 04:45:00 | 3327 | drilling -- drill | ok | Continued drilling 8 1/2" hole section from 3302 m to 3327 m MD. Drilling parameters : Flow 2100-2200 lpm / SPP 216-238 bar / String RPM 180 / WOB 3-8 MT / Torque 11-20 kNm / ECD 1,61-1,63 sg. Limited ROP to and cut back flowrate to 2100 lpm due to increasing ECD. Downlinked powerdrive to stop build. Got problems with mudpump#2 and mudpump#3.
| 04:45:00 | 05:15:00 | 3327 | interruption -- o ther | ok | Troubleshot mudpumps. Not able to start mudpump #3. Mudpump #2 gave wrong output on stroke setting. Decided to drill ahead using mudpump #1 only.
| 05:15:00 | 06:00:00 | 3346 | drilling -- drill | ok | . ROP 30 m/hrs.
Continued drilling 8 1/2" hole section from 3327 m to 3346 m MD. Drilling parameters : Flow 2100 lpm / SPP 214 bar / String RPM 180 / WOB 3-6 MT / Torque 21 kNm / ECD 1,61 sg
| 06:00:00 | 08:15:00 | 3385 | drilling -- drill | ok | Drilled 8 1/2" hole section from 3346 m to 3385 m MD. Drilling parameters : Flow 2100 lpm / SPP 220 bar / String RPM 180 / WOB 2-5 MT / Torque 20-23 kNm / ECD 1,61-1,62 sg / ROP 20-30 m/hrs.
| 08:15:00 | 08:30:00 | 3385 | drilling -- drill | ok | Performed SCR's.
| 08:30:00 | 17:30:00 | 3510 | drilling -- drill | ok | Continued drilling 8 1/2" hole section from 3385 m to section TD at 3510 m MD. Drilling parameters : Flow 2100 lpm / SPP 220 bar / String RPM 180 / WOB 3-12 MT / Torque 13-23 kNm / ECD 1,59-1,60 sg / ROP 10-30 m/hrs. Racked back one stand of drillpipe.
| 17:30:00 | 20:15:00 | 3507 | drilling -- circul ating conditioni ng | ok | Circulated hole clean with 3 x bottoms up. Reciprocated stand while pumping. Parameters : Flow 2100 lpm / SPP 212 bar / String RPM 150-180. Observed clean shakers after 3 x bo ttoms up.
| 20:15:00 | 20:45:00 | 3507 | drilling -- trip | ok | Took up down weight 195/149 MT. Recorded off bottom torque at 10/15/20 RPM - 14-16 kNm. Sent downlink to set LWD tools according to Schlumberger instructions.
| 20:45:00 | 21:00:00 | 3507 | drilling -- trip | ok | Flowchecked well - well static. Meanwhile held toolbox meeting prior to POOH.
| 21:00:00 | 21:45:00 | 3307 | drilling -- trip | ok | Pulled 5 stand wet from 3507 m to 3307 m MD. Pulling speed ~10 m/min. No overpull observed.
| 21:45:00 | 22:15:00 | 3307 | drilling -- trip | ok | Flowchecked well - well static. Pumped 5 m3 1,65 sg slug.
| 22:15:00 | 00:00:00 | 2780 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5 1/2" DP from 3307 m to 2780 m MD.
2008-02-16 | 00:00:00 | 00:15:00 | 2740 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5 1/2" DP from 2780 m to 2740 m MD inside 9 5/8" casing shoe. Recorded up down weight 163/137 MT. Recorded torque at 20 RPM - 7 kN m.
| 00:15:00 | 00:45:00 | 2754 | drilling -- trip | ok | Flowchecked well -well static. Meanwhile inspected and serviced TDS. Dropped 2 3/4" drift with pigtail in drillpipe.
| 00:45:00 | 03:15:00 | 1331 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5 1/2" DP from 2754 m to 1331 m MD.
| 03:15:00 | 04:00:00 | 1331 | drilling -- trip | ok | Broke out x-over. Changed from 5 1/2" to 5" handling equipment. Re-inserted 2 3/4" drift into 5" DP as it would not pass the x-over.
| 04:00:00 | 05:30:00 | 110 | drilling -- trip | ok | POOH with 8 1/2" drilling BHA on 5" DP from 1331 m to 110 m MD.
| 05:30:00 | 06:00:00 | 110 | drilling -- trip | ok | Removed PS-21 slips. Inserted masterbushing and bowls. Worked to free 2 3/4" drift which was stuck in jar.
| 06:00:00 | 07:00:00 | 53 | drilling -- trip | ok | Freed 2 3/4" drift. Racked back jar/HWDP and 1 stand of 5" HWDP.
| 07:00:00 | 07:15:00 | 53 | drilling -- trip | ok | Held toolbox talk prior to laying out LWD/MWD/drilling assemblies.
| 07:15:00 | 09:45:00 | 0 | drilling -- trip | ok | Broke out and laid down NM HWDP. Removed RA-source. Broke out and laid down Isonic, Telescope, Ecoscope and Powerdrive.
| 09:45:00 | 10:00:00 | 0 | drilling -- trip | ok | Cleaned and tidied drillfloor.
| 10:00:00 | 10:15:00 | 0 | drilling -- wait | ok | General muster alarm. Crews mustered according to list. Non critical alarm.
| 10:15:00 | 10:45:00 | 0 | drilling -- trip | ok | Continued to clean and tidy drillfloor. Meanwhile changed rollers for IBOP actuator on TDS.
| 10:45:00 | 11:45:00 | 0 | drilling -- trip | ok | -Inspected, cleaned and greased PS-21 slips
-Moved power rollers on cantilever
-Prepared for running WL
Meanwhile
Prepared for picking up 5 1/2" DP from deck.
| 11:45 | 12:00:00 | 0 | drilling -- trip | ok | Held toolbox talk prior to inspection and service on AFT PRS.
| 12:00:00 | 12:45:00 | 0 | drilling -- other | ok | Inspected and serviced AFT PRS. Found loose bar (54 cm / 560 g) sitting in hoses/junction box below upper drive.
| 12:45:00 | 13:15:00 | 0 | interruption -- o ther | ok | Evaluated finding. Suspected drag chain in PRS beam.
| 13:15:00 | 13:45:00 | 0 | interruption -- o ther | ok | Inspected drag chain in PRS beam. Could not identify bar (FG) comming from PRS beam.
| 13:45:00 | 14:15:00 | 0 | interruption -- o ther | ok | Performed derrick inspection from PRS to crown block.
| 14:15:00 | 19:00:00 | 0 | interruption -- o ther | ok | Removed lid and inspected inside PRS upper drive. Found rotational dragchain in AFT PRS upper drive to be damaged. Identified origin of loose bar (FG) to be cross member in rotational dragchain. Assessed damage. Decided to perform repair of dragchain.
| 19:00:00 | 00:00:00 | 0 | interruption -- o ther | ok | -Built cable head for WL
-Laid out MDT tools
-Rigged load sensors on WL unit
Meanwhile :
Repaired rotational dragchain in AFT PRS upper drive.
2008-02-17 | 00:00:00 | 01:00:00 | 0 | interruption -- other | ok | Repaired rotational dragchain in AFT PRS upper drive. Meanwhile tested MDT tools
| 01:00:00 | 02:15:00 | 0 | interruption -- other | ok | Repaired rotational dragchain in AFT PRS upper drive. Temporarily halted testing of MDT tools due to loading of drillpipe onto cantilever/pipe-deck.
| 02:15:00 | 03:15:00 | 0 | interruption -- other | ok | Repaired rotational dragchain in AFT PRS upper drive. Meanwhile tested MDT tools.
| 03:15:00 | 06:00:00 | 0 | formation evaluation -- log | ok | Tested MDT tools. Calibrated weight sensor. Brought WL rigging equipment to drillfloor.
| 06:00:00 | 08:45:00 | 0 | formation evaluation -- log | ok | Rigged up sheaves and cable. Brought logging tools to drillfloor.
| 08:45:00 | 09:00:00 | 0 | formation evaluation -- log | ok | Held toolbox talk prior to making up logging string.
| 09:00:00 | 10:00:00 | 0 | formation evaluation -- log | ok | Made up MDT toolstring.
| 10:00:00 | 10:30:00 | 0 | formation evaluation -- log | ok | Tested MDT tools on surface prior to RIH.
| 10:30:00 | 10:45:00 | 0 | formation evaluation -- log | ok | Re-positioned lower sheave due to unfavorable cable allignment.
| 10:45:00 | 11:15:00 | 0 | formation evaluation -- log | ok | RIH with MDT logging string on 7/48 cable. Perfomed shallow test - negative.
| 11:15:00 | 11:45:00 | 0 | formation evaluation -- log | ok | POOH with MDT logging tools. Performed checks on surface - ok.
| 11:45:00 | 16:30:00 | 3245 | formation evaluation -- log | ok | RIH with MDT logging string on 7/48 cable from surface to station #1 at 3245 m MD. Correlated MDT tool. Attempted to activate MDT probe - negativ e.
| 16:30:00 | 17:45:00 | 2671 | interruption -- repair | ok | Pulled MDT tool from 3245 m to 2671 m MD inside 9 5/8" casing shoe. Troubleshot tool failure - negative.
| 17:45:00 | 19:30:00 | 0 | interruption -- repair | ok | POOH with MDT logging string on 7/48 cable from 2671 m MD to surface.
| 19:30:00 | 23:00:00 | 0 | interruption -- repair | ok | Checked cable, cable head and surface cables - ok.
| 23:00:00 | 00:00:00 | 0 | interruption -- repair | ok | Isolated and checked MDT string components as required.
2008-02-18 | 00:00:00 | 00:30:00 | 0 | workover -- wai t | ok | General alarm - crews mustered according to list. Announced possible gas in wellhead area. Removed WL toolstring from well - well stable - stood by for securing well. Investiga ted alarm and found fault on gas sensor. Resumed work.
| 00:30:00 | 03:15:00 | 0 | interruption -- r epair | ok | Continued isolating and checking MDT string components as required.
| 03:15:00 | 03:30:00 | 0 | interruption -- r epair | ok | Found both MRPO pumps in MDT toolstring to be faulty. Only one back up MRPO pump available on rig. Discussed situation. Decided to run simplified string with only 1 pump.
| 03:30:00 | 05:45:00 | 0 | interruption -- r epair | ok | Traced tools for simplifed MDT toolstring. Brought tools to drillfloor. Made up and tested simplified MDT toolstring.
| 05:45:00 | 06:00:00 | 0 | interruption -- r epair | ok | RIH with simplified MDT toolstring on 7/48 cable.
| 06:00:00 | 07:30:00 | 2700 | interruption -- r epair | ok | RIH witth MDT toolstring on 7/48 cable from surface to 2700 m MD inside 9 5/8" shoe. Rested MDT toolstring for 30 min to allow for temperature adaption.
| 07:30:00 | 08:00:00 | 3270 | interruption -- r epair | ok | RIH with MDT toolstring on 7/48" cable from 2700 m to 3270 m MD.
| 08:00:00 | 08:15:00 | 3245 | interruption -- r epair | ok | Correlated toolstring and placed MDT probe at 3245 m MD sample point in Heather.
| 08:15:00 | 09:30:00 | 3245 | formation evalu ation -- log | ok | Obatined pressure point sample at 3245 m MD in Heather. Attmepted to RIH - cable stuck with MDT at 3345 m MD.
| 09:30:00 | 10:15:00 | 3245 | formation evalu ation -- log | ok | Worked MDT toolstring and found string to be stuck. No tension on cable head observed when pulling surface tension of max pull 12000 llbs - wire probably stuck/keyseated in f ormation. Depth on mechanical counter 3233 m MD.
| 10:15:00 | 12:00:00 | 3245 | interruption -- fi sh | ok | Continued to work WL with max 12000 lbs pull. Observed movement of WL unit. Secured WL unit with chains. Checked sheave wheels on drillfloor.
| 12:00:00 | 14:30:00 | 3245 | interruption -- fi sh | ok | Put 12000 lbs tension in WL and put on brake. Depth on mechancial counter 3232 m MD with 12000 lbs tension.
| 14:30:00 | 22:00:00 | 3245 | interruption -- fi sh | ok | Worked WL several times. Slacked off to 5000 lbs and picked up to max tension 12000 lbs several tiems - not able to make progress. Prepared for doing cut and thread fishing o n drillpipe. Prepared fishing procedure. Decided to do fluid sampling at stuck point in Heather prior to fishing.
| 22:00:00 | 23:00:00 | 3245 | formation evalu ation -- log | ok | Pumped to clear tool of mud. Activated MDT probe.
| 23:00:00 | 00:00:00 | 3245 | formation evalu ation -- log | ok | Stepped up MDT pump in increments. Performed MDT sampling at 3245 m MD according to Schlumberger procedure.
2008-02-19 | 00:00:00 | 02:30:00 | 3245 | formation eval uation -- log | ok | Perfomed MDT sampling at 3245 m MD. Observed 170 bar diff pressure over probe. Filled 2 ea 450 cc bottles with formation fluid. Contamination ~13%. Total volume pumped ~3 0 litres.
| 02:30:00 | 03:00:00 | 3245 | interruption -- fish | ok | Worked WL up and down in attempt to get free - negativ. Ran probe out/in and re-attempted freeing WL - negative. Slacked off WL to 3000 lbs tension => depth on mechanical co unter 3245 m MD.
| 03:00:00 | 03:15:00 | 3245 | interruption -- fish | ok | Held pre-job meeting prior to rigging up for cut and thread fishing.
| 03:15:00 | 06:00:00 | 3245 | interruption -- fish | ok | Put 7200 lbs tension on WL. Fitted T-clamp on 7/48 cable and slacked off WL. Cut 7/48 cable with 5-6 m loose end and fitted spear on same. Fitted spearhead overshot and 2 x fis hing weights to winch side of wireline. Removed sheave wheel from TDS. Removed sheave wheel from aft samson post.
| 06:00:00 | 08:45:00 | 0 | interruption -- fish | ok | Rigged up for cut and thread fishing. Suspended upper sheave in dedicated sling in derrick. Suspended lower sheave in V-door above HTS, secured same with slings.
| 08:45:00 | 09:15:00 | 0 | interruption -- fish | ok | Held toolbox talk prior to performing cut and thread.
| 09:15:00 | 10:00:00 | 0 | interruption -- fish | ok | Picked up singel and made up x-over. Laid out single.
| 10:00:00 | 11:15:00 | 0 | interruption -- fish | ok | Held toolbox talk prior to inserting PS-30 automatic slips.
| 11:15:00 | 13:30:00 | 0 | interruption -- fish | ok | Rigged up and changed to PS-30 automatic slips. Slacked off wire and hung off in slips with T-bar.
| 13:30:00 | 14:00:00 | 0 | interruption -- fish | ok | Pull tested T-bar. Performed toolbox talk for continuation of operations.
| 14:00:00 | 14:45:00 | 0 | interruption -- fish | ok | Re-set grip on T-bar in order to get more slack on wire and be able to lay grapple/drain sub on the drilfloor. Ran WL up/down to test counter balance weights on wire - ok. Threade d first joint.
| 14:45:00 | 16:15:00 | 13 | interruption -- fish | ok | Picked up first joint. Made up grapple and drain sub. RIH with 5 1/2" DP single.
| 16:15:00 | 19:00:00 | 13 | interruption -- fish | ok | Observed damage on cable due to unfavorable angel when spinning in the drilpipe, wire partly cut through. Suspended WL in C-plate and cut off damaged wire. Fitted spearhead and fishing weights on winch side of wireline.
| 19:00:00 | 00:00:00 | 13 | interruption -- fish | ok | Rigged down upper sheave. Attached upper sheave in crown block. Removed 5" weco coupling and blind cap on top of TDS. Put on weco nut acting as wear bushing. Threaded WL through topdrive.
2008-02-20 | 00:00:00 | 06:00:00 | 268 | interruption -- fish | ok | Ran 5 1/2" DP singles over 7/48 wireline from 13 m to 268 m MD according to cut and thread procedure.
| 06:00:00 | 15:15:00 | 780 | interruption -- fish | ok | Ran 5 1/2" DP singles over 7/48 wireline from 268 m to 780 m MD according to cut and thread procedure. Laid out singles #26 and #28 due to stuck protectors.
| 15:15:00 | 19:00:00 | 780 | interruption -- fish | ok | Laid out 5 1/2" DP singles on pipedeck. Measured and drifted joints. Simultaneoulsy re-arranged stands in derrick.
| 19:00:00 | 19:30:00 | 780 | interruption -- fish | ok | Held toolbox talk prior to continuing cut and thread.
| 19:30:00 | 00:00:00 | 1090 | interruption -- fish | ok | Continued running 5 1/2" DP singles over 7/48 wireline from 780 m to 1090 m MD according to cut and thread procedure. Checked wireline and TDS top in coupling for wear every 25 joints.
2008-02-21 | 00:00:00 | 04:15:00 | 1438 | interruption -- fish | ok | Ran 5 1/2" DP singles over 7/48 wireline from 1090 m to 1438 m MD according to cut and thread procedure.
| 04:15:00 | 06:00:00 | 1438 | interruption -- fish | ok | Laid out 5 1/2" DP singles on pipedeck. Measured and drifted joints. Moved weight bars on winch side of wiereline in order to move stress points. Checked rope socket - ok.
| 06:00:00 | 10:30:00 | 1438 | interruption -- fish | ok | Laid out 5 1/2" singles on pipedeck. Cleaned and checked threads. Measured and drifted joints.
| 10:30:00 | 10:45:00 | 1438 | interruption -- fish | ok | Held toolbox talk prior to continuing cut and thread operation.
| 10:45:00 | 11:45:00 | 1500 | interruption -- fish | ok | Ran 5 1/2" singles over 7/48 wireline from 1438 m to 1500 m MD.
| 11:45:00 | 12:45:00 | 1500 | interruption -- fish | ok | Wireline caught up behind AFT PRS arm. Removed wire and checked for damage - ok.
| 12:45:00 | 14:15:00 | 1640 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1500 m to 1640 m MD.
| 14:15:00 | 15:45:00 | 1640 | interruption -- fish | ok | Cut back winch side of wireline. Re-built rope socket and fitted spearhead and new weights.
| 15:45:00 | 18:00:00 | 1750 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1640 m to 1750 m MD. Observed hydraulic leakage from TDS.
| 18:00:00 | 18:30:00 | 1750 | interruption -- other | ok | Repaired hydraulic leakage on TDS.
| 18:30:00 | 21:15:00 | 1850 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1750 m to planned side entry sub depth of 1850 m MD.
| 21:15:00 | 22:30:00 | 1850 | interruption -- fish | ok | Held toolbox talk for installing side entry sub. Assessed weather conditions and forecast. High winds > 40 knots and unfavorable forecast. Not able to perform riding belt operations required to re-position upper sheave wheel. Decided to continue running 5 1/2" DP singels over wireline to shoe depth.
| 22:30:00 | 00:00:00 | 1989 | interruption -- fish | ok | Continued running 5 1/2" singles over 7/48 wireline from 1750 m to 1989 m MD.
2008-02-22 | 00:00:00 | 06:00:00 | 2595 | interruption -- fish | ok | Ran 5 1/2" singles over 7/48 wireline from 1989 m to 2595 m MD. Winds 35- 40 knots.
| 06:00:00 | 07:30:00 | 2704 | interruption -- fish | ok | Ran 5 1/2" singles over 7/48 wireline from 2595 m to 2704 m MD.
| 07:30:00 | 07:45:00 | 2704 | interruption -- fish | ok | Held toolbox talk prior to rigging TDS work platform.
| 07:45:00 | 08:00:00 | 2704 | interruption -- fish | ok | Lowered and positioned TDS work platform.
| 08:00:00 | 08:30:00 | 2704 | interruption -- fish | ok | Pulled wireline through TDS and secured same. Installed 5" weco blind plug in TDS top-in coupling.
| 08:30:00 | 08:45:00 | 2704 | interruption -- fish | ok | Retracted and secured TDS work platform.
| 08:45:00 | 09:15:00 | 2704 | interruption -- fish | ok | Performed derrick inspection due to period of high winds.
| 09:15:00 | 10:00:00 | 2704 | interruption -- fish | ok | Pressure tested TDS 5" weco blind plug and K5 manifold valve 5/10 min 20/345 bar. Re-routed wireline over TDS.
| 10:00:00 | 10:15:00 | 2704 | interruption -- fish | ok | Made up 4 m 5" pup joint to 5" x 5 1/2" x-over, threaded wireline through same.
| 10:15:00 | 10:45:00 | 2704 | interruption -- fish | ok | Changed to 5" inserts in elevator. Picked up 5" pup/x-over and made up same to string.
| 10:45:00 | 11:00:00 | 2704 | interruption -- fish | ok | Held toolbox talk prior to removeing PS-30 automatic slips.
| 11:00:00 | 11:30:00 | 2707 | interruption -- fish | ok | Removed PS-30 automatic slips, dressed same for 5" DP and re-installed in rotary. Ran in on 5" DP to 2707 m MD.
| 11:30:00 | 12:00:00 | 2707 | interruption -- fish | ok | Took 9000 lbs tension on WL. Fitted T-bar to wireline and hung off on 5" DP.
| 12:00:00 | 19:00:00 | 2707 | interruption -- fish | ok | Fitted WL in sideentry sub. Cut WL and built rope sockets on winch and well ends according to Schlumberger procedure. Built WL torpedo. Changed from 5 1/2" to 5" saver sub on TDS.
| 19:00:00 | 00:00:00 | 2707 | interruption -- waiting on w eather | ok | -Inspected TDS torque wrench
-Inspected and greased PDM, HTS, IR, PS-21 and DP elevators
-Installed drag chain guide on AFT PRS
-Pressure tested standpipe and kill manifolds
-Repaired trip tank pump
Meanwhile :
Waited on weather. Winds 60-70 knots.
2008-02-23 | 00:00 | 04:15:00 | 2707 | interruption -- w aiting on weathe r | ok | -Installed drag chain guide on AFT PRS
-Pressure tested standpipe and kill manifolds
Meanwhile :
Waited on weather. Winds 50-60 knots.
| 04:15 | 05:15:00 | 2707 | interruption -- fi sh | ok | Wind down to 45 knots. Performed derrick inspection after period of high winds. Assessed rigging alternatives for removal of upper sheave wheel in crown block.
| 05:15:00 | 05:30:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk prior to removing upper sheave wheel.
| 05:30:00 | 06:00:00 | 2707 | interruption -- fi sh | ok | Barriered off drilfloor for aloft work. Brought rigging equipment to derrick. Rigged down upper sheave wheel.
| 06:00:00 | 08:15:00 | 2707 | interruption -- fi sh | ok | Rigged down WL sheave wheel from crown block. Lowered sheave wheel to drillfloor. Re-made torpedo due to tangeled wires in derrick. Powered up WL. Cleared and tidied drillfloo r.
| 08:15:00 | 08:30:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk for repositioning WL sheave.
| 08:30:00 | 09:30:00 | 2707 | interruption -- fi sh | ok | Repositioned WL sheave in derrick. Attached wireline over sheave.
| 09:30:00 | 09:45:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk prior to making up side entry sub.
| 09:45:00 | 10:30:00 | 2707 | interruption -- fi sh | ok | Made up side entry sub to toolstring according to Schlumberger instructions.
| 10:30:00 | 10:45:00 | 2707 | interruption -- fi sh | ok | Held toolbox talk prior to testing IBOPs on TDS.
| 10:45:00 | 11:45:00 | 2707 | interruption -- fi sh | ok | Rigged up swage with 1502 weco to TDS. Hooked up cement hose. Stopped for ESD test.
| 11:45:00 | 15:00:00 | 2707 | interruption -- ot her | ok | -Changed die holders and dies on TDS torque wrench
-Cleaned and tidied drillfloor and shaker areas
-Continued installation of dragchain guide on AFT PRS
Halted operation for ongoing ESD test.
Meanwhile :
| 15:00:00 | 16:00:00 | 2707 | interruption -- fi sh | ok | Pressure tested upper/lower IBOP to 30/345 bar 5 /10 min. Meanwhile continued ESD testing.
| 16:00:00 | 16:30:00 | 2707 | interruption -- fi sh | ok | Picked up stand of 5" DP and made up to side entry sub. Inserted rubber seals in side entry sub. Clamped 7/48 cable in side entry sub cut out.
| 16:30:00 | 16:45:00 | 2750 | interruption -- fi sh | ok | RIH with 5" DP from 2707 to 2750 m MD, held wireline tension contant at ~7000 lbs.
| 16:45:00 | 20:00:00 | 2750 | interruption -- fi sh | ok | Broke circulation at 9 5/8" shoe and stepped up rate to 700 lpm as limited by erosion figures for side entry sub. Circulated bottoms up. Standpipe pressure rose from 10 bar to 30 bar throughout circulation. Mud weight out 1,39 sg rising to 1,43 sg towards the end. Mud weight in 1,45 sg. Gas peaked at 7% and levelled out on 0,3% towards end of circulation.
| 20:00:00 | 21:00:00 | 2750 | interruption -- fi sh | ok | Held toolbox talk prior to running into open hole. Meanwhile flowchecked well and allowed well to equalize due to pipe/annulus imbalance.
| 21:00:00 | 00:00:00 | 2996 | interruption -- fi sh | ok | RIH with 5" DP from 2750 m to 2996 m MD, held wireline tension contant at ~7000 lbs. Made up TDS to each stand to limit backflow. At 2835 m MD, got indications on downhole ten sion that WL and fish were free, attempted to pull fish free with 12000 lbs WL tension - negative - WL still stuck.
2008-02-24 | 00:00:00 | 02:00:00 | 3202 | interruption -- fish | ok | RIH with 5" DP from 2996 m to 3202 m MD, held wireline tension contant at ~7000 lbs. Made up TDS to each stand to limit backflow. Hole condtions good - no significant drag observed.
| 02:00:00 | 02:15:00 | 3202 | interruption -- fish | ok | Broke circulation and cleaned grapple pumping 300 strokes at 1000 lpm. Observed imbalance pipe/annulus when stopped pumping - SPP 5 bar. Good corrspondance with dow nhole pressure of 430 bar read from log and 1,47 sg mudweight in annulus.
| 02:15:00 | 02:45:00 | 3202 | interruption -- fish | ok | RIH with 5" DP from 3202 m MD and caught fish at 3221 m MD. Set down ~5 MT on fish and observed indication of succesful catch on surface and downhole WL tension.
| 02:45:00 | 03:00:00 | 3192 | interruption -- fish | ok | Picked up 10 m while allowing wireline to slack off - observed surface and downhole WL tension decreasing.
| 03:00:00 | 06:00:00 | 3167 | interruption -- fish | ok | Pulled 5" DP while feeding torpedo through upper and lower sheaves. Had to dismantle wire guides on lower sheave for torpedo to pass. Fitted T-bar and hung off wire in rotary. Slacked off wire and removed from depth counters on WL unit. Spooled torpedo onto WL drum and inserted WL back in depth counters.
| 06:00:00 | 09:00:00 | 2710 | interruption -- fish | ok | POOH wet with 5" DP from 3167 m to 2710 m MD. Maintained ~5000 lbs tension in wirieline while spooling in.
| 09:00:00 | 09:45:00 | 2710 | interruption -- fish | ok | Flowchecked well - well static - ok. Removed snatch block from wireline.
| 09:45:00 | 10:30:00 | 2710 | interruption -- fish | ok | Pumped 5 m3 1,65 sg slug at 700 lpm and chased to drillfloor.
| 10:30:00 | 11:45:00 | 2710 | interruption -- fish | ok | Released electrical weakpoint. Powered down logging unit.
| 11:45:00 | 14:45:00 | 2710 | interruption -- fish | ok | POOH with WL inside 5 1/2" DP from 2710 m MD to surface.
| 14:45:00 | 15:30:00 | 2707 | interruption -- fish | ok | Broke out side entry sub and laid down same. Cut loose WL from side entry sub. Rigged down lower sheave and secured upper sheave above V-door.
| 15:30:00 | 15:45:00 | 2707 | interruption -- fish | ok | Held toolbox talk prior to changing handling equipment.
| 15:45:00 | 16:00:00 | 2707 | interruption -- fish | ok | Changed slips segments. Re-activated guides in PS-30 automatic slips.
| 16:00:00 | 16:30:00 | 2703 | interruption -- fish | ok | Broke out and and laid down 5" x 5 1/2" x-over with 5" pup joint.
| 16:30:00 | 20:15:00 | 0 | interruption -- fish | ok | POOH with 5 1/2" DP from 2703 m MD to surface.
| 20:15:00 | 22:15:00 | 0 | interruption -- fish | ok | Installed C-plate in rotary and hung off MDT toolstring. Broke off tool socket sitting in grapple. Parted and pulled toolstring sections using tugger. Broke off grapple and circulatio n sub and set back last stand of 5 1/2" DP.
| 22:15:00 | 22:30:00 | 0 | drilling -- bop/wellh ead equipment | ok | Held toolbox talk prior to picking up jet sub and BOP test plug.
| 22:30:00 | 00:00:00 | 160 | drilling -- bop/wellh ead equipment | ok | Cleared and tidied drillfloor. Picked up and made up jet sub. RIH on 5" DP from surface to 160 m MD.
2008-02-25 | 00:00:00 | 01:15:00 | 160 | drilling -- bop/wellhead equipment | ok | Washed accross subsea wellhead with jet sub 4 times pumping at 3000 lpm.
| 01:15:00 | 03:00:00 | 300 | drilling -- bop/wellhead equipment | ok | Made up test plug and RIH with same on 5" DP. Landed test plug in subsea wellhead/wearbushing at 140 m MD. Flushed lines from cement unit and verified line up.
| 03:00:00 | 06:00:00 | 300 | drilling -- bop activities | ok | Tested 18 3/4" surface BOP against tests plug in subsea wellhead, 20/345 bar 5/10 min.
| 06:00:00 | 11:00:00 | 300 | drilling -- bop activities | ok | -Changed elevators
-Cleaned and maintained drillfloor equipment
-Removed 7/48 WL sheaves from derrick
-Serviced TDS
Meanwhile :
Tested 18 3/4" surface BOP against test plug in subsea wellhead, 20/345 bar 5 /10 min.
| 11:00 | 11:45:00 | 160 | drilling -- bop/wellhead equipment | ok | POOH with 5 1/2" DP from 300 m to 160 m MD. Broke out and laid down test plug.
| 11:45:00 | 12:00:00 | 0 | drilling -- bop/wellhead equipment | ok | POOH with 5" DP from 160 m MD to surface. Broke out and laid down jet sub.
| 12:00:00 | 13:30:00 | 0 | formation evaluation -- log | ok | Cleaned and tidied drillfloor prior to bringing in logging tools.
| 13:30:00 | 13:45:00 | 0 | formation evaluation -- log | ok | Held toolbox talk prior to running MDT toolstring.
| 13:45:00 | 14:30:00 | 41 | formation evaluation -- log | ok | Ran MDT toolstring in sections to 41 m MD using C-plate and tugger according to Schlumberger instructions.
| 14:30:00 | 14:45:00 | 41 | formation evaluation -- log | ok | Changed dies in IR. Made up AH-3 1/2" x 4 1/2" IF x-over to 5" DP stand. Made up x-over to MDT logging string.
| 14:45:00 | 15:15:00 | 41 | formation evaluation -- log | ok | Connected locomotive to docking head. Schlumberger tetsed MDT toolstring. Disconnected locomotive.
| 15:15:00 | 15:30:00 | 41 | formation evaluation -- log | ok | Held toolbox talk prior to RIH with MDT toolstring on 5" DP.
| 15:30:00 | 16:00:00 | 200 | formation evaluation -- log | ok | RIH with MDT toolstring on 5" DP from 41 m to 200 m MD. Max running speed 2 min/stand.
| 16:00:00 | 16:30:00 | 200 | formation evaluation -- log | ok | Removed master bushing and inserted PS-30 automatic slips in rotary.
| 16:30:00 | 17:45:00 | 734 | formation evaluation -- log | ok | RIH with MDT toolstring on 5" DP from 200 m to 734 m MD. Max running speed 2 min/stand.
| 17:45:00 | 18:00:00 | 734 | formation evaluation -- log | ok | Broke circulation and brought pumps up to 1800 lpm for 5 mins.
| 18:00:00 | 19:00:00 | 734 | formation evaluation -- log | ok | Installed 5" x 5 1/2" x-over. Changed to 5 1/2" handling equipment.
| 19:00:00 | 00:00:00 | 2267 | formation evaluation -- log | ok | RIH with MDT toolstring from 734 m to 2267 m MD on 5 1/2" DP. Max running speed 2 min/stand. Circulated 500 lpm / 3 mins every 500 m.
2008-02-26 | 00:00:00 | 02:00:00 | 2751 | formation evalua tion -- log | ok | RIH with MDT toolstring from 2267 m to 2751 m MD on 5 1/2" DP. Max running speed 2 min/stand. Circulated 500 lpm / 3 mins every 500 m.
| 02:00:00 | 02:30:00 | 2755 | formation evalua tion -- log | ok | Installed and made up 5 1/2" x 5" x-over and 5" pup joint for circulation.
| 02:30:00 | 04:15:00 | 2755 | formation evalua tion -- log | ok | Circulated 2 x bottoms up pumping at 2000 lpm / SPP 93 bar. Gas peaked at 6,6% on 1st bottom up and levelled out on 0,2% after 2nd bottom up. MW in/out 1,44/1,44 sg. Te sted rheology and found mud to be in good condition.
| 04:15:00 | 06:00:00 | 2755 | formation evalua tion -- log | ok | Rigged upper and lower sheave wheels. Deactivated guides in PS-30 automatic slips. Lifted side entry sub with tugger and put locomotive into pipe. Spooled out approx 100 m on WL. Stabbed on side entry sub and lowered upper sheave wheel to centre position.
| 06:00:00 | 10:00:00 | 2759 | formation evalua tion -- log | ok | Made up side entry sub. Made up 5" stand for pumping down locomotive. Pumped down locomotive while spooling out wireline. Pumpe rate 420-510 lpm / SPP 15-18 bar.
| 10:00:00 | 10:15:00 | 2759 | formation evalua tion -- log | ok | Increased pump rate to 1000 lpm / SPP 37 bar before latching locomotive in docking head. Observed 7 bar pressure increase when docking.
| 10:15:00 | 10:30:00 | 2759 | formation evalua tion -- log | ok | Powered up logging tools. Schlumberger tested MDT toolstring.
| 10:30:00 | 11:00:00 | 2759 | formation evalua tion -- log | ok | Clamped 7/46 cable in side entry cut out. Tested cable docking by applying 3500 lbs overpull on wireline for 5 mins - ok.
| 11:00:00 | 11:30:00 | 2759 | formation evalua tion -- log | ok | Held toolbox talk prior to RIH with MDT toolstring on 5" DP / 7/46 cable. Went through well control contingencies. Function tested hydraulic wireline cutter - ok.
| 11:30:00 | 20:15:00 | 3421 | formation evalua tion -- log | ok | RIH with 5" DP and 7/46 cable. Pumped 650 lpm when moving string downwards. Performed pressure point sampling in Hugin formation from 3252 m to 3412 m MD accordin g to instructions from geologist. Hole condition good - no significant drag observed.
| 20:15:00 | 00:00:00 | 3417.5 | formation evalua tion -- log | ok | Correlated and took station at 3417,5 for fluid sampling. Performed fluid sampling. Lined up to trip tank and monitored well continously while performing sampling.
2008-02-27 | 00:00:00 | 00:45:00 | 3417.5 | formation evalu ation -- log | ok | Performed fluid sampling at 3417,5 m MD. Obtained 2 ea 450 cc samples. Monitored well on trip tank.
| 00:45:00 | 02:45:00 | 3412.5 | formation evalu ation -- log | ok | Pumped 6 m3 slug and allowed active to stabilize. Correlated and took station at 3412,5 m MD.
| 02:45:00 | 04:30:00 | 3412.5 | formation evalu ation -- log | ok | Performed fluid sampling at 3412,5 m MD. Monitored well on trip tank. Observed downhole tool failure. Adequate sample not obtained from this station.
| 04:30:00 | 05:15:00 | 3412.5 | interruption -- r epair | ok | Troubleshot tool failure. Not able to function probe and pumps indicating problems with high voltage circuit. Checked surface equipment and confirmed ok. Discussed situation. D ecided to start pulling out of hole.
| 05:15:00 | 06:00:00 | 3244 | interruption -- r epair | ok | Pulled logging tool free with ~5 MT overpull on block. Got overpull alarm 18 000 lbs on downhole tension. Communication with logging tools ok, but still unable to function high v oltage circuit. POOH with 5" DP from 3412,5 m to 3244 m MD. Maintained 2500 lbs pull in wireline while pulling out.
| 06:00:00 | 08:15:00 | 2757 | interruption -- r epair | ok | POOH with 5" DP from 3244 m to 2757 m MD. Hole in good condtion - no significant drag observed.
| 08:15:00 | 10:15:00 | 2757 | interruption -- r epair | ok | Removed clamps from side entry sub. Took overpull on wireline and released locomotive from docking head.
| 10:15:00 | 10:45:00 | 2755 | interruption -- r epair | ok | Broke out side entry sub and laid down locomotive.
| 10:45:00 | 11:30:00 | 2755 | interruption -- r epair | ok | Checked locomotive and cable - ok. Cut cable loose from side entry sub.
| 11:30:00 | 13:00:00 | 2755 | formation evalu ation -- log | ok | Circulated bottoms up at 2000 lpm / 82-95 bar SPP. Gas peaked at 6,6% at bottoms up. MW in/out 1,45 sg.
| 13:00:00 | 13:30:00 | 2755 | formation evalu ation -- log | ok | Flow checked well - well static - ok.
| 13:30:00 | 14:00:00 | 2755 | formation evalu ation -- log | ok | Pumped 6 m3 1,62 sg slug and chased to drillfloor. Allowed active to stabilize.
| 14:00:00 | 15:00:00 | 2751 | formation evalu ation -- log | ok | Held toolbox talk. Changed inserts in PS-30 automaitic slips. Broke out and laid down 5" pup joint and 4 1/2" IF x 5 1/2" FH x-over.
| 15:00:00 | 15:30:00 | 2550 | formation evalu ation -- log | ok | POOH with MDT toolstring on 5 1/2" DP from 2751 m to 2550 m MD. Got problems with drawwork.
| 15:30:00 | 16:00:00 | 2550 | interruption -- o ther | ok | Troubleshot problems with drawwork.
| 16:00:00 | 20:00:00 | 734 | formation evalu ation -- log | ok | POOH with MDT toolstring on 5 1/2" DP from 2550 m to 734 m MD.
| 20:00:00 | 20:15:00 | 734 | formation evalu ation -- log | ok | Changed handling equipment from 5 1/2" to 5". Broke out and laid down 4 1/2" IF x 5 1/2" FH x-over.
| 20:15:00 | 21:30:00 | 41 | formation evalu ation -- log | ok | POOH with MDT toolstring on 5" DP from 334 m to 41 m MD.
| 21:30:00 | 23:00:00 | 0 | formation evalu ation -- log | ok | Parted and pulled MDT toolstring sections using C-plate and tugger. Found signs of short circuit in bulkhead coupling. Inner rubber packing on quicksilver probe was worn and tor n.
| 23:00:00 | 00:00:00 | 0 | formation evalu ation -- log | ok | Cleared and tidied drillfloor. Ran stand of 5" DP to help breaking off 5" saver sub.
2008-02-28 | 00:00:00 | 03:45:00 | 0 | formation evalu ation -- log | ok | Changed from 5" to 5 1/2" saver sub in TDS. Changed die holders and dies in TDS torque wrench. Pulled 5" stand and racked back. Broke and laid down 5" pup, 5" x 5 1/2" x-over and AH-3 1/2" x 4 1/2" IF x-over. Meanwhile packed and disconnected MDT and WL containers for backload/removal.
| 03:45:00 | 06:00:00 | 0 | formation evalu ation -- log | ok | Cleared and tidied drillfloor. Brought casing running equipment to V-door. Removed PS-30 automatic slips. Installed Odfjell FMS in rotary. Positioned Odfjell casing tong on rails in f ront of IR. Prepared for rigging down WL sheave.
| 06:00:00 | 07:00:00 | 0 | formation evalu ation -- log | ok | RD WL sheave and installed HTS roller section. Drifted pipe on setback.
| 07:00:00 | 09:30:00 | 0 | drilling -- casin g | ok | Held tool box talk for RU to run 7" liner. Moved HTS rollers to aft end of cantiliver. Changed inserts in elevator and RU Odfjell csg tong.
| 09:30:00 | 12:30:00 | 40 | drilling -- casin g | ok | Held tool box talk prior to running 7" liner. MU and RIH with shoe track and landing collar. Checked shoe and float collar for flow-through. Thread locked first 4 connections.
| 12:30:00 | 18:15:00 | 289 | drilling -- casin g | ok | Installed pip-tag 0.34 m below top of collar on 1.92 m pup-joint in RA assembly. Estimated RA depth is 3216.17 m, but final depth will be given when 7" liner is set.
RIH with 7" liner from 40 m to 289 m MD, filling every 5th joint. Max running speed was 5 joints/hr
| 18:15:00 | 00:00:00 | 734 | drilling -- casin g | ok | RIH with 7" liner from 289 m to 734 m MD, filling every 5th joint. Max running speed was 9 joints/hr.
2008-02-29 | 00:00:00 | 01:30:00 | 842 | drilling -- casing | ok | RIH with 7" liner from 734 m to 842 m MD, filling every 5th joint. Max running speed was 5 joints/hr. Filled liner completely before picking up hanger assembly.
| 01:30:00 | 03:30:00 | 850 | drilling -- casing | ok | Changed to 5½" DP elevators. P/U hanger/TSP packer assembly and MU same as per Weatherford procedure. Removed 7" FMS slips, installed master bushing. Filled PBR with Hi-visc mud. Took up/down weight 105/95 MT.
| 03:30:00 | 05:30:00 | 850 | drilling -- casing | ok | RD Odfjell csg tong. Removed HTS rollers. Cleared and cleaned rig floor.
| 05:30:00 | 06:00:00 | 860 | drilling -- casing | ok | PU 1 std of 5 1/2" HWDP. Changed to PS21 slips. RIH with 7" liner hanger on 5 1/2" HWDP from 850 m to 860 m MD.
| 06:00:00 | 07:15:00 | 925 | drilling -- casing | ok | RIH with 7" liner hanger on 5 1/2" HWDP from 860 m to 925 m MD.
| 07:15:00 | 09:15:00 | 925 | interruption -- oth er | ok | Changed out 2 stds of 5 1/2" HWDP with 5 1/2" DP.
| 09:15:00 | 00:00:00 | 3392 | drilling -- casing | ok | RIH with 7" liner from 925 m to 3392 m MD, filling every 5th stds. Max running speed was 8 stds/hr in cased hole and 5 stds/hr in open hole. Broke circulation at shoe at 2750 m, 1000 lpm / 53 bar.
2008-03-01 | 00:00:00 | 00:45:00 | 3392 | drilling -- casi ng | ok | Took 15 MT weight at 3392 m MD. MU TDS and attempted to work past tight spot with 20-30 MT. Up weight 181 MT / down weight 141 MT. Applied 9400 Nm RH torque when working s tring up. Released torque when working down.
| 00:45:00 | 01:30:00 | 3392 | drilling -- casi ng | ok | Broke circulation, 230 lpm / 37 bar and established rate at 530 lpm / 49 bar. Washed down to tight spot applying max 20 MT. Observed pressure increasing to 60 bar. Shut down pumpe. Recorded 22 bar back pressure trapped below shoe. Applied 9400 Nm RH torque and worked string up. Recorded up weight of 151 MT, 30 MT upweight less than previous. Liner hang er RT most likely released from 7" liner.
| 01:30:00 | 02:30:00 | 3392 | drilling -- casi ng | ok | Discussed further action and monitored well on trip tank.
| 02:30:00 | 02:45:00 | 3392 | drilling -- casi ng | ok | Attempted to break circulation, negativ. Stopped pump at 45 bar after 243 ltrs pumped. Bleed off pressure to zero.
| 02:45:00 | 03:30:00 | 3392 | drilling -- casi ng | ok | Discussed further action with town and monitored well on trip tank.
| 03:30:00 | 04:30:00 | 3399 | drilling -- casi ng | ok | PU and established up weight at 151 MT. Slacked off weight at 130 MT and observed no drag. Unable to tag liner. Broke circulation 220 lpm / 22 bar which indicated that we were circula ting through 5 1/2" DP and liner hanger RT. 7" liner most likely dropped further down.
| 04:30:00 | 06:00:00 | 3340 | drilling -- casi ng | ok | POOH with 7" liner hanger RT on 5 1/2" DP from 3399 m to 3340 m MD.
| 06:00:00 | 09:30:00 | 1520 | drilling -- casi ng | ok | POOH with 7" liner hanger RT on 5 1/2" DP from 3340 m to 1520 m MD.
| 09:30:00 | 10:30:00 | 1520 | interruption -- waiting on we ather | ok | Stopped POOH due to 65 knots wind. Installed TIW and monitored well on trip tank. Performed wind checks.
| 10:30:00 | 16:45:00 | 0 | drilling -- casi ng | ok | POOH with 7" liner hanger RT on 5 1/2" DP from 1520 m to OOH. Inspected liner hanger RT. Found hydraulic release activated. All items intact on RT.
| 16:45:00 | 18:00:00 | 0 | drilling -- casi ng | ok | Cleared rig floor and serviced PS21 slips. Installed and function tested PS21 slips.
Had approx. 30 min interruption in operation due to 65 knots wind.
| 18:00:00 | 20:15:00 | 443 | drilling -- trip | ok | RIH with 20 std 5 1/2" DP 24.7 lbs/ft to 443 m.
| 20:15:00 | 22:15:00 | 443 | drilling -- trip | ok | Stopped RIH and had time-out due to sensor target bracket (570 g) dropped from TDS. Investigated and reported dropped object situation prior to re-commencing operations.
| 22:15:00 | 23:30:00 | 806 | drilling -- trip | ok | RIH with 20 std 5 1/2" DP 24.7 lbs/ft from 443 to 806 m.
| 23:30:00 | 00:00:00 | 720 | drilling -- trip | ok | LO 5 1/2" DP 24.7 lbs/ft in singles from 806 m to 720 m.
2008-03-02 | 00:00:00 | 06:00:00 | 309 | drilling -- trip | ok | LO 5 1/2" DP 24.7 lbs/ft in singles from 720 m to 309 m.
| 06:00:00 | 07:00:00 | 0 | drilling -- trip | ok | LO 5 1/2" DP 24.7 lbs/ft in singles from 309 m to OOH.
| 07:00:00 | 07:30:00 | 0 | drilling -- trip | ok | Held time-out for safety with day crew. Inspected derrick in daylight due to yesterdays dropped object.
| 07:30:00 | 09:00:00 | 444 | drilling -- trip | ok | RIH with 5 1/2" DP 24.7 lbs/ft to 444 m.
| 09:00:00 | 10:45:00 | 0 | drilling -- trip | ok | LO 10 stds of 5 1/2" DP 24.7 lbs/ft in singles.
| 10:45:00 | 16:00:00 | 0 | interruption -- maint ain | ok | Had tool box talk with drill crew. Performd cut and slip of drill line.
| 16:00:00 | 19:45:00 | 0 | drilling -- trip | ok | Continued to LO stds of 5 1/2" DP 24.7 lbs/ft in singles.
| 19:45:00 | 20:30:00 | 0 | drilling -- casing | ok | Changed to 3 1/2" handling equipment and installed master bushings to be able to MU spear assembly. Found that pack-off on spear assembly was wrong size. Discussed further action.
| 20:30:00 | 21:00:00 | 0 | drilling -- casing | ok | Changed back to 5 1/2" handling equipment. Made arrangement with town to mobilize the correct size pack-off with helicopter.
| 21:00:00 | 22:15:00 | 0 | drilling -- trip | ok | Continued to LO stds of 5 1/2" DP 24.7 lbs/ft in singles.
| 22:15:00 | 23:00:00 | 0 | drilling -- casing | ok | Changed to 3 1/2" handling equipment and installed master bushings to be able to MU spear assembly.
| 23:00:00 | 00:00:00 | 0 | drilling -- casing | ok | Held tool box talk prior to picking up spear. MU spear assembly according to Weatherford's instructions.
2008-03-03 | 00:00:00 | 00:30:00 | 0 | drilling -- ca sing | ok | Continued MU spear assembly according to Weatherford's instructions.
| 00:30:00 | 01:45:00 | 0 | drilling -- ca sing | ok | Re-arranged DP in derrick whilst waiting for new pack-off for spear assembly to arrive with helicopter.
| 01:45:00 | 03:00:00 | 0 | drilling -- ca sing | ok | Installed and MU new pack-off on spear assembly.
| 03:00:00 | 06:00:00 | 693 | drilling -- ca sing | ok | RIH with spear assembly. Changed to 5 1/2" handling equipment and installed PS21 slips. RIH with spear assembly on 3 stands of 5 1/2" HWDP from 11 m to 129 m MD. RIH with spea r assembly on 5 1/2" DP from 129 m to 693 m MD.
| 06:00:00 | 09:30:00 | 2466 | drilling -- ca sing | ok | Meanwhile changed out csg tong on fwd iron roughneck.
RIH with spear assembly on 5 1/2" DP from 693 m to 2466 m MD.
| 09:30:00 | 12:00:00 | 2466 | drilling -- ca sing | ok | , when no gas in returns. Pumped at total of 175 m3. Meanwhile circulating, inspected PRS and dragchain. Found lock nuts loose and missing.
Broke circulation at 2466 m and pumped 104 m3 1.45 sg mud at 2000 lpm / 88-94 bar. Continued to circulate due to gas peaks at 3.35%. Reduced circulation rate to 1000 lpm / 29,8 bar
| 18:00:00 | 20:00:00 | 2562 | drilling -- ca sing | ok | RIH with spear assembly on 5 1/2" DP from 2466 m to 2562 m MD while circulating 490 lpm / 18.4 bar. Upweight 152 MT / down weight 130 MT. Observed pressure increasing to 45 bar at 2562 m when sliding string into 7" liner. TOL = 2557 m MD. Stopped pumping and bled off pressure.
| 20:00:00 | 21:00:00 | 2563 | drilling -- ca sing | ok | Continued to RIH 1.5 m and activated grapple with 3 left hand turns. First attempt to engage grapple failed, but the second attempt was sucessfull. Took 10 MT overpull. Established cir culation at 265 lpm / 32 bar. PU to 191 MT (10 MT above liner weight) and circulated for 15 min. PU to 226 MT (45 MT overpull) and observed 7" liner break free.
| 21:00:00 | 00:00:00 | 3122 | drilling -- ca sing | ok | Changed bit depth to include 7" liner. Pumped OOH 265 lpm / 32 bar with 7" liner on 5 1/2" DP from 3414 m to 3122 m MD.
2008-03-04 | 00:00:00 | 02:45:00 | 2755 | drilling -- casing | ok | Pumped OOH 265 lpm / 32 bar with 7" liner on 5 1/2" DP from 3122 m to 2755 m MD.
| 02:45:00 | 05:30:00 | 2755 | drilling -- casing | ok | Circulated btms up at csg shoe to clear passage around 7" liner and liner hanger, 1000 lpm / 59 bar. Continued to circulate due to gas peaks at 6.8%. Pumped at total of 113 m3. Flow checked well prior to POOH.
| 05:30:00 | 06:00:00 | 2716 | drilling -- casing | ok | Pumped slug and POOH with 7" liner on 5 1/2" DP from 2755 m to 2716 m MD.
| 06:00:00 | 14:45:00 | 867 | drilling -- casing | ok | POOH with 7" liner on spear assembly from 2716 m to 867 m MD.
Spaced out inside BOP. Flow checked for 15 min on last joint of 5 1/2" DP. Changed out PS21 with master bushing before POOH with 2 stds of 5 1/2" HWDP.
| 14:45:00 | 17:45:00 | 852 | drilling -- casing | ok | LO bumper sub. Held pre-job meeting and SJA. Released spear and LO same.
| 17:45:00 | 19:45:00 | 852 | drilling -- casing | ok | Held tool box talk with involved personnel. RU Odfjell csg tong with low marking dies and csg handling equipment.
| 19:45:00 | 20:15:00 | 844 | drilling -- casing | ok | LO liner hanger.
| 20:15:00 | 00:00:00 | 560 | drilling -- casing | ok | POOH with 7" liner and RB in derrick from 844 m to 560 m MD.
2008-03-05 | 00:00:00 | 05:30:00 | 0 | drilling -- casing | ok | POOH with 7" liner and RB in derrick from 560 m to OOH.
| 05:30:00 | 06:00:00 | 0 | drilling -- casing | ok | RD Odfjell csg tong and csg handling equipment.
| 06:00:00 | 08:00:00 | 0 | drilling -- casing | ok | RD Odfjell csg tong and csg handling equipment.
| 08:00:00 | 11:30:00 | 75 | drilling -- casing | ok | PU and MU 8 1/2" wiper trip BHA.
| 11:30:00 | 16:00:00 | 1010 | drilling -- casing | ok | Held time-out for safety due to dropped pin from fwd PRS dragchain. Highlighted "red zone" policy.
RIH with 8 1/2" wiper trip BHA on 5" DP from 75 m to 1010 m MD.
| 16:00:00 | 17:15:00 | 1010 | drilling -- casing | ok | MU TDS and tested MWD, 2000 lpm / 146 bar. Changed mud pumps and stand pipes to optimize signal from MWD.
| 17:15:00 | 19:00:00 | 1501 | drilling -- casing | ok | RIH with 8 1/2" wiper trip BHA on 5" DP from 1010 m to 1501 m MD.
| 19:00:00 | 19:30:00 | 1501 | drilling -- casing | ok | Held time-out for safety due to dropped pin from fwd PRS dragchain. Highlighted "red zone" policy.
| 19:30:00 | 21:30:00 | 1501 | drilling -- casing | ok | .
Inspected aft PRS dies. Moved 5 1/2" HWDP from finger board. Installed totco ring in 5" DP. Changed to 5 1/2" handling equipment and installed X-over
| 21:30:00 | 00:00:00 | 2146 | drilling -- casing | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 1501 m to 2146 m MD. Filled pipe every 10 stds.
2008-03-06 | 00:00:00 | 02:15:00 | 2751 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 2146 m to 2751 m MD. Filled pipe every 10 stds.
| 02:15:00 | 04:00:00 | 2751 | drilling -- casi ng | ok | MU TDS and filled pipe and broke circulation at 9 5/8" csg shoe with 500 lpm / 21 bar. Up weight 149 MT / down weight 122 MT. Circulated btms up at 2000 lpm / 164 bar. Max ga s 2.2%. ECD = 1.58 sg.
| 04:00:00 | 06:00:00 | 3320 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 2751 m to 3320 m MD. Filled pipe every 10 stds.
| 06:00:00 | 07:00:00 | 3420 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3320 m to 3395 m MD. Worked pipe to pass tight spot at 3395 m. MU TDS and rotated pipe 1/2 turn. Worked past tight spot and continued RIH to 3420 m.
| 07:00:00 | 09:15:00 | 3478 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3420 m to 3478 m MD. Worked pipe to pass tight spot. MU TDS and applied 30 rpm and pumped 500 lpm / 38 bar. Worked past t ight spot and reamed up to 3420 m. Came down from 3420 m to 3478 m with no rotation and no flow.
| 09:15:00 | 09:30:00 | 3510 | drilling -- casi ng | ok | Washed down with 8 1/2" wiper trip BHA on 5 1/2" DP from 3478 m to 3510 m MD, 1400 lpm / 128 bar, 50 rpm / 13-14 kNm.
| 09:30:00 | 13:00:00 | 3510 | drilling -- casi ng | ok | Circulated 3 x btms up and conditioned mud at 3510 m whilst rotating and reciprocating string. Increased flow in steps up to 2200 lpm / 206 bar, 150 rpm / 13-17 kNm to be able t o control ECD. Max MW out of hole 1.56 sg. Final ECD 1.57 sg. Max gas 9.3%.
| 13:00:00 | 17:45:00 | 3387 | drilling -- casi ng | ok | RB 1 std and circulated btms up whilst rotation and reciprocating pipe from 3397 m to 3357 m, 2200 lpm / 198 bar, 100 rpm / 12-14 kNm.
RB 1 std from 3510 m to 3478 m. No obstruction encountered.
RB and reamed 1 std from 3437 m to 3397 m. Observed tight spots at 3428 m and 3423 m. Reamed through tigh spots with reduced flow of 1500 lpm due to packing off. Staged up parameteres to 2200 lpm / 200 bar while working through tight spots.
Worked 1 std from 3478 m to 3437 m, 2200 lpm / 201 bar, 150 rpm / 12-15 kNm.
| 17:45:00 | 18:45:00 | 3510 | drilling -- casi ng | ok | RIH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3387 m to 3508 m MD. No obstruction encountered. Observed 1.5 m fill at TD.
| 18:45:00 | 20:30:00 | 3510 | drilling -- casi ng | ok | Circulated btms up at 3510 m, 2200 lpm / 196 bar, 100 rpm / 12-14 kNm. Up weight 178 MT / down weight 134 MT.
Pumping 500 lpm / 19 bar, 1000 lpm / 54 bar, 1500 lpm / 102 bar. Distance from neutral to up weight is 0.6 m.
Readings to give comparison for liner running:
Rotating 10 rpm / 11-12 kNm, 15 rpm / 11-13 kNm, 20 rpm / 10-13 kNm. Rotating upweight 172 MT / rotating down weight 137 MT.
| 20:30:00 | 21:00:00 | 3508 | drilling -- casi ng | ok | Flow checked well. Static.
| 21:00:00 | 00:00:00 | 3114 | drilling -- casi ng | ok | POOH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3508 m to 3271 m MD wet. No obstruction encountered. Pumped slug. Continued to POOH from 3271 m to 3114 m MD. Pulled through tight spot at 3237 m with 25 MT overpull. Worked pipe several times to pass tight spot.
2008-03-07 | 00:00:00 | 01:00:00 | 2748 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5 1/2" DP from 3114 m to 2748 m MD.
| 01:00:00 | 01:30:00 | 2748 | drilling -- casing | ok | Flow checked well inside shoe. Static. Dropped 2 3/4" rabbit.
| 01:30:00 | 04:30:00 | 1500 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5 1/2" DP from 2748 m to 1500 m MD.
Torque reading at 7" liner hanger setting depth: 10 rpm / 6-8 kNm, 15 rpm / 6-9 kNm, 20 rpm / 6-9 kNm. At 7" liner hanger setting depth; up weight 147 MT / down weight 125 MT.
| 04:30:00 | 05:00:00 | 1500 | drilling -- casing | ok | Changed to 5" handling equipment.
| 05:00:00 | 06:00:00 | 928 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5" DP from 1500 m to 928 m MD.
| 06:00:00 | 07:45:00 | 74 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5" DP from 928 m to 74 m MD.
| 07:45:00 | 08:15:00 | 74 | drilling -- casing | ok | Flow checked well prior to pulling BHA through BOP. Meanwhile held tool box meeting prior to BHA handling.
| 08:15:00 | 08:30:00 | 74 | drilling -- casing | ok | Installed net around fwd PRS for prevention of dropped objects.
| 08:30:00 | 11:30:00 | 0 | drilling -- casing | ok | POOH with 8 1/2" wiper trip BHA on 5" DP from 74 m to 46 m MD. Removed PS21 slips and installed master bushings. LO 8 1/2" wiper trip BHA from 46 m to OOH. Cle aned and cleared rig floor of excess equipment.
| 11:30:00 | 14:45:00 | 0 | drilling -- casing | ok | Held tool box talk for RU to run 7" liner. Installed HTS rollers. Changed inserts in elevator and RU Odfjell csg tong.
| 14:45:00 | 16:00:00 | 0 | drilling -- casing | ok | Inspected PRS and TDS for loose items. Greased PRS and TDS.
| 16:00:00 | 18:00:00 | 39 | drilling -- casing | ok | Held tool box talk prior to running 7" liner. MU and RIH with shoe track and landing collar. Checked shoe and float collar for flow-through.
| 18:00:00 | 00:00:00 | 434 | drilling -- casing | ok | Installed pip-tag 0.34 m below top of collar on 2.05 m pup-joint in RA assembly. Estimated RA depth is 3230.76 m, but final depth will be given when 7" liner is set.
RIH with 7" liner from 39 m to 434 m MD, filling every 5th joint. Cleaned and re-doped pin end. Max running speed was 9 joints/hr
2008-03-08 | 00:00:00 | 06:00:00 | 812 | drilling -- casin g | ok | LO joint #139 and changed out box on joint #140. Replaced joint #139 with joint #115.
RIH with 7" liner from 434 m to 812 m MD, filling every 5th joint. Cleaned and re-doped pin end. Max running speed was 6 joints/hr.
| 06:00:00 | 07:00:00 | 835 | drilling -- casin g | ok | RIH with 7" liner from 434 m to 812 m MD, filling every 5th joint. Cleaned and re-doped pin end. Filled liner completely before picking up hanger assembly.
| 07:00:00 | 08:45:00 | 850 | drilling -- casin g | ok | Changed to 5½" DP elevators. P/U hanger/TSP packer assembly and MU same as per Weatherford procedure. Removed 7" FMS slips, installed master bushing. Filled PBR w ith drillwater and checked shear pins. Took up/down weight 105/95 MT.
| 08:45:00 | 10:15:00 | 850 | drilling -- casin g | ok | RD Odfjell csg tong. Removed HTS rollers. BO XO on HWDP and drifted same. Cleared and cleaned rig floor.
| 10:15:00 | 11:30:00 | 963 | drilling -- casin g | ok | PU 1 std of 5 1/2" HWDP. Changed to PS21 slips. RIH with 7" liner hanger on 5 1/2" HWDP from 850 m to 963 m MD.
| 11:30:00 | 20:30:00 | 3392 | drilling -- casin g | ok | RIH with 7" liner from 963 m to 3392 m MD, filling every 5th stds. Broke circulation at shoe at 2756 m for 5 min, 500 lpm / 17 bar. Worked past tight spot at 3358 and turned pip e 1/2 turn. Max running speed was 10 stds/hr in cased hole and 6 stds/hr in open hole.
| 20:30:00 | 22:30:00 | 3510 | drilling -- casin g | ok | RIH with 7" liner from 3392 m to 3468 m MD, filling every 5th stds. MU last std and broke circulation. Staged up pumps to 340 lpm / 23 bar and washed down. Tagged TD at 35 10 m MD. Up weight 190 MT / down weight 142 MT.
| 22:30:00 | 23:00:00 | 3508 | drilling -- casin g | ok | Installed and MU cmt head. Spaced out liner to 3508 m / top liner hanger at 2665,6 m.
| 23:00:00 | 00:00:00 | 3508 | drilling -- casin g | ok | Established circulation and increased pump rate in steps to 1140 lpm / 78 bar. Circulated 1 1/2 open hole volume (45 m3). Meanwhile pressure tested cmt line to 345 bar.
2008-03-09 | 00:00:00 | 00:15:00 | 3508 | drilling -- c asing | ok | Continued to circulate 1 1/2 open hole volume, 1140 lpm / 78 bar.
| 00:15:00 | 01:30:00 | 3508 | drilling -- c asing | ok | Continued to pressure up to 175 bar to relese setting tool. Held 1 min. Continued to pressure up to shear out ball seat. Sheared at 228 bar. PU to verify that liner was released. Up weight 158 MT / down weight 134 MT.
Reduced pump rate to 200 lpm. Dropped the ball from the cmt head with liner in tension and chased the ball with 500 lpm / 30.6 bar. Landed ball after 653 stks pumped. Pressured up to 1 35 bar. Held 2 min. Bled down to 70 bar. Sat down 25 MT of drill pipe weight to verify that hanger was set. OK.
| 01:30:00 | 03:00:00 | 3508 | drilling -- c asing | ok | Sat down weight to 130 MT. Established circulation while rotating and increased pump rate in steps up to 1200 lpm / 74 bar, 20 rpm / 10-12 kNm. Pumped 95 m3. Meanwhile held pre-job meeting for cmt job.
| 03:00:00 | 05:30:00 | 3508 | drilling -- c asing | ok | Lined up to rig pumps and pumped 19 stks before flag indicated dart had dropped. Displaced cement with 45 m3 OBM at 1200 lpm, 15 rpm / 15-18 kNm with full returns. Slowed down pu mp rate to 500 lpm after 1930 strks. FCP = 42 bar. Stopped pumping after 2052 + 19 = 2071 strks pumped. Observed torque increased to 26 kNm after 2071 strks pumped, but had no bu mp.
Mixed and pumped 15.9 m3 1.90 sg cement slurry at 680 lpm / 80 bar and displaced cement with 0.9 m3 freshwater to rig floor. Dropped dart to release top wiper plug.
Pumped 10 m3 base oil, 780 lpm / 80 bar and 15 m3 of 1.65 sg tuned spacer E+ at 665 lpm / 80 bar with mud pumps while rotating liner 15 rpm / 12 kNm. Lined up to cmt unit through cmt hose. Dropped dart to release bottom wiper plug.
| 05:30:00 | 06:00:00 | 3508 | drilling -- c asing | ok | Checked for back flow. Ok. RD cmt hose.
| 06:00:00 | 08:00:00 | 3508 | drilling -- c asing | ok | Sat TSP packer according to Weatherford procedure. Closed annular and pressured up to 300 bar. Pressure tested TSP packer to 300 bar / 10 min with 1.45 sg OBM.
| 08:00:00 | 09:15:00 | 3508 | drilling -- c asing | ok | Released liner hanger RT by pressuring up to 70 bar. Pulled and measured RT out of PBR. Increased rate to 1000 lpm when pressure dropped. Dropped 2 sponge balls and circulated DP clean. Circulated out excess cmt, 2000 lpm / 80 bar. Observed cmt and spacer in returns. Circulation pressure increased to 98 bar and then level out.
| 09:15:00 | 10:15:00 | 3508 | drilling -- c asing | ok | LO cmt head and 10 ft pup joint.
| 10:15:00 | 18:45:00 | 112 | drilling -- c asing | ok | .
POOH with 7" liner hanger RT on 5 1/2" DP from 2667 m to 112 m MD.
RU rollers on HTS and cleared rig floor of excess equipment prior to LO pipe in singles. LO 13 stds of 5 1/2" DP 24.7 lbs/ft in singles. Pumped 3 m3 1.63 sg slug, 1000 lpm / 7 bar at 594 m
| 18:45:00 | 20:30:00 | 0 | drilling -- c asing | ok | POOH with 7" liner hanger RT on HWDP from 112 m to OOH. Removed PS21 auto slips and installed manual slips. Disconnected HTS back rollers. BO and LD 7" liner hanger RT. Found both wiper plugs attached to liner hanger RT and both darts and one sponge ball inside RT.
| 20:30:00 | 21:45:00 | 0 | drilling -- c asing | ok | Changed to 3 1/2" handling equipment. PU 3 1/2" fishing assembly. Broke connections and LO Mærsk pup joint and XO. Cleaned and cleared rig floor.
| 21:45:00 | 00:00:00 | 0 | drilling -- c asing | ok | RU 7" csg tong and handling equipment. Inspected PRS dies and rollers.
2008-03-10 | 00:00:00 | 00:30:00 | 0 | drilling -- casing | ok | PU 7" liner shoe track std and attempted to break baker locked connections. Unsucessful. RB in derrick.
| 00:30:00 | 04:30:00 | 738 | drilling -- casing | ok | RIH with 7" liner stds from derrick to 738 m MD. Removed grub screws from top-most centralizer/stop collar on each std.
| 04:30:00 | 06:00:00 | 671 | drilling -- casing | ok | Installed HTS back rollers. POOH and LO 7" liner in singles from 738 m to 671 m MD.
| 06:00:00 | 14:00:00 | 0 | drilling -- casing | ok | POOH and LO 7" liner in singles from 671 m to OOH.
| 14:00:00 | 14:45:00 | 0 | drilling -- casing | ok | PU 7" liner shoe track std and attempted to break baker locked connections with csg tong without sucess.
| 14:45:00 | 17:45:00 | 0 | drilling -- casing | ok | Meanwhile performed csg test. Observed pressure rise to 290 bar before dropping, 2426 ltrs pumped and 1600 ltrs returned.
RD csg tong and 7" liner handling equipment.
| 17:45:00 | 20:00:00 | 0 | drilling -- casing | ok | PU 7" liner shoe track std and broke baker locked connections using manual tongs. Cleaned and cleared rig floor and changed to 5 1/2" handling equipme nt.
| 20:00:00 | 21:15:00 | 44 | drilling -- bop/wellhead equi pment | ok | PU and MU jet sub assembly. RIH and washed BOP cavity. Staged up pumps to 3125 lpm / 43 bar and washed through cavity several times.
| 21:15:00 | 22:30:00 | 184 | drilling -- bop/wellhead equi pment | ok | Made up test plug and inspected seals. RIH with same on 5 1/2" DP. Landed test plug in subsea wellhead/wearbushing at 140 m MD. Flushed lines from c ement unit and verified line up.
| 22:30:00 | 00:00:00 | 184 | drilling -- bop activities | ok | Tested 18 3/4" surface BOP against test plug in subsea wellhead, 20/345 bar 5/10 min.
2008-03-11 | 00:00:00 | 05:30:00 | 184 | drilling -- bop activities | ok | Meanwhile performed derrick inspection, cleaned moonpool area and prepared for greasing manifolds.
Tested 18 3/4" surface BOP against test plug in subsea wellhead, 20/345 bar 5/10 min.
| 05:30:00 | 06:00:00 | 165 | drilling -- bop/wellhead equipment | ok | POOH with jet sub/BOP test plug on 5 1/2" DP from 184 m to 165 m MD.
| 06:00:00 | 07:00:00 | 0 | drilling -- bop/wellhead equipment | ok | POOH with jet sub/BOP test plug on 5 1/2" DP from 165 m to OOH. Broke out and LD test plug.
| 07:00:00 | 08:00:00 | 0 | drilling -- other | ok | RU 3 1/2" handling equipment. MU kelly cock and grey valve assembly for testing.
| 08:00:00 | 12:30:00 | 0 | drilling -- other | ok | Meanwhile changed out drill line spooler.
Tested 3 1/2" kelly cock and grey valve. Tested kill and standpipe manifolds. Tested 5 1/2" kelly cock and grey valve.
| 12:30:00 | 13:00:00 | 0 | drilling -- other | ok | Took time-out for safety due to dropped bulldog clamps from drill line.
| 13:00:00 | 16:00:00 | 0 | interruption -- other | ok | Continued to change out drill line spooler.
| 16:00:00 | 17:15:00 | 13 | drilling -- trip | ok | Held tool box meeting with involved personnel. MU and RIH with 6" PDC bit and scraper assembly from surface to 13 m.
| 17:15:00 | 18:00:00 | 13 | interruption -- other | ok | Repaired damaged fittings on HTS rollers.
| 18:00:00 | 00:00:00 | 550 | drilling -- drill | ok | Meanwhile tested choke manifolds.
RIH with 6" PDC bit and scraper assembly from 13 m to 26 m. Changed to PS21 slips. Continued to RIH with 6" PDC bit and scraper assembly on 3 1/2" DP from 26 m to 550 m. PU 3 1/2" DP in singles. Max running speed was 14 joints/hr.
2008-03-12 | 00:00:00 | 02:00:00 | 804 | drilling -- drill | ok | RIH with 6" PDC bit and scraper assembly on 3 1/2" DP from 550 m to 804 m. Max running speed was 13 joints/hr.
| 02:00:00 | 03:45:00 | 804 | drilling -- other | ok | Changed from 3 1/2" handling equipment to 5 1/2" handling equipment.
| 03:45:00 | 06:00:00 | 1977 | drilling -- drill | ok | RIH with 6" PDC bit and scraper assembly on 5 1/2" DP from 804 m to 1977 m.
| 06:00:00 | 08:00:00 | 2650 | drilling -- drill | ok | RIH with 6" PDC bit and scraper assembly on 5 1/2" DP from 1977 m to 2650 m.
| 08:00:00 | 09:30:00 | 2650 | drilling -- circulating conditioning | ok | Broke circulation with rotation and circulated btms up, 1824 lpm / 290 bar, 20 rpm / 7 kNm. Up weight 141 MT / down weight 122 MT / rotating weight 130 MT.
| 09:30:00 | 13:00:00 | 3430 | drilling -- drill | ok | Entered 7" liner PBR with reduced flow, 400 lpm / 45 bar. Observed no drag. Continued RIH with 6" PDC bit and scraper assembly on 5 1/2" DP from 2650 m to 3430 m.
| 13:00:00 | 15:30:00 | 3430 | completion -- circulat ing conditioning | ok | / 300 bar, 60 rpm / 10 kNM. Circulated 1 1/2" btms up at 1790 lpm / 300 bar. RB one std and flow checked well static. Ok.
MU TDS and washed down with scraper string from 3430 m to 3460 m, 1110 lpm / 143 bar. Up weight 159 MT. Pulled back and scraped liner interval 3440-3450 m, 1790 lpm
| 15:30:00 | 16:30:00 | 3228 | drilling -- drill | ok | POOH with 6" PDC bit and scraper assembly on 5 stds of 5 1/2" DP wet from 3430 m to 3228 m. Flow checked well static. Ok.
| 16:30:00 | 21:15:00 | 807 | drilling -- drill | ok | Pumped slug and continued to POOH with 6" PDC bit and scraper assembly on 5 1/2" DP from 3228 m to 807 m.
| 21:15:00 | 23:00:00 | 807 | drilling -- other | ok | Changed from 5 1/2" handling equipment to 3 1/2" handling equipment. Serviced foldable fingerboard.
Meanwhile flow checked well static. Ok.
| 23:00:00 | 00:00:00 | 685 | drilling -- drill | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 807 m to 685 m.
2008-03-13 | 00:00:00 | 00:30:00 | 578 | drilling -- d rill | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 685 m to 578 m.
| 00:30:00 | 01:30:00 | 578 | interruptio n -- maintain | ok | Observed yellow UFO flying/falling from derrick and out side/aft of derrick. Inspected PRS, derrick and drillfloor, but were not able to man-ride due to 50 knots wind. Nothing out of the ordi nary was found.
| 01:30:00 | 02:45:00 | 57 | drilling -- d rill | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 578 m to 57 m.
| 02:45:00 | 04:30:00 | 57 | interruptio n -- other | ok | Retrieved 3 1/2" DP std that was pulled out of fingerboard by PRS lower arm due to human error. Held time-out for safety. Prepared equipment to be used for retrieving std. Instected finger board. RB 3 1/2" DP std in fingerboard.
| 04:30:00 | 06:00:00 | 0 | drilling -- t rip | ok | POOH with 6" PDC bit and scraper assembly on 3 1/2" DP from 57 m to OOH. LD 6" PDC bit and scraper assemblies.
| 06:00:00 | 06:30:00 | 0 | drilling -- t rip | ok | Held tool box talk prior to make up and RIH with EZSV plug and Circ. Sub. Made up EZSV plug and Circ. Sub.
| 06:30:00 | 07:00:00 | 42 | drilling -- d rill | ok | RIH with EZSV plug and Circ. Sub to 42 m.
| 07:00:00 | 07:15:00 | 42 | drilling -- o ther | ok | Held tool box talk with day shift prior to change to PS -21 slips and RIH with EZSV plug and Circ. Sub on 3½" DP.
| 07:15:00 | 08:00:00 | 42 | drilling -- o ther | ok | Changed to PS -21 slips and functioned same.
| 08:00:00 | 10:45:00 | 792 | drilling -- d rill | ok | Continued RIH with EZSV plug and Circ. Sub on 3½" DP from 42m to 792m at 2 min/std.
| 10:45:00 | 11:30:00 | 792 | drilling -- o ther | ok | Held tool box talk and changed over to 5½" surface handling equipment.
| 11:30:00 | 19:00:00 | 3448 | drilling -- d rill | ok | Continued RIH with EZSV plug and Circ. Sub on 5½" DP from 792m to 2625m at 2 min/std. Reduced RIH speed as entering the 7" line at 2661m, continue to RIH to 3448m EZSV plug se tting depth.
| 19:00:00 | 20:15:00 | 3448 | drilling -- o ther | ok | Took up/down weight 168/136 MT. Established circulation at 220 lpm 12 bars. Reciprocated the string, increased rate in stages to 670 lpm 53 bars. Stopped circulation and positioned EZ SV plug at setting depth at 3448m up stroke. Installed the EZSV plug as per Halliburton procedure. Picked up 20 MT to shear the tension sleeve. Set down 10 MT on EZSV plug. Picked u p to 3440m.
| 20:15:00 | 20:30:00 | 3440 | drilling -- o ther | ok | Held tool box talk prior to R/U for pressure testing of the EZSV plug and the 7" liner.
| 20:30:00 | 22:15:00 | 3440 | drilling -- o ther | ok | Rigged up surface lines, flushed lines and tested same to 300 bars 5 min. Closed upper pipe rams and tested the EZSV plug and 7" liner to 300 bars 10 min. 2023 litres pumped and same in return.
| 22:15:00 | 22:45:00 | 3440 | drilling -- o ther | ok | Rigged down surface test lines.
| 22:45:00 | 23:00:00 | 3440 | drilling -- o ther | ok | Flow checked prior to POOH with the EZSV plug RT and the circ sub.
| 23:00:00 | 00:00:00 | 3252 | drilling -- d rill | ok | POOH wet with 5 std to 3252m.
2008-03-14 | 00:00:00 | 04:30:00 | 791 | drilling -- drill | ok | Pumped slug of 5.5m³ 1.66 SG. Continued POOH with 5½" DP and EZSV RT from 3252m to 791m.
| 04:30:00 | 05:00:00 | 791 | drilling -- drill | ok | Held tool box talk prior to change over to 3½" surface handling equipment. Performed same.
| 05:00:00 | 06:00:00 | 525 | drilling -- drill | ok | Continued POOH with 3½" DP EZSV RT from 791m to 525m
| 06:00:00 | 07:15:00 | 0 | drilling -- drill | ok | POOH with 3½" DP and EZSV plug RT to surface.
| 07:15:00 | 07:45:00 | 0 | drilling -- trip | ok | Changed out PS -21 slips to master bushing. L/O EZSV plug RT.
| 07:45:00 | 08:00:00 | 0 | drilling -- other | ok | Held tool box talk prior to RIH with BOP/riser clean out assy.
| 08:00:00 | 11:45:00 | 314 | drilling -- other | ok | Functioned shear rams. Picked up clean out assy and RIH and cleaned BOP, riser and WH. Function tested BOP rams and annular.
| 11:45:00 | 13:15:00 | 0 | drilling -- other | ok | POOH with clean out assy and laid out same.
| 13:15:00 | 14:00:00 | 0 | drilling -- other | ok | Cleaned and cleared rig floor. Inspected aft PRS. Performed daily derrick inspection. Simultaneously prepared mule shoe for 7" line clean out assy.
| 14:00:00 | 15:45:00 | 32 | completion -- circulating conditioning | ok | .
Held tool box talk and broke out 6" bit and bit sub and made up 3½" mule shoe. Made up Razor Back assy. Installed PS-21 slips
| 15:45:00 | 17:45:00 | 776 | completion -- circulating conditioning | ok | RIH with 3½" mule shoe and Razor Back assy. From 32m to 776m.
| 17:45:00 | 19:00:00 | 776 | completion -- circulating conditioning | ok | Held tool box talk and picked up Weaterford PBR polish mill.
| 19:00:00 | 19:15:00 | 778 | completion -- circulating conditioning | ok | Held tool box talk prior to install the 9 5/8" clean out assy.
| 19:15:00 | 20:00:00 | 831 | completion -- circulating conditioning | ok | Changed to 5½" DP handling equipment. Installed the 9 5/8" clean out assy.
| 20:00:00 | 20:30:00 | 831 | completion -- circulating conditioning | ok | Made up to TDS and broke circulation with 1000 lpm 72 bars. Installed PS-21 slips. Observed hydraulic leak in Aft PRS.
| 20:30:00 | 21:30:00 | 831 | interruption -- other | ok | Repaired hydraulic leak on Aft PRS.
| 21:30:00 | 00:00:00 | 2080 | completion -- circulating conditioning | ok | Continued RIH with clean out assy. from 831m to 2080m
2008-03-15 | 00:00:00 | 01:15:00 | 2646 | completion -- circul ating conditioning | ok | Continued RIH with clean out assy. from 2080m to 2646m.
| 01:15:00 | 02:15:00 | 2646 | completion -- circul ating conditioning | ok | Circulated 50m³ OBM at 2100 lpm 295 bars. Took up/down weight zero/20 rpm. 144/123 MT - 137/129 MT.
| 02:15:00 | 03:00:00 | 2848 | completion -- circul ating conditioning | ok | Entered the 7" liner. Continued RIH with clean out assy. from 2646m to 2848m
| 03:00:00 | 03:30:00 | 2848 | completion -- circul ating conditioning | ok | Made up the 10 3/4" casing scraper assy.
| 03:30:00 | 05:30:00 | 3380 | completion -- circul ating conditioning | ok | Continued RIH with clean out assy. from 2857m to 3380m
| 05:30:00 | 06:00:00 | 0 | completion -- circul ating conditioning | ok | Commenced to wash down from 3380m to 3420m. 40 rpm, 1000 lpm, 110 bars.
| 06:00:00 | 07:30:00 | 3445 | completion -- circul ating conditioning | ok | Continued RIH washing down from 3420m, tagged the PBR 1,5 m deep (at 2662,3 m) with 2 MT, with mule shoe at 3445m, and polished at 500 lpm, 40 bars and 13 kNm.
| 07:30:00 | 10:45:00 | 3435 | completion -- circul ating conditioning | ok | Scraped 7"/9 5/8"/10 3/4" casing, dressed/polished 7" liner top. Pulled back to 3435m, increased pump rate to 1960 lpm, 292 bars and conditioned mud.
| 10:45:00 | 12:30:00 | 3445 | completion -- circul ating conditioning | ok | Opened BOP. PU, relaxed well commisioner element.
Set the Well Commissioner as per SPS instruction. Up/down weight with out pumping 167/137 MT, RIH and set down 13 MT on PBR. Closed upper pipe rams and pressured up the Well Commissioner in steps to 70 bars and monitored. Simultaneously held tool box talk prior to perform inflow test of the 7" liner and liner lap.
| 12:30:00 | 13:45:00 | 3445 | completion -- circul ating conditioning | ok | Displaced choke & kill line to Base oil, then soap mix to fill lines.
| 13:45:00 | 16:00:00 | 3445 | completion -- circul ating conditioning | ok | Pumped 26 m³ Base oil + STP volume with 320 lpm, final pump pressure 147 bars (first 5m³ pumped at ~1000 lpm to clean lines). Final static pressure equaled = 134 bars, monitored same for 30 min. Re-set packer with 13.5 MT. New up/down weight 153/125 MT. Lined up to cement unit and equalised pressure across IBOP.
| 16:00:00 | 18:00:00 | 3445 | completion -- circul ating conditioning | ok | Bled down the drill pipe pressure in stages to 10 bars prior to performing inflow test. 680 liters bled back. Inflow tested the 7" liner and liner lap.
| 18:00:00 | 18:30:00 | 3445 | completion -- circul ating conditioning | ok | Pressured up DP to 138 bars with cement unit to equalize pressure across the Well Commissioner, 633 litres pumped.
| 18:30:00 | 18:45:00 | 3444 | completion -- circul ating conditioning | ok | Picked up 150 MT and let Well Commissioner relax. Picked up 6m. Equalized CMT unit and bled down CMT lines. Ran back in to 3444m.
| 18:45:00 | 19:00:00 | 3444 | completion -- circul ating conditioning | ok | Emptied trip tank.
| 19:00:00 | 19:45:00 | 3444 | completion -- circul ating conditioning | ok | Held tool box talk prior to pumping the washing train.
| 19:45:00 | 00:00:00 | 3444 | completion -- circul ating conditioning | ok | Pumped washing train as per Halliburton program: 10 m3 dope cleaner pill, 30 m3 hivis push pill, 15 m3 hivis soap pill, 10 m3 seawater, 15 m3 hivis soap pill, 3200 lpm, 300 bar
s. Chased wash train with 209m³ of completion fluid, 2200 lpm, 155 bars. Checked packer fluid after displacement: < 0.01% solids.
2008-03-16 | 00:00:00 | 03:30:00 | 3444 | completion -- circulating condi tioning | ok | Cleaned all surface lines, kill-, choke-line and manifold. Circulated well and checked packer fluid for solids, only trace of solids.
| 03:30:00 | 04:00:00 | 3420 | completion -- circulating condi tioning | ok | Racked back one std in derrick. Held tool box talk prior to pressure testing the 7" liner/liner lap.
| 04:00:00 | 04:45:00 | 3420 | completion -- circulating condi tioning | ok | Lined up to the trip tank observed unstable gain. Closed in the well, investigated instability. No pressure built up. Checked the trip tank equipment, found t hat foaming was the reason.
| 04:45:00 | 05:30:00 | 3420 | completion -- circulating condi tioning | ok | Performed manually flow check of the well, static.
| 05:30:00 | 06:00:00 | 3420 | completion -- circulating condi tioning | ok | Made CMT hose and leak tested same to 345 bars for 5min. Commenced pressure test of well to 345 bars.
| 06:00:00 | 06:45:00 | 3420 | completion -- circulating condi tioning | ok | Pressure tested the well to 345 bars 10 min. Pumped 2.2m³ - return 2.2m³. Rigged down surface equipment.
| 06:45:00 | 07:45:00 | 3420 | completion -- circulating condi tioning | ok | Installed TIW valve & flow checked well. Added de-foamer to trip tank.
| 07:45:00 | 08:00:00 | 3420 | interruption -- maintain | ok | Held tool box talk prior to slip and cut of drill line.
| 08:00:00 | 11:00:00 | 3420 | interruption -- maintain | ok | Commenced to slip and cut drill line. Found threads in deadman anchor block damaged. Simultaneously monitored well over the trip tank.
| 11:00:00 | 15:30:00 | 3420 | interruption -- maintain | ok | Re-cut the threads in the deadman anchor block. Simultaneously installed the Fairings on F-12 for the PR TBC using the ROV.
| 15:30:00 | 16:15:00 | 3420 | interruption -- maintain | ok | Disconnected the hang of line & re-calibrated the main block/TDS. Functioned Crown-O-matic, set at 54.4 m. Simultaneously installed the Fairings on F-7 for the PR TBC using the ROV.
| 16:15:00 | 18:30:00 | 2846 | completion -- circulating condi tioning | ok | Held tool box and changed to PS-21 slips. POOH from 3420m to 2846m.
| 18:30:00 | 19:00:00 | 2840 | completion -- circulating condi tioning | ok | Laid out the Razor back BHA # 3.
| 19:00:00 | 22:15:00 | 770 | completion -- circulating condi tioning | ok | Continued POOH with 5½" DP and wash string, from 2840m to 770m.
| 22:15:00 | 23:00:00 | 760 | completion -- circulating condi tioning | ok | Laid out the Razor back BHA #2.
| 23:00:00 | 00:00:00 | 735 | completion -- circulating condi tioning | ok | Changed to 3½" handling equipment. Picked up one std of 3½" from the derrick, continued POOH with 3½" DP and laid out in singles from 770m to 735m.
2008-03-17 | 00:00:00 | 03:30:00 | 475 | completion -- circulating conditioni ng | ok | Continued POOH with 3½" DP and laid out in singles from 735m to 475m.
| 03:30:00 | 06:00:00 | 475 | interruption -- wait | ok | Stopped POOH due to exhaust from the production turbine blowing into the rig floor. Installed safety valve on to the 3½" DP. Monitored well on th e trip tank.
| 06:00:00 | 07:00:00 | 474 | interruption -- wait | ok | Continued waiting due to exhaust fumes blowing into the rig floor.
| 07:00:00 | 11:00:00 | 10 | completion -- circulating conditioni ng | ok | Held tool box talk and continued POOH with 3½" DP and washing string. Laid out 3½" DP in singles.
| 11:00:00 | 11:15:00 | 10 | completion -- circulating conditioni ng | ok | Commenced to rig up 5½" DP handling equipment, found that the Razor back could not fit into the basket. Rigged back up the 3½" handling equi pment.
| 11:15:00 | 15:45:00 | 10 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor. Meanwhile held tool box talk prior to installation of the GTV plug. Meanwhile continued making up the flow line at WH for F-7. Prepared for nippling of BOP.
| 15:45:00 | 16:15:00 | 0 | completion -- circulating conditioni ng | ok | Broke out the Razor back assy and laid out same.
| 16:15:00 | 17:00:00 | 0 | plug abandon -- mechanical plug | ok | Changed to 5½" handling equipment and picked up the GTV RT/GTV plug.
| 17:00:00 | 17:15:00 | 0 | plug abandon -- mechanical plug | ok | Prepared for RIH with the GTV plug on 5½" HWDP.
| 17:15:00 | 20:30:00 | 0 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
| 20:30:00 | 21:00:00 | 44 | plug abandon -- mechanical plug | ok | RIH with the GTV plug on 5½" HWDP from surface to 44m.
| 21:00:00 | 21:30:00 | 44 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
| 21:30:00 | 23:45:00 | 564 | plug abandon -- mechanical plug | ok | RIH with the GTV plug on 5½" HWDP from 44m to 564m
| 23:45:00 | 00:00:00 | 564 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
2008-03-18 | 00:00:00 | 01:45:00 | 564 | interruption -- wait | ok | Shut down operation due to exhaust fumes blowing into the rig floor.
| 01:45:00 | 02:30:00 | 616 | plug abandon -- mechanical plug | ok | RIH with the GTV plug on 5½" HWDP/DP from 564m to 616m.
| 02:30:00 | 03:15:00 | 616 | plug abandon -- mechanical plug | ok | Broke out one double and made up TIW, pump in sub and 3m 5½" DP pup. Made up to TDS.
| 03:15:00 | 03:30:00 | 616 | plug abandon -- mechanical plug | ok | Took up/down weight 98/91 MT. Set GTV plug at per Baker procedure. Bottom of the plug at 617m mid. element 614.5m, slips 615m and top of plug at 612m.
| 03:30:00 | 04:45:00 | 617 | plug abandon -- mechanical plug | ok | Made 2" 1502 chiksan, flushed lines. Attempted to leak test line, found to much air in the system. Filled up system and leak tested line to TIW and IB OP 380 bars 5 min.
| 04:45:00 | 05:30:00 | 617 | plug abandon -- mechanical plug | ok | Pressure tested the GTV plug from below to 380 bars 10 min., volume pumped 1.75m³ - 1.73m³ in return.
| 05:30:00 | 06:00:00 | 617 | plug abandon -- mechanical plug | ok | Rigged down surface lines TIW, pump in sub and 5½" DP pup. Disengaged running tool from plug.
| 06:00:00 | 07:00:00 | 610 | plug abandon -- mill | ok | Spotted 10m³ of hi-vis on top of GTV plug.
| 07:00:00 | 07:45:00 | 0 | plug abandon -- mill | ok | Held tool box talk prior to break/lay out the GTV RT.
| 07:45:00 | 09:00:00 | 0 | plug abandon -- mill | ok | Inspected the aft PRS's dies. POOH with the GTV RT from 612m to above the BOP.
| 09:00:00 | 09:45:00 | 0 | plug abandon -- mill | ok | Held tool box talk and closed the shear rams and pressure tested the GTV plug from above to 345 bars 10 min., volume pumped 830 litres - return 83 0 litres.
| 09:45:00 | 10:00:00 | 0 | plug abandon -- mill | ok | Laid out the GTV RT.
| 10:00:00 | 10:15:00 | 0 | plug abandon -- mill | ok | Cleaned and cleared the rig floor.
| 10:15:00 | 11:00:00 | 139 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and picked the wear bushing RRT. M/U on 5½" RIH and engaged the wear bushing at 139m took 60 MT over pull to free the wear b ushing.
| 11:00:00 | 12:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | POOH with the wear bushing. Laid out wear bushing and RRT. Found metal chip on the wear bushing.
| 12:30:00 | 12:45:00 | 0 | drilling -- casing | ok | Picked up WH jetting sub.
| 12:45:00 | 13:15:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor.
| 13:15:00 | 14:00:00 | 0 | drilling -- casing | ok | RIH with the WH jetting sub from surface to 129m. Discussed forward plan with town.
| 14:00:00 | 16:45:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor.
| 16:45:00 | 18:00:00 | 0 | drilling -- casing | ok | Continued RIH to 138m and washed WH area with 5 rpm 2650 lpm 17 bars. POOH and laid out jetting sub.
| 18:00:00 | 00:00:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor. Meanwhile cleaned the moon pool, pit room and pump room.
2008-03-19 | 00:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor. Meanwhile cleaned the moon pool, pit room and pump room.
| 06:00:00 | 15:45:00 | 0 | interruption -- wait | ok | Operation suspended due to exhaust fumes blowing into the rig floor. Meanwhile cleaned the moon pool, pit room, pump room and general ma intenance.
| 15:45:00 | 16:30:00 | 0 | completion -- bop/wellhead equipm ent | ok | Held tool box talk and picked/made up the 10 3/4" Lock down sub.
| 16:30:00 | 17:00:00 | 130 | completion -- bop/wellhead equipm ent | ok | RIH with the 10 3/4" Lock down sub to 130 m took up/down weight 78/74 MT.
| 17:00:00 | 17:30:00 | 139.3 | completion -- bop/wellhead equipm ent | ok | Installed the 10 3/4" Lock down sub at 139.27m, as per Vetco procedure.
| 17:30:00 | 17:45:00 | 139.3 | completion -- bop/wellhead equipm ent | ok | Performed line test from CMT unit to the rig floor to 207 bars 5 min.
| 17:45:00 | 18:45:00 | 139.3 | completion -- bop/wellhead equipm ent | ok | Pressure up to 207 bars 5 min to fully set of the 10 3/4" Lock down sub. Volume pumped 275 litres - 250 litres in return.
| 18:45:00 | 19:00:00 | 139 | completion -- bop/wellhead equipm ent | ok | Released the 10 3/4"Lock down sub RT.
| 19:00:00 | 21:00:00 | 0 | completion -- bop/wellhead equipm ent | ok | POOH with the 10 3/4" Lock down sub RT and laid out same.
| 21:00:00 | 22:45:00 | 0 | interruption -- waiting on weather | ok | WOW. Meanwhile inspected and serviced the aft PRS.
| 22:45:00 | 23:15:00 | 0 | interruption -- waiting on weather | ok | WOW. Held time out due to LTA on main deck.
| 23:15:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | WOW. Continued servicing the aft PRS.
2008-03-20 | 00:00:00 | 03:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Serviced and inspected the TDS.
| 03:00:00 | 05:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Changed out the wash pipe.
| 05:00:00 | 06:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Cleaned and cleared the rig floor
| 06:00:00 | 07:15:00 | 0 | interruption -- waiting on weath er | ok | WOW. Cleaned and cleared the rig floor.
| 07:15:00 | 19:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Performed general maintenance. Cleaned kill manifold. Had derrick inspection. Serviced Carrier rollers, spinner and tracks on aft Roughn eck.
| 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weath er | ok | WOW. Cleaned rig floor. Cleaned pit # 7. Performed maintenance on the aft PRS and the TDS.
2008-03-21 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on w eather | ok | WOW. Greased the UPR track on the PRS beam. Functioned main flow line valve 1250 psi. Transported 6 flood light to the finger board level in the derrick.
| 06:00:00 | 19:00:00 | 0 | interruption -- waiting on w eather | ok | WOW prior to retrieve the HP drilling riser. Meanwhile cleaned stand pipe/Choke line manifold. Changed oil on the TDS. Performed general maintenance and PM's. Changed out the cathead wire.
| 19:00:00 | 00:00:00 | 0 | eather | ok | 00:00 43/48 30° 6.1/9.7 360°
22:00 41/47 30° 6.1/9.7 360°
23:00 42/47 30° 6.2/9.8 10°
Knots deg m deg
Time Wind speed Wind direction Sea Wave direction
stallation of flood light in derrick.
|  |  |  | interruption -- waiting on w | ok | WOW prior to retrieve the HP drilling riser. Meanwhile prepared tools and lifting equipment, for nippling down the Diverter,BOP and the HPDR. Commenced in
2008-03-22 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | 00:30 40/45 30° 6.4/10.1 360°
02:00 42/47 30° 6.1/9.6 10°
03:00 39/43 30° 6.0/9.6 10°
04:30 37/41 20° 5.6/8.8 360°
05:00 35/41 30° 5.3/8.4 10°
06:00 34/38 20° 4.9/7.9 10°
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
WOW prior to retrieve the HP drilling riser. Continued installation of flood light in derrick.
| 06:00:00 | 19:00:00 | 0 | interruption -- waiting on weather | ok | 07:00 24/30 30° 4.4/10 10°
09:00 18/26 28° 4/10.4 30°
11:00 14/20 24° 3.7/7.8 40°
13:00 9/15 7° 3/9.4 340°
15:00 15/21 300° 2.8/9.8 225°
17:00 20/23 315° 2.9/8.9 250°
19:00 19/22 320° 2.6/4.1 340°
Moved CTS funnel from F-9 to F-1. Installed cover in CTS funnel.
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
WOW prior to retrieve the HP riser. Meanwhile installed flood light in derrick. Commenced changing out the seal assy of BOP door. Cleaned pit # 9 & 11. Perf ormed general maintenance and PM's.
| 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | 21:00 18/22 320° 2.6/4.2 320°
23:00 20/23 340° 2.5/4 340°
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
WOW prior to retrieve the HP riser. Installed flood light in derrick. Cleaned pit # 6,8 & 10.
2008-03-23 | 00:00:00 | 06:00:00 | 0 | interruption -- | ok | WOW prior to retrieve the HP riser. Completed installation of the flood light in the derrick. House keeping in the moon pool.
|  |  |  | ther | ok | 01:00 7/9 360° 2.7/3.9 340°
03:00 11/15 340° 2.4/4.1 340°
05:00 15/18 350° 2.7/4.3 340°
07:00 12/14 350° 2.9/4.6 340°
Knots deg m deg
Time Wind speed Wind direction Sea Wave direction
| 06:00:00 | 19:00:00 | 0 | interruption -- | ok | WOW prior to retrieve the HP riser. Changed out of BOP door seal assy, greased manual valves on choke/kill line. Cleaned pit. Performed general maintenance and PM's.
|  |  |  | ther | ok | 08:00 17/23 330° 2.6/4.1 350°
10:00 2.3/3.6
12:00 1.6/2.6
14:00 1.3/2.1
14:30-19:00 Not able to work at rig floor, due to exhaust fumes.
16:00 21/24 350° 1.8/2.9 330°
18:00 23/26 340° 3.1/5.0 340°
Knots deg m deg
Time Wind speed Wind direction Sea Wave direction
| 19:00:00 | 00:00:00 | 0 | interruption -- | ok | WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Performed general maintenance and PM's. Greased valves on BOP. Disconnected the CRI hose
|  |  |  | ther | ok | 00:00 26/32 320° 3.3/5.7 340°
20:00 18/28 330° 3.7/5.9 350°
22:00 22/26 330° 3.6/5.7 340°
Knots deg m deg
Time Wind speed Wind direction Sea Wave direction
g at 190 bars.
|  |  |  | waiting on wea | ok | from F-12 and removed the check valve. Connected up the CRI hose again and opened to annulus, annulus pressure 52 bars. Attempted to inject seawater into F-12, stopped pumpin
2008-03-24 | 00:00:00 | 06:00:00 | 0 | eather | ok | 02:00 17/20 320° 3.6/5.8 340°
04:00 30/34 320° 3.1/5.8 340°
06:00 15/18 340° 2.7/4.3 340°
07:00 29/33 350° 3.6/5.8 340°
Knots deg m deg
Time Wind speed Wind direction Sea Wave direction
e keeping in the moon pool.
|  |  |  | interruption -- waiting on w | ok | WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Installed CRI check valve on to F-14. Greased valves on BOP. Hous
| 06:00:00 | 14:00:00 | 0 | interruption -- waiting on w | ok | 07:00-10:30 No access to rig floor, due to exhaust fumes.
08:00 15/17 340° 4.2/6.7 340°
10:00 25/28 340° 3.9/6.3 340°
12:00 26/30 340° 3.6/5.8 340°
12:45-14:00 No access to rig floor, due to exhaust fumes
14:00 3.7/5.9 350°
Knots deg m deg
Time Wind speed Wind direction Sea Wave direction
WOW prior to retrieve the HP riser. Performed general maintenance and PM's.
| 14:00:00 | 19:00:00 | 139 | interruption -- waiting on w eather | ok | 16:00 23/26 330° 3.9/6.2 330°
16:30-19:00 No access to rig floor, due to exhaust fumes
18:00 23/27 360° 3.9/6.2 340°
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
WOW prior to retrieve the HP riser. Meanwhile RIH with test plug and landed of in sub sea WH. Attempted to pressure test against plug. POOH with test pl ug.
| 19:00:00 | 00:00:00 | 0 | interruption -- waiting on w | ok | 00:00 17/22 320° 3.9/6.3 340°
20:00 3.8/6.1 340°
22:00 20/24 320° 4.0/6.3 340°
Knots deg m deg
Time Wind speed Wind direction Sea Wave direction
WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Performed general maintenance and PM's.
2008-03-25 | 00:00:00 | 04:00:00 | 0 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. Not able to work at rig floor, due to exhaust fumes. Performed general maintenance and PM's.
| 04:00:00 | 06:00:00 | 139 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. Meanwhile re-RIH with test plug with polypack seals and landed of in sub sea WH. Pressure tested plug to 25/345 bars 5/10 min.
| 06:00:00 | 15:30:00 | 139 | interruption -- waiting on weat her | ok | 12:30 27/32 320° 4.5/7.2 340°
14:30 24/30 320° 4.6/7.3 340°
14:45-15:30 No access to rig floor, due to exhaust fumes
16:30 23/25 340° 4.6/7.4 340°
18:30 23/27 340° 4.2/6.6 340°
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
WOW prior to retrieve the HP riser. Pressure tested BOP and TDS 20/345 bars 5/10 min. Performed derrick inspection.
| 15:30:00 | 19:00:00 | 0 | interruption -- waiting on weat her | ok | 16:30 23/25 340° 4.6/7.4 340°
16:30-18:30 No access to rig floor, due to exhaust fumes
18:30 23/27 340° 4.2/6.6 340°
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
WOW prior to retrieve the HP riser. POOH with the test plug assy. Racked back string in derrick and laid out the test plug.
| 19:00:00 | 00:00:00 | 0 | interruption -- waiting on weat her | ok | 19:00-20:30 No access to rig floor, due to exhaust fumes 23:00-00:00 No access to rig floor, due to exhaust fumes
21:00 17/19 330° 4.2/6.7 340°
22:30 15/17 330° 3.5/5.5 340°
23:15 15/17 350° 3.1/5.0 340°
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
WOW prior to retrieve the HP riser. Prepared for N/D diverter. Checked tool for making up the Claxton tool.
2008-03-26 | 00:00:00 | 00:30:00 | 0 | interruption -- waiting on weat her | ok | WOW prior to retrieve the HP riser. No access to rig floor, due to exhaust fumes.
| 00:30:00 | 03:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and N/D diverter and BOP. Had gas turbines shut down at 01:25 due to exhaust fumes blowing into the rig floor.
| 03:00:00 | 03:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Held tool box talk prior to M/U the Claxton tool.
| 03:15:00 | 06:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Landed the Claxton tool on to the HPDR. Made Claxton tool to 1300 ft-lbs.
| 06:00:00 | 07:00:00 | 0 | interruption -- waiting on weat her | ok | 06:30 22/25 350°
Time Wind speed Wind direction Knots deg
WOW prior to retrieve the HP riser.
| 07:00:00 | 11:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | 08:30 13/15 020° 3,5/5,5 340°
Shut in F-12 for production. Simultaneously prepared for retrieving HPDR BOP joint. Moved CRI hose line from F-12 to F-14. Installed hot stab, for rele asing of riser TBC.
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
| 11:00:00 | 15:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | 11:30 6/11 030* 2,6/4,1 340°
13:30 4/10 050° 2,2/3,4 340°
15:00 1/3 110° 2,1/3,4 350°
Knots deg m deg
Loosen BOP/Tension joint flange. At 11:15 confirmed production shut in. Time Wind speed Wind direction Sea Wave direction
| 15:00:00 | 15:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | Removed horizontal tension support for riser in the moon pool.
| 15:30:00 | 16:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Loosen the remaining 4 bolts on BOP/tension joint flange.
| 16:00:00 | 16:45:00 | 0 | drilling -- bop/wellhead equip ment | ok | Picked up the BOP joint and racked back one DP stand.
| 16:45:00 | 17:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | R/U elevator on slings to allow, for laying out the Claxton tool with pup joint attached. Removed master bushing and outer ring.
| 17:30:00 | 18:15:00 | 0 | drilling -- bop/wellhead equip ment | ok | Pulled the BOP joint above the RT. Installed outer ring and the master bushing. Preserved the BOP joint flange. Laid out the BOP joint.
| 18:15:00 | 18:30:00 | 0 | drilling -- bop/wellhead equip ment | ok | R/D slings on elevator.
| 18:30:00 | 19:00:00 | 0 | drilling -- bop/wellhead equip ment | ok | Made up riser lifting sub on one DP std.
| 19:00:00 | 20:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and RIH with C-type lifting sub and made up same to Tension joint. Simultaneously disconnected the Claxton tool from the BOP joint.
| 20:45:00 | 21:45:00 | 139 | drilling -- bop/wellhead equip ment | ok | 21:30 4/8 160°
Installed Spider.
Time Wind speed Wind direction Knots deg
| 21:45:00 | 00:00:00 | 139 | drilling -- bop/wellhead equip ment | ok | Held tool box talk and applied 130 MT on to the string. Commenced to remove tension cylinders.
2008-03-27 | 00:00:00 | 01:45:00 | 139 | drilling -- | ok | 00:20 7/12 160° 1,3/2,1 360°
Continued rigging down the tension system.
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
| 04:30:00 | 06:00:00 | 95 | drilling -- | ok | 05:00 11/15 170° 1,5/2,4 360°
Disconnected flange bolt on HPDR flange and picked up double.
Time Wind speed Wind direction Sea Wave direction Knots deg m deg
| 19:15:00 | 21:30:00 | 0 | bop/wellhead equipme nt | ok | fairrings. Landed off HPDR standard joint #1 in riser spider. Broke bolts on flange. Observed loose skirt on TBC connector, bolts partly unscrewd and 2 bolts missing. Thi ghtended bolts on TBC skirt.
|  |  |  | drilling -- | ok | Pulled HPDR standard joint #1 and placed coupling in working height above riser spider. Removed
2008-03-28 | 00:00:00 | 01:30:00 | 0 | drilling -- bop/well head equipment | ok | Broke bolts on flange between lower pup and stress joint.
| 01:30:00 | 02:30:00 | 0 | drilling -- wait | ok | Due to findings made by production department, halted operation for inspection in wellhead area. A support bracket on the F-12 flowline/piping was found to be ripped off. Mærsk rig management decided not to start production due to the circumstances. Further investigation/assessment needed before starting production.
| 02:30:00 | 03:30:00 | 0 | drilling -- bop/well head equipment | ok | Landed HPDR lower pup joint on HTS cradle with simultaneous lift by deck crane and block. Removed handling flange. Re-slung HPDR lower pup joint and lifted to basket on mai n deck.
| 03:30:00 | 05:15:00 | 0 | drilling -- bop/well head equipment | ok | Installed handling flange type C on TBC joint. Pulled out TBC joint and laid down on HTS cradle with simultaneous lift by block and deck crane. Removed handling flange. Lifted TBC joint to basket on main deck.
| 05:15:00 | 06:00:00 | 0 | interruption -- wait ing on weather | ok | Meanwhile: Cleared and tidied rigfloor. Brought F-4 flexible hose onto HTS. Held toolbox talk prior to transferring flexible hose to XMT deck.
WOW for running production riser.
| 06:00:00 | 19:00:00 | 0 | interruption -- wait ing on weather | ok | -Cleared XMT deck for reception of F-4 flexible hose
-Landed BOP on test stump and made up NT-2 connector
-Suspended flexibel hose in roof and jacked to position for hook up
-Tested door seal on BOP
-Transferred F-4 flexible hose to XMT deck
Meanwhile :
Waited on weather.
| 19:00:00 | 00:00:00 | 0 | interruption -- wait ing on weather | ok | -Assisted production in equalizing across DHSV
-Worked on hooking up flexible hose
Meanwhile :
Waited on weather.
2008-03-29 | 00:00:00 | 06:00:00 | 0 | interruption -- waiting on weather | ok | -Changed gasket on test stump and made up NT-2 connecto r
-Lifted F-4 XMT to moonpool
-Tested BOP - 6 month 15 K test - had lekage on test stump
-Transferred tension cylinders for F-14 to XMT deck
-Worked on hooking up flexible hose
Meanwhile :
Waited on weather.
| 06:00 | 20:00:00 | 0 | interruption -- waiting on weather | ok | -Moved guide funnel to F-4 and installed debris cover
-Performed 6 month BOP test to 15 K
-Performed derrick inspection
-Repaired 10 MT tugger in moonopol
Meanwhile :
Waited on weather for running production riser.
| 20:00:00 | 00:00:00 | 0 | interruption -- waiting on weather | ok | -Lifted TBC joint to drillfllor
-Performed pre-operational checks on TBC
-Performed repair of BX elevator
Meanwhile :
Waited on weather for running production riser.
2008-03-31 | 00:00:00 | 01:00:00 | 101 | drilling -- b op/wellhea d equipme nt | ok | Held toolbox talk prior to lifting in tension joint. Removed BX-elevator. Installed 2 wire slings between bails and elevator. Picked up tension joint with deck crane and laid same on HTS cradl
e. Hooked up aft sling in tugger to get further in on drillfloor. Latched BX elevator around lift sub below 3 m pup joint. Lifted tension joint to upright position with simultaneous lift on deck cran e and block.
| 01:00:00 | 02:30:00 | 101 | drilling -- b op/wellhea d equipme nt | ok | Removed handling flange type F. Installed guide pins and landed tension joint on 3rd PR double. Made up connection using bolt tensioner tools. Pressure tested connection through test por t 5 min / 345 bar using hand pump. Installed bolt protector caps. Installed fairrings.
| 02:30:00 | 04:00:00 | 120 | drilling -- b op/wellhea d equipme nt | ok | Released BX elevator and removed slings. Installed BX elevator in bails. Re-latched tension joint. Removed spider and installed master bushing. RIH with tensioner joint, installed bowl and hung off riser on 3 m 5 1/2" pup joint.
| 04:00:00 | 04:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Made up 5 1/2" landing stand. RIH with production riser on 5 1/2" DP. Guided TBC into guide funnel while observing with ROV. Used ROV C-guide for stabbing TBC. Positioned ROV with manipulator camera pointing upwards in guide funnel cut out window. Observed TBC relative to VX ring and top wellhead while comming down with production riser. Stopped riser motion w hen ~10 cm TBC swallow was obtained.
| 04:45:00 | 05:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Detached lift sling on two points on each side of the hinge of the guide funnel. Unlocked hinge bolts and split guide funnel. Removed guide funnel by means of ROV and tuggers.
| 05:45:00 | 06:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | RIH with production riser and landed TBC on top of wellhead. Set down 10 MT. Ran hotstab and minireel hose along guidewire.
| 06:00:00 | 07:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Established hot stab in port A and set valves on ROV lock panel to "lock". Verified TBC fully landed. Locked TBC by pressuring up through minireel to 3000 psi. Observed movement of indic ator rods as prescribed. Maintained pressure for 15 mins. Set valves on ROV lock panel to parking position. Meanwhile assissted production in equalising across F-12 DHSV using cement unit.
| 07:00:00 | 07:15:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Performed overpull test to 116 MT hookload / 20 MT overpull.
| 07:15:00 | 08:30:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Removed hotstab and installed dummy stab. Moved hotstab to receptacle on panel B. Set valves to lower dog flush and injected hydraulic fluid / corrosion inhibitor through minireel.
| 08:30:00 | 09:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Installed bleeder valve on top of tension joint running flange to prepare for pressure test.
| 09:00:00 | 10:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Flushed and filled riser while venting air through valve on top of tension joint running flange. Closed valve. Lined up cement unit to standpipe and verified line-up by putting 15 bar on IBOP and opening same.
| 10:00:00 | 11:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Pressure tested production riser to 20/200 bar 5/10 min - ok. Pumped 680 liter and got full return when bleeding back. Observed for leaks around TBC with ROV - ok. Maintained 20 MT ov erpull on TBC while performing pressure test.
| 11:00:00 | 11:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Reduced hookload to 107 MT / 10 MT overpull on TBC. Took measurement for contact ring relative to Centralizer deck. Meanwhile pumped corrosion inhibitor in TBC upper piston cavity thr ough hotstab port B.
| 11:45:00 | 13:45:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Unstabbed hotstab and installed dummy stab in receptacle B. Landed riser guide funnel on F-5 using ROV and tugger support. Installed hatches on all levels in wellhead module for slot F-3 and F-5.
| 13:45:00 | 14:15:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Held toolbox talk prior to installing tensioner assembly.
| 14:15:00 | 21:30:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Hoisted tension ring and removed nylon guide in Centralizer deck. Installed centralizer and boat collision stool in Centralizer deck. Placed wooden beams on boat collision stool and landed t ension ring on top. Installed contact ring below mark on riser contact grooves. Installed and assembled tension assy half hubs with shimms and made up tension ring lock plates. Connecte d 2 tension cylinders. Elevated tension assembly with tension cylinders and checked contact ring allignement. Made up contact ring. Connected 2 tension cylinders.
| 21:30:00 | 22:15:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Pressured up on tension cylinders to 4 x 90 bar (150 MT) and transferred tension from block to tension cylinders on Centralizer deck. Slacked off drillstring to obtain marginal overpull (~1 M T) at cutting height.
| 22:15:00 | 23:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Installed centralizer assembly in Tensioner deck.
| 23:00:00 | 00:00:00 | 140 | drilling -- b op/wellhea d equipme nt | ok | Installed Norse cutting equipment on riser. Barriered off Centralizer deck.
2008-04-01 | 00:00:00 | 00:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | Installed Norse cutting equipment on riser.
| 00:30:00 | 04:30:00 | 140 | drilling -- bo p/wellhead equipment | ok | -Brought wellhead to drillfloor
-Installed flood lights in derrick
-Painted tuggerchains and control panels on drillfloor
-Tested Gray valve and FOSVs to 345 bar
-Varco checked both PRS's with focus on falling objects
Cut riser according to Norse procedure.
Meanwhile :
| 04:30:00 | 05:15:00 | 140 | drilling -- bo p/wellhead equipment | ok | Released top part of riser when cut obtained. Re-configuered cutting jig with 45 deg blades for machining bevel. Put protective ball on top of cut to avoid swarf falling into well.
| 05:15:00 | 06:00:00 | 140 | drilling -- bo p/wellhead equipment | ok | Cut 45 deg bevel on riser circumference.
| 06:00:00 | 07:15:00 | 140 | drilling -- bo p/wellhead equipment | ok | Rigged down Norse cutting equipment. Removed swarf and smoothed down cut. Marked deck for wellhead orientation.
| 07:15:00 | 08:15:00 | 140 | drilling -- bo p/wellhead equipment | ok | Packed and removed cutting equipment. Cleared and tidied wellhead decks.
| 08:15:00 | 09:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Pulled landing stand and laid out handling flange and riser cut off.
| 09:00:00 | 09:15:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to lowering WH with dual lift.
| 09:15:00 | 10:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Lowered WH to tensioner deck and landed same on top of riser.
| 10:00:00 | 16:30:00 | 0 | drilling -- bo p/wellhead equipment | ok | Orientated WH with valve stack pointing 45 deg relative to PORT/FWD. Pressure tested BT-seals to 35 bar - ok. Energized plastic in upper annd lower BT seal. Tested seals to 207 bar / 1 0 min - ok. Locked in 1000 psi after test. Energized slips with cap srews according to Vetco procedure. Pull tested WH with tugger - ok. Installed valves on A and B annulus outlets. Mean while loosended bolts on BOP NT-2 connector on stump. Made preparations to run BOP riser joint.
| 16:30:00 | 16:45:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to installing BOP riser joint.
| 16:45:00 | 17:45:00 | 0 | drilling -- bo p/wellhead equipment | ok | Ran BOP riser joint using block and dedicated slings and landed on wellhead. Made up NT-2 connector. Retrieved lift slings.
| 17:45:00 | 18:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to nippling BOP.
| 18:00:00 | 22:30:00 | 0 | drilling -- bo p/wellhead equipment | ok | Nippled up BOP. Meanwhile prepared for installing diverter.
| 22:30:00 | 22:45:00 | 0 | drilling -- bo p/wellhead equipment | ok | Held toolbox talk prior to installing slick joint and diverter.
| 22:45:00 | 00:00:00 | 0 | drilling -- bo p/wellhead equipment | ok | Installed diverter in housing.
2008-04-02 | 00:00:00 | 00:30:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Installed diverter in housing.
| 00:30:00 | 02:15:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Ran slickjoint and landed same on top of BOP. Removed running slings from bails and installed elevator.
| 02:15:00 | 03:30:00 | 0 | drilling -- bop activi ties | ok | Function tested BOP shear ram - ok. RIH with test plug for testing BOP connection. Function tested BOP rams and annular - ok. Landed test plug in surface wellhead. Performed line test an d verified line up by opening HCR with 35 bar - ok.
| 03:30:00 | 04:15:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Pressured up to 35 bar using cement unit - mismatch pumped vs theoretical volume. Suspected pressuring up against GT plug. Opened B-annulus valves to vent underneath plug and press ure dropped immediatly. Leakage observed across test plug despite steady pressure 35 bar indicating that plug did not vent into pipe when doing pressure test. Discussed situation - decided to re-attempt test while keeping B-annulus valves open.
| 04:15:00 | 05:15:00 | 0 | drilling -- bop activi ties | ok | Increased pumprate to 50 lpm and put 100 bar differential across plug, leakage decreased and pressure curve indicated that plug was sealing. Achieved steady pressure curve at 100 bar. Ble d off pressure to 35 bar and held test for 5 mins (1,7 bar drop / 5 min). Steady fluid returns observed from B-annulus. Pressured up to 345 bar and tested connectors + inner A annulus valve f or 10 min - 1,3 bar drop - ok. Shifted valves on A annulus. Held pressure and pressure tested outer A annulus valve for 10 min - 0,7 bar drop - ok. Pumped and bled back 43 liter (35=>345 ba r). Still minor fluid returns from B-annulus outlet but gradually decreasing.
| 05:15:00 | 05:30:00 | 0 | drilling -- bop activi ties | ok | POOH with 5 1/2" DP stand and test plug. Observed dirt/mud residues plug. Found pieces of steel in the mud residues. Strapped pipe and found landing point 20,45 m vs theoretical 20,81 m - but likely that plug landed too shallow.
| 05:30:00 | 06:00:00 | 0 | drilling -- bop/wellh ead equi pment | ok | Made up bowl protector to running tool and made up to stand of 5 1/2" DP. Meanwhile hooked up tension cylinders on BOP.
| 06:00:00 | 08:30:00 | 20 | drilling -- casing | ok | Installed bowl protector according to Vetco instructions. POOH with 5 1/2" DP stand and laid down RT. Meanwhile hooked up BOP tension cylinerders in moonpool.
| 08:30:00 | 09:00:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to retrieving annulus insert.
| 09:00:00 | 09:30:00 | 0 | drilling -- casing | ok | Checked equipment prior to RIH.
| 09:30:00 | 10:30:00 | 0 | drilling -- casing | ok | Picked up and made up annulus insert J-slot retrieval tool.
| 10:30:00 | 10:45:00 | 76 | drilling -- casing | ok | RIH with retrieval tool on 5 1/2" HWDP landing string from surface to 76 m MD.
| 10:45:00 | 11:00:00 | 76 | drilling -- casing | ok | Mærsk crewchange. Held toolbox talk prior to continuing operation.
| 11:00:00 | 12:00:00 | 120 | drilling -- casing | ok | RIH with retrieval tool on 5 1/2" HWDP landing string from 76 m to 120 m MD. Made up TDS and took torque readings wiith annular closed (200 psi on strip bottle). Torque 0,3-0,6 kNm at 5 r pm.
| 12:00:00 | 13:30:00 | 139.7 | drilling -- casing | ok | Tagged annulus insert at 139,68 m MD. Engaged J-slot and confirmed with 1 MT overpull.
| 13:30:00 | 14:15:00 | 139.7 | drilling -- casing | ok | Closed annnular and backed out insert with 3 lefthand turns. Max torque 5 kNm. Observed for pressure build up - none obeserved. Continued backing out annular insert with another 3 leftha nd turns - observed 6" travel - ok.
| 14:15:00 | 14:30:00 | 139.7 | drilling -- casing | ok | Opened annular. Attempted to pull free - had 18 MT overpull. Continued rotating left and came free with annular insert.
| 14:30:00 | 15:00:00 | 138 | drilling -- casing | ok | Flowchecked well - well static.
| 15:00:00 | 15:45:00 | 138 | drilling -- casing | ok | Emptied trip tanks. Displaced well to 1,03 sg completion fluid at 1000 lpm. Pumped a total of 26 m3.
| 15:45:00 | 16:45:00 | 138 | drilling -- casing | ok | Broke out TDS. POOH with annular insert on 5 1/2" HWDP landing string from 138 m MD to surface.
| 16:45:00 | 17:00:00 | 0 | drilling -- casing | ok | Broke out annular insert RT. Worked to free annular insert free from J-slot running tool due to debris jamming the sleeve.
| 17:00:00 | 17:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to making up Smith 10 3/4" spear.
| 17:15:00 | 18:15:00 | 0 | drilling -- casing | ok | Made up spear to 5 1/2" HWDP (LS-1), checked serial no - ok. Broke spear and inserted 9,632" nominal grapple. Made up spear using rig tongs.
| 18:15:00 | 19:45:00 | 0 | drilling -- casing | ok | Made up adjustment sub setting tool to stand of 5 1/2" HWDP (LS-2), checked serial no - ok.
| 19:45:00 | 21:30:00 | 140.5 | drilling -- casing | ok | Performed extra washing trip in order to clean tie-back adapter. Made up bullnose/jet sub. RIH on 5 1/2" DP from surface to 140 m MD. Stepped up pumps to 3500 lpm / SPP 68 bar. Passed t ie-back adapter and pulled back while pumping and rotating with 5 rpm. Pumped a total of 25 m3. Took returns to separate pit. POOH with jet sub.
| 21:30:00 | 22:00:00 | 0 | drilling -- casing | ok | Made up bowl protector RT and RIH on stand of 5 1/2" DP to 20 m. Caught bowl portector and POOH.
| 22:00:00 | 22:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to rig up 10 3/4" casing running equipment.
| 22:15:00 | 23:15:00 | 0 | drilling -- casing | ok | Cleared and tidied drillfloor prior to bringing in casing running equipment.
| 23:15:00 | 00:00:00 | 0 | drilling -- casing | ok | Installed BX-3 elevator, changed inserts and function tested same.
2008-04-03 | 00:00:00 | 02:00:00 | 0 | drilling -- cas ing | ok | Moved Mærsk casing tong from drawwork deck storage and moved in front of IR.
| 02:00:00 | 05:00:00 | 0 | drilling -- cas ing | ok | Hooked up casing tong. Changed head on PDM to accommodate 10 3/4" casing. Moved HTS rollers from FWD to AFT end of cantilever. Dressed PS-30 casing with 10 3/4" inserts/di es. Removed masterbushing and installed PS-30 in rotary. Hooked up PS-30 slip. Programmed and tested casing tong - negative.
| 05:30:00 | 06:00:00 | 0 | drilling -- cas ing | ok | Function tested casing tong - ok.
| 06:00:00 | 07:00:00 | 3 | drilling -- cas ing | ok | Picked up tie-back adapter and checked seals and acme thread. Installed tie-back adapter in slips. Secured same with dogcollar.
| 07:00:00 | 08:00:00 | 3 | drilling -- cas ing | ok | Picked up first 10 3/4" joint and stabbed on to tie-back adapter. Had problems with Mærsk casing tong. Not able to get torque/turn curves on computer.
| 21:00:00 | 23:00:00 | 108 | drilling -- cas ing | ok | RIH with 10 3/4" tie-back casing from surface to 108 m MD according to tally.
| 23:00:00 | 00:00:00 | 119 | drilling -- cas ing | ok | Picked up and made up 10 3/4" hanger / adjustable sub assy. Landed hanger in slips. Broke off casing hanger handling tool. Checked casing hanger. Changed from BX3 to 5 1/2" BX elevator.
2008-04-04 | 00:00:00 | 00:15:00 | 119 | drilling -- casing | ok | Picked up pre-made 5 1/2" HWDP (LS-1) with 10 3/4" Itco spear with PRS. Attempted to make up stand to TDS - negative - slipped in TDS back up dies.
| 00:15:00 | 01:15:00 | 119 | interrupti on -- oth er | ok | Broke off TDS from stand. Set down stand in PRS. Lowered TDS and inspected torque wrench dies, removed swarf from dies. Re-attempted make up to stand in TDS - ok.
| 01:15:00 | 01:30:00 | 139 | drilling -- casing | ok | Ran 10 3/4" Itco spear 3 m into 10 3/4" tie-back casing and latched same. Took up/down weight 82/79 MT. RIH with tie-back casing on 5 1/2" HWDP (LS-1). Put meter marks from casing ha nger landing shoulder. Tagged with 4 MT at ~139,4 m, i.e. 30-40 cm shallow - no colour marks observed in WH B-annulus outlet. Re-attempted tag - same depth.
| 01:30:00 | 02:30:00 | 139 | drilling -- casing | ok | Evaluated situation. Checked drawings for potential hang-ups. Checked tally and joints left on deck - ok. Made two attempt to index pipe before tagging again - same depth. Sudden overpull of 14 MT observed after pulling some 30 cm above tag depth.
| 02:30:00 | 03:15:00 | 139 | drilling -- casing | ok | Decided to attempt to screw in 1-2 turn in order to verify tie-back adapter depth. RIH and tagged approx 10 cm deeper than earlier. Observed lower orange and white band in B-annulus outle
t. Measured required distance for adjustment sub travel (15") and decieded to continue according to plan.
| 03:15:00 | 04:15:00 | 139 | drilling -- casing | ok | Set torqe limit to 2700 Nm. Made 3 attempts to enter tie-back adapter. Entered tie-back adapter on 4th attempt and observed weight increasing about 3-4 MT for each turn. Slacked off to neu tral (80 MT) for each turn achieved. String stalled out at 2700 Nm after 5+ turns achieved. Took 10 MT overpull. Rotated at 1 rpm. Attempted make up to 10 000 Nm (optimum torque) - spear started to slip at 5500 Nm. Re-engaged spear. Adjusted torque setting to minimum torque 6600 Nm -spear started to slip at 5500 Nm. Re-enaged spear. Set torque limit to 10 000 Nm, incre ased rotation to 3 RPM. String stalled out on 10 000 NM (optimum torque) - ok.
| 04:15:00 | 04:45:00 | 139 | drilling -- casing | ok | Took 30 MT overpull to check pre-tension in casing towards datum. Streched pipe approx 2" and observed lower white band through B-annulus outlet.
| 04:45:00 | 06:00:00 | 139 | drilling -- casing | ok | Rigged down Odfjell casing tong and removed PS-30 slips. Installed masterbushing and bowl.
| 06:00:00 | 09:00:00 | 0 | interrupti on -- oth er | ok | Jammed torque wrench on TDS. Inspected equipment and found that wrong die-holders had been installed. Changed die-holders.
| 09:00:00 | 09:15:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to picking up adjustment sub activation tool.
| 09:15:00 | 10:15:00 | 28 | drilling -- casing | ok | RIH with adjustment sub and located same at 28,4 m MD. Checked serial numbers on pipe. Made up TDS.
| 10:15:00 | 11:00:00 | 28 | drilling -- casing | ok | Pressured up on drillpipe to 140 bar to activate horizontal dogs. Pulled back 0,4 m and confirmed engaged in vertical dog profile by 9 MT overpull. Rotated string with 22 righthand turns. Obs erved colored band through B-annulus outlet to confirm adjustment sub collapsing. Increased overpull to 30 MT and continued rotating until TDS stalled out on 9 kNm and overpull reduced. Slacked off string to 28,4 m MD mark and waited for 2 min. Bleed off pressure on DP. Obtained a total of 17" travel on adjustment sub.
| 11:00:00 | 11:45:00 | 0 | drilling -- casing | ok | POOH with adjustment sub activation tool and racked back in derrick.
| 11:45:00 | 12:00:00 | 0 | drilling -- casing | ok | Made up Drillquip straddle cup tester.
| 12:00:00 | 12:30:00 | 28 | drilling -- casing | ok | RIH with straddle cup tester and located same at 28,4 m MD across metal seal in adjustment sub. Meanwhile held toolbox talk for pressure testing.
| 12:30:00 | 13:00:00 | 28 | drilling -- casing | ok | Lined up cement unit on standpipe. Performed line test to 380 bar.
| 13:00:00 | 14:30:00 | 28 | drilling -- casing | ok | Pressure tested adjustment sub (metal seal) to 380 bar / 10 min - ok. Kept B-annulus open throughout test.
| 14:30:00 | 15:00:00 | 140.5 | drilling -- casing | ok | RIH with straddle cup tester from 28,4 m and located same across tie-back adpater at 140,5 m MD.
| 15:00:00 | 16:00:00 | 140.5 | drilling -- casing | ok | Filled pipe with approx 1,8 m3 packer fluid prior to testing. Pressured up to 380 bar - observed leakage from B-annulus outlet - not able to obtain test.
| 16:00:00 | 16:15:00 | 130.5 | drilling -- casing | ok | Pulled back 10 m to put cuptester in blank pipe to test tool. Pressured up - not able to obtain test - straddle cup test leaking.
| 16:15:00 | 17:30:00 | 0 | drilling -- casing | ok | POOH with straddle cup tester from 130,5 m MD to surface. Laid out cup tester and inspected same. Found no tears or flaws, but OD reduced significantly (9,85"/9,70" vs originally 10,13")
| 17:30:00 | 17:45:00 | 0 | drilling -- casing | ok | Held toolbox talk prior to rigging casing running equipment.
| 17:45:00 | 18:00:00 | 0 | drilling -- casing | ok | Rigged up casing running equipment. Found a yellow sheared allen bolt on walkway along drillfloor. Suspended operation and evaluated situation.
| 18:00:00 | 20:00:00 | 0 | interrupti on -- oth er | ok | Isolated aft PRS and TDS and inspected same with manrider. Found origin of bolthead to be from backside of aft PRS upper grip head.
| 20:00:00 | 00:00:00 | 0 | interrupti on -- oth er | ok | -Brought Vetco/BOT equipment to cantilever
-Installed BX3 elevator in bails
Meanwhile :
Parked aft PRS for repair. Performed repair work on aft PRS. Broke out and re-thightended in total 24 allen/hex bolts with prescribed momentum (600 ft lbs). Replaced broken bolt.
2008-04-05 | 00:00:00 | 02:30:00 | 0 | interruption -- other | ok | Repaired aft PRS. Meanwhile prepared for rigging casing running equipment.
| 02:30:00 | 03:45:00 | 0 | drilling -- casing | ok | Rigged up Odfjell casing tong adn PS-30 slips dressed for 10 3/4" casing.
| 03:45:00 | 04:00:00 | 0 | drilling -- casing | ok | Held toolbox talk for running 10 3/4" hanger running tool on 10 3/4" casing.
| 04:00:00 | 05:00:00 | 0 | drilling -- casing | ok | Made up 10 3/4" x 1502 swedge to 8 m 10 3/4" casing joint. Laid out casing joint.
| 05:00:00 | 05:30:00 | 0 | interruption -- waiting o n weather | ok | Suspended operation due to reported fumes. Wind direction 330. Assessed situation. Decided to resume operation.
| 05:30:00 | 06:00:00 | 0 | drilling -- casing | ok | Picked up 10 3/4" casing hanger RT and hung off in slips. Picked up joint of 10 3/4" casing and made up to RT. Picked up joint with pre-made swedge.
| 06:00:00 | 07:00:00 | 20 | drilling -- casing | ok | Made up pup joint with pre-made 1502 swedge. RIH and landed casing hanger RT at 20 m MD. Set of weight of landing string. Entered hanger RT threads using ch ain tong. Made up RT with 9 lefthand turns using casing tong.
| 07:00:00 | 07:15:00 | 20 | drilling -- casing | ok | Held toolbox talk prior to pressure testing.
| 07:15:00 | 08:00:00 | 20 | drilling -- casing | ok | Rigged up 1502 chicksan from swedge to cement hose hub on drillfloor.
| 08:00:00 | 08:45:00 | 20 | drilling -- casing | ok | Lined up to cement pump and flushed lines. Performed line test to 380 bar - ok. Exhaust fumes detected on drillfloor.
| 08:45:00 | 09:30:00 | 20 | drilling -- casing | ok | Pressured up on cement unit and tested upper tie-back/adjustment sub/tie-back adapter to 380 bar /10 min - ok. Pumped and bled back 587 litres.
| 09:30:00 | 21:30:00 | 20 | interruption -- waiting o n weather | ok | -Cleaned and tidied in moonpool
-Cleaned and tidied in wellhead module
-Housekeeping in heavy tool store
21:30 - shut down gas turbines to get working conditions on drillfloor.
Exhaust fumes on drillfoor and drillers cabin. Suspended drillfloor operations. Checked wind and conditions every 30 min. Monitored well from shaker control room.
Meanwhile :
| 21:30:00 | 23:45:00 | 0 | drilling -- casing | ok | Resumed work on drillfloor. Broke out casing hanger RT with 10 turns. Unable to latch elevator on 10 3/4" casing, had to use singel joint elevator and tugger. Pulled 10 3/4" landing string. Broke out RT. Broke out 1502 swedge.
| 23:45:00 | 00:00:00 | 0 | drilling -- casing | ok | Rigged down casing tong.
2008-04-06 | 00:00:00 | 00:30:00 | 0 | drilling -- casing | ok | Rigged down casing tong. Removed PS-30 slips. Observed dropped object on drillfloor - hex/allen bolt head from aft PRS. Suspended operations for investigation. Fenced off drillfloor.
| 00:30:00 | 03:00:00 | 0 | interruption -- other | ok | Inspected aft PRS. Discussed way forward. Parked and isolated aft PRS. Secured backside of aft PRS gripper head with cover and trailer straps for dropped obje ct prevention.
| 03:00:00 | 03:45:00 | 0 | drilling -- casing | ok | Resumed operations. Removed BX3 elevator and installed 5 1/2" DP elevator. Cleared drillfloor from casing handing equipment.
| 03:45:00 | 04:45:00 | 0 | drilling -- casing | ok | Ran 2 x 5 1/2" DP singels and made up to MS-seal running tool. Meanwhile laid out DP singels on deck to cater for continued operations.
| 04:45:00 | 06:00:00 | 0 | drilling -- casing | ok | Made up control lines to MS-seal RT. Function tested and adjusted dogs and stroke on MS seal RT.
| 06:00:00 | 07:00:00 | 20 | drilling -- casing | ok | Locked MS seal running tool in surface WH, observed 0,4 l return - ok. Performed 10 MT overpull to confirm latch - ok. Set MS seal assembly by applying 4300 p si. Observed 1,62" travel / 3,5 liter returned fluid - ok.
| 07:00:00 | 07:45:00 | 20 | drilling -- casing | ok | Pressure tested MS seal through test port in surface wellhead to 380 bar / 10 min - ok.
| 07:45:00 | 08:15:00 | 20 | drilling -- casing | ok | Released dogs in MS seal RT by rotating 5 turns to the right.
| 08:15:00 | 09:00:00 | 0 | drilling -- casing | ok | POOH with MS seal RT on 5 1/2" DP stand. Broke RT tool and laid down.
| 09:00:00 | 09:15:00 | 0 | drilling -- casing | ok | Held toolbx talk before running bowl protector.
| 09:15:00 | 10:00:00 | 20 | drilling -- casing | ok | Made up bowl protector RT. RIH and set bowl protector at 20,10 m MD.
| 10:00:00 | 10:45:00 | 0 | drilling -- casing | ok | Broke out RT and laid down same. Laid out 2 joints of 5 1/2" DP.
| 10:45:00 | 11:30:00 | 0 | drilling -- casing | ok | Held toolbox talk and prepared for running casing drift. Experienced problems with programming PDM.
| 11:30:00 | 13:15:00 | 0 | interruption -- other | ok | Troubleshot PDM. Unable to travel to port aft pipe bay.
| 13:15:00 | 14:00:00 | 0 | drilling -- casing | ok | Tested PDM - ok. Tested stabbing. Discussed issues related to pipe handling.
| 14:00:00 | 14:15:00 | 0 | drilling -- casing | ok | Picked up 9,567" casing drift and made up to 5 1/2" HWDP single.
| 14:15:00 | 17:15:00 | 140 | drilling -- casing | ok | RIH with 9,567" casing drift from surface to 140 m MD on 5 1/2" HWDP singels. Re-arranged pipe on cantilever deck.
| 17:15:00 | 18:15:00 | 245 | drilling -- casing | ok | RIH with 9,567" casing drift from 140 m to 245 m MD on 5 1/2" DP singles. Detected exhaust fumes on drillfloor.
| 18:15:00 | 19:15:00 | 245 | interruption -- waiting on weather | ok | Exhaust fumes on drillfloor. Made up TDS and spaced out for BOP. Abandoned drillfloor. Shut down one of the gas turbines to reduce exhaust fumes.
| 19:15:00 | 21:45:00 | 580 | drilling -- casing | ok | Resumed operations. Continued to RIH with 9,567" drift from 245 m to 580 m MD.
| 21:45:00 | 00:00:00 | 223 | drilling -- casing | ok | POOH with 9,567" drift on 5 1/2" DP from 580 m to 223 m MD. Laid out singles on deck when pulling out. Performed kick drill.
2008-04-07 | 00:00:00 | 02:00:00 | 0 | drilling -- casing | ok | POOH with 9,567" drift on 5 1/2" HWDP from 223 m to surface. Laid out singles on deck when pulling out. Observed dropped object on drillfloor - half crest of external lock ring / simmer ring for pin, 70 mm x 2 mm / 10 grammes. Suspended operations for investigation. Fenced off drillfloor.
| 02:00:00 | 02:45:00 | 0 | interruption -- oth er | ok | Inspected rig equipment. Found source of dropped object to be cherry picker main hydraulic lift cylinder. No risk of larger dropped object from equipment - lock ring served no pur pose.
| 02:45:00 | 04:00:00 | 0 | drilling -- casing | ok | Resumed operations. Held toolbox talk. Made up GTV pulling tool to stand of drillpipe hanging in block. Ran stand carefully through BOP. RIH to 80 m MD on 5 1/2" HWDP singl es. Observed leakage on BX-elevator.
| 04:00:00 | 05:30:00 | 80 | interruption -- oth er | ok | Fixed BX elevator. Changed 3 ea hydraulic hoses/fittings running from TDS to BX elevator.
| 05:30:00 | 06:00:00 | 130 | drilling -- casing | ok | RIH with GTV pulling tool from 80 m to 130 m MD on 5 1/2" HWDP singles.
| 06:00:00 | 09:00:00 | 600 | drilling -- casing | ok | RIH with GTV pulling tool from 130 m to 600 m MD on 5 1/2" singles.
| 09:00:00 | 09:30:00 | 615 | drilling -- casing | ok | Tagged plug with 2 MT at 615 m MD.
| 09:30:00 | 10:30:00 | 615 | drilling -- casing | ok | Pulled back 1 joint and made up DP to TDS. Displaced his-vis at 2400 lpm. Pumped a total of 37 m3 1,03 sg completion fluid.
| 10:30:00 | 10:45:00 | 615 | drilling -- casing | ok | Held toolbox talk prior to releasing plug.
| 10:45:00 | 11:15:00 | 615 | drilling -- casing | ok | Due to unsactisfactory cleanliness of completion fluid, pumped additional 26 m3 at 2400 lpm.
| 11:15:00 | 12:00:00 | 610 | drilling -- casing | ok | Latched onto plug and confirmed by 10 MT overpull. No pressure observed on standpipe but slight gain in triptank indicating equlized plug. Rotated at 5 rpm righthand while holding 3 MT overpull, released plug with 10 turns, no gain observed. Pulled back 5 m and waited for elastomer element to relax.
| 12:00:00 | 12:30:00 | 610 | drilling -- casing | ok | RIH with plug to 620 m MD to confirm released. Pulled 5 1/2" single and gained 0,2 m3 in trip tank due to swabbing plug.
| 12:30:00 | 14:00:00 | 578 | drilling -- casing | ok | Pulled 3 x 5 1/2" singles while pumping at 200 lpm. Swabbing stopped when plug entered 10 3/4" casing.
| 14:00:00 | 17:15:00 | 145 | drilling -- casing | ok | POOH with GTV plug on 5 1/2" DP singles from 578 m to 145 m MD.
| 17:15:00 | 20:15:00 | 0 | drilling -- casing | ok | POOH with GTV plug on 5 1/2 HWDP singles from 145 m MD to surface.
| 20:15:00 | 20:45:00 | 0 | drilling -- casing | ok | Broke out and laid down GTV plug and pulling tool.
| 20:45:00 | 22:30:00 | 0 | drilling -- casing | ok | Made up secondary bowl protector pulling tool. RIH and latched secondary bowl protector. Strapped pipe while POOH, measured 20,45 m to tubing hanger landing shoulder. Ma de up kick assembly.
| 22:30:00 | 22:45:00 | 0 | completion -- co mpletion string | ok | Held toolbox talk for rigging up tubing running equipment.
| 22:45:00 | 00:00:00 | 0 | completion -- co mpletion string | ok | Positioned HTS and moved rollers on cantilever. Cleared drillfloor. Positioned control line reel on fwd pipe setback. Meanwhile installed NPR plug with ballseat in tailpipe joint.
2008-04-08 | 12:15:00 | 19:00:00 | 48 | interruption | ok | -Removed 10 allen/hex bolts from fwd PRS
-Repaired handrails and kick plates in derrick
Found casing tong to be programmed with wrong torque values. Optimum torque set to 15660 ft lbs instead of 15660 Nm. Two tubing connections on assy#2 overtorqued. No back-up ass embly available. Discussed situation. Evaluated and discussed further actions with town. Got confirmation that VamTop thread should be good within 30% overtorque. Decided to do drift r un through overtorqued couplings to verify no deformation or restrictions.
Meanwhile :
2008-04-09 | 00:00:00 | 02:45:00 | 561 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 238 m to 561 m MD. Running speed 30 sec per joint. Checked self filling of tubing - ok.
| 02:45:00 | 03:15:00 | 561 | completion -- completion string | ok | Handover for short change of Mærsk crew. Held toolbox talk for continued operations. Greased PS-30 and elevator.
| 03:15:00 | 06:00:00 | 750 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 561 m to 750 m MD. Reduced running speed to 1 min per joint in 9 5/8" casing. Checked self filling of tubing - ok.
| 06:00:00 | 06:45:00 | 834 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 750 m to 834 m MD.
| 06:45:00 | 08:00:00 | 834 | completion -- completion string | ok | Bad make up on joint #189, laid out same. Broke out box on joint #190. Inspected pin and made up new box on joint #190. Moved mobile cherry picker to aft part of drillfloor for use on aft PRS.
| 08:00:00 | 10:00:00 | 963 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 834 m to 963 m MD.
| 10:00:00 | 10:45:00 | 963 | completion -- completion string | ok | Bad make up on joint #177, laid out same. Broke out box on joint #178. Inspected pin and made up new box on joint #178.
| 10:45:00 | 15:00:00 | 1345 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 963 m to 1345 m MD.
| 15:00:00 | 16:15:00 | 1333 | completion -- completion string | ok | Not able to make up joint #146, laid out same. Inspected box - negative. Laid out joint 145.
| 16:15:00 | 17:45:00 | 1434 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 1333 m to 1434 m MD.
| 17:45:00 | 18:00:00 | 1434 | completion -- completion string | ok | Inspected threads on joint #134 - negative - laid out joint.
| 18:00:00 | 18:30:00 | 1455 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 1434 m to 1455 m MD.
| 18:30:00 | 19:45:00 | 1455 | completion -- completion string | ok | Inspected threads on joint #129 - negative - laid out joint. Mærsk crew change and toolbox talk.
| 19:45:00 | 00:00:00 | 1743 | completion -- completion string | ok | RIH with 7" 29# S13%Cr tubing from 1455 m to 1743 m MD.
2008-04-10 | 00:00:00 | 01:45:00 | 1938 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing from 1743 m to 1938 m MD.
| 01:45:00 | 02:30:00 | 1938 | completion -- c ompletion strin g | ok | Bad make up on joint #90, laid out same. Washed and inspected threads on pipedeck. Applied API mod lubeseal dope to pin ends on pipedeck.
| 02:30:00 | 05:15:00 | 2164 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing from 1938 m to 2164 m MD.
| 05:15:00 | 05:30:00 | 2164 | completion -- c ompletion strin g | ok | Held toolbox talk prior to picking up completion assy#3 DHSV. Counted joints left on deck 84 - ok.
| 05:30:00 | 06:00:00 | 2164 | completion -- c ompletion strin g | ok | Picked up completion assy#3 DHSV. Made up completion assy#3 and ran through RT. Isolated pipe guides on PS-30 slips.
| 06:00:00 | 08:00:00 | 2164 | completion -- te st scsssv | ok | PU and installed one tubing joint above TRSCSSV assembly. Flushed control line. Connected control line to TRSCSSV and leak tested to 570 bar/10 min. Bled pressure down to zer
o. Checked slips alignement. Made guide arrangement for control line from tubing to CL drum. Pressured up control line to 420 bar to keep TRSCSSV open while RIH.
| 08:00:00 | 16:30:00 | 2645 | completion -- c ompletion strin g | ok | RIH with 7" 29# S13%Cr tubing with CL and clamps from 2164 m to 2645 m MD.
Up weight 172 MT / down weight 141 MT. Distance between up and down weight was 0.3 m.
| 16:30:00 | 17:00:00 | 2645 | completion -- c ompletion strin g | ok | Held tool box talk before entering 7" liner.
| 17:00:00 | 17:45:00 | 2645 | completion -- c ompletion strin g | ok | Lined up to pump down kill line and to be able to observe overflow from top of tubing. Verified line up with 15 bar.
| 17:45:00 | 18:30:00 | 2649 | completion -- c ompletion strin g | ok | Closed annular BOP at 280 psi. Attempted to reverse circulate, neg. Leaked through annular. Closed annular BOP at 580 psi. Reverse circulated using clean brine at 50 lpm / 3 bar a nd 100 lpm / 3.5 bar to get a reference. Observed returns. Stopped circulating and opened annular BOP.
RIH with 7" 29# S13%Cr tubing with CL and clamps from 2645 m to 2649 m MD.
| 18:30:00 | 21:00:00 | 2662.2 | completion -- c ompletion strin g | ok | Performed reverse circulation exercise 50-100 lpm / 3.5 bar. Moved string down in 30 cm increments from 2659.8 m to 2662.2 m and repeated reverse circulation exercise with sam e pressure response (50-100 lpm / 3.5 bar).
RIH with 7" 29# S13%Cr tubing with CL and clamps from 2649 m to 2659.8 m MD.
| 21:00:00 | 23:15:00 | 2662.2 | completion -- c ompletion strin g | ok | POOH with 7" 29# S13%Cr tubing with CL and clamps from 2662.2 m to 2644 m MD. PU 2.89 m pup joint to space out to be able to close annular without a coupling or a clamp in th e interval. RIH with 7" 29# S13%Cr tubing from 2644 m to 2662.2 m MD.
| 23:15:00 | 00:00:00 | 2662.8 | completion -- c ompletion strin g | ok | Performed reverse circulation exercise 50-100 lpm / 3.5 bar. Moved string down in 20 cm increments from 2662.2 m to 2662.8 m.
2008-04-11 | 08:15:00 | 09:15:00 | 2647 | completion | ok | Installed communication collar onto hanger and made 5 right hand turns until it shouldered out on TH. Wrapped CL 3 times around hanger neck. Connected TRSCSSV CL to 1/4" communi cation port at btm of communication collar.
PU tubing hanger RT with 7" #29 pup joint. Backed out THRT piston retaining screws and MU THRT to communication collar with 8 turns left hand rotation. Connected TRSCSSV CL to 1/ 4" communication ports on top of THRT.
| 10:30:00 | 13:00:00 | 2665 | completion | ok | Leak tested TH in port 1 and 2 on surface well head to 70 bar/5 min to verify that TH had landed correctly. Engaged TH lock down ring by applying 207 bar. Performed pull test with 15 MT overpull to verify TH lock down. SO weight.
Removed C-plate. Ran in with THRT below rotary. Installed bowls. PU and MU joints for landing string. Up weight 173 MT / down weight 144 MT. RIH with 7" 29# S13%Cr tubing, TH and THRT on landing string from 2647 m to 2665,2 m MD. Got indications when ratcheting muleshoe and seals entered 7" liner PBR. Landed TH on no-go shoulder in surface tubing head. SO weight.
| 16:00:00 | 17:00:00 | 2665 | completion | ok | Closed TRSCSSV. Bled down to 5 bar above TRSCSSV and function tested TRSCSSV for 10 min. Bled back 36 ltrs. Observed 0.2 bar drop. Equalized and opened TRSCSSV.
Pressured up tubing against NPR plug at 2648 m MDRT to 30 bar / 10 min to check tubing integrity before initiating packer setting. 70 ltrs pumped. Kept 570 bar on TRSCSSV CL. Observ ed 0.3 bar drop.
| 17:30:00 | 19:00:00 | 2665 | completion | ok | Bled down pressure to 320 bar. 60 ltrs bled back. Closed TRSCSSV and bled off pressure above to 250 bar. Bled back 35 ltrs. Inflow tested TRSCSSV with 70 bar diff / 30 min. Inflow test OK.
Bled off pressure above TRSCSSV to 10 bar. Bled back 120 ltrs. Inflow tested TRSCSSV with 310 bar diff / 30 min. Inflow test OK. Equalized and opened TRSCSSV using 157 ltrs. Bled of f pressure in tubing to zero. Bled back 800 ltrs.
| 20:00:00 | 21:00:00 | 2665 | -- test scss sv | ok | L. Pumped 125 ltrs and observed 0.2 bar drop on low pressure test. Pumped 1130 ltrs (total) and observed 2.1 bar (0.5%) drop on high pressure test. Had flow on both tubing and B- annulus while pressuring up A-annulus due to ballooning effect. No flow observed when pumps was shut in. Bled pressure down to zero and had 1100 ltrs in return. Closed TRSCSSV.
|  |  |  | completion | ok | Pressured up A-annulus to leak test packer from below and TH from below to 35/380 bar for 5/10 min pumping brine at 70 lpm. Kept tubing open on drill floor and 570 bar on TRSCSSV C
2008-04-12 | 00:00:00 | 00:30:00 | 0 | completio n -- test s csssv | ok | POOH with running string and LD RT.
| 00:30:00 | 02:45:00 | 0 | completio n -- compl etion strin g | ok | RD completion handling equipment.
| 02:45:00 | 03:45:00 | 0 | completio n -- compl etion strin g | ok | PU 2 joints of 5 1/2" HWDP and RIH and drained riser.
| 03:45:00 | 06:00:00 | 0 | completio n -- compl etion strin g | ok | ND and pulled diverter.
| 06:00:00 | 10:15:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Continued ND diverter. Went trough SJA and procedure with day crew. Attached slings to slick joint. Prepared barriers, handrails and slings. Lifted out diverter. Installed outer ring and master bushings. Loosened nuts on slick joint.
| 10:15:00 | 12:00:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Held tool box talk and reviewed SJA and procedures. Disconnected tension cylinders in WH module.
| 12:00:00 | 13:15:00 | 0 | drilling -- bop/wellh ead equip ment | ok | ND NT2 connection on BOP. Informed production department to shut in well at 12.30.
| 13:15:00 | 14:00:00 | 0 | interruptio n -- wait | ok | Waited on production to shut in well. Meanwhile removed 2 HP hoses connected to WH.
| 14:00:00 | 14:45:00 | 0 | drilling -- bop/wellh ead equip ment | ok | ND slick joint and BOP.
| 14:45:00 | 16:15:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Dismantled scaffolding on NT2 connection in moonpool and installed slings on riser. RU for disconnecting riser NT2 connection and disconnected same.
| 16:15:00 | 17:30:00 | 0 | drilling -- bop/wellh ead equip ment | ok | Dismantled scaffolding in moonpool. PU riser and terminated control lines on well head. Installed carrier on HTS. Installed hatch on weather deck and master bushings on rig floor. Hoisted ri ser to rig floor and retracted same.
| 17:30:00 | 19:15:00 | 0 | completio n -- test s csssv | ok | Disconnected control lines from communication collar and hoisted same to rig floor. Installed hatch in moonpool. Installed outer ring and master bushings on rig floor. Installed anti vibration r ing on TH. Removed one control line exit block on multi bowl. Unwrapped required length of CL around TH neck and fed control line through dedicated port on multi bowl. Fed high pressure packings and fittings onto CL and MU fittings to threads in multi bowl. Installed dart in BPV in TH by hand. Installed 137 VG seal ring on top of multi bowl and VG 63 seal ring on top of TH.
| 19:15:00 | 20:30:00 | 0 | completio n -- test s csssv | ok | MU ferrule swagelock fittings for CL. Installed seal rings and CL exit block. Installed seal ring on top of spacer spool.
Pressure tested and energized BT seals through ports 7/8. Tested VG 63 connection trough test port 9/10 to 35 bar/5 min. Tested TH void, grafoil seals and BT seals 35/380 bar for 5/10 min via test port 5/6.
Removed hatch to F-4. Lowered spacer spool down from rig floor with TDS until NT2 box connector landed out on top of WH. MU locking dogs until connection leveled out. MU actuation scr ews with 800 ft-lbs. Disconnected slings and removed same.
| 20:30:00 | 00:00:00 | 0 | moving -- skid | ok | Skidded cantiliver 1.5 m starboard and as far aft as possible to be able to possition crane for lifting XMT.
2008-04-13 | 00:00:00 | 02:00:00 | 0 | completion -- bop/well head equipment | ok | Held tool box meeting. Connected crane hook to one of the two chackles in the end of the chain hoist and wire sling. Disconnected transport plate. Lifted XMT to wireline de ck and landed it on wooden beams, where it hung suspended in crane hook and resting on wooden beams with 1 MT.
| 02:00:00 | 05:15:00 | 0 | moving -- skid | ok | Skidded rig to sea fastening position to gain access for lifting XMT with the port aft deck crane.
| 05:15:00 | 06:00:00 | 0 | completion -- bop/well head equipment | ok | Held tool box meeting. Attempted to lift XMT from wireline deck to F-4 wellhead. Could not reach F-4. Decided to skid further to starboard.
| 06:00:00 | 07:00:00 | 0 | moving -- skid | ok | Skidded 0.6 m further starboard and reached max skidded position starboard and fwd (sea fastning position).
| 07:00:00 | 09:00:00 | 0 | moving -- skid | ok | Meanwhile held toolbox meeting and went through procedures and SJA with day crew.
Unable to reach F-4 and F-5 with port aft deck crane. Evalutated alternative methode for landing of XMT.
| 09:00:00 | 10:30:00 | 0 | moving -- skid | ok | Meanwhile lined up from CMT onto F-12 kill valve. Lined up over choke manifold to equalize above TRSCSSV. Tested lines. Equalized TRSCSSV with 84 bar and opened s ame. Started production from F-12.
Skidded port and aft out to F-4.
| 10:30:00 | 11:00:00 | 0 | moving -- skid | ok | Held time-out for safety. Talked about everyones right to stop the operation if anything is unclear or confusing. Went through operational plan and safety aspects involved.
| 11:00:00 | 12:00:00 | 0 | moving -- skid | ok | Installed staircase to cantiliver.
| 12:00:00 | 13:30:00 | 0 | completion -- bop/well head equipment | ok | Removed big moonpool hatch and lowered XMT to moonpool. Re-installed hatch.
| 13:30:00 | 15:30:00 | 0 | moving -- skid | ok | Transfered XMT from turtle to weather deck and skidded cantiliver to port and fwd to position XMT in center.
| 15:30:00 | 16:15:00 | 0 | interruption -- wait | ok | Waited on production to shut in well.
| 16:15:00 | 16:45:00 | 0 | completion -- bop/well head equipment | ok | Attached TDS to XMT. Positioned and disconnected base plate.
| 16:45:00 | 17:30:00 | 0 | moving -- skid | ok | Meanwhile bled down all pressures on F-12 to zero bar.
Skidded rig fwd and port to position XMT over F-4 for final installation.
| 17:30:00 | 18:45:00 | 0 | completion -- bop/well head equipment | ok | Moved hatch on weather deck to allow XMT to pass through. Lowered XMT until 1 m above F-4 spacer spool.
| 18:45:00 | 20:15:00 | 0 | completion -- bop/well head equipment | ok | Held tool box meeting. Lowered XMT on to spacer spool with TDS and verified correct orientation.
MU graylock connection. Re-built scaffolding around XMT for proper working environment. Checked alignment of flanges between flow hose and XMT. Pressure tested seal ring 35 bar/10 min through test port 3/4 on spacer spool to confirm proper seal.
| 20:15:00 | 00:00:00 | 0 | completion -- bop/well head equipment | ok | Installed flow line spool. Disconnected lifting wire from TDS. Connected flexible flow line to flow line spool. Re-installed hatch.
2008-04-14 | 00:00:00 | 02:45:00 | 0 | interruption -- wait | ok | Postphoned XMT tests to assist production to start up F-12. Lined up from CMT onto F-12 kill valve. Lined up over choke manifold to equalize above TRSCSSV. Test ed lines. Equalized TRSCSSV and opened same. Started production from F-12.
| 02:45:00 | 06:00:00 | 0 | completion -- bop/wellhead equipment | ok | Held tool box meeting. Opened HMV with Seawell test pump. Lined up from cmt unit and connected hose on KWV. Performed line test to 20 bar for 5 min.
| 06:00:00 | 07:30:00 | 0 | completion -- bop/wellhead equipment | ok | Trouble shoot line up from cmt unit through valves and hose from moonpool to KWV due to failing line test. Detected exhaust fumes in WH area.
| 07:30:00 | 08:15:00 | 0 | interruption -- wait | ok | Exhaust fumes in well head area. Abandoned WH. Shud down on of the gas turbines to reduce exhaust fumes.
| 08:15:00 | 08:30:00 | 0 | completion -- bop/wellhead equipment | ok | Performed line test to 30/380 bar for 5/10 min against KWV. 2.2 bar drop on high pressure test.
| 08:30:00 | 10:15:00 | 0 | completion -- bop/wellhead equipment | ok | Attempted to pressure test XMT body and VG 63 ring to 30/380 bar for 5/10 min against dart in BPV. Failed due to leaking dart/BPV.
| 10:15:00 | 12:30:00 | 0 | completion -- bop/wellhead equipment | ok | Held tool box talk. Removed XMT tree cap. Opened HMV. RIH with retrieving tool for dart on stinger and retrieved dart. POOH with dart. RIH and installed new dart. Flushed XMT. Closed HMV.
| 12:30:00 | 13:00:00 | 0 | completion -- bop/wellhead equipment | ok | Attempted to pressure test XMT body and VG 63 ring to 30/380 bar for 5/10 min against dart in BPV. Failed due to leaking dart/BPV.
| 13:00:00 | 14:00:00 | 0 | completion -- bop/wellhead equipment | ok | Pulled dart and BPV. Installed a new BPV and dart. Flushed XMT.
| 14:00:00 | 14:30:00 | 0 | completion -- bop/wellhead equipment | ok | Pressure tested XMT body and VG 63 ring to 30/380 bar for 5/10 min against dart in BPV. 2.5 bar drop on high pressure test.
| 14:30:00 | 16:00:00 | 0 | completion -- bop/wellhead equipment | ok | 1.9 bar drop.
Equalized pressure above MMV. Opened MMV and closed HMV. Bled of any pressure above HMV to 10 bar. Inflow test HMV to 120 bar differential pressure for 15 min. 2.4 bar drop.
Equalized pressure across HMV. Opened HMV. Bled off pressure. Closed valves.
Pressured up to 130 bar against BPV & dart. Close MMV and bled off pressure above MMV to 10 bar. Inflow tested MMV to 120 bar differential pressure for 15 min.
| 16:00:00 | 17:00:00 | 0 | completion -- bop/wellhead equipment | ok | Removed XMT tree cap. Opened HMV. RIH with retrieving tool for dart on stinger and retrieved dart. POOH with dart. Pulled BPV from TH.
| 17:00:00 | 17:30:00 | 0 | completion -- bop/wellhead equipment | ok | Re-installed XMT tree cap. Close HMV. Test three cap 380 bar/10 min against SV. Bled off pressure.
| 17:30:00 | 18:00:00 | 0 | completion -- bop/wellhead equipment | ok | Pressure test TRSCSSV CL exit block to 570 bar/15 min, using BOT pump. Test ok. No indication that TRSCSSV opened. Bled off 155 ml on line.
| 18:00:00 | 19:00:00 | 0 | completion -- bop/wellhead equipment | ok | Evalutated options for flushing flowline and made plan for flowline test. Handover with new crew.
| 19:00:00 | 20:45:00 | 0 | completion -- bop/wellhead equipment | ok | Held tool box meeting. Hooked up flexible hose and lined up for pressure testing flowline. Flushed through XMT PWV, KWV and lo-torque to cement unit with pot-wat er.
| 20:45:00 | 21:30:00 | 0 | completion -- bop/wellhead equipment | ok | Attempted to pressure test flow line and XMT to 30/345 bar for 5/10 min. Observed leak at flange on flexible hose.
| 21:30:00 | 00:00:00 | 0 | completion -- bop/wellhead equipment | ok | Inspected, greased and torqued up flange on flow line flexible hose.
Meanwhile worked on varco bolts on AFT PRS and installed tension cylinders on F-14.
2008-04-15 | 00:00:00 | 02:15:00 | 0 | completion -- bop/wellhead equipme nt | ok | Inspected, greased and torqued up flange on flow line flexible hose.
Meanwhile worked varco bolt on AFT PRS and installed tension cylinders on F-14.
| 02:15:00 | 04:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Flushed through XMT to cmt unit prior to testing flowline. Pressure tested flow line and XMT to 30/345 bar for 5/10 min. 1.1 bar drop on low pressure test and 1.7 bar drop on high pressure test.
| 04:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Commisioned XMT.
Meanwhile worked on varco bolts on AFT PRS and installed tension cylinders on F-14.
| 06:00:00 | 12:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Installed instrumentation on F-4 XMT. Connected umbilical to bulk head plate.
Meanwhile changed out chain on HTS, emptied trip tank and repaired sensor on gate valve shakers. Started to change out one tension cylinder on F-14. Carried out work s cope with climbers in derrick.
| 12:00:00 | 12:45:00 | 0 | interruption -- wait | ok | Waited on production to restart after production shut-down.
| 12:45:00 | 16:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Energized instrumentation on XMT.
Meanwhile changed out one tension cylinder on F-14 and cleaned area. lined up from cement unit onto F-12 kill valve. Lined up over choke manifold. Equalized TRSCSSV with 94 bar and opened same. Started production from F-12. Carried out work scope with climbers in derrick.
| 16:30:00 | 17:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Function tested XMT pressure transmitters.
Meanwhile retrieved base plate from weather deck to moonpool. Carried out work scope with climbers in derrick.
| 17:00:00 | 19:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile performed housekeeping on cantilever. Carried out work scope with climbers in derrick.
Mounted umbilical termination plate on XMT.
| 19:30:00 | 21:30:00 | 0 | completion -- bop/wellhead equipme nt | ok | Meanwhile worked on Varco bolts on aft PRS. Built suspended scaffolding for repair on fwd PRS. parked and landed BOP on test stump.
Tested annulus pressure transmitters on XMT.
| 21:30:00 | 22:45:00 | 0 | completion -- bop/wellhead equipme nt | ok | Function tested PWV and HMV on XMT with process operator present. Feed back on valve position to process control room read OK.
Meanwhile continued building suspended scaffolding for fwd PRS in paralell with securing bolts on aft PRS.
| 22:45:00 | 00:00:00 | 0 | completion -- bop/wellhead equipme nt | ok | Commenced commisioning of XMT. Verified documentation from Vetco Gray and Aibel. Performed pre-commisioning checks.
Meanwhile continued building suspended scaffolding for fwd PRS in paralell with securing bolts on aft PRS. Started to lift parts for fwd PRS onto scaffolding.
2008-04-16 | 00:00:00 | 06:00:00 | 0 | completion -- bop/wellhead equipment | ok | Meanwhile continued building suspended scaffolding for fwd PRS in paralell with securing bolts on aft PRS.
Performed pre-commisioning checks of valves on XMT. Function tested MMV and SV and XMT with process operator present. Feed back on valve pos ition to control room read OK.
| 06:00:00 | 07:00:00 | 0 | completion -- bop/wellhead equipment | ok | Meanwhile continued building suspended scaffolding for fwd PRS in parallell with securing bolts on aft PRS.
Performed pre-commisioning checks of valves on XMT. Function tested MMV and SV and XMT with process operator present. Feed back on valve pos ition to control room read OK.
| 07:00:00 | 17:00:00 | 0 | completion -- bop/wellhead equipment | ok | Commisioned XMT.
Meanwhile performed derrick inspection with climbers and worked on BOP.
| 17:00:00 | 00:00:00 | 0 | workover -- wait | ok | Meanwhile erected scaffolding platform for fwd PRS and performed 3-montly maintenance on BOP.
Waiting on WL equipment and personnel to arrive on rig. Completed commisioning of XMT 38 hrs ahead of plan.
2008-04-17 | 00:00:00 | 06:00:00 | 0 | workover -- wait | ok | Meanwhile erected scaffolding platform for fwd PRS and performed 3-montly maintenance on BOP.
Waiting on WL equipment and personnel to arrive on rig.
| 06:00:00 | 11:00:00 | 0 | workover -- wait | ok | Meanwhile performed derrick inspection with climbers and performed 3-montly maintenace on BOP.
Waiting on WL equipment and personnel to arrive on rig.
| 11:00:00 | 12:30:00 | 0 | workover -- rig up/dow n | ok | Meanwhile equalized above DHSV on F-12 with cmt unit to re-start production. Observed leak in F-12 XMT. Meanwhile performed derrick inspection with climbers and performed 3-montly maintenace on BOP.
Prepared for RU wireline equipment and tested dual and trippel BOP's.
| 12:30:00 | 19:00:00 | 0 | workover -- rig up/dow n | ok | Meanwhile identified leak on F-12 XMT to be in MEG injection valve.
Meanwhile performed derrick inspection with climbers and performed 3-montly maintenace on BOP.
Prepared for RU wireline equipment and tested dual and trippel BOP's.
| 19:00:00 | 20:45:00 | 0 | workover -- rig up/dow n | ok | Meanwhile continued to work on scaffolding platform for fwd PRS.
Prepared for RU wireline equipment and tested dual and trippel BOP's.
| 20:45:00 | 00:00:00 | 0 | workover -- rig up/dow n | ok | Held tool box meeting. Spotted WL equipment on rig floor and hooked up BCU and pump skids. Prepared riser and BOP for lifting down to moonpool are a.
Meanwhile changed MEG injection valve on F-12 and re-tested valve to 325 bar/30 min.
2008-04-18 | 00:00:00 | 02:15:00 | 0 | workover -- ri g up/down | ok | Meanwhile equalized above DHSV on F-12 with cmt unit to re-start production. Production on F-12 started 02:00. Meanwhile built scaffolding bridge from cantiliver to Schlumberger WL deck (port aft leg).
Spotted WL equipment on rig floor and hooked up BCU and pump skids. Prepared riser and BOP for lifting down to moonpool area.
| 02:15:00 | 06:00:00 | 0 | workover -- ri g up/down | ok | Held tool box meeting. Hooked up chicksan line in moonpool from cmt unit to both F-12 and F-4 with seperate high pressure hoses. Lifted off hatch on F-4. Leak tested line from cmt unit to XMT KWV with LTV4 closed 30/380 bar for 5/10 min. Dropped 0.75 bar/10 min. Verified no pressure under XMT cap and removed same.
| 06:00:00 | 11:00:00 | 0 | workover -- ri g up/down | ok | Lowered the assembled XO, pump-in sub and short riser section through the rotary with tugger from drill floor and connected it to XMT. Installed BOP's with dual placed on top of trippl e BOP.
| 11:00:00 | 12:15:00 | 0 | workover -- ri g up/down | ok | Built scaffolding around BOP's to enabling handling of riser above BOP's.
| 12:15:00 | 13:30:00 | 0 | workover -- ri g up/down | ok | Installed riser sections to rig floor.
| 13:30:00 | 17:00:00 | 0 | interruption -- rig up/down | ok | Opened SV. Attempted to pressure test riser sections and BOP's without sucess. Identified leak in FMC drain valve. Bled off pressure. Closed SV. Attempted to rectify the leaking valv e without sucess.
| 17:00:00 | 21:00:00 | 0 | workover -- ri g up/down | ok | Built grease injection head, with cable head already installed and one lubricator section on rig floor. PU grease injection head and one lubricator section using tugger. Connected two more lubricator sections. Installed sheave wheels.
Meanwhile drained riser and installed new FMC drain valve.
| 21:00:00 | 22:15:00 | 0 | workover -- ri g up/down | ok | Meanwhile transfered operation of HMV and TRSCSSV to pump skid in moonpool. Production operator was present during the transfer.
Opened SV partly and flushed and filled lubricator with packer fluid using cement unit through KWV. Attempted to pressure test wireline rig-up. Observed leak in lubricator XO below t ool catcher.
PU and MU WL toolstring for pulling NPR plug and installed in lubricator. Connected lubricator at in-situ sub.
| 22:15:00 | 23:00:00 | 0 | interruption -- rig up/down | ok | BO lubricator and toostring. Changed leaking o-ring in XO. MU toolstring and re-connected lubricator.
| 23:00:00 | 23:45:00 | 0 | workover -- ri g up/down | ok | Opened SV partly and flushed and filled lubricator with packer fluid using cement unit through KWV. Pressure tested wireline rig-up 30/185 bar for 5/10 min against HMV. Dropped 0.7 5 bar/10 min. Filled lubricator with 700 ltrs. Bled off pressure in lubricator/rig-up to cmt unit. Closed SV.
Pressured up and opened HMV and TRSCSSV using WL pump in moonpool. Observed for leak on well head for 10 min. No leak observed. Opened SV.
| 23:45:00 | 00:00:00 | 0 | workover -- w ire line | ok | Started RIH WL toolstring for pulling NPR plug. Production shut down at 23:57 and had shut down WL unit. Re-powered up WL unit.
2008-04-19 | 00:00:00 | 01:15:00 | 0 | workover -- wire line | ok | Hooked up pump on rig floor to needle valve on lubricator to equalize and open TRSCSSV in F-4. Ran through TRSCSSV at 496 m MDRT and verified that it was fully open.
RIH WL toolstring for pulling NPR plug from surface to TRSCSSV at 496 m MDRT. Found that TRSCSSV was closed. Decided not to wait for cmt unit - production needed to equalize and open TRSCSSV on F-12 to re-start production.
| 01:15:00 | 03:00:00 | 0 | workover -- wire line | ok | Continued RIH WL toolstring for pulling NPR plug to 2600 m MDRT using running procedures for new cables. Running speed 40 m/min. Did not bleed off pressure while RIH and had 11-12 bar in well at 2600 m. Up weight 710 kg / Hanging weight 530 kg / RIH weight 422 kg.
| 03:00:00 | 04:00:00 | 0 | workover -- wire line | ok | RIH and latched GS pulling tool into NPR plug at 2649.7 m. Jared down to equalize ports in the plug. Waited 15 min for pressure across plug to equalize. Pressure dropped to 10 bar. Bleed off pressure. Released NPR plug by jaring up once. Got 150 kg increase in string weight. Waited 30 min to allow elements to retract.
| 04:00:00 | 06:00:00 | 0 | workover -- wire line | ok | POOH with NPR plug. Observed that weight dropped back to up weight while POOH. RIH and latched GS pulling tool into NPR plug at 2649.7 m. Pressured up well to 10 bar. Jarred d own to equalize ports in the plug. Waited 15 min for pressure across plug to equalize. No pressure drop observed.
Released NPR plug by jaring up 105 hits. Adjusted stress point on cable after 60 hits with jar. Got approx 300 kg increase in string weight. Bleed off pressure. Waited 30 min to allow el ements to retract.
| 06:00:00 | 09:00:00 | 0 | workover -- wire line | ok | POOH with NPR plug on 7/32 cable, worked through TRSCSSV at 496 m with 200 kg overpull. Closed SV using 42 turns and closed HMV. Bled off pressure in XMT, riser and lubricato r to closed drain.
| 09:00:00 | 10:30:00 | 0 | workover -- r ig up/down | ok | RD lubricator and cut wireline as per Seawell instructions. LD and inspected BHA and NPR plug. Plug had only small rift on rubber element.
| 10:30:00 | 11:45:00 | 0 | completion -- test scsssv | ok | Held tool box meeting. Attempted to increase TRSCSSV CL pressure to 570 bar with Seawell pump without sucess. Max pressure of 540 bar with Seawell pump. RU Vetco pump to p ressure up CL to 570 bar.
| 11:45:00 | 12:45:00 | 0 | completion -- test scsssv | ok | Lined up to test 7" tubing/liner to 380 bar through KWV with cmt pump. Opened LTV1 and LTV2. Pressured up well to test 7" tubing/liner to 35/380 bar for 5/10 min against EZSV plug at 3448 m MDRT. Pumped 1195 ltrs and bled back 1190 ltrs. Dropped 1.6 bar/10 min. Closed HMV. Adjusted TRSCSSV CL pressure to 520 bar.
| 12:45:00 | 15:00:00 | 0 | workover -- r ig up/down | ok | Installed Check Valve in test line to cmt unit. Performed line test from cmt unit against KWV to 185 bar/10 min. Dropped 0.9 bar/10 min. Bled down to 10 bar on cmt unit to inflow test C heck Valve. Bled down pressure between KWV and Check Valve to closed drain.
Meanwhile RU scaffolding and lubricator to grease head.
| 15:00:00 | 20:45:00 | 0 | workover -- r ig up/down | ok | RU additional lubricator sections needed for perforation runs. Lifted riser sections to rig floor. Modified scaffolding to a higher level to be able to assemble lubricator. RU to run 7/16" electric line. Prepared grease injection head. MU cable head with PGGT.
| 20:45:00 | 23:00:00 | 0 | workover -- r ig up/down | ok | Installed cable head and PGGT with bottom nose in riser. Connected WL riser at in-situ sub. Confirmed correct line up from cmt unit. Opened SV and KWV on XMT. Filled up riser and leak tested WL rigup to 30/185 bar for 5/10 min with cmt pump against HMV. Dropped 0.6 bar/10 min. Bled off pressure to closed drain. Closed SV.
| 23:00:00 | 00:00:00 | 0 | workover -- r ig up/down | ok | Drained lubricator. Broke riser at in-situ sub and LD toolstring. Cleared drill floor. Installed nitrogen rack and regulator on drill floor.
2008-04-20 | 00:00:00 | 02:15:00 | 0 | interruption -- ri g up/down | ok | Discussed method for PU and MU perforation guns due to uncertified lifting cap.
| 02:15:00 | 02:45:00 | 0 | workover -- rig u p/down | ok | Held tool box meeting prior to PU and MU gun sections.
| 02:45:00 | 03:15:00 | 0 | workover -- rig u p/down | ok | Checked GR/CCL on rig floor. Shut down power to Schlumberger unit to follow procedure for MU perforation guns. Closed off rig floor, WH and XMT. Made PA announcement.
| 03:15:00 | 06:00:00 | 0 | workover -- rig u p/down | ok | PU gun sections from cantiliver onto HTS with crane. Connected toolstring and swivel to gun and lifted guns into riser using both tugger and electric line with gooseneck. Conne cted and hung off all three gun sections in C-plate.
| 06:00:00 | 08:45:00 | 0 | workover -- rig u p/down | ok | MU firing head, PGGT and new swiwel to guns hung off in riser. Connected upper toolstring to guns hanging in riser and armed guns. PU tension on toolstring and took off C-pl ate.
| 08:45:00 | 09:15:00 | 0 | workover -- rig u p/down | ok | Connected lubricator and tested in-situ sub to 30/185 bar for 5/10 min with Seawell test pump. Ok.
| 09:15:00 | 13:00:00 | 3442 | workover -- wire line | ok | Opened HMV and observed 2 bar WHP. Verified TRSCSSV was open. Opened SV and RIH with 4.5" TCP guns on 7/16" electric line from surface to 3442 m MD. Up weight 28 50 kg / Running weight 1500 kg.
| 13:00:00 | 13:30:00 | 3426 | workover -- perf orate | ok | Bled 50 bar WHP down to zero through closed drain. Correlated guns to shooting depth using GR. Hanging weight 2570 kg. Fired guns and perforated interval #1 from 3408.5 m to 3422.0 m MD. Positiv confirmation that guns had fired, but observed no increase in WHP.
| 13:30:00 | 15:30:00 | 0 | workover -- wire line | ok | POOH and logged GR/CCL to above production packer. POOH with perforation guns to OOH. Powered down logging unit at 70 m below seabed. Made PA announcement and pulled cable head into tool catcher. Closed SV to verify BHA OOH.
| 15:30:00 | 20:30:00 | 0 | workover -- rig u p/down | ok | Broke lubricator at in-situ sub. BO and LD guns using sertified lifting sub. Observed that all shots had fired.
Closed HMV. Observed no WHP. Opened bleed to closed drain as a precaution. Opened needle valve and confirmed that lubricator was empty and that the well was on vacuu m.
| 20:30:00 | 22:00:00 | 0 | workover -- rig u p/down | ok | PU gun sections from cantiliver onto HTS with crane. MU lifting sub and lifted guns into riser. Connected and hung off all three gun sections in C-plate.
| 22:00:00 | 23:30:00 | 0 | workover -- rig u p/down | ok | Built and tested new cable head. Checked CCL on rig floor. Shut down power to Schlumberger unit according to procedure for MU perforation gun.
| 23:30:00 | 00:00:00 | 0 | workover -- rig u p/down | ok | MU firing head, CAL-B and new swiwel to guns hung off in riser. Connected upper toolstring to guns hanging in riser and armed guns.
2008-04-21 | 01:00:00 | 04:00:00 | 3300 | workover | ok | Meanwhile worked on synergi report for derrick, performed general maintenace and prepared BOP for pressure test.
RIH with 4.5" TCP guns on 7/16" electric line from surface to 3300 m MD.
| 04:30:00 | 05:15:00 | 3390.3 | workover | ok | No obvious indication that guns has fired, but observed short circuit in string and CCL stopped working. Observed no increase in WHP. PU weight increased with 100 kg (3100 kg).
RIH with guns to shooting depth. No WHP. Up weight 2985 kg / Running weight 1540 kg. Hanging weight 2330 kg. Fired guns and perforated interval #2 from 3395.0 m to 3408.5 m MD.
| 07:45:00 | 13:00:00 | 0 | interrupti on -- rig up/down | ok | Disarmed guns and removed firing head. Found leak in rope socket/cable head which caused short circuit in toolstring. Built and tested new cable head. Checked CCL on rig floor. Shut dow n power to Schlumberger unit according to procedure for MU perforation gun.
| 13:00:00 | 14:00:00 | 0 | interrupti on -- rig up/down | ok | MU firing head, CAL-B and new swiwel to guns hung off in riser. Connected upper toolstring to guns hanging in riser and armed guns. PU tension on toolstring and took off C-plate. Connecte d lubricator and tested in-situ sub to 30/185 bar for 5/10 min with Seawell test pump. Ok. Opened HMV and observed 0 WHP. Verified TRSCSSV was open. Opened SV.
| 14:00:00 | 15:00:00 | 701 | interrupti on -- rig up/down | ok | RIH with 4.5" TCP guns on 7/16" electric line from surface to 701 m MD.
| 15:00:00 | 15:45:00 | 360 | interrupti on -- rig up/down | ok | POOH with perforation guns from 701 m to 360 m MD due to weak CCL signal.
| 15:45:00 | 17:30:00 | 3408 | interrupti on -- rig up/down | ok | Schlumberger discussed with town and confirmed that CCL was ok. RIH with 4.5" TCP guns on 7/16" electric line from 360 m to 3408 m MD.
| 17:30:00 | 18:15:00 | 3390.3 | interrupti on -- rig up/down | ok | Correlated depth to 2 m pup-joint in 7" liner at 3228.38-3230.42 m tally depth / 3229.5 -3231.5 m WL dept correlated with GR on reservoar log using CCL. RIH with guns to shooting depth. No WHP. Fired guns and perforated interval #2 from 3395.0 m to 3408.5 m MD. Positiv indication that guns fired.
| 18:15:00 | 20:30:00 | 0 | interrupti on -- rig up/down | ok | POOH with perforation guns from 3390 m to OOH. Powered down logging unit at 70 m below seabed. Made PA announcement and pulled cable head into tool catcher. Closed SV to verify B HA OOH. Closed HMV. Observed no WHP. Opened bleed to closed drain as a precaution. Opened needle valve and confirmed that lubricator was empty and that the well was on vacuum. Br oke lubricator at in-situ sub. Confirmed that guns had fired.
| 20:30:00 | 21:45:00 | 0 | -- rig up/ down | ok | /bullheaded 3 m3 100% MEG at 180 lpm and 8 bar into well with cmt pump to provide cusion above closed TRSCSSV. Displaced MEG to above TRSCSSV by chasing it with 5.5 m3 packer f luid at 180 lpm and 8-20 bar. WHP started to increase after approx. 3 m3 packer fluid pumped.
|  |  |  | workover | ok | Connected lubricator and tested in-situ sub to 30/185 bar for 5/10 min with Seawell test pump. Ok. Opened HMV and observed 0 WHP. Verified TRSCSSV was open. Opened KWV. Pumped
2008-04-22 | 00:00:00 | 01:00:00 | 0 | workover -- rig up/ down | ok | BO and LD guns using certified lifting sub. Observed that all shots had fired.
| 01:00:00 | 03:00:00 | 0 | workover -- rig up/ down | ok | RD lubricatoor on rig floor. Disconnected and pulled riser sections above BOP to rig floor.
| 03:00:00 | 03:45:00 | 0 | workover -- rig up/ down | ok | Opened HMV and confirmed 0 WHP below. Closed HMV and opened KWV. Leak tested XMT cross to 123 bar / 10 min against closed HMV. Dropped 0.6 bar / 10 min. Bled off pressure to zero bar. Closed KWV.
| 03:45:00 | 06:00:00 | 0 | workover -- rig up/ down | ok | Held tool box meeting. RD hydraulic BOP hoses. Disconnected WL BOP's and transfered to overhead crane in moonpool. Transported BOP's to main deck. Dismantl ed scaffolding around BOP's.
| 06:00:00 | 07:00:00 | 0 | workover -- rig up/ down | ok | Installed tree cap and tested same 35/380 bar for 5/10 min against closed SV using Seawell test pump and 100% MEG. Bled off pressure.
| 07:00:00 | 08:45:00 | 0 | workover -- rig up/ down | ok | RD HP line from XMT KWV to cmt unit. Installed 1502 weco blind cap outside KWV and opened KWV. Leak tested KWV cap to 35/380 bar for 5/10 min aginst closed SV using Seawell test pump and 100% MEG.
| 08:45:00 | 09:30:00 | 0 | workover -- rig up/ down | ok | Meanwhile RD scaffolding on rig floor and cleared rig floor of excess equipment.
Transfered operation of HMV and TRSCSSV to platform system/production. Filled in and signed "Well handover document" and handed over well from Volve D&W to Mærsk Production at 09:00.
| 09:30:00 | 10:45:00 | 0 | workover -- rig up/ down | ok | ****************END OF OPERATIONS****************
Removed scaffolding around moonpool hatch and installed hatch.
2010-09-23 | 16:30:00 | 22:30:00 | 0 | workover -- rig up/dow n | ok | Well handed over from production department. Skidded rig in position. Changed to workover hatch. Meanwhile held pre job meeting with involved perso nnel.
| 22:30:00 | 00:00:00 | 0 | workover -- rig up/dow n | ok | Held tool box meeting on rig floor. Leak tested XMT cross to 20/100 bar for 5/10 min.
2010-09-24 | 00:00:00 | 01:30:00 | 0 | workover -- rig up/d own | ok | Installed chiksan manifold on TKV and leak tested same to 20/100 bar for 5/10 min.
| 01:30:00 | 05:00:00 | 0 | workover -- rig up/d own | ok | Meanwhile checked and tested RST toolstring on surface.
Removed XMT top cap and installed lower riser and BOP. Leak tested lower riser/BOP connections and function tested BOP. Lowered down upper riser from rig flo or and stabbed riser onto BOP.
| 05:00:00 | 06:00:00 | 0 | workover -- rig up/d own | ok | Held tool box talk and lifted up lubricator and GIH in elevator. Started to install toolstring into lubricator.
| 06:00:00 | 07:45:00 | 0 | workover -- rig up/d own | ok | Continued installing toolstring into lubricator.
| 07:45:00 | 09:15:00 | 0 | workover -- wait | ok | Waited due to broken bolt in the wheel for KWV. Mechanic attempted to chang bolt without success and found a temporary solution.
| 09:15:00 | 10:00:00 | 0 | workover -- rig up/d own | ok | Leak tested rig up. 20/100 bar for 5/10 min. Opened well. WHP = 7 bar.
| 10:00:00 | 10:45:00 | 498 | workover -- wire lin e | ok | RIH with BHA#1, RST. Stopped in DHSV at 498 m.
| 10:45:00 | 11:15:00 | 498 | workover -- wait | ok | Lined up AWS pump, pumped MEG into well and equalized DHSV at 39 bar.
| 11:15:00 | 13:30:00 | 3420 | workover -- wire lin e | ok | Continued RIH with BHA#2, RST to 3420 m.
| 13:30:00 | 14:00:00 | 3420 | workover -- wire lin e | ok | Ran correlation passes. Adjusted the depth according to reference log.
| 14:00:00 | 21:15:00 | 3230 | workover -- wire lin e | ok | Logged RST-D in IC mode from 3390 to 3230 m at 0.5 m/min.
| 21:15:00 | 21:45:00 | 3400 | workover -- wire lin e | ok | RIH to 3400 m.
| 21:45:00 | 22:30:00 | 3230 | workover -- wire lin e | ok | Logged RST in Sigma mode from 3390 to 3230 m at 4,5 m/min.
| 22:30:00 | 22:45:00 | 3400 | workover -- wire lin e | ok | RIH to 3400 m.
| 22:45:00 | 00:00:00 | 3370 | workover -- wire lin e | ok | Logged RST-D in IC mode from 3390 to 3370 m at 0.5 m/min.
2010-09-25 | 00:00:00 | 06:00:00 | 3260 | workover -- wire li ne | ok | Continued logging RST-D in IC mode from 3370 to 3260 m at 0.5 m/min.
| 06:00:00 | 08:00:00 | 3230 | workover -- wire li ne | ok | Continued logging RST-D in IC mode from 3260 to 3230 m at 0.5 m/min.
| 08:00:00 | 10:45:00 | 0 | workover -- wire li ne | ok | POOH with BHA #1.
| 10:45:00 | 13:00:00 | 0 | workover -- rig up/ down | ok | OOH. WHP 37 bar. Closed well and inflow tested HMV. Bled off and flushed lubricator with N2. Held toolbox meeting.
| 13:00:00 | 14:00:00 | 0 | workover -- rig up/ down | ok | LD RST toolstring and inspected same.
| 14:00:00 | 14:45:00 | 0 | workover -- rig up/ down | ok | Closed BOP. Flushed riser with N2 through KWV to blow down.
| 14:45:00 | 16:15:00 | 0 | workover -- rig up/ down | ok | Closed DHSV and bled down to 8 bar. Inflow tested DHSV. Bled off pressure above and closed well. Lined up and leak tested XMT cross.
| 16:15:00 | 18:30:00 | 0 | workover -- rig up/ down | ok | Held toolbox meeting and LD lubricator onto cat walk machine. Lifted upper riser section to rig floor with top drive. Lifted BOP away in moon pool. RD lower riser.
| 18:30:00 | 21:00:00 | 0 | workover -- rig up/ down | ok | Handed well over to Production department.
Removed chiksan manifold on KWV and installed end cap. Installed XMT top cap. Leak tested KWV end cap and XMT top cap to 20/345 bar for 5/10 min. Disconnect ed local control panel for HMV and DHSV.
| 21:00:00 | 00:00:00 | 0 | workover -- rig up/ down | ok | Disassambled riser and lubricator and lifted out riser sections from rig floor.
2010-09-26 | 00:00:00 | 06:00:00 | 0 | workover -- rig up/dow n | ok | Cleared rig floor off remaining WL equipment.Tidied and cleaned rig floor. Skidded rig in parking position. Prepared and packed WL equipment for demobilization.
END OF OPERATION
2012-09-11 | 07:00:00 | 11:00:00 | 0 | workover -- wire line | ok | Received WL equipment from boat.
| 11:00:00 | 13:00:00 | 0 | workover -- wire line | ok | Removed containers, tanks, equipment and prepared pipe deck area for spotting wireline equipment.
| 13:00:00 | 17:00:00 | 0 | workover -- wire line | ok | Started to spot WL equipment on pipe deck.
| 17:00:00 | 21:00:00 | 0 | workover -- wire line | ok | Leak tested BOP on stump. Started to prepare WL equipment.
| 21:00:00 | 21:20:00 | 0 | workover -- wire line | ok | Held Mearsk Toolbox Talk together with Maersk personnel prior to build lubricator. Held AWS check card meeting prior to thread the cable through GIH and toolcatcher.
| 21:20:00 | 00:00:00 | 0 | workover -- wire line | ok | Lifted and spotted Smart skid in front of winch. Lifted toolcatcher and GIH to rig floor. Threaded the cable through GIH and tool catcher, prior to build cable head. Built lubricator with fork lift on main deck.
2012-09-12 | 00:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Waited on Mearsk electrician, prior to hook up all wireline units. Electrician busy with other jobs. Meanwhile lifted BOP down to BOP deck through hatch on drill floor and prepared wireline equipment.
| 06:00:00 | 09:00:00 | 0 | interruption -- wait | ok | Waited on Mearsk electrician, prior to hook up all wireline units. Electrician busy with other jobs. Meanwhile prepared wireline equipment.
| 09:00:00 | 12:00:00 | 0 | workover -- wire line | ok | Hooked up wireline units to power and F&G.
| 12:00:00 | 14:00:00 | 0 | workover -- wire line | ok | Assembled lubricator and riser on rig floor.
| 14:00:00 | 17:00:00 | 0 | workover -- wire line | ok | Prepared wireline equipment. Meanwhile built cable head.
| 17:00:00 | 21:00:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile built cable head and megged same. Tried to connect logging unit to internet, no success.
| 21:00:00 | 21:30:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile held start up meeting with night crew.
| 21:30:00 | 00:00:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile tested counter system and RST tool.
2012-09-13 | 00:00:00 | 06:00:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile tested RST tool.
| 06:00:00 | 10:30:00 | 0 | interruption -- wait | ok | Waited for Production Department to prepare well for handover. Meanwhile tested RST tool.
| 10:30:00 | 11:00:00 | 0 | workover -- wire line | ok | Well handed over from production department.
| 11:00:00 | 11:30:00 | 0 | workover -- wire line | ok | Held DOP#1 meeting prior to R/U on well.
| 11:30:00 | 13:00:00 | 0 | workover -- wire line | ok | Leak tested XMT cross to 20/120 bar for 5/10 min. Meanwhile prepared to install lower riser and BOP.
| 13:00:00 | 13:30:00 | 0 | workover -- other | ok | Held brief prior to install lower riser and BOP.
| 13:30:00 | 16:30:00 | 0 | workover -- wire line | ok | Removed XMT top cap and installed lower riser and BOP. Leak tested lower riser/BOP connections to 20/120 bar for 5/10 min.
| 16:30:00 | 17:15:00 | 0 | workover -- wire line | ok | Lowered down lower lubricator from rig floor and stabbed lubricator onto BOP.
| 17:15:00 | 17:30:00 | 0 | workover -- other | ok | Held brief prior to install toolstring into lubricator.
| 17:30:00 | 19:00:00 | 0 | workover -- wire line | ok | Installed toolstring into lubricator.
| 19:00:00 | 19:30:00 | 0 | workover -- wire line | ok | Held brief prior to lift up lubricator and GIH in elevator.
| 19:30:00 | 22:30:00 | 0 | workover -- wire line | ok | Connected hoses and lifted up lubricator and GIH in elevator. Connected toolstring and stabbed upper lubricator unto lower lubricator.
| 22:30:00 | 23:00:00 | 0 | workover -- other | ok | Held DOP#2 meeting prior to RIH with RST toolstring.
| 23:00:00 | 00:00:00 | 0 | workover -- wire line | ok | Prepared to leak test R/U.
2012-09-14 | 00:00:00 | 02:00:00 | 0 | workover -- wire line | ok | .
Leak tested R/U to 20/120 bar for 5/10 min. Opened well. WHP = 42 bar
| 02:00:00 | 02:15:00 | 0 | workover -- other | ok | Held well controll drill prior to RIH.
| 02:15:00 | 02:50:00 | 556 | workover -- wire line | ok | RIH with BHA#1, RST to 556 m.
| 02:50:00 | 03:20:00 | 556 | workover -- wire line | ok | Performed test of RST according to Schlumberger procedure.
| 03:20:00 | 05:20:00 | 3420 | workover -- wire line | ok | Continued RIH with BHA#1, RST to 3420 m.
| 05:20:00 | 06:00:00 | 3420 | workover -- wire line | ok | Ran correlation passes. Adjusted the depth according to reference log.
| 06:00:00 | 07:05:00 | 3210 | workover -- wire line | ok | Logged RST-D in Sigma mode from 3400 to 3210 m at 4,5 m/min.
| 07:05:00 | 07:30:00 | 3420 | workover -- wire line | ok | RIH to 3420 m.
| 07:30:00 | 14:20:00 | 3215 | workover -- wire line | ok | Logged RST-D in IC mode pass#1 from 3410 to 3215 m at 0,5 m/min.
| 14:20:00 | 15:00:00 | 3420 | workover -- wire line | ok | RIH to 3420 m.
| 15:00:00 | 23:00:00 | 3215 | workover -- wire line | ok | Logged RST-D in IC mode pass#2 from 3410 to 3215 m at 0,5 m/min.
| 23:00:00 | 23:30:00 | 3420 | workover -- wire line | ok | RIH to 3420 m.
| 23:30:00 | 00:00:00 | 3380 | workover -- wire line | ok | Logged RST-D in IC mode pass#3 from 3410 to 3380 m at 0,5 m/min.
2012-09-15 | 00:00:00 | 06:00:00 | 3180 | workover -- wire line | ok | Logged RST-D in IC mode pass#3 from 3380 to 3250 m at 0,5 m/min.
| 06:00:00 | 07:40:00 | 3220 | workover -- wire line | ok | Continued logging RST-D in IC mode pass#3 from 3250 to 3220 m at 0,5 m/min.
| 07:40:00 | 09:30:00 | 0 | workover -- wire line | ok | POOH from 3220 m to surface. WHP:42 bar.
| 09:30:00 | 11:00:00 | 0 | workover -- test scsssv | ok | OOH. Closed in SWAB and HMV. Inflow tested same. Opened HMV and inflow tested DHSV.
| 11:00:00 | 12:30:00 | 0 | workover -- wire line | ok | L/D upper lubricator on drill floor and removed BHA#1, RST-D logging tool.
| 12:30:00 | 13:00:00 | 0 | workover -- oth er | ok | Performed brief prior to rig down.
| 13:00:00 | 15:10:00 | 0 | workover -- wire line | ok | Lifted lower lubricator to rig floor with top drive. Lifted BOP away in moon pool. R/D lower riser.
| 15:10:00 | 19:00:00 | 0 | workover -- wire line | ok | END OF OPERATION
Removed chiksan manifold on KWV and installed end cap. Installed XMT top cap. Leak tested KWV end cap and XMT top cap to 20/345 bar for 5/10 min. Disconnected local panal for HMV and DHSV. Handed well over to production department.
2016-10-01 | 15:00:00 | 16:00:00 | 0 | moving -- skid | ok | Continued to skid cantilever to F-04 9m inboard/1.25m port. Continued work with Aft PRS
Reporting continued from F-99.
| 16:00:00 | 16:30:00 | 0 | moving -- skid | ok | Installed covers to skidding system. Meanwhile held TBT for connecting HP hose to F-04 and for removal of well head cover/installation of split cover
| 16:30:00 | 17:30:00 | 0 | plug abandon -- o ther | ok | Connected HP hose to F-04. Meanwhile tested aft PRS. Prepared subs for pressure testing
| 17:30:00 | 19:00:00 | 0 | plug abandon -- o ther | ok | Performed line test down to XMT. Performed test of XMT cross 20/345bar for 5/10min. Good test
| 19:00:00 | 19:15:00 | 0 | plug abandon -- o ther | ok | Performed Pre-job Meeting to remove moonpool hatches
| 19:15:00 | 20:15:00 | 0 | plug abandon -- o ther | ok | Removed hatches and installed split hatch
| 20:15:00 | 21:30:00 | 0 | plug abandon -- o ther | ok | Adjusted scaffolding around Xmas tree. Prepared lines and bled off A and B annulus to MGS. Worked to fill A and B annulus with sea water. Bled off pressure and remo ved Tree cap from Xmas tree w/ rigfloor winch
| 21:30:00 | 23:45:00 | 0 | plug abandon -- o ther | ok | Hooked up hydraulic pump for local control of DHSV an HMV. Meanwhile worked to fill A and B annulus with sea water, carried out TBT for R/U cement head
| 23:45:00 | 00:00:00 | 0 | plug abandon -- o ther | ok | Worked to P/U cement head in moonpool using overhead crane and transfered to TDS lifting chains
2016-10-02 | 00:00:00 | 00:45:00 | 0 | plug aba ndon -- o ther | ok | Worked to P/U cement head in moonpool using overhead crane and transfered to TDS lifting chains
| 00:45:00 | 01:45:00 | 0 | plug aba ndon -- o ther | ok | M/U cement head to the Xmas tree, installed split hatch in moonpool
| 01:45:00 | 03:30:00 | 0 | plug aba ndon -- o ther | ok | Built scaffolding around cement head in moonpool
| 03:30:00 | 03:45:00 | 0 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to pressure test cement head
| 03:45:00 | 04:45:00 | 0 | plug aba ndon -- o ther | ok | Confirmed line up, flushed and pressure tested cement head and bleed off manifold to 20/345 bar for 5/10 min
| 04:45:00 | 05:00:00 | 0 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting before bullheading operation
| 05:00:00 | 05:30:00 | 0 | plug aba ndon -- o ther | ok | Lined up to pump into the well. Opened HMV. Wellhead pressure went up to 20 bar. Bled off pressure to MGS. Pressured up DHSV control line to 520bar. Pressured up above DHSV to equalize pressure. Observed indecation of DHSV openning on hydraulic pump pressure gauge.
| 05:30:00 | 06:00:00 | 0 | plug aba ndon -- o ther | ok | Pumped 10m3 of wash pill, 1100 l/min - 134bar
| 06:00:00 | 08:00:00 | 0 | plug aba ndon -- o ther | ok | Bullheaded sea water into the well, 1300 l/min - 143 bar, totally pumped 140m3. Meanwhile carried out TBT for cement job
| 08:00:00 | 09:45:00 | 0 | plug aba ndon -- o ther | ok | Lined up valves on the cement head, released bottom dart, mixed and pumped 13.6m3 1,90SG cement, 600l/min. Pressure 130 bar, decreasing to 90bar, indicating cement moving down in t he tubing. Displaced lines w/ 0,9m3 of Hi-vis pill. Released top dart. Pumped 12,2m3 of Hi-vis (totally pumped 13,1m3 of Hi-vis). Displaced w/ 37,7m3 of sea water at initial rate of 1000lpm. I ncreased pumping rate to 1300l/min - 101bar. Reduced pumping rate in the end of displacement to 700l/min - 83bar. Switched to contamination pill. Observed rapid increase in pressure whil e pumping contamination pill indicating cement plugging into perforations. Shut down after having pumped 3,5m3 contamination pill, 111 bar and monitored WH pressure decline. Recorded fi nal stabilized squeeze pressure of 60bar. Closed swab valve.
Verified volumes pumped by checking volumes left in the pits and silos. Theoretical top of cement 2755mMD. DHSV was cycled 3 times after 30m3 of sea water displacement was pumped
| 09:45:00 | 13:00:00 | 0 | plug aba ndon -- o ther | ok | Flushed manifolds after cement job. Worked aloft in derrick to repair crown grease system. Lined up and prepare to pressure test BOP. Meanwhile WOC
| 13:00:00 | 13:45:00 | 0 | plug aba ndon -- o ther | ok | Performed BOP test No1 20/345 bar 5/10 minutes. Cycleed HMV and MMV. Meanwhile WOC
| 13:45:00 | 14:45:00 | 0 | plug aba ndon -- o ther | ok | Lined up for BOP test No2, flushed 0.5m3 through kill and choke lines
| 14:45:00 | 15:45:00 | 0 | plug aba ndon -- o ther | ok | Performed BOP test No2 20/345 bar 5/10 minutes. Cycled HMV and MMV. Meanwhile pumped out dirty side of skimmer tank to mill tank, WOC
| 15:45:00 | 17:00:00 | 0 | plug aba ndon -- o ther | ok | Lined up and performed BOP test No3 20/345 bar 5/10 minutes. Continued to clear out dirty side of skimmer tank, transfered to mud pits 7.5m3. Lined up to bleed off pressure from XMT 110 bar down to 62bar. Meanwhile WOC
| 17:00:00 | 17:30:00 | 0 | plug aba ndon -- o ther | ok | Opened all low torque valves on cement head and pressure tested rig up against SV to 310 bar/10 minutes. Meanwhile WOC
| 17:30:00 | 18:15:00 | 0 | plug aba ndon -- o ther | ok | Closed HMV , bled off pressure above HMV from 72bar to 0. Opened SV, pressured up to 72bar to equalize, opened HMV. Pressured up well against cement plug with cement pump to 310b ar/10min. Pumped 620liters. Good pressure test.
| 18:15:00 | 19:15:00 | 0 | plug aba ndon -- o ther | ok | Carried out inflow test of cement plug. Bled down pressure in tubing to 10 bar. Monitored pressure pressure for 30 min. Pressure increased 3.6 bar with clear decreasing trend towards the en
d. Good inflow test
| 19:15:00 | 22:00:00 | 0 | plug aba ndon -- o ther | ok | . Good HP inflow test. Equalized pressure above DHSV, pressured up control line to DHSV to 520bar to open DHSV. Bled off tubing pressure to 20bar. 710l bled off. Closed DHSV. Bled off r emaining pressure from Xmas tree. Meanwhile performed TBT to R/D cement head
Carried out inflow test of DHSV. Equalized pressure and opened swab valve, applied 310 bar to tubing. 770l pumped. Closed DHSV. Bled off pressure in tubing above DHSV to 240 bar. Monitored pressure above DHSV for 30 min for 70bar LP inflow test. Pressure increased 1.5bar in 30 min with decreasing trend towards the end. Good LP inflow test. Bled down pressure in tubing above DHSV to 10bar. 110l bled off. Monitored pressure above DHSV for 30 min for 300bar HP inflow test. Pressure increased 2,4bar in 30 min with decreasing trend towards the end
| 22:00:00 | 23:30:00 | 0 | plug aba ndon -- o ther | ok | Closed SV. R/D cement head. Removed hydraulic control hoses to HMV and DHSV. Broke off bleed off manifold from kill wing side
| 23:30:00 | 00:00:00 | 0 | plug aba ndon -- o ther | ok | Worked to installed BPV plug for drop protection and Xmas tree lifting cap. Meanwhile performed BOP test No4
2016-10-03 | 00:00:00 | 00:15:00 | 0 | plug abandon -- ot her | ok | Continued to install BPV plug for drop protection and Xmas tree lifting cap. Meanwhile worked to perform BOP test No5
| 00:15:00 | 02:30:00 | 0 | plug abandon -- ot her | ok | Remove scaffolding from around Xmas tree and R/D electric and hydraulic lines from Xmas tree. Meanwhile performed pre-job meeting to N/D Xmas tree, pressure te sted BOP test No5
| 02:30:00 | 03:15:00 | 0 | plug abandon -- ot her | ok | Removed hatches and beam between slots. Meanwhile worked to pressure test BOP test No6, 7
| 03:15:00 | 04:00:00 | 0 | plug abandon -- ot her | ok | Removed master bushing and outer ring. Lowered diverter chains on TDS bails to wellhead and attached to X-tree. Meanwhile pressure tested BOP test No7
| 04:00:00 | 04:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to lift Xmas tree
| 04:15:00 | 05:15:00 | 0 | plug abandon -- ot her | ok | Took weight as per lifting plan and removed Grayloc clamp. Lifted X-tree to moonpool. Transfered load to gantry crane in moonpool. Attached lifting arrangement fro m TDS to Spacer spool
| 05:15:00 | 06:30:00 | 0 | plug abandon -- ot her | ok | Released NT-2 connector on wellhead, had difficulties to release 2x tight bolts. Meanwhile prepared HP riser on rig floor
| 06:30:00 | 08:15:00 | 0 | plug abandon -- ot her | ok | Cut control lines, installed communication collar and dart on BPV, cleaned up seal area. Meanwhile P/U riser from HTS
| 08:15:00 | 08:45:00 | 0 | plug abandon -- ot her | ok | Installed covers in moonpool using rigfloor winch
| 08:45:00 | 09:15:00 | 0 | plug abandon -- ot her | ok | P/U and RIH HP riser and M/U NT-2 connector
| 09:15:00 | 11:00:00 | 0 | plug abandon -- ot her | ok | Removed scaffolding from test stump and built scaffolding around HP Riser. Performed checks prior to skid BOP to well center. Meanwhile worked to M/U TDS test a ssembly
| 11:00:00 | 11:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to move BOP to well center
| 11:15:00 | 12:00:00 | 0 | plug abandon -- ot her | ok | Skidded BOP to well center and landed off on HP riser. Meanwhile pressure tested kelly hose to 20/345 bar, 5/10 min
| 12:00:00 | 12:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to M/U NT-2 connector
| 12:15:00 | 13:30:00 | 0 | plug abandon -- ot her | ok | M/U NT-2 connector. Meanwhile pressure tested upper/lower IBOPs and 2x FOSVs to 20/345 bar, 5/10 min
| 13:30:00 | 13:45:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to connect tension cylinders
| 13:45:00 | 15:00:00 | 0 | plug abandon -- ot her | ok | R/U tension system
| 15:00:00 | 15:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to handle slick joint
| 15:15:00 | 16:00:00 | 0 | plug abandon -- ot her | ok | Removed master bushing, RIH with Slick joint and M/U same, measured RKB to top of Annular = 5.78m
| 16:00:00 | 16:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to handle diverter
| 16:15:00 | 17:45:00 | 0 | plug abandon -- ot her | ok | P/U and RIH w/ diverter and landed off. Continued M/U slick joint. Meanwhile removed chains from bails and connected overshot hose. Energized overshot, lined up a nd filled hole with 3m3. No leaks observed
| 17:45:00 | 18:00:00 | 0 | plug abandon -- ot her | ok | Lined up cement unit through kill HCR, closed BSRs. Applied 20 bar to kill HCR valve to confirm line up
| 18:00:00 | 18:30:00 | 0 | plug abandon -- ot her | ok | With slick joint made up, fine tuned tension cylinders for equal pull
| 18:30:00 | 19:00:00 | 0 | plug abandon -- ot her | ok | Performed connection test to 20/345 bar 5/10 min, good test
| 19:00:00 | 19:30:00 | 0 | plug abandon -- ot her | ok | Finished to M/U slick joints, cleaned and cleared rig floor
| 19:30:00 | 20:00:00 | 0 | plug abandon -- ot her | ok | Changed handling equipment to 3.5in DP
| 20:00:00 | 20:15:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to retrieve dart and BPV
| 20:15:00 | 21:15:00 | 0 | plug abandon -- ot her | ok | Retrieved dart from BPV
| 21:15:00 | 21:45:00 | 0 | plug abandon -- ot her | ok | Retrieved BPV
| 21:45:00 | 22:15:00 | 0 | plug abandon -- ot her | ok | R/B 3.5in DP, L/D retrieval tool
| 22:15:00 | 22:30:00 | 0 | plug abandon -- ot her | ok | Changed handling gear, prepared for running THRT
| 22:30:00 | 22:45:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to R/U casing tong
| 22:45:00 | 23:30:00 | 0 | plug abandon -- ot her | ok | R/U casing tong
| 23:30:00 | 23:45:00 | 0 | plug abandon -- ot her | ok | Performed Pre-job Meeting to run w/ THRT and landing string
| 23:45:00 | 00:00:00 | 0 | plug abandon -- ot her | ok | P/U and RIH with tubing hanger running tool (THRT).
2016-10-04 | 00:00:00 | 02:00:00 | 0 | plug aba ndon -- o ther | ok | Continued to P/U and M/U tubingTHRT and landing string. POOH, installed control lines and inspected THRT. RIH and landed off THRT on TH. Observed top box of landing string is too high for casing tong to be able to M/U swedge.
| 02:00:00 | 02:15:00 | 0 | interrupti on -- rep air | ok | Performed Pre-job Meeting to rearrange landing string to be able to M/U swedge w/ casing tong. Started to position upper pup joint of landing string for casing tong to break off. Observed hy draulic oil leak from elevator
| 02:15:00 | 03:00:00 | 0 | interrupti on -- rep air | ok | Identified faulty hydraulic hose inside of the elevator and changed same
| 03:00:00 | 05:30:00 | 0 | interrupti on -- rep air | ok | /U swedge
Broke top 6m pup from landing string. M/U swedge using aft PRS and casing tong. Realized that it is not possible to break swedge while connected to TH with THRT. Broke off swedge using aft PRS and casing tong. Located 4m tubing joint (3m + 1m pups) on the pipe deck. M/U same to landing string, M/U 1m pup joint to landing string. Achieved sufficient stick up to be able to M
| 05:30:00 | 06:15:00 | 0 | interrupti on -- rep air | ok | Attempted to engage THRT to TH. No success, POOH, checked THRT, observed shear pins sheared prematurely. Repaired THRT
| 06:15:00 | 07:00:00 | 0 | plug aba ndon -- o ther | ok | RIH and landed off THRT, engaged tool and confirmed w/ 2t overpull. Applied pressure to shear pin and then rotated string 8x turns CCW into communication collar
| 07:00:00 | 08:00:00 | 0 | plug aba ndon -- o ther | ok | Connected cement hose and LT valve, flushed hose. Pressure tested same to 100 bar. Lined up pumps through cement hose. Applied pressure of 520bar to DHSV control lines. Pressured u p well above DHSV, observed DHSV equalized and opened at 100 bar pressure. No indications of gas below DHSV/in the well observed. Bled off pressure from the well through the cement hose to MGS to 0. Closed DHSV. Verified no pressure in the A-annulus
| 08:00:00 | 08:15:00 | 0 | plug aba ndon -- o ther | ok | Broke off swedge
| 08:15:00 | 08:30:00 | 0 | plug aba ndon -- o ther | ok | Released TH and and pulled 180t on hook load. String stretch of 0,75m
| 08:30:00 | 08:45:00 | 0 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to R/U WL equipment
| 08:45:00 | 09:30:00 | 0 | plug aba ndon -- o ther | ok | R/U wireline equipment
| 09:30:00 | 11:45:00 | 2616 | plug aba ndon -- o ther | ok | RIH w/ cutter BHA, run #9 from surface 2616 m. Average running speed 20 m/min.
| 11:45:00 | 13:00:00 | 2621 | plug aba ndon -- o ther | ok | Correlated across interval 2616 - 2638 . Positioned cutter at 2621 m . Performed cut. Observed backflow from pipe after tubing was cut
| 13:00:00 | 15:00:00 | 0 | plug aba ndon -- o ther | ok | POOH from 2621 m to surface. Average pulling speed 22 m/min. Backflow at rotary gradually decreased and eventually stopped
| 15:00:00 | 15:30:00 | 0 | plug aba ndon -- o ther | ok | R/D wireline equipment
| 15:30:00 | 15:45:00 | 0 | plug aba ndon -- o ther | ok | Performed flowcheck. Static
| 15:45:00 | 17:00:00 | 2600 | plug aba ndon -- o ther | ok | POOH w/ tubing and tubing hanger on landing string. Spooled control line. L/D landing string and TH on deck
| 17:00:00 | 17:45:00 | 2600 | plug aba ndon -- o ther | ok | Installed casing slips and control line spooler
| 17:45:00 | 18:00:00 | 2600 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to pull and L/D 7in tubing
| 18:00:00 | 18:15:00 | 2595 | plug aba ndon -- o ther | ok | L/D 3x pup joints
| 18:15:00 | 19:00:00 | 2573 | plug aba ndon -- o ther | ok | Pulled and L/D 2x joints of tubing
| 19:00:00 | 19:15:00 | 2573 | plug aba ndon -- o ther | ok | Performed Pre-job Meeting to pull and L/D 7in tubing w/ new crew
| 19:15:00 | 19:30:00 | 2573 | plug aba ndon -- o ther | ok | Checked red zone barriers and equipment
| 19:30:00 | 00:00:00 | 2109 | plug aba ndon -- o ther | ok | Pull and L/D 7in tubing from 2573m to 2109m, spooled control line. Pulled and L/D DHSV assembly. Average pulling speed 8,5 joints/hour. Totally pulled 39joints and DHSV assy
2016-10-05 | 00:00:00 | 00:30:00 | 2049 | plug abandon -- other | ok | Pulled and L/D the remaining 5x joints of 7in tubing. Average pulling speed 7joints/hour. Totally pulled 45x joints and DHSV assy
| 00:30:00 | 00:45:00 | 2049 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to M/U swedge
| 00:45:00 | 01:15:00 | 2049 | plug abandon -- cement plu g | ok | M/U swedge assembly w/ casing tong
| 01:15:00 | 03:00:00 | 2049 | plug abandon -- other | ok | Removed control line drum. Moved casing tong. Broke off swedge from FOSV. Install 5,5in inserts in BX elevator. M/U 1x std of 5,5in DP. Removed casing slips and installed DP slips. Clear ed rig floor
| 03:00:00 | 03:30:00 | 2049 | plug abandon -- cement plu g | ok | RIH w/ 7in tubing on 5,5in DP from 2049m to 2291. Average RIH speed 485m/hour
| 03:30:00 | 03:45:00 | 2291 | plug abandon -- cement plu g | ok | Filled pipe
| 03:45:00 | 04:15:00 | 2616 | plug abandon -- cement plu g | ok | RIH w/ 7in tubing on 5,5in DP from 2291m to 2616m. Average RIH speed 650 m/hour
| 04:15:00 | 04:30:00 | 2616 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting prior to circulating well to sea water
| 04:30:00 | 06:00:00 | 2616 | plug abandon -- cement plu g | ok | Started to circulate well to sea water. Staged up pumps to 3000 l/min - 78bar. Observed dirty fluid in returns. OIW reading is above 100ppm. No gas. After 50m3 pumped pulled 3m above c ombination wiper plug. Continued circulating. Shakers overflowed, reduced the rate to 2200l/min - 56bar. Circulated additional 112 m3. Observed clear returns after total of 162 m3 pumped. OIW content less than 30 ppm. Stopped pumps. Installed pump in sub w/ LT valve.
| 06:00:00 | 06:45:00 | 2614 | plug abandon -- cement plu g | ok | R/B 1x stand. Installed side entry sub assembly and connected cement hose, spaced out to 2614m bottom of tubing string
| 06:45:00 | 07:00:00 | 2614 | plug abandon -- cement plu g | ok | Lined up/prepared to pump wash pill
| 07:00:00 | 07:15:00 | 2614 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to place pump balance cement plug
| 07:15:00 | 08:00:00 | 2614 | plug abandon -- cement plu g | ok | Pumped 20m3 wash pill with mud pumps, 2700l/min - 79bar. Applied 20 bar behind IBOP, verified line up
| 08:00:00 | 09:30:00 | 2416 | plug abandon -- cement plu g | ok | Balanced cement plug (2616 m - 2416 m ): Mixed and pumped 9,4 m3 of 1,9 SG cement slurry, 600 l/min. Displaced the cement to the rig floor with 2900 l of drill water. Zeroed volume coun ters. Displaced the cement with 37 m3 (1670 strokes) of SW, 2900 l/min/ 51 bar. Pulled out of cement to 2416m at 4 min/stand. Theoretical TOC 2416 m MD.
| 09:30:00 | 10:15:00 | 2372 | plug abandon -- cement plu g | ok | Installed sponge ball. Pumped 10m3 hi-vis at 2400l/min / 43 bar. Circulated out cement at max of 3400 l/min/ 116 bar. Diverted returns overboard. L/D pup joint and R/B 1x stand to 2372m. Meanwhile WOC
| 10:15:00 | 10:30:00 | 2372 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to wash BOP w/ jetting tool. Meanwhile WOC
| 10:30:00 | 12:00:00 | 2372 | plug abandon -- cement plu g | ok | Installed closed FOSV and BOP wash tool, made 10x passes in BOP and well head area at 1500 LPM / 12 bar, operated rams and annular once. L/D BOP wash tool. Meanwhile WOC
| 12:00:00 | 12:15:00 | 2372 | plug abandon -- other | ok | Performed Pre-job Meeting to L/D DP. Meanwhile WOC
| 12:15:00 | 14:15:00 | 2052 | plug abandon -- other | ok | Installed pipe deck rollers. POOH and L/D singles of 5,5in DP from 2372m to 2052m. Meanwhile WOC
| 14:15:00 | 14:30:00 | 2052 | plug abandon -- cement plu g | ok | Removed DP slips and installed master bushing. Meanwhile WOC
| 14:30:00 | 14:45:00 | 2052 | plug abandon -- cement plu g | ok | Performed Pre-job Meeting to R/U casing tong. Meanwhile WOC
| 14:45:00 | 15:15:00 | 2049 | plug abandon -- cement plu g | ok | R/U casing tong and broke off swedge from top of tubing string. Meanwhile WOC
| 15:15:00 | 15:45:00 | 2049 | plug abandon -- cement plu g | ok | R/D casing tong. Meanwhile WOC
| 15:45:00 | 16:00:00 | 2084 | plug abandon -- cement plu g | ok | P/U spear BHA, set in catch position and engaged into tubing string, RIH to 2084m. Meanwhile WOC
| 16:00:00 | 17:00:00 | 2365 | plug abandon -- cement plu g | ok | RIH w/ 5,5in DP from 2084m to 2365m. Average tripping speed 612 m/hour. Performed kick drill. Meanwhile WOC
| 17:00:00 | 19:00:00 | 2365 | plug abandon -- other | ok | Performed maintenance on TDS. Cleared chiksans from wellhead. Worked on PMs on drilling equipment. Tested back up BX elevators, good test. Meanwhile WOC
| 19:00:00 | 00:00:00 | 2365 | plug abandon -- other | ok | Cleaned in moonpool. Worked to service both PRSs and TDS. Installed drill pipe slips. Meanwhile WOC
2016-10-06 | 00:00:00 | 02:00:00 | 2436 | plug aban don -- ce ment plug | ok | Initiated circulation and RIH to tag cement. Down weight 129t. Slowly washed down from theoretical TOC of 2416m to 2426m. 500l/min - 11bar. No indication of cement, stable pressure. Co ntinued RIH. Observed increase in pressure to 13-14bar and no change of weight indicating poor cement. Stopped RIH at 2436m, 20m below theoretical TOC. Picked up string 10m and circ ulated well over shackers at max 2000l/min - 100bar. Shackers plugged with cement returns. Diverted returns overboard. Continued circulated until no cement observed in returns. Totally cir culated 108m3. Meanwhile WOC
| 02:00:00 | 02:30:00 | 2405 | interruptio n -- wait | ok | Waited for cement, total of 2 hours from 1st tagging attempt
| 02:30:00 | 02:45:00 | 2438 | plug aban don -- ce ment plug | ok | Initiated circulation and RIH to tag cement. Down weight 126t. Slowly washed down from 2436m, 500l/min - 10bar, pressure dropped to 8 bar after reaching 2438m. Tagged TOC w/ 10t. Co nfirmed TOC at 2438m (22m below theoretical TOC)
| 02:45:00 | 03:00:00 | 2438 | plug aban don -- ce ment plug | ok | Released spear from tubing string. Pulled string 2m up, confirmed spear released, up weight of 82t. Top of tubing 389m
| 03:00:00 | 03:15:00 | 389 | plug aban don -- oth er | ok | Performed Pre-job Meeting to L/D 5.5in DP. Meanwhile performed flowcheck. Stable
| 03:15:00 | 05:15:00 | 0 | plug aban don -- oth er | ok | POOH w/ spear and L/D 5.5in DP
| 05:15:00 | 05:30:00 | 0 | plug aban don -- ce ment plug | ok | Performed Pre-job Meeting to L/D spear BHA
| 05:30:00 | 05:45:00 | 0 | plug aban don -- ce ment plug | ok | Removed DP slips, installed master bushing
| 05:45:00 | 06:15:00 | 0 | plug aban don -- ce ment plug | ok | L/D spear BHA
| 06:15:00 | 06:45:00 | 0 | plug aban don -- ce ment plug | ok | Removed power rollers. Cleaned and cleared rig floor
| 06:45:00 | 07:45:00 | 20 | plug aban don -- oth er | ok | P/U wash tool. RIH from surface to 20.5 m. Jetted wellhead w/ 2200 l/min, 10 rpm, moved string 1m up/down. POOH, L/D jetting tool
| 07:45:00 | 08:00:00 | 0 | plug aban don -- oth er | ok | Performed Pre-job Meeting to P/U MS-T seal retrieval tool
| 08:00:00 | 10:00:00 | 20 | plug aban don -- oth er | ok | P/U and M/U MS-T seal retrieval tool and tested same RIH to 20.5m and engaged MS-T seal retrieval tool. Pulled seal free with 80t overpull POOH from 20,5m and L/D MS-T seal and retrie val tool
| 10:00:00 | 10:15:00 | 0 | plug aban don -- cut | ok | Performed Pre-job Meeting to P/U cutter BHA
| 10:15:00 | 10:30:00 | 10 | plug aban don -- cut | ok | P/U and RIH cutter BHA to 9,5m
| 10:30:00 | 11:00:00 | 123 | plug aban don -- cut | ok | RIH w/ cutter BHA, positioned knives at 123m
| 11:00:00 | 11:30:00 | 123 | plug aban don -- cut | ok | M/U TDS, took parameters. Cut 10 3/4in surface casing tieback at 123m, 400 l/min - 50bar, 80 rpm, 2-10 kNm. Observed good indications of cut: pressure drop and reduction of torque
| 11:30:00 | 11:45:00 | 10 | plug aban don -- cut | ok | Flowchecked for 5min, stable. POOH to 9,5m
| 11:45:00 | 12:00:00 | 0 | plug aban don -- cut | ok | L/D cutter BHA
| 12:00:00 | 12:15:00 | 0 | plug aban don -- equ ipment rec overy | ok | Performed Pre-job Meeting to R/U casing tong
| 12:15:00 | 13:15:00 | 0 | plug aban don -- equ ipment rec overy | ok | R/U casing tong on the rig floor
| 13:15:00 | 13:30:00 | 103 | plug aban don -- oth er | ok | RIH w/ spear and engage in 10 3/4in surface casing hanger, pulled casing to surface
| 13:30:00 | 13:45:00 | 103 | plug aban don -- equ ipment rec overy | ok | Performed Pre-job Meeting to pull and L/D 10 3/4in casing
| 13:45:00 | 14:00:00 | 98 | plug aban don -- equ ipment rec overy | ok | Broke out pup joint and casing hanger, L/D same
| 14:00:00 | 14:30:00 | 98 | plug aban don -- equ ipment rec overy | ok | Changed BX Elevators to BX-4s and PDM head
| 14:30:00 | 16:15:00 | 0 | plug aban don -- equ ipment rec overy | ok | POOH and L/D 10 3/4in caing tieback from 103m to surface
| 16:15:00 | 17:00:00 | 0 | plug aban don -- equ ipment rec overy | ok | R/D casing tong and changed BX elevators
| 17:00:00 | 17:15:00 | 0 | plug aban don -- oth er | ok | Performed Pre-job Meeting to change saver sub to left hand one
| 17:15:00 | 18:30:00 | 0 | plug aban don -- oth er | ok | Placed 3m pup in rotary. Screwed in TDS and broke off saver sub. L/D pup with saver sub on top. RIH 1x stand with left hand DP. M/U left hand saver sub to stand, screwed in TDS and M/ U to saver sub
| 18:30:00 | 18:45:00 | 0 | plug aban don -- oth er | ok | R/B stand and P/U torque tool
| 18:45:00 | 19:15:00 | 140 | plug aban don -- oth er | ok | RIH w/ torque tool on LH drill pipe to 140m
| 19:15:00 | 19:30:00 | 140 | plug aban don -- oth er | ok | Washed profile area 1500l/min - 9bar. Released tieback adapter w/ 38kNm
| 19:30:00 | 19:45:00 | 140 | plug aban don -- oth er | ok | Performed Pre-job Meeting to change handling gear, L/D 5,5in LH DP
| 19:45:00 | 20:45:00 | 140 | plug aban don -- oth er | ok | Removed master bushing, installed DP slips. Changed PDM head
| 20:45:00 | 21:45:00 | 7 | plug aban don -- oth er | ok | R/B 1x stand of LH DP, L/D 16x joints of LH DP
| 21:45:00 | 22:15:00 | 0 | plug aban don -- oth er | ok | L/D torque tool
| 22:15:00 | 22:30:00 | 0 | plug aban don -- oth er | ok | L/D 4x singles of LH DP from the stand previously R/B
| 22:30:00 | 22:45:00 | 0 | plug aban don -- oth er | ok | Removed DP slips, installed master bushing
| 22:45:00 | 23:00:00 | 0 | plug aban don -- oth er | ok | Performed Pre-job Meeting to change saver sub back to right hand one
| 23:00:00 | 00:00:00 | 0 | plug aban don -- oth er | ok | Worked to change saver sub back to right hand one
2016-10-07 | 00:00:00 | 00:15:00 | 0 | plug abandon - | ok | Worked to change saver sub back to the right hand one
| 00:15:00 | 00:30:00 | 0 | plug abandon - | ok | Performed Pre-job Meeting to P/U spear BHA
| 00:30:00 | 01:15:00 | 128 | plug abandon - | ok | RIH w/ ITCO spear BHA
| 01:15:00 | 02:00:00 | 0 | plug abandon - | ok | Engaged spear in tieback adapter fish, pulled w/ 6t overpull. POOH w/ fish to surface
| 02:00:00 | 02:45:00 | 0 | plug abandon - | ok | R/B spear BHA, L/D tieback adapter stump
| 02:45:00 | 03:00:00 | 0 | plug abandon - | ok | Performed TBT to P/U perforation guns
| 03:00:00 | 05:30:00 | 148 | plug abandon - | ok | M/U and RIH w/ perforation BHA to 148m bottom shot depth
| 05:30:00 | 06:15:00 | 148 | plug abandon - | ok | Closed UPR, opened choke. Confirmed line up. Filled string. Opened UPR, Broke off TDS and dropped 1 3/8 ball in string. M/U TDS. Closed UPR and opened choke. Fired guns with 160 l/min - 130 bar. Top shot at 145m, bottom shot at 148m. Continued to circulate w/ 160l/min
| 06:15:00 | 07:00:00 | 148 | plug abandon - | ok | Circulated 1000 lpm / 5 bar. Maximum gas reading 0,41 %.
| 07:00:00 | 07:30:00 | 148 | - perforate | ok | Unable to circulate on TT due to contaminated OBM mixed with water. Emptied both TTs and re-filled TTs with clean SW.
|  |  |  | plug abandon - | ok | Stopped pumps and closed choke. Monitored well.
| 07:30:00 | 07:45:00 | 148 | plug abandon - | ok | Opened UPR and choke Flowchecked well for 10 min, static.
| 07:45:00 | 08:15:00 | 14 | plug abandon - | ok | POOH w/ perforation BHA from 148 m to 14 m.
| 08:15:00 | 08:30:00 | 14 | plug abandon - | ok | Changed to 4 1/2" inserts in BX-elevator.
| 08:30:00 | 09:00:00 | 0 | plug abandon - | ok | L/D perforation BHA.
| 09:00:00 | 09:15:00 | 0 | plug abandon - | ok | Performed TBT for cutting 10 3/4" casing
| 09:15:00 | 09:30:00 | 0 | plug abandon - | ok | Removed master bushing. Installed PS-21 slips.
| 09:30:00 | 09:45:00 | 0 | plug abandon - | ok | P/U and M/U 10 3/4" cutter BHA.
| 09:45:00 | 10:15:00 | 312 | plug abandon - | ok | RIH w/ 10 3/4" cutter BHA on 5 1/2" DP from surface to 312 m.
| 10:15:00 | 10:30:00 | 312 | - cut | ok | Filled DP. Initiated circulation 500 lpm / 73 bar, 50 rpm / 0 to 3 kNm.
|  |  |  | plug abandon - | ok | M/U TDS. Recorded up/down weight 76 / 71 ton.
| 10:30:00 | 10:45:00 | 312 | plug abandon - | ok | Cut 10 3/4" casing at 312 m, 400 lpm, 50 rpm. SPP dropped, good indication of cut.
| 10:45:00 | 11:00:00 | 312 | plug abandon - | ok | Lined up to TT and performed flowcheck, well static.
| 11:00:00 | 11:30:00 | 9.5 | plug abandon - | ok | POOH w/ 10 3/4" cutter BHA on 5 1/2" DP from 312 m to 9,5 m.
| 11:30:00 | 11:45:00 | 0 | plug abandon - | ok | L/D cutter BHA.
| 11:45:00 | 12:00:00 | 0 | plug abandon - | ok | Cleaned and cleared drill floor.
| 12:00:00 | 12:15:00 | 0 | plug abandon - | ok | Performed TBT for drops inspection prior to milling 10 3/4" casing hanger.
| 12:15:00 | 13:00:00 | 0 | plug abandon - | ok | Performed drops inspection of TDS, and both PRSs.
| 13:00:00 | 15:15:00 | 72 | plug abandon - | ok | M/U CH milling BHA
| 15:15:00 | 15:45:00 | 139.9 | plug abandon - | ok | RIH w/ CH milling BHA on 5 1/2" DP from 72 m to 110 m.
| 15:45:00 | 19:00:00 | 140.1 | plug abandon - | ok | Milled ID in 10 3/4" CH to 12 1/4". 100 rpm / 9-18 kNm, 2000 lpm / 10,8 bar, 4-5 ton WOB. Increased WOB to 8 - 10 ton after milling first 20 cm.
| 16:15:00 | 16:45:00 | 139.9 | - mill | ok | M/U TDS and continued RIH, tagged top of 10 3/4" CH at 139,9m. Pulled up and filled string.
| 19:00:00 | 21:15:00 | 141 | plug abandon - | ok | Continued milling 10 3/4" CH, 100 rpm / 10 - 16 kNm, 2000 lpm / 11 bar, WOB 8 - 10 ton. Stalled out several times
| 21:15:00 | 21:30:00 | 142 | - mill | ok | Dressed off approximately 5 cm of top of 10 3/4" casing, 120 rpm / 5 - 10 kNm, 2000 lpm / 10 bar.
|  |  |  | plug abandon - | ok | Tagged top of 10 3/4" casing 1 m below 10 3/4" CH.
| 21:30:00 | 22:00:00 | 110 | plug abandon - | ok | Circulated 2 x B/U w/ 3000 lpm / 22 bar. R/B 1 stand 5 1/2" DP.
| 22:00:00 | 22:30:00 | 110 | - mill | ok | Meanwhile: Flowchecked well, static. Performed TBT for L/O milling BHA.
|  |  |  | plug abandon - | ok | Performed drops inspection of TDS.
| 22:30:00 | 23:00:00 | 72 | plug abandon - | ok | POOH w/ CH milling BHA on 5 1/2" DP from 110 m to 72 m.
| 23:00:00 | 00:00:00 | 0 | - other | ok | B/O and L/O CH milling BHA.
|  |  |  | plug abandon - | ok | R/B 8 1/4" DC.
2016-10-08 | 00:00:00 | 00:30:00 | 0 | plug abandon -- mill | ok | Cleaned and cleared drill floor
| 00:30:00 | 00:45:00 | 0 | plug abandon -- equipm ent recovery | ok | Performed TBT for RIH with spear and retrieve 10 3/4" casing
| 00:45:00 | 01:00:00 | 0 | plug abandon -- equipm ent recovery | ok | M/U spear BHA
| 01:00:00 | 01:30:00 | 147 | plug abandon -- equipm ent recovery | ok | RIH w/ 10 3/4" spear in catch mode on 5 1/2" DP from surface to 147 m
| 01:30:00 | 02:30:00 | 170 | plug abandon -- equipm ent recovery | ok | POOH with 10 3/4" casing on 5 1/2" landing string from 147 m to surface.
| 02:30:00 | 02:45:00 | 170 | plug abandon -- equipm ent recovery | ok | Released spear at surface and R/B spear BHA
| 02:45:00 | 03:00:00 | 170 | plug abandon -- equipm ent recovery | ok | Performed TBT for R/U casing handling equipment and pulling casing.
| 03:00:00 | 06:00:00 | 0 | plug abandon -- equipm ent recovery | ok | Continued POOH with 10 3/4" casing from 170 m to surface. Average 10 joints/hr.
L/D casing pup joint.
| 06:00:00 | 08:15:00 | 0 | plug abandon -- equipm ent recovery | ok | R/D handling equipment.
| 08:15:00 | 08:30:00 | 0 | plug abandon -- other | ok | Performed TBT for running 13 3/8" EZSV plug
| 08:30:00 | 09:15:00 | 24 | plug abandon -- mecha nical plug | ok | P/U and M/U EZSV plug and RT. Installed centralizer on RT. L/D double 5 1/2" DP. P/U and M/U 3 pup joints for space out
| 09:15:00 | 10:30:00 | 306 | plug abandon -- other | ok | RIH w/ 13 3/8" EZSV plug from 24 m to 306 m.
| 10:30:00 | 10:45:00 | 306 | plug abandon -- other | ok | P/U and M/U pump-in sub.
| 10:45:00 | 11:15:00 | 306 | plug abandon -- mecha nical plug | ok | M/U TDS and washed setting area with 560 lpm / 6 bar.
Set 13 3/8" EZSV plug at 306m. Tagged EZSV plug with 10 ton.
| 11:15:00 | 12:30:00 | 305 | plug abandon -- cement plug | ok | Circulated with clean SW until clean returns. Reduced to 900 lpm when hi-vis at shakers. Increased flow to 2440 lpm when clean SW in returns. Meanwhile: Flushed TTs.
Pumped 10 m3 wash pill followed by 10 m3 hi-vis pill at 2000 lpm / 9 bar.
| 12:30:00 | 12:45:00 | 305 | plug abandon -- cement plug | ok | Performed TBT for cement job
| 12:45:00 | 13:45:00 | 305 | plug abandon -- cement plug | ok | Applied 20 bar behind FOSV and confirmed line-up. Leak tested surface lines to 100 bar / 3min.
Balanced OH to surface cement plug in 13 3/8" casing (305 m - 205 m ): Pumped 10 m3 DW at 1000 lpm with cement unit. Mixed and pumped 7,8 m3 1,95sg cement slurry at 600 lpm. Displaced cement with 2 m3 DW at 1000 lpm with cement unit.
Closed flow line and opened dump line. R/U cement hose to pump-in sub.
| 13:45:00 | 14:00:00 | 305 | plug abandon -- cement plug | ok | R/D cement hose. B/O and L/O pump-in sub.
| 14:00:00 | 14:30:00 | 160 | plug abandon -- cement plug | ok | POOH w/ EZSV RT on 5 1/2" DP from 305 m to 160 m.
| 14:30:00 | 15:00:00 | 160 | plug abandon -- cement plug | ok | Installed 2x sponge balls. Circulated BU, 2000 lpm.
| 15:00:00 | 15:30:00 | 80 | plug abandon -- cement plug | ok | POOH w/ EZSV RT on 5 1/2" DP from 160 m to 80 m. M/U BOP jetting tool and FOSV.
| 15:30:00 | 17:00:00 | 80 | plug abandon -- cement plug | ok | Jetted BOP 8 x passes up/down, 1450 lpm, 50 rpm. Operated annular preventer and pipe rams. B/O and L/O BOP jetting tool and FOSV.
| 17:00:00 | 17:15:00 | 80 | plug abandon -- cement plug | ok | Removed PS-21 slips and installed master bushing.
| 17:15:00 | 17:30:00 | 0 | plug abandon -- cement plug | ok | POOH and L/D the EZSV RT.
| 17:30:00 | 19:00:00 | 0 | plug abandon -- other | ok | RIH with 3 std 8 1/4" DC. L/O 2 x singles to cantilever.
| 19:00:00 | 21:15:00 | 0 | plug abandon -- other | ok | Performed TBT with ongoing crew. Performed manual tong training. L/O 7 joints 8 1/4" DC.
| 21:15:00 | 22:00:00 | 0 | plug abandon -- other | ok | L/O 10 3/4" spear BHA
| 22:00:00 | 23:15:00 | 0 | plug abandon -- other | ok | L/O 3 joints 6 3/4" DC
| 23:15:00 | 00:00:00 | 0 | plug abandon -- other | ok | L/O 5 joints over-torqued 5 1/2" DP
2016-10-09 | 00:00:00 | 01:15:00 | 0 | plug abandon -- other | ok | L/O 13 joints 5 1/2" over-torqued DP
| 01:15:00 | 03:00:00 | 0 | plug abandon -- other | ok | .
L/O 4 joints over-torqued 5 1/2" HWDP. Used manual tongs to break one of the connections
| 03:00:00 | 03:15:00 | 0 | plug abandon -- other | ok | Changed handling equipment for pulling diverter.
Cleaned and cleared drill floor.
| 03:15:00 | 03:30:00 | 0 | plug abandon -- other | ok | Performed TBT for N/D BOP
| 03:30:00 | 04:15:00 | 0 | plug abandon -- other | ok | N/D diverter and pulled slickjoint.
| 04:15:00 | 04:45:00 | 0 | plug abandon -- other | ok | Load shifted weight from tension system to BOP carrier.
| 04:45:00 | 05:30:00 | 0 | plug abandon -- other | ok | Disconnected BOP tension system. Meanwhile: Disconnected BOP NT2 connector
| 05:30:00 | 05:45:00 | 0 | plug abandon -- other | ok | Skidded BOP over to test stump
| 05:45:00 | 06:15:00 | 0 | plug abandon -- other | ok | Removed scaffolding around HP-riser. Meanwhile: Performed TBT for pulling HP-riser
| 06:15:00 | 07:00:00 | 0 | plug abandon -- other | ok | Pulled HP-riser to drill floor. Installed master bushing.
| 07:00:00 | 07:15:00 | 0 | plug abandon -- other | ok | Performed TBT for L/O HP-riser to HTS and installing hatches in moonpool
| 07:15:00 | 07:30:00 | 0 | plug abandon -- other | ok | L/O HP-riser to HTS
| 07:30:00 | 09:00:00 | 0 | plug abandon -- other | ok | Installed hatches in moonpool.
Meanwhile: Cleaned and preserved slickjoint
2016-10-10 | 10:45:00 | 13:15:00 | 0 | interruption -- wait | ok | L/O 3 1/2" DP from set-back. Meanwhile: Performed PMs.
Meanwhile:
Waited on supply boat with equipment for pulling production riser
| 13:15:00 | 15:00:00 | 0 | interruption -- wait | ok | Canged handling equipment to handle 5 1/2" DP. L/O 5 1/2" DP from set-back.
Meanwhile:
Waited on supply boat with equipment for pulling production riser
| 15:00:00 | 19:00:00 | 0 | plug abandon -- other | ok | Continued L/O 5 1/2" DP from set-back. Meanwhile:
Removed remaining hoses and electrical cables from WH
| 19:00:00 | 19:15:00 | 0 | plug abandon -- other | ok | Performed TBT for L/D diverter
| 19:15:00 | 20:45:00 | 0 | plug abandon -- other | ok | Meanwhile: Performed TBT for building scaffolding around BOP connector on test stump.
R/U and attached lifting equipment to TDS and diverter. L/O diverter and secured same on main deck.
Removed diverter lifting equipment from TDS.
| 20:45:00 | 21:30:00 | 0 | plug abandon -- other | ok | Prepared 1502 hoses/chiksan at WH Built scaffolding around BOP.
| 21:30:00 | 22:15:00 | 0 | plug abandon -- other | ok | Lifted PR cutter BHA to HTS
N/U BOP NT2 connector on test stump. Prepared lifting equipment on moonpool hatch. Lifted multibowl NT2 connector to drill floor.
| 22:15:00 | 23:00:00 | 0 | plug abandon -- other | ok | Continued N/U BOP NT2 connector on test stump
| 23:00:00 | 00:00:00 | 0 | plug abandon -- other | ok | Removed hatch in moonpool.
2016-10-11 | 00:00:00 | 00:45:00 | 0 | plug abandon -- other | ok | Lowered NT2 connector for multibowl. M/U NT2 connector on multibowl.
| 00:45:00 | 01:00:00 | 0 | plug abandon -- other | ok | Installed master bushing and removed box ring from rotary.
| 01:00:00 | 01:15:00 | 0 | plug abandon -- other | ok | Performed TBT for handling PR cutter BHA
| 01:15:00 | 04:15:00 | 134.9 | plug abandon -- other | ok | P/U and M/U cutter BHA and RIH with same. P/U and M/U mutlibowl RT.
| 04:15:00 | 04:30:00 | 134.9 | plug abandon -- other | ok | RIH w/ BHA and M/U multibowl RT in WH. Took 20 ton OP to verify RT engaged in WH. M/U TDS
| 04:30:00 | 05:00:00 | 0 | plug abandon -- other | ok | Performed debrief after M/U BHA.
| 05:00:00 | 05:30:00 | 0 | plug abandon -- other | ok | Performed TBT for R/D tension cylinders on PR
| 05:30:00 | 07:00:00 | 0 | plug abandon -- other | ok | Bled off pressure in PR tension cylinders, observed 35 ton increase on weight indicator
| 07:00:00 | 07:15:00 | 0 | plug abandon -- other | ok | Prepared WH/tension ring for removal
| 07:15:00 | 11:30:00 | 0 | plug abandon -- other | ok | Continued bleeding off tension cylinders.
Performed TBT for removing tension cylinders with ongoing crew
R/D tension cylinders, left the cylinders hanging from top mounting point. Secured tension cylinders.
| 11:30:00 | 12:00:00 | 0 | plug abandon -- other | ok | Meanwhile: Assisted crane with backload. Cleaned shaker pits.
| 12:00:00 | 15:30:00 | 0 | plug abandon -- other | ok | Performed information meeting with all involved personnel for riser pulling operations.
R/D boat collision stool and prepared to remove centralizers from centralizer deck. Connected 3 x weco 1502 hoses to WH outlets.
| 15:30:00 | 19:00:00 | 0 | interruption -- wait | ok | Assisted crane with backload. Continued cleaning shaker pits.
Meanwhile:
Meanwhile: Assisted crane with backload. Continued cleaning shaker pits.
Performed housekeeping on cantilever. Removed pipes and equipment from cantilever to make space for riser joints.
Waited on supply boat for riser equipment
| 19:00:00 | 19:15:00 | 0 | plug abandon -- other | ok | Performed TBT for R/U riser handling equipment
| 19:15:00 | 20:30:00 | 0 | plug abandon -- other | ok | Installed beams on cantilever deck for L/O riser joints.
R/U tailing arm and saddle on HTS. Continued to clear cantilever.
| 20:30:00 | 21:00:00 | 0 | plug abandon -- other | ok | Performed information meeting with all involved personnel for riser pulling operations.
| 21:00:00 | 23:45:00 | 0 | plug abandon -- other | ok | Continued to clear cantilever. Installed deck beams on cantilever.
| 23:45:00 | 00:00:00 | 0 | plug abandon -- other | ok | Spotted riser handling equipment. Meanwhile: Cleared drill floor.
2016-10-12 | 00:00:00 | 01:00:00 | 0 | plug abandon -- other | ok | Continued spotting riser handling equipment. Meanwhile: Cleared drill floor.
| 01:00:00 | 01:15:00 | 0 | plug abandon -- other | ok | Performed TBT for cutting the production riser and pulling the multibowl to drill floor.
| 01:15:00 | 01:30:00 | 0 | plug abandon -- other | ok | Staged up pump rate to 900 lpm, observed water leaking over the top of the multibowl
Took 5 ton overpull.
| 01:30:00 | 01:45:00 | 0 | plug abandon -- other | ok | Stopped pumping. Checked scribe line to confirm multibowl running tool still engaged to the multibowl.
| 01:45:00 | 02:00:00 | 0 | plug abandon -- other | ok | Observed multibowl/riser turned 1/4 turn clockwise at successful cut.
Staged up pump rate to 2300 lpm / 87 bar. Continued pumping for approximately 15 min, lost overpull, good indication of cut
| 02:00:00 | 02:15:00 | 0 | plug abandon -- other | ok | P/U slowly to confirm successful cut.
| 02:15:00 | 03:00:00 | 0 | plug abandon -- other | ok | Removed hoses and valves from multibowl.
| 03:00:00 | 03:30:00 | 0 | plug abandon -- other | ok | Pulled riser and multibowl to drill floor.
Removed master bushing and installed the big C-plate.
| 03:30:00 | 03:45:00 | 0 | plug abandon -- other | ok | Disengaged multibowl RT by rotating elevator.
| 03:45:00 | 04:00:00 | 0 | plug abandon -- other | ok | Installed small C-plate and false rotary.
| 04:00:00 | 04:45:00 | 0 | plug abandon -- other | ok | B/O and attempted to rack back multibowl RT. Unable to rack back due to too long assebly. Parked AFT PRS with multibowl RT out of the way.
| 04:45:00 | 06:00:00 | 0 | plug abandon -- other | ok | Pulled inner string and R/B 2 x 5 1/2" DP stands. R/B cutter BHA
| 06:00:00 | 06:15:00 | 0 | plug abandon -- other | ok | P/U and M/U multibowl RT. Removed C-plate.
| 06:15:00 | 07:00:00 | 0 | plug abandon -- other | ok | Pulled up riser until first flange at centralizer deck. Cleaned flange for marine growth.
| 07:00:00 | 07:15:00 | 0 | plug abandon -- other | ok | Performed TBT for pulling and cutting riser
| 07:15:00 | 07:45:00 | 0 | plug abandon -- other | ok | Pulled tensioner joint above drill floor. Cleaned flange for marine growth on WH deck.
| 07:45:00 | 08:00:00 | 0 | plug abandon -- other | ok | Installed master bushing and elevator. Landed riser on elevator.
| 08:00:00 | 09:00:00 | 0 | plug abandon -- other | ok | Installed hole cover to collect swarf
R/U cutting machine.
| 09:00:00 | 09:45:00 | 0 | plug abandon -- other | ok | Cut tensioner joint
| 09:45:00 | 10:00:00 | 0 | plug abandon -- other | ok | Collected swarf.
R/D cutting machine.
| 10:00:00 | 11:15:00 | 0 | plug abandon -- other | ok | L/O tensioner joint
| 11:15:00 | 12:30:00 | 0 | plug abandon -- other | ok | Cleared drill floor.
Removed running tool. Changed handling equipment. Installed cradle on HTS
| 12:30:00 | 12:45:00 | 0 | plug abandon -- other | ok | Lifted riser. Removed master bushing
| 12:45:00 | 13:00:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #2). Cleaned flanges on WH deck
| 13:00:00 | 13:15:00 | 0 | plug abandon -- other | ok | Installed master bushing and elevator. Removed fairing and landed riser onto elevator
| 13:15:00 | 14:00:00 | 0 | plug abandon -- other | ok | R/U cutting machine and hole cover. Cut riser
| 14:00:00 | 14:15:00 | 0 | plug abandon -- other | ok | Collected swarf.
R/D cutting machine.
| 14:15:00 | 14:45:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #2).
| 14:45:00 | 15:15:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #3).
| 15:15:00 | 15:30:00 | 0 | plug abandon -- other | ok | Installed master bushing and elevator. Landed riser onto elevator.
Removed master bushing. Pulled flange through rotary.
| 15:30:00 | 16:00:00 | 0 | plug abandon -- other | ok | R/U cutting maching and cut riser
| 16:00:00 | 16:15:00 | 0 | plug abandon -- other | ok | R/D cutting maching. Collected swarf
| 16:15:00 | 16:30:00 | 0 | plug abandon -- other | ok | L/D riser joint (lift #3)
| 16:30:00 | 17:00:00 | 0 | plug abandon -- other | ok | Pulled master bushing. Pulled flange through rotary, installed master bushing and elevator. Landed riser onto elevator.
Pulled riser joint (lift #4).
| 17:00:00 | 17:30:00 | 0 | plug abandon -- other | ok | R/U cutting maching and attempted cut riser. Knifes worn out and broken.
| 17:30:00 | 19:00:00 | 0 | plug abandon -- other | ok | Changed knifes and continued cutting riser.
Experienced knifes not cutting evenly due to ovality of riser.
| 19:00:00 | 19:15:00 | 0 | plug abandon -- other | ok | Continued cutting riser.
Meanwhile: Performed TBT with ongoing crew.
| 19:15:00 | 19:30:00 | 0 | plug abandon -- other | ok | R/D cutting maching. Collected swarf
| 19:30:00 | 20:00:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #4).
| 20:00:00 | 20:45:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #5)
Removed master bushing. Pulled flange through rotary, installed master bushing and elevator. Landed riser onto elevator.
| 20:45:00 | 22:15:00 | 0 | plug abandon -- other | ok | Experienced knifes not cutting evenly due to ovality of riser.
R/U cutting manchine and cut riser.
| 22:15:00 | 22:30:00 | 0 | plug abandon -- other | ok | R/D cutting machine. Collected swarf
| 22:30:00 | 22:45:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #5).
| 22:45:00 | 23:15:00 | 0 | plug abandon -- other | ok | Pulled riser (lift #6).
Removed master bushing. Pulled flange through rotary, installed master bushing and elevator. Landed riser onto elevator.
| 23:15:00 | 23:45:00 | 0 | plug abandon -- other | ok | R/U cutting machine and cut riser.
| 23:45:00 | 00:00:00 | 0 | plug abandon -- other | ok | R/D cutting machine. Collected swarf.
2016-10-13 | 00:00:00 | 00:15:00 | 0 | plug abandon -- other | ok | L/O riser joint (lift #6).
| 00:15:00 | 00:45:00 | 0 | plug abandon -- other | ok | Installed master bushing and hole cover in rotary
Lifted riser (lift #7). Removed master bushing. Pulled riser.
| 00:45:00 | 01:15:00 | 0 | plug abandon -- other | ok | L/O riser joint.
| 01:15:00 | 02:15:00 | 0 | plug abandon -- other | ok | Installed hole covers and hatches.
| 02:15:00 | 02:30:00 | 0 | plug abandon -- other | ok | Changed elevator to handle BHA.
Meanwhile: Removed scaffolding in moonpool.

## Casing
Casing Size | Intervals |  |  | Grade | Weight Lbs/ft | Thread Type | No. Joints | Centalisers (No.) | Remarks | Mud Wt | Depth mTVD DFE (m) | MW(SG)
| From (m) | To (m)
30” | 139.7 | 165.3 |  | X-65 | 456.6 | ABB RL-4 | 1 | - | Housing & XO | 1.03
[6 empty] | HC |  |  |  |  | 0
30” | 165.3 | 251.2 | 824.147 | X-52 | 133 | ABB ST-2 FE | 8 | - |  |  | 146
13 3/8” | 139.7 | 1351.2 | 4433.0709 | P-110 | 72 | Vam Top | 110 | 1 on shoe joint, 1 | Connection to |  | 146 | 1.03
[8 empty] | on Intermadiate, 1 on first joint | the first joint Baker locked. | 1.03 | 256 | 1.03
95/8” | 593.3 | 2760.5 | 9056.7585 | C-95 | 53.5 | Vam Top | 180 | - | X-Over at | 1.4 | 256 | 1.03
|  |  | 0 | [5 empty] | 593.3m |  | 1333.9 | 1.03
10 3/8” | 139.7 | 593.3 | 1946.5223 | C-95 | 60.7 | Vam Top | 38 | 2438-2485m -5 | - |  | 1333.9 | 1.03
|  |  | 0 |  |  |  |  | 2747-3100m -31 |  |  | 1363 | 1.03
7” | 2660,8 | 3508 | 11509.1864 | 13 Crs- | 29 | Vam Top HT | 70 | - | Connection to the first 4 joints | 1.4-1.45 | 1363 | 1.4
|  |  | 0 | 110 |  |  |  |  | Baker locked. |  | 1370 | 1.4
[11 empty] | 1370 | 1.4
[11 empty] | 2490 | 1.4
[11 empty] | 2490 | 1.4
[11 empty] | 2607.5 | 1.4
[11 empty] | 2607.5 | 1.4
[11 empty] | 2795.2 | 1.4
[11 empty] | 2795.2 | 1.4
[11 empty] | 2993 | 1.4
[11 empty] | 2993 | 1.4
[11 empty] | 3138.8 | 1.45

## Summary
15/9-F-4 Well Summary Sheet
| Well Type | [5 empty] | Well name : | 15/9-F-4 | [5 empty] | Objective : | To establish a water injection well |  |  |  | Coordinate Sys.: |  | xxx |  | Wellhead
| Deviated Water Injector Well | [5 empty] | Field : | Volvo Field | [5 empty] | Target Tolerance: | Circle of 50 m radius at Kh.7-A TOP |  |  |  | Surface : |  | xxx | xxx
[7 empty] | Type : | Injector Well | [5 empty] | Offset wells : | F-12, F-7 |  |  |  | Lat. = 58°26’29.807” N Long. = 01°53’14.929” E
[19 empty] | Target: xxx |  | N xxx | E xxxx xxx mTVDss
[19 empty] | GE (mtrs) : |  | 0
[19 empty] | DFE (mtrs) : |  | 54
| Prognosed Formation Tops Depths |  |  |  |  | Pore Pressure |  | Frac. Pressure |  | Hole |  |  | Section Length | C A S I N G
| Geological Column | Lithology | Depth mTVDss | Depth mTVD DFE | Depth mTVD DFE |  | EMW |  | Frac EMW | Risk | Remarks | Recommends | BHA | Size | Mass | Grade/ |  |  | interval |  | CEMENT |  | MUD | LOGS / CORING
|  |  | (m) | (m) | (ft) | (psi) | (psi/ft) | (psi) | (psi/ft) |  |  |  | (mtr) | (inch) | (lbs/ft) | coupling |  |  | (m)
36" Section TD |  |  |  | 95.5 |  | 160.5 | 256 | 36" |  |  |  |  | Section Length | 30" Casing | 456.6 | X-65 | CS | ABB RL-4 | 139.7 | 165.3
| 36" Hole Section | [11 empty] | pup joint |  | 133 | X-52 | CS | HC | 165.3 | 251.2 | Lead cmt:- |  | Spud Mud / Gel / Polymer
| A | Loose sand | 91 | 145 | 475.7218 | [8 empty] | Normal Size Shallow Cellar | [6 empty] | Grad :- |  | Grad :- | Survey
[21 empty] | TOC :- |  | Wt: | Mud Samples
[21 empty] | Excess :- |  | PV :-
[14 empty] | Casing accessories:- | [8 empty] | YP :-
[14 empty] | Housing & XO | [6 empty] | Tail cmt:-
[14 empty] | ROV | [6 empty] | Grad :-
[14 empty] | Guide Bushing | [6 empty] | TOC :-
Automated Slips
[14 empty] | CART | [6 empty] | Excess :
17-1/2" Section TD |  |  |  | 1077.9 | 3536.4173 | 256 | 1333.9 | 17.5 |  |  |  |  | Section Length | 13 3/8" Casing | 72 | P-110 | CS | Vam Top | 139.7 | 1351.2
| 17 1/2" Hole Section | [9 empty] | Problems with torque setting on casing tongs |  | Gauged bit | Normal Size Shallow Cellar | [6 empty] | Lead cmt:- |  | Spud Mud / Gel / Polymer
| A | SS | 106.5 | 160.5 | 526.5748 | [5 empty] | Failed to orient tool face due to high torque |  | Stabilizers | Bottom tubing head flange flush with top cellar | [6 empty] | Grad :- |  | Grad :- | Survey
[11 empty] | Set scribline and measured corrections on GWD and MWD. |  | Hydraulic Jar | [7 empty] | TOC :- |  | Wt: | Mud Samples
[11 empty] | Leakage in TDS |  | pup joint | Casing accessories:- | [6 empty] | Excess :- |  | PV :-
[14 empty] | One Jt Shoetrack, Install shoe and FC on pipe rack | [8 empty] | YP :-
Tail cmt:-
| B1 | SS/Clay | 829 | 883 | 2896.9816 | 984.9738 | 0.34 | [13 empty] | Grad :-
[14 empty] | RRTS Packer | [6 empty] | TOC :-
| B2 | Clay/SS/LS | 1008 | 1062 | 3484.252 | 1184.6457 | 0.34 | [13 empty] | Excess :
| C | Clay | 1172 | 1226 | 4022.3097 | 1367.5853 | 0.34
12-1/4" Section TD |  |  |  | 1273.7 | 4178.8058 | 1333.9 | 2607.6 | 12.25 |  |  |  |  | Section Length | 9 5/8" Casing | 53.5 | C-95 | CS | Vam Top | 593.3 | 2760.5
12 1/4" Hole Section | [9 empty] | Not able to handle cutting returns | X-Over at 593.3m | lower viscosity | pup joint | [7 empty] | Lead Cmt:- |  | TYPE:
[11 empty] | Tong jammed to coupling |  | Jar | Casing accessories: | [6 empty] | Grad :- |  |  | Survey
[11 empty] | Not ble to open PS-30 slips |  |  | Shoe track: | [6 empty] | Excess : |  | Grad :- | Mud Samples
[11 empty] | Cuttings slurry routed to boat due to injection pump is out of operation. |  |  | Centralizers | [6 empty] | TOC :- |  | Wt :-
| C | Clay | 1279.9 | 1333.9 | 4376.3123 | 1969.3406 | 0.45 | 2888.3661 | 0.66 |  |  |  |  | CART | [6 empty] | Tail cmt:- |  | Vis :-
| D1 | Clay/SS/LS | 2207.2 | 2261.2 | 7418.6352 | 3412.5722 | 0.46 | [13 empty] | Grad :- |  | YP :-
| D2 | Shale/Sand | 2269.4 | 2323.4 | 7622.7034 | 3430.2165 | 0.45 | [13 empty] | TOC :- |  | PV :-
[21 empty] | Excess : |  | FL :-
| D3 | Clay | 2333.7 | 2387.7 | 7833.6614 | 3603.4843 | 0.46 | [13 empty] | Tail cmt:- |  | Vis :-
| D4 | Clay/SS/LS | 2419 | 2473 | 8113.5171 | 3732.2178 | 0.46 | [13 empty] | Grad :- |  | YP :-
| E | LS | 2527.6 | 2581.6 | 8469.8163 | 3896.1155 | 0.46 | [13 empty] | Details from Hall. proposal |  | Details from Barroid proposal
8 1/2" Section TD |  |  |  | 531.2 | 1742.7822 | 2607.6 | 3138.8 | 8.5 |  |  |  |  | Section Length | 10 3/8" Liner | 60.7 | C-95 |  | Vam Top | 139.7 | 593.3
8 1/2" Hole Section | [12 empty] | BHA | [7 empty] | Lead cmt:- |  | Oil Base Mud
[21 empty] | Grad :- |  | Grad :- | Survey
| E | LS | 2553.6 | 2607.6 | 8555.1181 | 4790.8661 | 0.56 | 6074.1339 | 0.71 | [11 empty] | TOC :- |  |  | Mud Samples
Casing accessories:-
| F1 | LS/Marl | 2652.2 | 2706.2 | 8878.6089 | 4972.021 | 0.56 | [6 empty] | Shoe track: | [6 empty] | Excess :
| F2 | SS/SH | 2733.7 | 2787.7 | 9145.9974 | 4938.8386 | 0.54 | [6 empty] | Centralizers:
Overlap:
| G | Clay | 2799.3 | 2853.3 | 9361.2205 | 4867.8346 | 0.52 | [6 empty] | Markers:
| H | Clay/LS | 2893 | 2947 | 9668.6352 | 5124.3766 | 0.53
| I | SS/Clay/LS/Coal | 2933 | 2987 | 9799.8688 | 5389.9278 | 0.55
| J | SS/Clay/Siltstone | 3038.6 | 3092.6 | 10146.3255 | 5073.1627 | 0.5
TD of Well | [7 empty] | 7 |  |  |  |  | Section Length | 7" Liner | 29 | 13 Csr-110 |  | Vam Top HT | 2660.8 | 3508
[10 empty] | Troubleshot mudpumps. Not able to start mudpump #3. Mudpump #2 gave wrong output on stroke setting. Decided to drill ahead using mudpump #1 only. | ROP increased from 5 to 35 m/hr. Flowchecked well - ok - well static. |  |  | hanger/TSP packer | [9 empty] | MDT logging string
[11 empty] | Observed increase in active of ~1 m3 over 5 mins. Flowcheked well on trip tanks - ok - well static |  |  | GTV Plug
Shut down operation due to exhaust fumes blowing into the rig floor.
Note on X18: ebmad0: 200m of Tail CMT from Bottom
Note on X31: ebmad0: 200m of Tail CMT from Bottom
General Drilling difficulties
* High Pressure :- Expected in the Intera-Khoman @ 2668 mbdf - MW to be 0.55 psi/ft.
* Gas chimney : - About 2.5 km S.W there is a gas chimney. Although non of the offset wells had any
increase in gas levels while drilling top hole, Shallow Gas procedures will be applied.

## Hole Sections
Hole Section | mMD |  | mTVD |  | Comment
36 | 146 | 256 | 160.5 | 256 | This section was drilled riserless with cuttings going to seabed. | The 36” hole was drilled without riser, using sea water as a drilling fluid, with the returns going to the seabed. ROV was standby observing for gas. There was no indication of shallow gas during drilling. We then can assume this section has a normal compaction as expected in a top hole. The d-exponent gave a scattered picture due to the loose nature of the uppermost sediments, and was of no use.
17.5 | 256 | 1360 | 256 | 1333.9 | This section was also drilled riserless with cuttings going to seabed. The only possible interpretation was made upon ROP breaks, and two formations characterised by dominance of sandstone had been picked. | This section was also drilled riserless, using sea water based mud of 1.03sg, with the returns going to the seabed observed using ROV. There was no indication of shallow gas during drilling what was expected due information gained from drilling the 8½” Pilot Hole on F-12 well. It can be assumed this section has a normal compaction as predicted in the drilling program. The maximum estimated pore pressure of 1.08sg extrapolated upon D-exponent calculations was picked out just above the Skade formation at the depth of 1220m.
12.25 | 1360 | 2770 | 1333.9 | 2607.6 | For the 12 ¼” section, spot samples were taken every 10m from 1370mMD until TD of section. Wet samples were collected every 30m until TD of section.
8.5 | 2770 | 3510 | 2607.6 | 3138.8 | Sampling depth for this section started at 2780mMD. Spot- and wet samples were taken every 10m until top Hugin. Sampling interval from top Hugin to TD at 3510mMD was spot and wet every 3m and one set of mudsamples (3300 m to TD) every 50m. In parts the samples were taken every 6 meters due to high ROP.

## Cement data
30"
| Lead | Tail | Capacity(bbl/ft) | Remedial
WT(SG) | 1.5 |  | 0.468 | 1.56
WT
Type | X-lite
Vol(m3) | 75 | 8.5 |  | 15
TOC | To surface | 247 MD
Excess | 50% | 50%
Yield | 2.3885 ft3/sk | 1.1487 ft3/Sk
Mix Fluid | 14.28 Gal/Sk | 5.01 Gal/SK
13 3/8"
| Lead | Tail | Capacity
WT(SG) | 1.56 | 1.92 | 0.1505
WT
Vol(m3) | 126 | 20
TOC
Excess
Yield
Mix Fluid
9 5/8"
| Lead | Tail | Capacity
WT(SG) | 1.9 |  | 0.678
WT
Vol(m3) | 17.3
TOC
Excess
Yield
Mix Fluid
7" liner
| Lead ? | Tail | Capacity
WT(SG) | 1.9 |  | 0.027
WT
Vol(m3) | 15.9
TOC
Excess
Yield
Mix Fluid

## Bit Record
Hole Section |  | 36” | 17½ | 12¼” | 8 ½” | 8 ½”
BHA Number |  | 1 | 2 | 3 | 4 | 5
Bit Number |  | 1 | 2 | 3 | 4 | 5
Bit size |  | 17½”x36”HO | 17½” | 12¼” | 8 ½” | 8 ½”
Manufacturer |  | Smith
Bit type |  | GS03BDODGVCPD | XR-ODVC | RSR616M | MDI616LHABPX
Serial number |  | - | MY8926 | 216528 | SCC001
Nozzles (n/32”) |  | 1x15, 3x18 | 4x20 | 3x16, 3x15 | 1x12, 5x11 | 3x12, 3x13
TFA (in2) |  | 0,917 | 1228 | 1107 | 0.575 | 0.721
Motor type |  | - | Powerpack | - | Vortex | -
Motor bend |  | - | 1,5º | - | - | -
MWD Type |  | Powerpulse |  | PowerDrive
Depth in (m) |  | 145 | 256 | 1360 | 2770 | 2993
Depth out (m) |  | 256 | 1360 | 2770 | 2993 | 3510
Metres formation drilled |  | 111 | 1104 | 1410 | 223 | 517
Hours on bottom: |  | 15,1 | 24,7 | 66,6 | 11.58 | 36.6
Hours on bottom: Cement |  | - | 1,5 | 10.1 | 3.8 | -
Circulation hours |  | 20.6 | 47 | 115.4 | 28.1 | 47.9
Total bit revolutions |  | (No signal) | 439 | 1409 | 205 | 402
Average ROP (m/hr) |  | 7,3 | 44,6 | 21,2 | 19.25 | 14.13
min-max Flow (l/min) |  | 720-4550 | 3070 – 4495 | 1650 – 3520 | 1940-2092 | 2070-2226
min-max Pressure (bar) |  | 6 – 85 | 75 – 148 | 159 – 220 | 222-257 | 202-235
min-max WOB (ton) |  | 1 – 7 | 1 – 8 | 1 – 9 | 4.8-9.3 | 3.2-8.3
min-max String RPm |  | 70 – 100 | 90 – 190 | 50 – 170 | 30-41 | 140-181
min-max Bit RPm |  | 70 – 100 | 0 – 55 | 50 – 170 | 181-203 | 140-181
min-max Torque (kNm) |  | 2025-12-05 | 2025-10-02 | 7 – 27 | 14.3-20.4 | 16.8-23.5
Average Torque (kNm) |  | 7 | 7 | 15 | 19.3 | 20.8
Mud Weight (g/cc) |  | 1,03 | 1,03 | 1,40 | 1.4 | 1.40 – 1.45
Mud Type |  | SW with hi-vis pills |  | Enviromul OBM | OBM-Standard | OBM-Standard
Start - end inclination |  | 0.00º – 0.09º | 0.09º – 15.49º | 15,49 – 29.63º | 29.63º - 35.31º | 35.31º - 54.67º
Max inclination |  | 0.28º | 15.49º | 29.63º | 35.31º | 55.23º
Start - end Azimuth |  | 220.00 - 109,43 | 220.00 - 148,23 | 148,23º - 133,70º | 133.7º - 165.62º | 165.62º - 202.72º
Lithology |  | - | - | Clay/Sand/Lim |  | Sandst/Limestone/ Marl
| I | 1 | 1 | 4 | 1 | 1
| O | 1 | 1 | 3 | 1 | 1
| D | BU | WT | CT | NO | WT
Grade | L | A | A | N | A | A
| B | E | E | X | X | X
| G | I | I | IN | In | I
| O | ER | NO | WT | NO | CT
| R | TD | TD | TD | BHA | TD
Reason pulled |  | TD reached | TD reached | TD reached | Stop for start up of production. Change BHA | Section TD

## Mud Used
MD(m) | Mud Name | Purpose | Mud Type | Weight (SG) | ECD(SG) | Rate(lpm) | Volume(m3) | SSP (bar)
256.5 |  |  | WBM | 1.35 |  | 4000 | 100
152 |  |  |  | 1.35 |  | 400
1355 |  |  | WBM | 1.4
1360 | hi-vis |  | WBM | 1.4 |  | 4500 | 225 | 135-200
380 |  |  | WBM | 1.4
800 |  |  | WBM | 1.4
1198 |  |  | WBM | 1.4
1351 | Seawater | Cement displacement |  |  |  |  | 890 litre
1350 |  | FIT |  | 1.395 |  | 3500
2525 | slug |  |  | 1.65 |  | 880 | 4.7 | 22
171 |  | Running Casing |  | 1.4
276 |  | Running Casing |  | 1.4
416 |  | Running Casing |  | 1.4
587 |  | Running Casing |  | 1.4
1550 |  | Running Casing |  | 1.4
1858 |  | Running Casing |  | 1.4
2151 |  | Running Casing |  | 1.4
2369 |  | Running Casing |  | 1.4
2369 |  | Running Casing |  | 1.4
2760.5 |  |  |  | 1.4 |  | 2000 | 1 csg vol | 57
2760.5 |  |  | OBM |  |  | 2000 | 10
2761.5 | Spacer |  |  |  |  | 2000 | 20
2751 |  |  |  | 1.4 |  | 1500 | 26 | 140
2760 |  |  |  | 1.4 |  | 1500 |  | 140
2760 |  | FIT |  |  | 1.65 |  |  | 64
2854 |  | Drilling |  | 1.4 | 1.51 | 2070 |  | 250
2917 |  | Drilling |  | 1.4 | 1.51 | 2070-2090 |  | 245-250
2993 |  | Drilling |  | 1.4 | 1.51 | 2070 |  | 245-255
3035 |  | Drilling |  | 1.45 | 1.59 | 2090-2225 |  | 200-220
3040 |  | Drilling |  |  | 1.59 | 2225 |  | 220
3064 |  | Drilling |  |  | 1.59 | 2225 |  | 220
3070 |  | Drilling |  |  | 1.59-1.60 | 2200 |  | 220
3095 |  | Drilling |  |  | 1.59-1.60 | 2200 |  | 220
3103 |  | Drilling |  |  | 1.6 | 2200 |  | 222
3265 |  | Drilling |  |  | 1.61-1.62 | 2200 |  | 220-231
3302 |  | Drilling |  |  | 1.62-1.63 | 2200 |  | 220-231
3327 |  | Drilling |  |  | 1.61-1.63 | 2100-2200 |  | 216-238
3346 |  | Drilling |  |  | 1.61 | 2100 |  | 214
3385 |  | Drilling |  |  | 1.61-1.62 | 2100 |  | 220
3510 |  | Drilling |  |  | 1.59-1.60 | 2100 |  | 220
3307 | slug | Trip |  | 1.65 |  |  | 5
2750 |  | Fishing |  | 1.39-1.45 |  | 700 |  | 10-30
3202 |  |  |  | 1.47 |  | 1000 |  | 430
2710 | slug | Fishing |  | 1.65 |  | 700 | 5
2755 |  | Logging |  | 1.44 |  | 2000 |  |  | 93
2755 |  |  |  | 1.45 |  | 2000 |  | 82-95
2755 | slug | Logging |  | 1.62 |  |  | 6
2466 |  | Running Casing |  | 1.45 |  | 2000-1000 | 104 | 88-94-29.8
2755 |  | Running Casing |  |  |  | 1000 | 113 | 59
2751 |  |  |  |  | 1.58 | 500 |  | 21
3510 |  |  |  | 1.56 | 1.57 | 2200 |  | 206
3508 |  |  | OBM |  |  | 780 | 10 | 80
3508 | Spacer |  |  | 1.65 |  | 665 | 15 | 80
3508 | Fresh water | Cement displacement |  |  |  |  | 0.9
112 | slug |  |  | 1.63 |  | 1000 | 3 | 7
791 | slug |  |  | 1.66 |  |  | 5.5
138 | Completion fluid |  |  | 1.03 |  | 2400 | 37
615
0 | hi-vis | Cement displacement |  |  |  |  | 0.9
0 | hi-vis | Cement displacement |  |  |  |  | 12.2
0 | Seawater | Cement displacement |  |  |  | 1000-1300-700 |  | 101-83
2416 |  | Cement displacement |  |  |  | 2900 | 37 | 51
305 |  | Cement displacement | DW |  |  | 1000 | 10
305 |  | Cement displacement | DW |  |  | 1000 | 2

## Cement Used
MD(m) | Cement Name | Cement Type | Weight (SG) | Rate(lpm) | Volume(m3) | Pressure(bar)
251 |  | X-lite | 1.5 | 800 | 75 | 13
1350 | lead |  | 1.56 | 800-1200 | 126 | 20
1351 | Tail |  | 1.92 | 800-1200 | 20 | 20
2760.5 |  |  | 1.9 | 800 | 17.3 | 40-45
3508 |  |  | 1.9 | 680 | 15.9 | 80
0 | Plug abandon |  | 1.9 | 600 | 13.6 | 130-90
2416 | Plug abandon |  | 1.9 | 600 | 9.4
305 | Plug abandon |  | 1.95 | 600 | 7.8